## CA
STATUS | CREATED BY | ISSUE DATE | PO NUMBER | REFERENCE | DUE DATE FACTORY | SKU | PRODUCT NAME | INCOMING STOCK | SUPPLIER | ORIGIN | SHIP TO | SHIPPING DATE SUPPLIER | TRANSIT | ETA WAREHOUSE UPDATES | SHIPPING INSTRUCTIONS | TRACKING NUMBER / UPDATES | IMPORTANT NOTE | PETER UPDATES | DELAY ISSUES | EST RECEIPT DATE ODOO | RECEPTION DATE WAREHOUSE | COMPLETED | SUPPLIER DELIVERY | TOTAL REAL LEAD TIME | Total LT in weeks
Received | Yannett Yeomans | 2025-07-11 | PO08140 | SO18055 | 2025-09-26 | AC-52-053-163-000 | Frame Assembly, F4D1, Allis-Chalmers CSO, c/w 316SS Shaft | 1 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-04-09 | LAND | 2025-10-03 |  |  |  |  | Problem with manufacture process, Hisco delayed too much | 2025-10-03 | 2026-04-14 | TRUE | 195 | 277
Received | Carlos Leon | 2025-08-20 | PO08231 | Stock | 2025-10-02 | AC-98-530-594-001 | Pedestal, 5x4/5x5/6x6 SRL & SRL-C, Cast Iron | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-02-11 | SEA | Around Week of Apr. 30 - May 1 |  | TCLU8795637 |  | possible arrival to vancouver port march 21st | Delay production due spring festival | 2025-12-15 | 2026-04-28 | TRUE | 132 | 251 | 35.8571
Received | Carlos Leon | 2025-08-20 | PO08231 | Stock | 2025-10-02 | AC-98-431-799-001 | Suction Side Casing, 5x4-14 SRL-C, Cast Iron | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-02-11 | SEA | Around Week of Apr. 30 - May 1 |  | TCLU8795637 |  | possible arrival to vancouver port march 21st | Delay production due spring festival | 2025-12-15 | 2026-04-28 | TRUE | 132 | 251 | 35.8571
Received | Carlos Leon | 2025-08-20 | PO08231 | Stock | 2025-10-02 | AC-98-431-797-501 | Gland Side Casing, 5x4-14 SRL-C, Cast Iron | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-02-11 | SEA | Around Week of Apr. 30 - May 1 |  | TCLU8795637 |  | possible arrival to vancouver port march 21st | Delay production due spring festival | 2025-12-15 | 2026-04-28 | TRUE | 132 | 251 | 35.8571
Received | Carlos Leon | 2025-10-17 | PO08371 |  | 2026-01-12 | AC-98-530-742-501 | Impeller (Closed),12x10-25 SRL-C, Natural Rubber | 1 | IGH | Mexico | CA WAREHOUSE | 2026-02-27 | LAND |  |  |  |  | confirmed SHIPMENT ETD FEB 27, 2026 |  | 2026-02-02 | 2026-01-12 | TRUE | 46 | 87
Received | Carlos Leon | 2025-10-28 | PO08393 | Stock | 2025-12-23 | AC-98-234-271-001 | Waterseal Bushing, 3x3 SRL-C, 316SS | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-01-06 | SEA | 2026-03-03 |  | 1071968361 |  | Prince Rupert, march 1st / Expected to arrive first week of april | delayed due heavy congestion | 2026-03-03 | 2026-03-30 | TRUE | 14 | 153 | 21.8571
Received | Carlos Leon | 2025-10-31 | PO08399 | Stock | 2025-12-19 | AC-98-431-768-501 | Shaft Assembly, 8x6-18 SRL-C, 1045 Steel | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-01-06 | SEA | 2026-02-10 |  | 1071968361 |  | Prince Rupert, march 1st / Expected to arrive first week of april | delayed due heavy congestion | 2026-02-10 | 2026-03-30 | TRUE | 18 | 150 | 21.4286
Received | Carlos Leon | 2025-11-04 | PO08407 |  | 2025-11-07 | AC-98-232-857-801 | Shim Set, A-C PWO-C Group 1, Plastic | 4 | Renewal Services Inc. | Canada | CA WAREHOUSE |  | LAND |  |  |  |  | Email requesting an updated sent on Nov 12th, 2025. Waiting response. |  | 2025-11-21 | 2025-11-17 | TRUE | -45968 | 13
Received | Carlos Leon | 2025-11-04 | PO08408 |  | 2025-11-07 | AC-98-234-109-001 | Sleeve Spacer, 2x2-10 SRL, Steel | 5 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE |  | LAND |  |  |  |  | Email requesting an updated sent on Nov 12th, 2025. Waiting response. |  | 2025-11-14 | 2025-11-17 | TRUE | -45968 | 13
Received | Carlos Leon | 2025-11-04 | PO08410 |  | 2025-11-06 | AC-98-233-815-001 | Half Seal Cage, 5x4/5x5/6x6 SRL & SRL-C, Steel | 3 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE |  | LAND |  |  |  |  | Email requesting an updated sent on Nov 12th, 2025. Waiting response. |  | 2025-11-12 | 2025-11-17 | TRUE | -45967 | 13
Received | Yannett Yeomans | 2025-11-05 | PO08412 |  | 2025-11-07 | AC-98-233-992-001 | Half Seal Cage, 3x3-10 SRL & SRL-C, Cast Iron | 6 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE |  | LAND | [5 empty] | Email requesting an updated sent on Nov 12th, 2025. Waiting response. | 2025-11-14 | 2025-11-17 | TRUE | -45968 | 12
Received | Yannett Yeomans | 2025-11-05 | PO08413 |  | 2025-11-07 | CR 17386, G-8690-93904 | Bearing Seal (Inboard), 3x3-10 SRL & SRL-C, Neoprene/Steel | 4 | Wajax Limited - Mississauga | Canada | CA WAREHOUSE | 2025-12-02 | LAND | Wed. Dec. 3, 2025 10:16 a.m. |  |  |  | Tue. Dec. 2, 2025 | Email requesting an updated sent on Nov 12th, 2025. Waiting response. Supplier confirms PO got overlooked. ETA Nov 18 | 2025-11-05 | 2025-12-03 | TRUE | 25 | 28
Received | Yannett Yeomans | 2025-11-05 | PO08413 |  | 2025-11-07 | CR11138, G-8690-93353 | Bearing Seal (Outboard), 2x2-10 SRL, Neoprene/Steel | 3 | Wajax Limited - Mississauga | Canada | CA WAREHOUSE | 2025-11-13 | LAND |  |  |  |  | Nov 13th, 2025 | Email requesting an updated sent on Nov 12th, 2025. Waiting response. Supplier confirms PO got overlooked. ETA Nov 19 | 2025-11-05 | 2025-12-03 | TRUE | 6 | 28
Received | Yannett Yeomans | 2025-11-05 | PO08413 |  | 2025-11-07 | CR16084, G-8690-93760 | Bearing Seal, 3x3-10 SRL & SRL-C (Outboard) & 2x2-10 (Inboard), Neoprene/Steel | 10 | Wajax Limited - Mississauga | Canada | CA WAREHOUSE | 2025-11-13 | LAND |  |  |  |  | Nov 13th, 2025 | Email requesting an updated sent on Nov 12th, 2025. Waiting response. Supplier confirms PO got overlooked. ETA Nov 20 | 2025-11-05 | 2025-12-03 | TRUE | 6 | 28
Received | Yannett Yeomans | 2025-11-05 | PO08413 |  | 2025-11-07 | SKF 6306, G-8050-30660 | Bearing (Inboard & Outboard), 2X2-10 SRL, Steel | 10 | Wajax Limited - Mississauga | Canada | CA WAREHOUSE | 2025-11-13 | LAND |  |  |  |  | Nov 13th, 2025 | Email requesting an updated sent on Nov 12th, 2025. Waiting response. Supplier confirms PO got overlooked. ETA Nov 20 | 2025-11-05 | 2025-12-03 | TRUE | 6 | 28
Received | Yannett Yeomans | 2025-11-05 | PO08414 |  | 2026-01-06 | AC-98-236-259-501 | Gland Assembly, 2x2-10 SRL, 316SS | 2 | IGH | Mexico | CA WAREHOUSE |  | LAND | ETA Jan 20th, 2026 |  |  |  |  | Arrived 01/12/2026 | 2026-01-20 | 2026-01-12 | TRUE | -46028 | 68
Received | Yannett Yeomans | 2025-11-05 | PO08415 | SO18159 | 2025-12-18 | AC-98-331-958-823 | Shaft Sleeve, 2x2-10 SRL, 420SS Heat Treated, Hardened | 5 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-01-06 | SEA | 2026-02-26 |  | 1071968361 |  | Prince Rupert, march 1st / Expected to arrive first week of april | delayed due heavy congestion | 2026-02-26 | 2026-03-30 | TRUE | 19 | 145
Received | Yannett Yeomans | 2025-11-05 | PO08416 |  | 2025-11-07 | AC-98-234-013-001 | Waterseal Bushing, 3x3-10 SRL, Cast Iron | 3 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE |  | LAND | [5 empty] | Email requesting an updated sent on Nov 12th, 2025. Waiting response. | 2025-11-06 | 2025-11-17 | TRUE | -45968 | 12 | 1.7143
Received | Yannett Yeomans | 2025-11-05 | PO08416 |  | 2025-11-07 | AC-98-234-104-001 | Waterseal Bushing, 2x2-10 SRL, Cast Iron | 2 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE |  | LAND | [5 empty] | Email requesting an updated sent on Nov 12th, 2025. Waiting response. | 2025-11-06 | 2025-11-17 | TRUE | -45968 | 12
Received | Ian Trottier | 2025-11-06 | PO08418 |  | 2025-11-14 | DU-SA3210AA00-TFR | Impeller Gasket, Durco Mark 2&3 Group 2, Teflon/Rubber | 28 | Hisco Pump Inc. | US | CA WAREHOUSE | 2025-12-01 | LAND | 2025-12-03 09:00 |  | COM002112574 |  |  | Email requesting an updated sent on Nov 19th, 2025. Waiting response. | 2025-11-28 | 2025-12-03 | TRUE | 17 | 27
Received | Taylor Cook | 2025-11-07 | PO08419 |  | 2025-11-14 | REM - N 09, G-8601-0009 | Bearing Lock Nut, Steel | 2 | BDI Canada Inc. | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2025-11-07 | 2025-11-11 | TRUE | -45975 | 4
Received | Taylor Cook | 2025-11-07 | PO08419 |  | 2025-11-14 | REM - N 09, G-8601-0009 | Bearing Lock Nut, Steel | 2 | BDI Canada Inc. | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2025-11-07 | 2025-11-11 | TRUE | -45975 | 4
Received | Emilka Guerra | 2025-11-07 | PO08420 | SO18176 | 2025-12-05 | W-RSL30029/A05 | Expeller Ring, 300 RSL, High Chrome | 1 | Super Cast Limited | China | CA WAREHOUSE | 2026-02-27 | SEA | arrived april 1st |  |  |  | left Tianjin for Toronto by sea on Jan 29, 2026 | Expected to arrive first week of april | 2026-02-13 | 2026-04-01 | TRUE | 84 | 145
Received | Emilka Guerra | 2025-11-07 | PO08421 |  | 2025-12-19 | GA-25232 | Cover Plate, G-Series 2.5" VSP, 1000 Series, Natural Rubber | 1 | IGH | Mexico | CA WAREHOUSE |  | LAND | ETA Jan 9th, 2026 |  |  |  |  | Arrived 01/12/2026 | 2026-01-09 | 2026-01-12 | TRUE | -46010 | 66
Received | Emilka Guerra | 2025-11-11 | PO08422 | Stock - SO18179 Qty 1 Frame Adapter - | 2025-12-30 | G-262-93 1013 | Frame Adapter, 10", 3196 MTX/LTX, Ductile Iron | 2 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA | 2026-03-10 |  |  |  |  | was expected to arrive end of Jan | 2026-03-10 | 2026-02-02 | TRUE | -46021 | 83
Received | Emilka Guerra | 2025-11-11 | PO08423 | Stock - SO18179 Qty 1 Frame Adapter - | 2025-12-30 | G-249-61 1216 | Casing, 2x3-10, 3196 MTX, CD4MCu | 2 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA | 2026-03-10 | [5 empty] | 2026-03-10 | 2026-02-02 | TRUE | -46021 | 83
Received | Emilka Guerra | 2025-11-11 | PO08424 | Stock | 2025-12-30 | AC-98-331-958-823 | Shaft Sleeve, 2x2-10 SRL, 420SS Heat Treated, Hardened | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA |  |  | 1071968361 |  | Prince Rupert, march 1st / Expected to arrive first week of april | delayed due heavy congestion | 2026-03-10 | 2026-03-30 | TRUE | -46021 | 139
IN TRANSIT & DELAYED | Emilka Guerra | 2025-11-11 | PO08424 | Stock | 2025-12-30 | AC-98-431-849-001 | Suction Side Casing, 3x3-10 SRL, Cast Iron | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-05-26 | SEA | ETA Warehouse mid-august | the vessel depart on May 26 | 20251217-11 Sea Waybill-No. 1074440607 | email sent on April 10th, 2026 Betty 4/23: Included in Comercial Invoice #20251217-11 | Betty 04/13: This part will be ready in about 7-10 days. Betty 04/22: The three new parts are being machined and should be ready soon. | Betty: we manufacture the two parts as one set(suction half casing&gland side casing),we hope you can oder them as a pair. | 2026-03-10 |  | FALSE | 147 | -45972 | -6567.4286
Received | Emilka Guerra | 2025-11-11 | PO08425 | Stock | 2026-01-01 | G-RC04064A01 1216 | Stuffing Box Cover, 15", 3196 XLT, CD4MCu, Big Bore, Non-Jacketed | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-02-11 | SEA | 2026-03-13 |  | BL# TAOTOR06921 |  |  |  | 2026-03-13 | 2026-04-08 | TRUE | 41 | 148
Received | Emilka Guerra | 2025-11-11 | PO08425 | Stock | 2026-01-01 | G-R196-MKS8 | Maintenance Kit, 8", 3196 STX | 10 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-02-11 | SEA | 2026-03-13 | [5 empty] | 2026-03-13 | 2026-03-18 | TRUE | 41 | 127
Received | Emilka Guerra | 2025-11-11 | PO08425 | Stock | 2026-01-01 | G-RD04540AA 1001 | Bearing Frame, 3196 MTX, Cast Iron, Includes Sight Glass and Plugs | 2 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-02-11 | SEA | 2026-03-13 | [5 empty] | 2026-03-13 | 2026-02-02 | TRUE | 41 | 83
Received | Emilka Guerra | 2025-11-11 | PO08425 | Stock | 2026-01-01 | G-262-93 1013 | Frame Adapter, 10", 3196 MTX/LTX, Ductile Iron | 2 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-02-11 | SEA | 2026-03-13 |  | BL: TAOTOR06811 / expected to arrive first week feb |  |  |  | 2026-03-13 | 2026-03-18 | TRUE | 41 | 127
Received | Emilka Guerra | 2025-11-11 | PO08425 | Stock | 2026-01-01 | G-0256-122 1216 | Impeller, 8x10-15G, 3196 XLT, CD4MCu | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-02-11 | SEA | 2026-03-13 | [5 empty] | 2026-03-13 | 2026-02-02 | TRUE | 41 | 83
Received | Emilka Guerra | 2025-11-11 | PO08425 | Stock | 2026-01-01 | G-76230X 2229 | Shaft Sleeve, 13" and 15", 3196 XLT, 316SS | 2 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-02-11 | SEA | 2026-03-13 | [5 empty] | 2026-03-13 | 2026-02-02 | TRUE | 41 | 83
Received | Emilka Guerra | 2025-11-12 | PO08431 |  | 2025-11-27 | AC-98-234-108-001 | Half Seal Cage, 2x2-10 SRL, Cast Iron | 4 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE | 2025-11-27 | LAND | 2025-12-04 |  |  |  |  | Email from supplier confirming package ready to be delivered. on Nov 28th | 2025-12-04 | 2025-12-01 | TRUE | 0 | 19
Received | Emilka Guerra | 2025-11-12 | PO08431 |  | 2025-11-27 | AC-98-234-104-001 | Waterseal Bushing, 2x2-10 SRL, Cast Iron | 1 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE | 2025-11-27 | LAND | 2025-12-04 |  |  |  |  | Email from supplier confirming package ready to be delivered. on Nov 28th | 2025-12-04 | 2025-12-01 | TRUE | 0 | 19
Received | Emilka Guerra | 2025-11-12 | PO08432 |  | 2025-11-17 | AC-98-233-700-003 | Bearing End Cover Gasket, 3x3-10 SRL & SRL-C | 10 | NC Industrial | US | CA WAREHOUSE |  | LAND | [6 empty] | 2025-11-24 | 2025-11-17 | TRUE | -45978 | 5
Received | Amanda Qiao | 2025-11-12 | PO08433 |  | 2025-11-24 | AC-98-233-993-001 | Water Seal Bushing, 3x3-10 SRL-C, Cast Iron | 2 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2025-11-13 | 2025-11-17 | TRUE | -45985 | 5
Received | Amanda Qiao | 2025-11-13 | PO08434 |  | 2025-11-17 |  | Warehouse accessories (pump build) | 1 | Wajax Limited - Mississauga | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2025-11-17 | 2025-11-17 | TRUE | -45978 | 4
Received | Amanda Qiao | 2025-11-13 | PO08434 |  | 2025-11-17 |  | Warehouse accessories (pump build) | 1 | Wajax Limited - Mississauga | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2025-11-17 | 2025-11-17 | TRUE | -45978 | 4
Received | Amanda Qiao | 2025-11-13 | PO08434 |  | 2025-11-17 |  | Warehouse accessories (pump build) | 1 | Wajax Limited - Mississauga | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2025-11-17 | 2025-11-17 | TRUE | -45978 | 4
Received | Amanda Qiao | 2025-11-13 | PO08434 |  | 2025-11-17 |  | Warehouse accessories (pump build) | 1 | Wajax Limited - Mississauga | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2025-11-17 | 2025-11-17 | TRUE | -45978 | 4
Received | Amanda Qiao | 2025-11-13 | PO08434 |  | 2025-11-17 |  | Warehouse accessories (pump build) | 2 | Wajax Limited - Mississauga | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2025-11-17 | 2025-11-17 | TRUE | -45978 | 4
IN TRANSIT | Emilka Guerra | 2025-11-13 | PO08435 | DR Warehouse | 2026-05-01 | AM-LH100S8-CD4-PUMP | Self-Priming Pump, DW-BE4/4-8S, CD4MCu, Pump Only | 1 | AMOS Fluid Technology Co., Ltd | China | DR WAREHOUSE | 2026-01-26 | SEA | 2026-04-09 |  | SHRNA26023670 | expected to arrive 2d to 3rd week of april | left Shanghai for Santo Domingo by sea on Feb 13, 2026 |  | 2026-04-09 |  | FALSE | -95 | -45974 | -6567.7143
IN TRANSIT | Emilka Guerra | 2025-11-13 | PO08435 | DR Warehouse | 2026-05-01 | AM-MH150S12-CD4-PUMP ONLY | Self-Priming Pump, DW-ME6/6-12S, CD4MCu, Pump Only | 1 | AMOS Fluid Technology Co., Ltd | China | DR WAREHOUSE | 2026-01-26 | SEA | 2026-04-09 |  | SHRNA26023670 | expected to arrive 2d to 3rd week of april | left Shanghai for Santo Domingo by sea on Feb 13, 2026 |  | 2026-04-09 |  | FALSE | -95 | -45974 | -6567.7143
IN TRANSIT | Emilka Guerra | 2025-11-13 | PO08435 | DR Warehouse | 2026-05-01 | AM-MH200C14-CD4-PUMP | Self-Priming Pump, DW-ME10/8-14W, CD4MCu, Pump Only | 1 | AMOS Fluid Technology Co., Ltd | China | DR WAREHOUSE | 2026-01-26 | SEA | 2026-04-09 |  | SHRNA26023670 | expected to arrive 2d to 3rd week of april | left Shanghai for Santo Domingo by sea on Feb 13, 2026 |  | 2026-04-09 |  | FALSE | -95 | -45974 | -6567.7143
IN TRANSIT | Emilka Guerra | 2025-11-13 | PO08435 | DR Warehouse | 2026-05-01 | AM-HH200C21-CD4-PUMP | Self-Priming Pump, DW-AE8/6-21W, CD4MCu, Pump Only | 1 | AMOS Fluid Technology Co., Ltd | China | DR WAREHOUSE | 2026-01-26 | SEA | 2026-04-09 |  | SHRNA26023670 | expected to arrive 2d to 3rd week of april | left Shanghai for Santo Domingo by sea on Feb 13, 2026 |  | 2026-04-09 |  | FALSE | -95 | -45974 | -6567.7143
Received | Taylor Cook | 2025-11-14 20:26 | PO08439 |  | 2025-12-01 | AC-52-050-313-000 | Shim Kit, Allis Chalmers CSO, Frame F4D1/F4B5 | 10 | Advanced Engineered Pump Inc. | Canada | CA WAREHOUSE | 2025-12-05 | LAND | [5 empty] | Monday december 8th the Po will be Delivered by the supplier | 2025-11-14 | 2025-12-19 | TRUE | 4 | 34.1488
Received | Emilka Guerra | 2025-11-18 | PO08446 |  | 2025-12-02 | AC-98-231-070-504 | Gland Side Liner, 3x3-10 SRL, Hypalon | 1 | Seal X Supply Inc. | Canada | CA WAREHOUSE |  | LAND | 2025-12-04 | [5 empty] | 2025-12-09 | 2025-12-04 | TRUE | -45993 | 16
Received | Emilka Guerra | 2025-11-18 | PO08446 |  | 2025-12-02 | AC-98-231-071-504 | Suction Side Liner, 3x3-10 SRL, Hypalon | 1 | Seal X Supply Inc. | Canada | CA WAREHOUSE |  | LAND | 2025-12-04 | [5 empty] | 2025-12-09 | 2025-12-04 | TRUE | -45993 | 16
Received | Emilka Guerra | 2025-11-18 | PO08446 |  | 2025-12-02 | AC-98-330-286-504 | Open Impeller 3x3-10 SRL | 1 | Seal X Supply Inc. | Canada | CA WAREHOUSE |  | LAND | 2025-12-04 | [5 empty] | 2025-12-09 | 2025-12-04 | TRUE | -45993 | 16
Received | Ian Trottier | 2025-11-18 | PO08448 | SO18192 | 2026-03-24 | AC-98-432-339-005P | Impeller, 12x10-17, PWO, 5-Vane, 316SS | 1 | Emnor Mechanical Inc. | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2026-03-31 | 2026-04-01 | TRUE | -46105 | 134
Received | Yannett Yeomans | 2025-11-18 | PO08442 | SO18253 | 2026-10-04 | 10548/0003 | Suction Liner 6x8, High Chrome | 5 | Super Cast Limited | China | MX WAREHOUSE |  | SEA | 2026-06-19 |  | LS15TJ2603790 |  | left Tianjin for Ensenada by sea on Mar 22, 2026. |  | 2026-04-16 |  | TRUE
Received | Yannett Yeomans | 2025-11-18 | PO08442 | SO18253 | 2026-10-04 | 10547/0003 | Impeller 6x8, High Chrome | 4 | Super Cast Limited | China | MX WAREHOUSE |  | SEA | 2026-06-19 |  | LS15TJ2603790 |  | left Tianjin for Ensenada by sea on Mar 22, 2026. |  | 2026-04-16 |  | TRUE
Received | Yannett Yeomans | 2025-11-18 | PO08442 | SO18253 | 2026-10-04 | 10544/0003 | Suction Liner 10x12, High Chrome | 4 | Super Cast Limited | China | MX WAREHOUSE |  | SEA | 2026-06-19 |  | LS15TJ2603790 |  | left Tianjin for Ensenada by sea on Mar 22, 2026. |  | 2026-04-16 |  | TRUE
Received | Amanda Qiao | 2025-11-19 | PO08450 |  | 19/11/2025 | GA-5502, CHECK SEAL 9155-0075-981 | Lip Seal (Upper), G-Series VSP | 7 | Wajax Limited - Mississauga | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2025-11-19 | 2025-12-08 | TRUE | #VALUE! | 19
Received | Ian Trottier | 2025-11-20 | PO08452 |  | 2025-12-05 | G-R72360 6956 | Shaft Sleeve, 3405-M, Ni-Chrome Boron On 316SS | 1 | Hisco Pump Inc. | US | CA WAREHOUSE | 2025-12-01 | LAND | 2025-12-03 09:00 |  | COM002112574 |  |  |  | 2025-12-12 | 2025-12-03 | TRUE | -4 | 13
Received | Ian Trottier | 2025-11-20 | PO08454 |  | 2026-01-29 | WO-2104511-001 | Wear Plate, Worthington 6-FRBH-142, 316SS | 2 | M&N Alloy Cast Products, Inc. | US | CA WAREHOUSE |  | LAND | 2026-02-04 | [5 empty] | 2026-02-06 | 2026-02-04 | TRUE | -46051 | 76
Received | Yannett Yeomans | 2025-11-20 | PO08455 | Stock | 2025-12-19 | W-32CWXR | Pump, W-Series 3/2 C-DHR, Natural Rubber | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA |  |  | 1071968361 |  | Prince Rupert, march 1st / Expected to arrive first week of april | delayed due heavy congestion | 2026-02-27 | 2026-03-30 | TRUE | -46010 | 130
Received | Emilka Guerra | 2025-11-21 | PO08456 |  | 2025-11-25 | SKF-34886, G-8690-23660 | Oil Seal (Inboard), 8x6-18 & 10x8-21 SRL-C, Nitrile | 3 | Wajax Limited - Mississauga | Canada | CA WAREHOUSE |  | LAND | December 8th, 2025 |  |  |  |  | Po had corrections / Po confirmed by the supplier on 12/05/2025 | 2025-12-12 | 2025-12-08 | TRUE | -45986 | 17
Received | Emilka Guerra | 2025-11-21 | PO08456 |  | 2025-11-25 | SKF-33700, G-8690-10164 | Oil Seal (Outboard), 8x6-18 & 10x8-21 SRL-C, Nitrile | 3 | Wajax Limited - Mississauga | Canada | CA WAREHOUSE |  | LAND | December 8th, 2025 |  |  |  |  | Po had corrections / Po confirmed by the supplier on 12/05/2025 | 2025-12-12 | 2025-12-08 | TRUE | -45986 | 17
Received | Emilka Guerra | 2025-11-21 | PO08456 |  | 2025-11-25 | SKF-22340 | Bearing Seal (Inboard & Outboard), 5x4-14 SRL/SRL-C, 6x6-15 SRL | 2 | Wajax Limited - Mississauga | Canada | CA WAREHOUSE |  | LAND | December 8th, 2025 |  |  |  |  | Po had corrections / Po confirmed by the supplier on 12/05/2025 | 2025-12-12 | 2025-12-08 | TRUE | -45986 | 17
Received | Emilka Guerra | 2025-11-21 | PO08456 |  | 2025-11-25 | NSK-22318EAE4 or FAG 22318 EAS M C3 or SKF 22318CC/W33, AC-00-813-261-541 | Roller Bearing (Outboard), 8x6-18 & 10x8-21 SRL-C | 4 | Wajax Limited - Mississauga | Canada | CA WAREHOUSE |  | LAND | December 8th, 2025 |  |  |  |  | Po had corrections / Po confirmed by the supplier on 12/05/2025 | 2025-12-12 | 2025-12-08 | TRUE | -45986 | 17
Received | Emilka Guerra | 2025-11-21 | PO08456 |  | 2025-11-25 | NSK-22218EAE4, AC-00-813-261-537 | Roller Bearing (Inboard), 8x6-18 & 10x8-21 SRL-C | 4 | Wajax Limited - Mississauga | Canada | CA WAREHOUSE |  | LAND | December 8th, 2025 |  |  |  |  | Po had corrections / Po confirmed by the supplier on 12/05/2025 | 2025-12-12 | 2025-12-08 | TRUE | -45986 | 17
Received | Emilka Guerra | 2025-11-21 | PO08459 | Stock | 2025-12-19 | W-ZAG65482/A05 | Agitator, 100 to 200 SP, High Chrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA |  |  | 1071968361 |  | Prince Rupert, march 1st / Expected to arrive first week of april | delayed due heavy congestion | 2026-02-27 | 2026-03-30 | TRUE | -46010 | 129
Received | Emilka Guerra | 2025-11-21 | PO08459 | Stock | 2025-12-19 | W-ZAS65813 | Agitator Shaft, 100 to 200 SP, 420SS | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA |  |  | 1071968361 |  | Prince Rupert, march 1st / Expected to arrive first week of april | delayed due heavy congestion | 2026-02-27 | 2026-03-30 | TRUE | -46010 | 129
Received | Emilka Guerra | 2025-11-21 | PO08459 | Stock | 2025-12-19 | W-SP10206A70800, W-SP10206B/A05 | Impeller (Agitator), 100RV-SP, High Chrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA |  |  | 1071968361 |  | Prince Rupert, march 1st / Expected to arrive first week of april | delayed due heavy congestion | 2026-02-27 | 2026-03-30 | TRUE | -46010 | 129
Received | Emilka Guerra | 2025-11-21 | PO08459 | Stock | 2025-12-19 | W-SP10092/A05 | Casing w/Flange, 100RV-SP, High Chrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA |  |  | 1071968361 |  | Prince Rupert, march 1st / Expected to arrive first week of april | delayed due heavy congestion | 2026-02-27 | 2026-03-30 | TRUE | -46010 | 129
Received | Emilka Guerra | 2025-11-21 | PO08459 | Stock | 2025-12-19 | W-RV10005N/D21 | Bearing Assembly, 100ZJL-RV, Ductile Iron Bearing Cylinder, 2100mm Steel Shaft | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA |  |  | 1071968361 |  | Prince Rupert, march 1st / Expected to arrive first week of april | delayed due heavy congestion | 2026-02-27 | 2026-03-30 | TRUE | -46010 | 129
Received | Emilka Guerra | 2025-11-21 | PO08459 | Stock | 2025-12-19 |  | Discharge Pipe, 100ZJL-RV, 2100mm, Steel | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA |  |  | 1071968361 |  | Prince Rupert, march 1st / Expected to arrive first week of april | delayed due heavy congestion | 2026-02-27 | 2026-03-30 | TRUE | -46010 | 129
Received | Emilka Guerra | 2025-11-21 | PO08459 | Stock | 2025-12-19 | W-SP10041/A05 | Back Liner, 100RV-SP, High Chrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA |  |  | 1071968361 |  | Prince Rupert, march 1st / Expected to arrive first week of april | delayed due heavy congestion | 2026-02-27 | 2026-03-30 | TRUE | -46010 | 129
Received | Emilka Guerra | 2025-11-21 | PO08459 | Stock | 2025-12-19 | D1J2311-6 | Suction Cover Liner, 2x3-11, Goulds JC, Frame 1J, High Chrome, OEM# 048940G0001228 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA |  |  | 1071968361 |  | Prince Rupert, march 1st / Expected to arrive first week of april | delayed due heavy congestion | 2026-02-27 | 2026-03-30 | TRUE | -46010 | 129
Received | Emilka Guerra | 2025-11-21 | PO08460 | Stock | 2026-02-01 | G-B02092A 1001 | Frame Foot, 3196 MTX, 8.25" Centerline | 2 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-01-02 | SEA | 2026-03-13 |  | BL: TAOTOR06843 |  |  |  | 2026-03-13 | 2026-02-02 | TRUE | -30 | 73
Received | Emilka Guerra | 2025-11-21 | PO08460 | Stock | 2026-02-01 | G-R100-111 1012 | Stuffing Box Cover, 7" & 8", 3196 MTX, Ductile Iron, Standard Bore, Non-Jacketed | 2 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-01-02 | SEA | 2026-03-13 |  | BL: TAOTOR06843 |  |  |  | 2026-03-13 | 2026-02-02 | TRUE | -30 | 73
Received | Emilka Guerra | 2025-11-21 | PO08460 | Stock | 2026-02-01 | G-247-45 1204 | Casing, 3x4-8G, 3196 MTX, Alloy 20 | 2 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-01-02 | SEA | 2026-03-13 |  | BL# TAOTOR06921 |  |  |  | 2026-03-13 | 2026-04-08 | TRUE | -30 | 138
Received | Emilka Guerra | 2025-11-21 | PO08460 | Stock | 2026-02-01 | G-254-50 1216 | Casing, 6x8-13, 3196 XLT, CD4MCu | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-01-02 | SEA | 2026-03-13 | [5 empty] | 2026-03-13 | 2026-03-18 | TRUE | -30 | 117
Received | Emilka Guerra | 2025-11-21 | PO08460 | Stock | 2026-02-01 | G-R104-707 1216 | Stuffing Box Cover, 13", 3196 XLT, CD4MCu, Standard Bore, Non-Jacketed | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-01-02 | SEA | 2026-03-13 |  | BL: TAOTOR06843 |  |  |  | 2026-03-13 | 2026-02-02 | TRUE | -30 | 73
Received | Emilka Guerra | 2025-11-21 | PO08461 |  | 2026-01-23 | AC-98-434-117-501 | Suction Side Liner, 12x10-25 SRL-C, Natural Rubber | 2 | IGH | Mexico | CA WAREHOUSE | 2026-02-27 | LAND | 2026-03-09 |  |  |  | confirmed SHIPMENT ETD FEB 27, 2026 | Email for POs sent on Jan 28th, 2026 Follow up for SHipment date sent on Feb 6th, 2026 | 2026-02-13 | 2026-03-09 | TRUE | 35 | 108
Received | Emilka Guerra | 2025-11-21 | PO08461 |  | 2026-01-23 | AC-98-332-251-501 | Suction Side Plate, 12x10-25 SRL-C, Natural Rubber | 1 | IGH | Mexico | CA WAREHOUSE | 2026-02-27 | LAND | 2026-03-09 |  |  |  | confirmed SHIPMENT ETD FEB 27, 2026 | Email for POs sent on Jan 28th, 2026 Follow up for SHipment date sent on Feb 6th, 2026 | 2026-02-13 | 2026-03-09 | TRUE | 35 | 108
Received | Emilka Guerra | 2025-11-21 | PO08461 |  | 2026-01-23 | AC-98-434-116-501 | Gland Side Liner, 12x10-25 SRL-C, Natural Rubber | 1 | IGH | Mexico | CA WAREHOUSE | 2026-02-27 | LAND | 2026-03-09 |  |  |  | confirmed SHIPMENT ETD FEB 27, 2026 | Email for POs sent on Jan 28th, 2026 Follow up for SHipment date sent on Feb 6th, 2026 | 2026-02-13 | 2026-03-09 | TRUE | 35 | 108
Received | Emilka Guerra | 2025-11-21 | PO08461 |  | 2026-01-23 | AC-98-431-676-501 | Gland Side Casing, 10x8-21 SRL-C, Cast Iron | 1 | IGH | Mexico | CA WAREHOUSE | 2026-02-27 | LAND | 2026-03-09 |  |  |  | confirmed SHIPMENT ETD FEB 27, 2026 | Email for POs sent on Jan 28th, 2026 Follow up for SHipment date sent on Feb 6th, 2026 | 2026-02-13 | 2026-03-09 | TRUE | 35 | 108
Received | Emilka Guerra | 2025-11-21 | PO08461 |  | 2026-01-23 | AC-98-231-108-503 | Suction Side Liner, 3x3-10 SRL-C, Neoprene | 1 | IGH | Mexico | CA WAREHOUSE | 2026-02-27 | LAND | 2026-03-09 |  |  |  | confirmed SHIPMENT ETD FEB 27, 2026 | Email for POs sent on Jan 28th, 2026 Follow up for SHipment date sent on Feb 6th, 2026 | 2026-02-13 | 2026-03-09 | TRUE | 35 | 108
IN TRANSIT & DELAYED | Emilka Guerra | 2025-11-24 | PO08463 | Stock | 2026-01-05 | AC-98-431-799-001 | Suction Side Casing, 5x4-14 SRL-C, Cast Iron | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-05-26 | SEA | ETA Warehouse mid-august | the vessel depart on May 26 | 20251217-11 Sea Waybill-No. 1074440607 | New follow up email sent on May 8th Naipu Booked vessel for May 22nd | Betty 04/19: still not shipped out, we plan to ship it around May 08. Betty 4/23: Included in Comercial Invoice #20251217-11 | ETD May/8 | 2026-03-16 |  | FALSE | 141 | -45985
Received | Emilka Guerra | 2025-11-24 | PO08463 | Stock | 2026-01-05 | AC-98-331-932-501 | Shaft Assembly, 5x4-14 SRL-C & 5x5-14 SRL, 1045 Steel | 8 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-02-10 | SEA | Around Week of Apr. 30 - May 1 |  | 1072493563 |  |  | YC: Container held in customs / waiting to be loaded onto the train | 2026-03-16 | 2026-04-28 | TRUE | 36 | 155
Received | Emilka Guerra | 2025-11-24 | PO08463 | Stock | 2026-01-05 | D-1J2311-2 | Casing, 2x3-11, Goulds JC, Frame 1J, High Chrome, OEM# 055891G0001228 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-02-10 | SEA | Around Week of Apr. 30 - May 1 |  | 1072493563 |  |  | YC: Container held in customs / waiting to be loaded onto the train | 2026-03-16 | 2026-04-28 | TRUE | 36 | 155 | 22.1429
Received | Emilka Guerra | 2025-11-24 | PO08464 |  | 2025-11-28 | G-R76295 | Lantern Ring, 3196 LTX, Teflon | 2 | Hisco Pump Inc. | US | CA WAREHOUSE | 2025-12-01 | LAND | 2025-12-03 09:00 |  | COM002112574 |  |  |  | 2025-12-23 | 2025-12-03 | TRUE | 3 | 9 | 1.2857
Received | Emilka Guerra | 2025-11-24 | PO08464 |  | 2025-11-28 | GO351-9607-NSN, G-70782 49 5127 | Casing Gasket, 15", 3196 XLT | 4 | Hisco Pump Inc. | US | CA WAREHOUSE | 2025-12-01 | LAND | 2025-12-03 09:00 |  | COM002112574 |  |  |  | 2025-12-23 | 2025-12-03 | TRUE | 3 | 9 | 1.2857
Received | Ian Trottier | 2025-11-25 | PO08466 |  | 2025-12-09 | AC-52-118-681-804 | Mechanical Seal, CSO, Type-9T, Carbon vs' Ceramic/Viton, O-Ring seat | 2 | The Alpha Seal Corporation | US | CA WAREHOUSE |  | LAND | [6 empty] | 2025-12-10 | 2025-12-11 | TRUE | -46000 | 16
Received | Emilka Guerra | 2025-11-25 | PO08467 |  | 2026-01-29 | AC-98-431-882-501 | Gland Side Casing, 2x2-10 SRL, Cast Iron | 1 | IGH | Mexico | CA WAREHOUSE | 2026-02-27 | LAND | 2026-03-10 |  |  |  | confirmed SHIPMENT ETD FEB 27, 2026 | Email for POs sent on Jan 28th, 2026 Follow up for SHipment date sent on Feb 6th, 2026 | 2026-02-19 | 2026-03-09 | TRUE | 29 | 104
Received | Emilka Guerra | 2025-11-25 | PO08469 | Stock | 2026-01-13 | AC-98-232-674-801 | Bearing Cover (Inboard), Allis Chalmers PWO, Frame A2, Oil, Cast Iron | 4 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-01-20 | SEA | 2026-03-24 | [5 empty] | 2026-03-24 | 2026-03-18 | TRUE | 7 | 113
Received | Emilka Guerra | 2025-11-25 | PO08469 | Stock | 2026-01-13 | AC-98-236-257-501 | Packing Gland (2 Half/Set), Allis Chalmers PWO, Group 2, 316SS | 3 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-02-11 | SEA | 2026-03-24 |  | BL# TAOTOR06921 |  |  |  | 2026-03-24 | 2026-04-08 | TRUE | 29 | 134
Received | Emilka Guerra | 2025-11-25 | PO08469 | Stock | 2026-01-13 | G-0B10592 1216 | Impeller, 3x4-13, 3196 LTX, CD4MCu, 6-Vane | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-02-11 | SEA | 2026-03-24 |  | BL# TAOTOR06921 |  |  |  | 2026-03-24 | 2026-04-08 | TRUE | 29 | 134
Received | Ian Trottier | 2025-11-25 | PO08470 |  | 2026-03-03 | M&N P/M# 5930/CD4, WO-2216122-CD4 | Impeller, Worthington 16FRBH224, CD4 | 1 | M&N Alloy Cast Products, Inc. | US | CA WAREHOUSE |  | LAND | 2026-01-14 |  |  |  |  | Arrived 01/14/2026 | 2025-11-26 | 2026-01-14 | TRUE | -46084 | 50
Received | Yannett Yeomans | 2025-11-25 | PO08471 |  | 2026-03-03 | 1904-10-23 | Impeller, Worthington 3-FRBH-141, CD4MCu | 1 | M&N Alloy Cast Products, Inc. | US | CA WAREHOUSE |  | LAND | 2026-03-10 |  |  |  |  | Arrived 01/09/2026 | 2026-03-10 | 2026-01-09 | TRUE | -46084 | 45
Received | Leriel Reyes | 2025-11-26 | PO08472 |  | 2026-01-14 | G-22BF1JAA5 | Pump, 1x2-7, 3656-S, Gould's, Closed Coupled, Cast Iron, Bronze Fitted | 1 | Interpump Ltd | Canada | CA WAREHOUSE |  | LAND | ETA Jan 16th, 2026 | [5 empty] | 2026-01-16 | 2026-01-21 | TRUE | -46036 | 56
Received | Leriel Reyes | 2025-11-26 | PO08472 |  | 14/01/2026 | G-RPK-3656-S | Seal Repair Kit, 3656-S | 1 | Interpump Ltd | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2026-01-16 | 2026-01-21 | TRUE | #VALUE! | 56
Received | Yannett Yeomans | 2025-11-27 | PO08474 |  | 2026-01-29 | SA-567160 | Gasket, Sala STHM-33WFR, Rubber | 4 | Hyperflo | Canada | CA WAREHOUSE |  | LAND | 2026-02-13 |  |  |  |  | Arrived 12/15/2025 | 2026-02-13 | 2025-12-15 | TRUE | -46051 | 18
Received | Yannett Yeomans | 2025-11-27 | PO08475 |  | 2026-01-29 | AC-98-432-037-001 | Bearing Cylinder Strap (Set of 2), 8x6/10x8 SRL-C, Cast Iron | 1 | IGH | Mexico | CA WAREHOUSE |  | LAND | [6 empty] | 2026-02-19 | 2026-03-09 | TRUE | -46051 | 102
Received | Yannett Yeomans | 2025-11-27 | PO08475 |  | 2026-01-29 | AC-98-332-762-801 | Stuffing Box, 12x10-25 or 14x12-29 SRL-C, Cast Iron | 1 | IGH | Mexico | CA WAREHOUSE |  | LAND | [6 empty] | 2026-02-19 | 2026-03-09 | TRUE | -46051 | 102
Received | Ian Trottier | 2025-11-27 | PO08476 |  | 2025-12-02 | G-B00294A 6956 | Shaft Sleeve, 3175-S, 316SS, Ni-Chrome Boron | 4 | Hisco Pump Inc. | US | CA WAREHOUSE | 2025-12-01 | LAND | 2025-12-03 09:00 |  | COM002112574 |  |  |  | 2025-12-09 | 2025-12-03 | TRUE | -1 | 6
Received | Ian Trottier | 2025-11-27 | PO08476 |  | 2025-12-02 | G-B00295A 6956 | Shaft Sleeve, 3175-M, 316SS, Ni-Chrome Boron | 1 | Hisco Pump Inc. | US | CA WAREHOUSE | 2025-12-01 | LAND | 2025-12-03 09:00 |  | COM002112574 |  |  |  | 2025-12-09 | 2025-12-03 | TRUE | -1 | 6
Received | Ian Trottier | 2025-11-27 | PO08476 |  | 2025-12-02 | G-B00296A 6956 | Shaft Sleeve, 3175-L, 316SS, Ni-Chrome Boron | 3 | Hisco Pump Inc. | US | CA WAREHOUSE | 2025-12-01 | LAND | 2025-12-03 09:00 |  | COM002112574 |  |  |  | 2025-12-09 | 2025-12-03 | TRUE | -1 | 6
Received | Yannett Yeomans | 2025-11-28 | PO08478 |  | 2025-12-15 | SA-013733-M2 | Wear Disc, 44 WFR, Sala STGVA-180, High Chrome | 1 | Hyperflo | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2025-12-22 | 2025-12-15 | TRUE | -46006 | 17
Received | Ian Trottier | 2025-11-28 | PO08479 |  | 2025-12-05 | LPE-0875-1250-B48, G-D08717A01 6241 | Thrust Bearing Labyrinth Seal (Outboard) w/O-Rings, 3196 STX, Carbon Teflon w/Viton | 1 | Hisco Pump Inc. | US | CA WAREHOUSE | 2025-12-01 | LAND | 2025-12-03 09:00 |  | COM002112574 |  |  |  | 2025-11-28 | 2025-12-03 | TRUE | -4 | 5
Received | Ian Trottier | 2025-11-28 | PO08479 |  | 2025-12-05 | G-D08717A02 6241 | Radial Bearing Labyrinth Seal (Inboard) w/O-Rings, 3196 STX, Carbon Teflon w/Viton | 1 | Hisco Pump Inc. | US | CA WAREHOUSE | 2025-12-01 | LAND | 2025-12-03 09:00 |  | COM002112574 |  |  |  | 2025-11-28 | 2025-12-03 | TRUE | -4 | 5
Received | Ian Trottier | 2025-11-28 | PO08480 |  | 2025-12-01 | G-262-93 1013 | Frame Adapter, 10", 3196 MTX/LTX, Ductile Iron | 1 | Hisco Pump Inc. | US | CA WAREHOUSE | 2025-12-01 | LAND | 2025-12-03 09:00 |  | COM002112574 |  |  |  | 2025-11-28 | 2025-12-03 | TRUE | 0 | 5
Received | Yannett Yeomans | 2025-11-28 | PO08481 |  | 2025-12-01 | AC-98-332-015-815 | Fastener Kit (Suction Side Plate), 8x6-18 SRL-C | 5 | M.B. Fasteners Inc. | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2025-12-08 | 2025-12-05 | TRUE | -45992 | 7
Received | Yannett Yeomans | 2025-11-28 | PO08481 |  | 2025-12-01 | AC-98-332-015-808 | Fastener Kit (Gland Side Liner), 8x6-18 & 10x8-21 SRL-C | 5 | M.B. Fasteners Inc. | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2025-12-08 | 2025-12-05 | TRUE | -45992 | 7
Received | Emilka Guerra | 2025-12-01 | PO08482 |  | 2025-12-04 | AC-98-131-246-504 AC-52-108-475-009 | Deflector (Water Slinger), 3x3-10 SRL/SRL-C, Neoprene/Steel | 5 | Advanced Engineered Pump Inc. | Canada | CA WAREHOUSE | 2025-12-05 | LAND | [5 empty] | Monday december 8th the Po will be Delivered by the supplier | 2025-12-29 | 2025-12-19 | TRUE | 1 | 18
Received | Amanda Qiao | 2025-12-01 | PO08483 |  | 2026-02-06 | AC-98-530-755-501 | Gland Side Casing, 3x3-10 SRL-C HD, Carbon Steel | 1 | IGH | Mexico | CA WAREHOUSE |  | LAND | [6 empty] | 2026-02-23 | 2026-03-09 | TRUE | -46059 | 98
Received | Ian Trottier | 2025-12-01 | PO08484 | SO18242 | 2026-02-09 | AC-52-319-380-001 | Frame Foot, Allis Chalmers CSO, Frame F4D1, fits 11" and 13" pumps, Cast Iron | 3 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-04-09 | LAND | 2026-02-12 | [5 empty] | 2026-03-09 | 2026-04-14 | TRUE | 59 | 134
Received | Ian Trottier | 2025-12-02 | PO08485 |  | 2025-12-08 | DU-DY43289A-CD4 | Casing, (Recessed), 3x3R-10, Durco Mark 2&3, Group 2, CD4 | 1 | Hisco Pump Inc. | US | CA WAREHOUSE | 2025-12-08 | LAND | 2025-12-12 | [5 empty] | 2025-12-03 | 2025-12-11 | TRUE | 0 | 9
Received | Ian Trottier | 2025-12-02 | PO08488 |  | 2025-12-16 | WO-9140000-034 | O-Ring (Impeller Nut), Worthington FRBH Frame 4, Buna | 1 | Hisco Pump Inc. | US | CA WAREHOUSE | 2025-12-08 | LAND | 2025-12-12 | [5 empty] | 2025-12-29 | 2025-12-11 | TRUE | -8 | 9
Received | Ian Trottier | 2025-12-02 | PO08488 |  | 2025-12-16 | WO-9070029-011 | Sleeve Gasket, Worthington FRBH, Frame 4 | 1 | Hisco Pump Inc. | US | CA WAREHOUSE | 2025-12-08 | LAND | 2025-12-12 | [5 empty] | 2025-12-29 | 2025-12-11 | TRUE | -8 | 9
Received | Ian Trottier | 2025-12-02 | PO08488 |  | 2025-12-16 | WO-9070000-013 | Casing Gasket, 22", Worthington FRBH | 1 | Hisco Pump Inc. | US | CA WAREHOUSE | 2025-12-08 | LAND | 2025-12-12 | [5 empty] | 2025-12-29 | 2025-12-11 | TRUE | -8 | 9
Received | Emilka Guerra | 2025-12-03 | PO08489 | Stock - SO18359 | 2026-01-14 | AC-98-233-733-513 | Deflector (Water Slinger), 8x6-18 & 10x8-21 SRL-C, Neoprene/Steel | 10 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-02-10 | SEA | Around Week of Apr. 30 - May 1 |  | TCLU8795637 |  | Naipu: confirmed shipped out | Email for follow up sent on April 10 | 2026-03-25 | 2026-04-28 | TRUE | 27 | 146
Received | Emilka Guerra | 2025-12-03 | PO08489 | Stock - SO18359 | 2026-01-14 | D-1J2311-14 | Suction Cover, 2x3-11, Goulds JC, Frame 1J, High Chrome, OEM# 050387G0001228 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-02-10 | SEA | Around Week of Apr. 30 - May 1 |  | TCLU8795637 |  | Naipu: confirmed shipped out | Email for follow up sent on April 10 | 2026-03-25 | 2026-04-28 | TRUE | 27 | 146
Received | Emilka Guerra | 2025-12-03 | PO08489 | Stock - SO18359 | 2026-01-14 | AC-98-331-936-801 | Bearing Cover (Inboard), 8x6-18 & 10x8-21 SRL-C, Cast Iron | 5 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-01-28 | SEA | March 27–31 |  | 1071968361 |  | Prince Rupert, march 1st / Expected to arrive first week of april |  | 2026-03-25 | 2026-03-30 | TRUE | 14 | 117
Received | Emilka Guerra | 2025-12-03 | PO08489 | Stock - SO18359 | 2026-01-14 | AC-98-331-901-801 | Bearing Cover (Outboard), 8x6-18 & 10x8-21 SRL-C, Cast Iron | 5 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-01-28 | SEA | March 27–31 |  | 1071968361 |  | Prince Rupert, march 1st / Expected to arrive first week of april |  | 2026-03-25 | 2026-03-30 | TRUE | 14 | 117
Received | Ian Trottier | 2025-12-03 | PO08490 |  | 2026-02-11 | G-243-58-2-1216 | Impeller W/Rings, 3405-M 6x8-17DV, CD4MCu | 1 | M&N Alloy Cast Products, Inc. | US | CA WAREHOUSE |  | LAND | 2026-01-27 | [5 empty] | 2025-12-04 | 2026-01-27 | TRUE | -46064 | 55
Received | Emilka Guerra | 2025-12-03 | PO08491 |  | 2025-12-17 | AC-98-233-732-001 | Waterseal Bushing, 8x6-18 & 10x8-21 SRL-C, Steel | 2 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE |  | LAND | ETA Jan 7th, 2026 |  |  |  |  | Arrived 01/14/2026 | 2026-01-07 | 2026-01-14 | TRUE | -46008 | 42
Received | Emilka Guerra | 2025-12-03 | PO08491 |  | 2025-12-17 | AC-98-233-731-001 | Half Seal Cage, 8x6-18 & 10x8-21 SRL-C, Steel | 2 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE |  | LAND | ETA Jan 7th, 2026 |  |  |  |  | Arrived 01/14/2026 | 2026-01-07 | 2026-01-14 | TRUE | -46008 | 42
Received | Emilka Guerra | 2025-12-03 | PO08491 |  | 2025-12-17 | AC-98-233-813-001 | Neck Bushing, 5x4/5x5/6x6 SRL & SRL-C | 2 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE |  | LAND | ETA Jan 7th, 2026 |  |  |  |  | Arrived 01/14/2026 | 2026-01-07 | 2026-01-14 | TRUE | -46008 | 42
Received | Ian Trottier | 2025-12-03 | PO08492 |  | 2025-12-12 | G-77-59 1001 | Bearing Housing, 3405-M, Cast Iron | 2 | Hisco Pump Inc. | US | CA WAREHOUSE | 2025-12-08 | LAND | 2025-12-12 | [5 empty] | 2025-12-03 | 2025-12-11 | TRUE | -4 | 8
Received | Ian Trottier | 2025-12-03 | PO08492 |  | 2025-12-12 | G-R72350 6956 | Shaft Sleeve, 3405-M, 316SS NCB Hardcoated | 1 | Hisco Pump Inc. | US | CA WAREHOUSE | 2025-12-08 | LAND | 2025-12-12 | [5 empty] | 2025-12-03 | 2025-12-11 | TRUE | -4 | 8
Received | Ian Trottier | 2025-12-03 | PO08492 |  | 2025-12-12 | G-R72360 6956 | Shaft Sleeve, 3405-M, Ni-Chrome Boron On 316SS | 1 | Hisco Pump Inc. | US | CA WAREHOUSE | 2025-12-08 | LAND | 2025-12-12 | [5 empty] | 2025-12-03 | 2025-12-11 | TRUE | -4 | 8 | 1.1429
Received | Ian Trottier | 2025-12-03 | PO08492 |  | 2025-12-12 | G-90285-1203 | Stuffing Box Bushing, 3405-L & 3316-L, 316SS | 2 | Hisco Pump Inc. | US | CA WAREHOUSE | 2025-12-08 | LAND | 2025-12-12 | [5 empty] | 2025-12-03 | 2025-12-11 | TRUE | -4 | 8 | 1.1429
Received | Emilka Guerra | 2025-12-03 | PO08497 | SO18347 | 2026-01-02 | 103127/1512 | Labyrinth Lock Nut, 8/6 to 14/12 F-AH, Metric | 10 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | 2026-03-12 | [5 empty] | 2026-03-12 | 2025-12-29 | TRUE | -46024 | 26
Received | Emilka Guerra | 2025-12-03 | PO08497 | SO18347 | 2026-01-02 | W-RSL30029/A05 | Expeller Ring, 300 RSL, High Chrome | 1 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | 2026-03-12 |  |  |  |  | Remaining parts sent Jan 18 / ETA Feb 15 to Prince Rupert | 2026-03-12 | 2025-12-29 | TRUE | -46024 | 26
Received | Emilka Guerra | 2025-12-03 | PO08497 | SO18347 | 2026-01-02 | W-RSL30029/A05 | Expeller Ring, 300 RSL, High Chrome | 2 | Super Cast Limited | China | CA WAREHOUSE | 2026-01-29 | SEA | 2026-03-12 |  |  |  | left Tianjin for Toronto by sea on Jan 29, 2027 |  | 2026-03-12 | 2025-12-29 | TRUE | 27 | 26
Received | Gerardo Hernandez | 2025-12-04 | PO08498 |  | 2025-12-25 | BG-A-402V | Mechanical Seal, Bell & Gossett, E-80 4x4-7B, Carbon/Ceramic/304SS | 20 | The Alpha Seal Corporation | US | CA WAREHOUSE |  | LAND | [6 empty] | 2025-12-04 | 2025-12-17 | TRUE | -46016 | 13
Received | Amanda Qiao | 2025-12-05 | PO08502 |  | 2026-01-12 | 81708064 | Single Cartridge Seal, 1 3/8", John Crane 4600 Series, 3196 STX or Durco Mark 3 Group 1, Standard Bore, Carbon vs Silicon Carbide w/Viton Elastomers | 10 | John Crane Canada Inc. | Canada | CA WAREHOUSE |  | LAND | [5 empty] | arrived 01/09/2026 | 2026-01-12 | 2026-01-09 | TRUE | -46034 | 35
Received | Ian Trottier | 2025-12-05 | PO08504 |  | 2025-12-19 | AC-52-126-488-803 | Mechanical Seal, Type-21, Allis-Chalmers 8000 Series, Carbon vs' Ni-Resist w/EPR Elastom | 1 | Advanced Engineered Pump Inc. | Canada | CA WAREHOUSE |  | LAND | ETA Jan 9th, 2026 | [5 empty] | 2026-01-09 | 2025-12-19 | TRUE | -46010 | 14
DELAYED PRODUCTION | Yannett Yeomans | 2025-12-05 | PO08503 | SO18368 | 19/03/26 | DSC-JHS20/16-560/0503 | Horizontal Split Case Pump, XS400-560, 420SS | 1 | Super Cast Limited | China | MX WAREHOUSE |  | SEA |  |  |  |  | Hunnan delayed delivery date to april 20 |  | 2026-03-20 |  | FALSE
DELAYED PRODUCTION | Yannett Yeomans | 2025-12-05 | PO08503 | SO18368 | 19/03/26 | 10637/2001 | Set of Coupling and Coupling Guard XS400-560, Cast Iron | 1 | Super Cast Limited | China | MX WAREHOUSE |  | SEA |  |  |  |  | Hunnan delayed delivery date to april 20 |  | 2026-03-20 |  | FALSE
DELAYED PRODUCTION | Yannett Yeomans | 2025-12-05 | PO08503 | SO18368 | 19/03/26 | 10638/1501 | Common base XS400-560I, Carbon Steel | 1 | Super Cast Limited | China | MX WAREHOUSE |  | SEA |  |  |  |  | Hunnan delayed delivery date to april 20 |  | 2026-03-20 |  | FALSE
Received | Ian Trottier | 2025-12-08 | PO08506 |  | 2026-03-02 | AC-52-217-769-504 | Rear Wear Plate, 10x8-17, Allis Chalmers CW, High Chrome | 1 | M&N Alloy Cast Products, Inc. | US | CA WAREHOUSE |  | LAND | 2026-02-24 | [5 empty] | 2025-12-08 | 2026-02-24 | TRUE | -46083 | 78
Received | Yannett Yeomans | 2025-12-08 | PO08507 | SO17489 | 2025-12-17 | GA-24073 | Discharge Pipe, 48", G-Series 2.5" VSP, 1000 Series, Neoprene Lined Inside and Out | 1 | IGH | Mexico | CA WAREHOUSE |  | LAND | [6 empty] | 2025-12-24 | 2026-03-09 | TRUE | -46008 | 91
Received | Yannett Yeomans | 2025-12-08 | PO08508 |  | 2025-12-12 | AC-52-235-695-005 | Oil Slinger, Allis Chalmers CSO, Steel | 3 | Advanced Engineered Pump Inc. | Canada | CA WAREHOUSE |  | LAND | ETA Dec 26th, 2025 | [5 empty] | 2025-12-26 | 2025-12-19 | TRUE | -46003 | 11
Received | Yannett Yeomans | 2025-12-08 | PO08508 |  | 2025-12-12 | AC-98-233-193-501 | Slinger Assembly, PWO Frame 2, Oil | 3 | Advanced Engineered Pump Inc. | Canada | CA WAREHOUSE |  | LAND | ETA Dec 26th, 2025 | [5 empty] | 2025-12-26 | 2025-12-19 | TRUE | -46003 | 11
Received | Yannett Yeomans | 2025-12-08 | PO08509 |  | 2025-12-11 | AC-52-431-816-007 | Casing Gasket, 10", Allis Chalmers CSO | 10 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND | ETA Dec 30th, 2025 | [5 empty] | 2025-12-30 | 2025-12-19 | TRUE | -46002 | 11
Received | Yannett Yeomans | 2025-12-08 | PO08509 | Stock | 2026-01-11 | G-R76293 | Lantern Ring, 3196 MTX, Teflon | 4 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND | ETA Dec 30th, 2025 |  |  |  |  | Arrived 12/19/2025 | 2025-12-30 | 2025-12-19 | TRUE | -46033 | 11
Received | Yannett Yeomans | 2025-12-08 | PO08510 |  | 2025-12-12 | Timken National 416271 | Oil Seal, Goulds JC, Frame 3J | 10 | Wajax Limited - Mississauga | Canada | CA WAREHOUSE |  | LAND | ETA Dec 22nd, 2025 | [5 empty] | 2025-12-22 | 2025-12-15 | TRUE | -46003 | 7
Received | Yannett Yeomans | 2025-12-08 | PO08511 | SO18377 | 2026-02-16 | AC-98-5414-HC2 | Impeller (Nesting Design), 5x4-14 SRL-C, High Chrome, 3-Piece Design | 2 | IGH | Mexico | CA WAREHOUSE |  | LAND | [6 empty] | 2026-03-02 | 2026-03-09 | TRUE | -46069 | 91
Received | Ian Trottier | 2025-12-08 | PO08512 | SO17211 | 2025-12-16 | G-RC01298A 1203 | Gland Assembly, 3196 LTX, 316SS | 1 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND | [6 empty] | 2025-12-08 | 2025-12-19 | TRUE | -46007 | 11
Received | Ian Trottier | 2025-12-08 | PO08512 | SO17211 | 2025-12-16 | G-0B10592 1216 | Impeller, 3x4-13, 3196 LTX, CD4MCu, 6-Vane | 1 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND | [6 empty] | 2025-12-08 | 2025-12-19 | TRUE | -46007 | 11
Received | Leriel Reyes | 2025-12-09 | PO08514 | Quote # 17540 | 2026-01-05 | BG-E-80-4x4-7B-SS-5HP | Vertical Inline Pump, Bell & Gossett, E-80 4x4, 7B, Stainless Steel/Cast Iron | 1 | Bramham Bros Limited | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2026-01-07 | 2026-03-05 | TRUE | -46027 | 86
Received | Emilka Guerra | 2025-12-09 | PO08515 | Stock | 2026-01-27 | G-262-94 1013 | Frame Adapter, 13", 3196 MTX/LTX, Ductile Iron | 3 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-01-20 | SEA | 2026-04-07 | [5 empty] | 2026-04-07 | 2026-03-18 | TRUE | -7 | 99
Received | Emilka Guerra | 2025-12-09 | PO08515 | Stock | 2026-01-27 | G-R100-534 1012 | Stuffing Box Cover, 13 ", 3196 LTX, Ductile Iron, Standard Bore, Non-Jacketed | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-02-11 | SEA | 2026-04-07 |  | BL# TAOTOR06921 |  |  |  | 2026-04-07 | 2026-04-08 | TRUE | 15 | 120
Received | Emilka Guerra | 2025-12-09 | PO08515 | Stock | 2026-01-27 | G-249-59 1012 | Casing, 3x4-13, 3196 MTX/LTX, Ductile Iron | 2 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-02-11 | SEA | 2026-04-07 |  | BL# TAOTOR06921 |  |  |  | 2026-04-07 | 2026-04-08 | TRUE | 15 | 120
Received | Emilka Guerra | 2025-12-09 | PO08516 |  | 2025-12-12 | N1300-0393, G-58101 393 | Bearing Housing Retaining Ring, 3196 MTX, Carbon Steel | 4 | BDI Canada Inc. | Canada | CA WAREHOUSE |  | LAND | 2025-12-12 | [5 empty] | 2025-12-22 | 2025-12-12 | TRUE | -46003 | 3
IN TRANSIT & DELAYED | Ian Trottier | 2025-12-10 | PO08518 | Stock - JC 1J - 1x1.5-11 Project | 2026-02-06 | D-1J11511-10 | Impeller, 1x1.5-11, Goulds JC, Frame 1J, High Chrome, OEM# 056185G4701228 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-05-26 | SEA | ETA Warehouse mid-august | the vessel depart on May 26 | 20251217-11 Sea Waybill-No. 1074440607 | reverse engineered | Betty 04/19: we can ship it after our Labor day holiday, around May 08. Betty 4/23: Included in Comercial Invoice #20251217-11 | email sent on April 17th | 2026-04-17 |  | FALSE | 109 | -46001
IN TRANSIT & DELAYED | Ian Trottier | 2025-12-10 | PO08518 | Stock - JC 1J - 1x1.5-11 Project | 2026-02-06 | D-1J11511-2 | Casing, 1x1.5-11, Goulds JC, Frame 1J, High Chrome, OEM# 056185G5101228 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-05-26 | SEA | ETA Warehouse mid-august | the vessel depart on May 26 | 20251217-11 Sea Waybill-No. 1074440607 | reverse engineered | Betty 04/19: we can ship it after our Labor day holiday, around May 08. Betty 4/23: Included in Comercial Invoice #20251217-11 | email sent on April 17th | 2026-04-17 |  | FALSE | 109 | -46001 | -6571.5714
IN TRANSIT & DELAYED | Ian Trottier | 2025-12-10 | PO08518 | Stock - JC 1J - 1x1.5-11 Project | 2026-02-06 | D-1J11511-6 | Suction Cover Liner, 1x1.5-11, Goulds JC, Frame 1J, High Chrome, OEM# 048935G0001228 | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-05-26 | SEA | ETA Warehouse mid-august | the vessel depart on May 26 | 20251217-11 Sea Waybill-No. 1074440607 | reverse engineered | Betty 04/19: we can ship it after our Labor day holiday, around May 08. Betty 4/23: Included in Comercial Invoice #20251217-11 | email sent on April 17th | 2026-04-17 |  | FALSE | 109 | -46001 | -6571.5714
IN TRANSIT & DELAYED | Ian Trottier | 2025-12-10 | PO08518 | Stock - JC 1J - 1x1.5-11 Project | 2026-02-06 | D-1J11511-14 | Suction Cover, 1x1.5-11, Goulds JC, Frame 1J, High Chrome, OEM# 050385G0001228 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-05-26 | SEA | ETA Warehouse mid-august | the vessel depart on May 26 | 20251217-11 Sea Waybill-No. 1074440607 | reverse engineered | Betty 04/19: we can ship it after our Labor day holiday, around May 08. Betty 4/23: Included in Comercial Invoice #20251217-11 | email sent on April 17th | 2026-04-17 |  | FALSE | 109 | -46001 | -6571.5714
IN TRANSIT & DELAYED | Ian Trottier | 2025-12-10 | PO08518 | Stock - JC 1J - 1x1.5-11 Project | 2026-02-06 | D-1x1.5-11-JC-HC | Pump, 1x1.5-11, Dynapro DC, Frame 1J, High Chrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-05-26 | SEA | ETA Warehouse mid-august | the vessel depart on May 26 | 20251217-11 Sea Waybill-No. 1074440607 | reverse engineered | Betty 04/19: we can ship it after our Labor day holiday, around May 08. Betty 4/23: Included in Comercial Invoice #20251217-11 | email sent on April 17th | 2026-04-17 |  | FALSE | 109 | -46001 | -6571.5714
Received | Ian Trottier | 2025-12-10 | PO08519 | SO18198 | 2026-03-13 | G-050619G000 1228 | Suction Cover, 8x10-18, Goulds JC Frame 4J, High Chrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-04-17 | SEA | ETA Warehouse June 10-15 |  | BL 1073610888 | EG: Included in Invoice # 20251212-11A | Betty confirmed shipment | Email requesting status sent on March 19th | 2026-05-29 | 2026-06-01 | TRUE | 35 | 173 | 24.7143
Received | Ian Trottier | 2025-12-10 | PO08520 |  | 2026-02-25 | MN# 71 | Impeller, 8x4-17, Allis Chalmers PWO, 317SS | 1 | M&N Alloy Cast Products, Inc. | US | CA WAREHOUSE |  | LAND | [5 empty] | Arrived 01/14/2026 | 2026-03-18 | 2026-01-14 | TRUE | -46078 | 35 | 5
IN TRANSIT & DELAYED | Jeff Bell | 2025-12-11 | PO08522 | SO16270 | 2026-02-23 | 150ZJ-F-HE2. 8/6 F-AH w/HE Impeller | Pump, W-Series, 8/6 DH, 150ZJF-HE, 28% Ultrachrome, Corrosion Resistant | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | BARRICK DIRECT SHIPPING | 2026-04-16 | SEA | Around June 5 - 10 |  | LS15TJ2603881 | Thursday 19th, march 2026 | The new ETD Tianjin is Apr 16.. shipped out. ✅ Shipping docs and pictures will be shared with you by Monday. The ETA Caucedo is June 5 to 10 | was delayed by draiwng confirmation, unable to come out until end of Feb. // now in Naipu's workshop, waiting for Naipu's PO08522 to ship together | 2026-04-05 |  | FALSE | 52 | -46002 | -6571.7143
Received | Amanda Qiao | 2025-12-12 | PO08524 |  | 2025-12-19 | DU-MY50754A82-CD4 | Impeller, 1.5x1-82, Durco Mark 3 Group 1, CD4MCu, Reverse Vane | 2 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND | ETA Dec 26th, 2025 | [5 empty] | 2025-12-26 | 2025-12-19 | TRUE | -46010 | 7
Received | Amanda Qiao | 2025-12-12 | PO08524 |  | 2025-12-19 | G-076781 1216 | Impeller, 1x1.5-6, 3196 STX, CD4MCu, 5-Vane | 2 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND | ETA Dec 26th, 2025 | [5 empty] | 2025-12-26 | 2025-12-19 | TRUE | -46010 | 7
Received | Amanda Qiao | 2025-12-12 | PO08524 |  | 2025-12-19 | DU-GUARD-M3G1 | Coupling Guard, Durco Mark 3 Group 1, Steel Fabricated, Drum Style | 1 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND | ETA Dec 26th, 2025 | [5 empty] | 2025-12-26 | 2025-12-19 | TRUE | -46010 | 7
Received | Amanda Qiao | 2025-12-12 | PO08525 | SO17581 Pump build, SO17839 Pump build | 2025-12-17 | BT-P148 | Baseplate, PoxyBase Plus Black Polymer Base, Size 148 | 2 | BaseTek, LLC | US | CA WAREHOUSE |  | LAND | 2025-12-18 |  |  |  |  | Item Pending | 2025-12-12 | 2025-12-18 | TRUE | -46008 | 6
Received | Emilka Guerra | 2025-12-12 | PO08530 | SO18354 | 2026-02-06 | W-TC3191/A05 | Impeller, 3/3 TC, High Chrome | 1 | Hebei Aisiengai Machinery and Equipment Sales Co., Ltd | China | BARRICK CONSOLIDATED | 2026-03-12 | SEA | Around Week of Apr. 30 - May 1 |  | ETD Prince Rupert: Apr 4, 2026. |  | left Tianjin for Toronto 03/12/2026 |  | 2026-04-17 | 2026-04-27 | TRUE | 34 | 136 | 19.4286
Received | Emilka Guerra | 2025-12-12 | PO08530 | SO18354 | 2026-02-06 | W-TC3041MS1/A05 | Back Liner, 3/3 TC, High Chrome | 1 | Hebei Aisiengai Machinery and Equipment Sales Co., Ltd | China | BARRICK CONSOLIDATED | 2026-03-12 | SEA | Around Week of Apr. 30 - May 1 |  | ETD Prince Rupert: Apr 4, 2026. |  | left Tianjin for Toronto 03/12/2026 |  | 2026-04-17 | 2026-04-27 | TRUE | 34 | 136 | 19.4286
Received | Emilka Guerra | 2025-12-12 | PO08530 | SO18354 | 2026-02-06 | MS-3/3TC-316SS | Mechanical Seal, 3/3 TC, 316SS | 1 | Hebei Aisiengai Machinery and Equipment Sales Co., Ltd | China | BARRICK CONSOLIDATED | 2026-03-12 | SEA | Around Week of Apr. 30 - May 1 |  | ETD Prince Rupert: Apr 4, 2026. |  | left Tianjin for Toronto 03/12/2026 |  | 2026-04-17 | 2026-04-27 | TRUE | 34 | 136 | 19.4286
Received | Emilka Guerra | 2025-12-15 | PO08534 | Stock - SO18600 | 2025-12-19 | G-R102-871 2238 | Shaft (Sleeve Type), 3175-S, 4140 Steel | 4 | Renewal Services Inc. | Canada | CA WAREHOUSE | 2025-12-19 | LAND | 2026-01-12 | [5 empty] | 2026-01-12 | 2026-02-02 | TRUE | 0 | 49
Received | Emilka Guerra | 2025-12-15 | PO08534 | Stock - SO18600 | 2025-12-19 | G-R102-871 2238 | Shaft (Sleeve Type), 3175-S, 4140 Steel | 4 | Renewal Services Inc. | Canada | CA WAREHOUSE |  | LAND | [5 empty] | FOllow up on Shipping sent on 01/16/2026 | 2026-01-12 | 2026-02-02 | TRUE | -46010 | 49
Received | Yannett Yeomans | 2025-12-15 | PO08536 | Stock | 2026-01-15 | D-2x3-11-JC-HC | Pump, 2x3-11, Dynapro DC, Frame 1J, High Chrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-01-15 | SEA | 2026-03-26 |  | BL 1073610888 | EG: Included in Invoice # 20251212-11A |  | Email requesting status sent on March 19th | 2026-01-15 | 2026-06-01 | TRUE | 0 | 168
Received | Emilka Guerra | 2025-12-15 | PO08538 | Stock - SO18635 - SO18730 - SO18841 - SO18898 - SO18929 | 2026-02-02 | DU-CY55737AK-DI | Bearing Housing Foot, 10" & 13" Pump, Durco Mark 3 Group 2, Ductile Iron Lead time: 7 weeks | 3 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-01-20 | SEA | 2026-04-17 | [5 empty] | 2026-04-17 | 2026-03-18 | TRUE | -13 | 93 | 13.2857
Received | Emilka Guerra | 2025-12-15 | PO08538 | Stock - SO18635 - SO18730 - SO18841 - SO18898 - SO18929 | 2026-02-02 | G-247-46 1012 | Casing, 3x4-8G, 3196 MTX, Ductile Iron | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-02-11 | SEA | 2026-04-17 |  | BL# TAOTOR06921 |  |  |  | 2026-04-17 | 2026-04-08 | TRUE | 9 | 114
Received | Emilka Guerra | 2025-12-15 | PO08538 | Stock - SO18635 - SO18730 - SO18841 - SO18898 - SO18929 | 2026-02-02 | G-256-65 1216 | Casing, 8x10-15G, 3196 XLT, CD4MCu | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-03-23 | SEA | 2026-04-17 |  | BL# TAOTOR06921 / DYNC-112 |  | expected to be transported to Qingdao port on March 23rd |  | 2026-04-17 | 2026-04-08 | TRUE | 49 | 114
Received | Emilka Guerra | 2025-12-15 | PO08538 | Stock - SO18635 - SO18730 - SO18841 - SO18898 - SO18935 | 2026-02-02 | G-104-554 1216 | Casing, 1x1.5-6, 3196 STX, CD4MCu | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-02-11 | SEA | 2026-04-17 |  | BL# TAOTOR06921 |  |  |  | 2026-04-17 | 2026-04-08 | TRUE | 9 | 114
Received | Emilka Guerra | 2025-12-15 | PO08538 | Stock - SO18635 - SO18730 - SO18841 - SO18898 - SO18929 | 2026-02-02 | G-104-554 1216 | Casing, 1x1.5-6, 3196 STX, CD4MCu | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-01-20 | SEA | 2026-04-17 | [5 empty] | 2026-04-17 | 17/04/26 | TRUE | -13 | #VALUE!
Received | Emilka Guerra | 2025-12-15 | PO08538 | Stock - SO18635 - SO18730 - SO18841 - SO18898 - SO18929 | 2026-02-02 | G-P1600S0S00 X060 | Power End, 3196 STX, 316SS Shaft (Sleeved Type), Oil Lubed | 2 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-02-11 | SEA | 2026-04-17 |  | BL# TAOTOR06921 |  |  |  | 2026-04-17 | 2026-04-08 | TRUE | 9 | 114
Received | Emilka Guerra | 2025-12-15 | PO08538 | Stock - SO18635 - SO18730 - SO18841 - SO18898 - SO18929 | 2026-02-02 | DU-DY52981A-CD4 | Casing, 1.5x1-82, Durco Mark 3 Group 1, CD4MCu | 3 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-03 | SEA | Around June 5 |  | batch number: DYNC-112 / ECU: TAOTOR07006 | was shipped by sea on 3rd April. | ETA Vancouver on May 7 |  | 2026-04-17 | 2026-05-19 | TRUE | 60 | 155
Received | Emilka Guerra | 2025-12-15 | PO08538 | Stock - SO18635 - SO18730 - SO18841 - SO18898 - SO18929 | 2026-02-02 | DU-MY50754A82-CD4 | Impeller, 1.5x1-82, Durco Mark 3 Group 1, CD4MCu, Reverse Vane | 2 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-02-11 | SEA | 2026-04-17 |  | BL# TAOTOR06921 |  |  |  | 2026-04-17 | 2026-04-08 | TRUE | 9 | 114 | 16.2857
Received | Emilka Guerra | 2025-12-15 | PO08538 | Stock - SO18635 - SO18730 - SO18841 - SO18898 - SO18929 | 2026-02-02 | DU-PE1Y5.25-316-S | Power End, Durco Mark 3 Group 1, 316SS Shaft (Solid) | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-02-11 | SEA | 2026-04-17 |  | BL# TAOTOR06921 |  |  |  | 2026-04-17 | 2026-04-08 | TRUE | 9 | 114
Received | Emilka Guerra | 2025-12-15 | PO08538 | Stock - SO18635 - SO18730 - SO18841 - SO18898 - SO18929 | 2026-02-02 | DU-CY53429A/FML-CD4 | Rear Cover, 6" & 8", Durco Mark 3 Group 1, CD4MCu, Flow Modifier Large Bore | 3 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-03 | SEA | Around June 5 |  | batch number: DYNC-112 / ECU: TAOTOR07006 | was shipped by sea on 3rd April. | ETA Vancouver on May 7 |  | 2026-04-17 | 2026-05-19 | TRUE | 60 | 155
Received | Emilka Guerra | 2025-12-15 | PO08538 | Stock - SO18635 - SO18730 - SO18841 - SO18898 - SO18929 | 2026-02-02 | OLPWZ011005B, G-A04951A218 | Bearing Isolator (Inboard), 3196 MTX/MTi, Bronze Rotor/Bronze Stator w/Viton | 10 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-02-11 | SEA | 2026-04-17 |  | BL# TAOTOR06921 |  |  |  | 2026-04-17 | 2026-04-08 | TRUE | 9 | 114 | 16.2857
Received | Emilka Guerra | 2025-12-15 | PO08538 | Stock - SO18635 - SO18730 - SO18841 - SO18898 - SO18929 | 2026-02-02 | G-0100-165 1216 | Impeller, 3x4-8G, 3196 MTX, CD4MCu, 5-Vane | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-02-11 | SEA | 2026-04-17 |  | BL# TAOTOR06921 |  |  |  | 2026-04-17 | 2026-04-08 | TRUE | 9 | 114
Received | Emilka Guerra | 2025-12-15 | PO08538 | Stock - SO18635 - SO18730 - SO18841 - SO18898 - SO18930 | 2026-02-03 | DU-AY38913AA-316 | Shaft Sleeve, Durco Mark 2&3 Group 2, 316SS | 6 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-01-20 | SEA | 2026-04-17 | [5 empty] | 2026-04-17 | 2026-03-18 | TRUE | -14 | 93
Received | Emilka Guerra | 2025-12-15 | PO08538 | Stock - SO18635 - SO18730 - SO18841 - SO18898 - SO18931 | 2026-02-04 | G-R100-111 1012 | Stuffing Box Cover, 7" & 8", 3196 MTX, Ductile Iron, Standard Bore, Non-Jacketed | 4 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-01-20 | SEA | 2026-04-17 | [5 empty] | 2026-04-17 | 2026-03-18 | TRUE | -15 | 93
Received | Emilka Guerra | 2025-12-15 | PO08538 | Stock - SO18635 - SO18730 - SO18841 - SO18898 - SO18932 | 2026-02-05 | G-76230X 2229 | Shaft Sleeve, 13" and 15", 3196 XLT, 316SS | 2 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-01-20 | SEA | 2026-04-17 | [5 empty] | 2026-04-17 | 2026-03-18 | TRUE | -16 | 93
Received | Emilka Guerra | 2025-12-15 | PO08538 | Stock - SO18635 - SO18730 - SO18841 - SO18898 - SO18933 | 2026-02-06 | G-R102-814 1013 | Frame Adapter, 15", 3196 XLT, Ductile Iron | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-01-20 | SEA | 2026-04-17 | [5 empty] | 2026-04-17 | 2026-03-18 | TRUE | -17 | 93
Received | Emilka Guerra | 2025-12-15 | PO08538 | Stock - SO18635 - SO18730 - SO18841 - SO18898 - SO18934 | 2026-02-07 | G-R104-562 1216 | Stuffing Box Cover, 6", 3196 STX, CD4MCu, Standard Bore, Non-Jacketed | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-01-20 | SEA | 2026-04-17 | [5 empty] | 2026-04-17 | 2026-03-18 | TRUE | -18 | 93
Received | Ian Trottier | 2026-01-16 | PO08539 | Stock | 2026-01-23 | 046692G161-2229 | Shaft Sleeve (Mechanical Seal), Goulds JC Frame 2J, 316SS | 1 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE |  | LAND | 2026-01-14 |  | PO has been updated, since supplier shipped the worng part. |  |  | This part was received in the warehouse however not found and registered properly until March 31st | 2026-01-16 | 2026-03-31 | TRUE | -46045 | 74
Received | Emilka Guerra | 2025-12-16 | PO08540 | SO18166 | 2025-12-19 | AC-98-233-404-001 | Shaft Sleeve, 10x8-21 SRL-C (Old Style), Steel | 2 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2026-01-02 | 2026-01-14 | TRUE | -46010 | 29
IN TRANSIT & DELAYED | Emilka Guerra | 2025-12-16 | PO08541 | SO18419 | 2026-02-01 | 10JKH, 7-Vane Impeller, CD4MCu | Impeller, 10JKH, Double Keyed, w/Wear Ring | 3 | Nanjing Wangyang Pumps Co., Ltd | China | BARRICK DIRECT SHIPPING | 2026-04-16 | SEA | Around June 5 - 10 |  | ECU: LS15TJ2603881 | The ETA Caucedo is June 5 to 10 | The new ETD Tianjin is Apr 16.. shipped out. ✅ Shipping docs and pictures will be shared with you by Monday. | now in Naipu's workshop, waiting for Naipu's PO08522 to ship together | 2026-03-16 |  | FALSE | 74 | -46007
Received | Yannett Yeomans | 2025-12-16 | PO08542 | SO16262 | 2026-03-10 | WO-2114552-316 | Impeller, Worthington 6-FRBH-223, 316SS | 1 | M&N Alloy Cast Products, Inc. | US | CA WAREHOUSE |  | LAND | 2026-01-29 | [5 empty] | 2026-03-16 | 2026-01-29 | TRUE | -46091 | 44 | 1900-01-05 06:51
Received | Leriel Reyes | 2025-12-16 | PO08546 | SO18369 | 2025-12-30 | BT-P264A | Baseplate, PoxyBase Plus Black Polymer Base, Size 264A | 1 | BaseTek, LLC | US | CA WAREHOUSE |  | LAND | 2026-01-23 | [5 empty] | 2025-12-29 | 2026-01-23 | TRUE | -46021 | 38
Received | Emilka Guerra | 2025-12-17 | PO08549 | SO18435 | 2025-12-26 | AC-98-331-958-803 | Shaft Sleeve, 5x4/5x5/6x6 SRL & SRL-C, Steel | 3 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE |  | LAND | 2026-01-22 | [5 empty] | 2026-01-09 | 2026-01-22 | TRUE | -46017 | 36
Received | Emilka Guerra | 2025-12-17 | PO08552 | Stock | 2026-01-30 | AC-98-234-268-001-SS | Waterseal Bushing, 5x4/5x5/6x6 SRL, 316SS | 10 | Super Cast Limited | China | CA WAREHOUSE | 2026-02-10 | SEA | Around Week of Apr. 30 - May 1 |  | TCLU8795637 |  | Naipu: confirmed shipped out / included in invoice |  | 2026-04-10 | 2026-04-28 | TRUE | 11 | 132
Received | Emilka Guerra | 2025-12-17 | PO08552 | Stock | 2026-01-30 | AC-98-231-120-501 | Suction Side Liner, 8x6-18 SRL-C, Natural Rubber | 8 | Super Cast Limited | China | CA WAREHOUSE | 2026-01-29 | SEA | 2026-10-04 |  | left Tianjin for Toronto by sea on Jan 29, 2026 |  | Expected to arrive first week of april | ARRIVED April 1st | 2026-04-10 | 2026-04-01 | TRUE | -1 | 105
Received | Ian Trottier | 2025-12-17 | PO08553 | SO17965, SO18436, and SO18437 | 2026-01-14 | G-77-59 1001 | Bearing Housing, 3405-M, Cast Iron | 2 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND | [6 empty] | 2026-01-23 | 2026-03-17 | TRUE | -46036 | 90
Received | Ian Trottier | 2025-12-17 | PO08553 | SO17965, SO18436, and SO18437 | 2026-01-14 | G-R72350 6956 | Shaft Sleeve, 3405-M, 316SS NCB Hardcoated | 1 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND | [6 empty] | 2026-01-23 | 2026-03-17 | TRUE | -46036 | 90
Received | Ian Trottier | 2025-12-17 | PO08553 | SO17965, SO18436, and SO18437 | 2026-01-14 | G-R72360 6956 | Shaft Sleeve, 3405-M, Ni-Chrome Boron On 316SS | 1 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND | [6 empty] | 2026-01-23 | 2026-03-17 | TRUE | -46036 | 90
Received | Ian Trottier | 2025-12-17 | PO08553 | SO17965, SO18436, and SO18437 | 2026-01-14 | G-R74777 1 1001 | Sleeve Nut (Right-hand), 3415-S, Cast Iron | 1 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND | [6 empty] | 2026-01-23 | 2026-03-17 | TRUE | -46036 | 90 | 12.8571
Received | Ian Trottier | 2025-12-17 | PO08553 | SO17965, SO18436, and SO18437 | 2026-01-14 | G-R74777 2 1001 | Sleeve Nut (Left-hand), 3415-S, Cast Iron | 1 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND | [6 empty] | 2026-01-23 | 2026-03-17 | TRUE | -46036 | 90
Received | Amanda Qiao | 2025-12-17 | PO08554 | SO18240 | 2026-02-17 | GA-556540 | Impeller, G-Series 6" VSP, 8100 Series, High Chrome | 2 | IGH | Mexico | CA WAREHOUSE |  | LAND | [6 empty] | 2025-12-17 | 2026-03-09 | TRUE | -46070 | 82
Received | Emilka Guerra | 2025-12-18 | PO08555 | SO18440 | 2026-12-02 | AC-52-120-564-003 | Impeller Wear Ring, 14x18-28, 3409-L, 316SS | 2 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-04-09 | LAND | 2026-03-13 | [5 empty] | 2026-03-13 | 2026-04-14 | TRUE | -237 | 117
Received | Emilka Guerra | 2025-12-19 | PO08559 | SO18454 | 2025-12-23 | 2001-12-04 | Sleeve Bearing (Stuffing Box), ThorPlas-Blue, HPCW | 1 | Millstream Engineering Inc. | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2025-12-29 | 2025-12-30 | TRUE | -46014 | 11
Received | Emilka Guerra | 2025-12-22 | PO08562 | Stock | 2026-02-02 | AC-98-131-246-511 | Deflector (Water Slinger), 5x5/5x4/6x6 SRL & SRL-C, Neoprene/Steel | 20 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-02-10 | SEA | Around Week of Apr. 30 - May 1 |  | TCLU8795637 |  | Naipu: confirmed shipped out / included in invoice |  | 2026-04-13 | 2026-04-28 | TRUE | 8 | 127
Received | Emilka Guerra | 2025-12-22 | PO08562 | Stock | 2026-02-02 | D-3J4614-6 | Suction Cover Liner, 4x6-14, Goulds JC, Frame 3J, High Chrome, OEM# 048944G0001228 | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-02-10 | SEA | Around Week of Apr. 30 - May 1 |  | TCLU8795637 |  | Naipu: confirmed shipped out / included in invoice |  | 2026-04-13 | 2026-04-28 | TRUE | 8 | 127 | 18.1429
Received | Emilka Guerra | 2025-12-22 | PO08563 | Stock | 2026-02-27 | AC-98-231-085-501 | Suction Side Liner, 6X6-15 SRL, Natural Rubber | 2 | IGH | Mexico | CA WAREHOUSE | 2026-04-14 | LAND | ETA Warehouse 29/abril |  | XP Ref. # 088414 |  |  | Manufacture issue | 2026-03-27 | 2026-04-29 | TRUE | 46 | 128 | 18.2857
Received | Emilka Guerra | 2025-12-22 | PO08563 | Stock | 2026-02-27 | AC-98-431-651-507 | Impeller (Closed), 8x6-18 SRL-C, Urethane | 1 | IGH | Mexico | CA WAREHOUSE | 2026-04-14 | LAND | ETA Warehouse 29/abril |  | XP Ref. # 088414 |  |  | Manufacture issue | 2026-03-27 | 2026-04-29 | TRUE | 46 | 128 | 18.2857
Received | Emilka Guerra | 2025-12-22 | PO08563 | Stock | 2026-02-27 | AC-98-234-808-501 | Gland Assembly, 12x10-25 SRL-C, Cast Iron | 1 | IGH | Mexico | CA WAREHOUSE | 2026-02-27 | LAND | 2026-03-09 |  |  |  | confirmed SHIPMENT ETD FEB 27, 2026 | Email for POs sent on Jan 28th, 2026 Follow up for SHipment date sent on Feb 6th, 2026 | 2026-03-27 | 2026-03-09 | TRUE | 0 | 77 | 11
Received | Emilka Guerra | 2025-12-22 | PO08565 | SO18445 | 2026-03-16 | AC-98-432-130-501 | Gland Side Casing, 12x10-25 SRL-C, Cast Iron | 1 | IGH | Mexico | CA WAREHOUSE | 2026-02-27 | LAND | 2026-03-09 |  |  |  | confirmed SHIPMENT ETD FEB 27, 2026 | Email for POs sent on Jan 28th, 2026 Follow up for SHipment date sent on Feb 6th, 2026 | 2026-04-17 | 2026-03-09 | TRUE | -17 | 77
Received | Ian Trottier | 2025-12-22 | PO08566 | SO18446 | 2026-01-09 | G-76230X 2156 | Shaft Sleeve, 13" and 15", 3196 XLT, Titanium | 1 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND | [6 empty] | 2026-01-16 | 2026-01-20 | TRUE | -46031 | 29
Received | Emilka Guerra | 2025-12-23 | PO08567 | SO18460 | 2026-03-03 | SA-567243 | Wear Disc, Sala 6x5 VSP-VF, High Chrome | 6 | Hyperflo | Canada | CA WAREHOUSE | 2026-03-24 | LAND | 2026-03-25 |  | 3304529268 |  |  |  | 2026-03-17 | 2026-03-26 | TRUE | 21 | 93
IN TRANSIT & DELAYED | Ian Trottier | 2025-12-24 | PO08570 | Stock | 2026-01-28 | G-10x12-22-JC-HC | Pump, 10x12-22, Goulds JC Frame 5J, High Chrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-05-26 | SEA | ETA Warehouse mid-august | the vessel depart on May 26 | 20251217-11 Sea Waybill-No. 1074440607 |  | Betty 4/23: Included in Comercial Invoice #20251217-11 | Email requesting status sent on March 19th / april 22nd | 2026-03-13 |  | FALSE | 118 | -46015 | -6573.5714
Received | Emilka Guerra | 2025-12-29 | PO08571 | SO18453 | 2026-02-01 | AC105-CS01-TEN, AC-52-430-298-002 | Seal Cage (Lantern Ring), Allis Chalmers CSO, Frame F4B3/F4B5/F4D1, Teflon | 4 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND | 2026-01-20 | [5 empty] | 2026-02-02 | 2026-01-20 | TRUE | -46054 | 22
Received | Amanda Qiao | 2025-12-30 | PO08573 |  | 2026-01-06 | DU-GUARD-M3G1 | Coupling Guard, Durco Mark 3 Group 1, Steel Fabricated, Drum Style | 1 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND | 2026-01-20 | [5 empty] | 2026-01-09 | 2026-01-20 | TRUE | -46028 | 21
IN TRANSIT & DELAYED | Ian Trottier | 2025-12-30 | PO08574 | Stock | 2026-03-02 | G-8x10-18-JC-HC | Pump, 8x10-18, Dynapro DC, Frame 3J, High Chrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-05-26 | SEA | ETA Warehouse mid-august | the vessel depart on May 26 | 20251217-11 Sea Waybill-No. 1074440607 |  | Betty 4/23: Included in Comercial Invoice #20251217-11 | Email requesting status sent on March 19th / april 22nd | 2026-05-18 |  | FALSE | 85 | -46021 | -6574.4286
Received | Ian Trottier | 2026-01-05 | PO08575 | SO18286 | 2026-02-06 | W-E4147/A49 | Impeller, 6/4 D or E-AH, Ultrachrome, Corrosion Resistant, 5-Vane | 1 | Super Cast Limited | China | CA WAREHOUSE |  | SEA |  |  | Expected to arrive first week of april | left Tianjin for Toronto by sea on Jan 29, 2026 |  |  | 2026-04-24 | 2026-04-01 | TRUE | -46059 | 86
Received | Ian Trottier | 2026-01-05 | PO08575 | SO18286 | 2026-02-06 | W-E424M/C23 | Shaft Sleeve (Mechanical Seal), 6/4 or 8/6 E or R-AH, 316SS | 1 | Super Cast Limited | China | CA WAREHOUSE |  | SEA |  |  | Expected to arrive first week of april | left Tianjin for Toronto by sea on Jan 29, 2026 |  |  | 2026-04-24 | 2026-04-01 | TRUE | -46059 | 86
Received | Ian Trottier | 2026-01-05 | PO08576 | SO18286 | 2026-01-20 | G-70014-1001 | Bearing Cover, (Coupling Side, Grease Lube), Goulds 3405-M, Cast Iron. | 1 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND | 2026-01-20 | [5 empty] | 2026-01-30 | 2026-01-20 | TRUE | -46042 | 15
Received | Emilka Guerra | 2026-01-06 | PO08578 | SO18487 | 2026-01-23 | 10JKH, 7-Vane Impeller, CD4MCu | Impeller, 10JKH, Double Keyed, w/Wear Ring | 3 | Nanjing Wangyang Pumps Co., Ltd | China | BARRICK DIRECT SHIPPING | 2026-03-16 | SEA |  |  |  |  | left Shanghai for Caucedo by sea on Mar 16, 2026 ✅ | delayed transit to may 28th | 2026-03-31 | 2026-04-28 | TRUE | 52 | 112 | 16
Received | Emilka Guerra | 2026-01-06 | PO08578 | SO18487 | 2026-01-23 | D-2001407-2507 | Bowl Wear Ring, 10JKH/M, 05.50x05.88x0.88, Duplex SS 2507 w/Ion Nitriding | 15 | Nanjing Wangyang Pumps Co., Ltd | China | BARRICK DIRECT SHIPPING | 2026-03-16 | SEA |  |  |  |  | left Shanghai for Caucedo by sea on Mar 16, 2026 ✅ | delayed transit to may 28th | 2026-03-31 | 2026-04-28 | TRUE | 52 | 112 | 16
Received | Emilka Guerra | 2026-01-06 | PO08579 | SO18487 | 2026-02-05 | 2001-12-05 | Sleeve Bearing (Bowl), ThorPlas-Blue, HPCW | 8 | Millstream Engineering Inc. | Canada | CA WAREHOUSE |  | LAND | 2026-01-30 | [5 empty] | 2026-02-13 | 2026-01-29 | TRUE | -46058 | 23
Received | Emilka Guerra | 2026-01-06 | PO08581 | Stock | 2026-01-27 | DU-AY51803A-TFR | Impeller Gasket, Durco Mark 3 Group 1, Teflon/Rubber | 5 | Renewal Services Inc. | Canada | CA WAREHOUSE |  | LAND | 2026-02-02 | [5 empty] | 2026-02-17 | 2026-02-02 | TRUE | -46049 | 27
Received | Emilka Guerra | 2026-01-07 | PO08583 | SO18504 | 2026-01-21 | SA-013733-M2 | Wear Disc, 44 WFR, Sala STGVA-180, High Chrome | 2 | Hyperflo | Canada | CA WAREHOUSE | 2026-03-24 | LAND | 2026-03-25 |  | 3304529268 |  |  |  | 2026-01-28 | 2026-03-26 | TRUE | 62 | 78
Received | Emilka Guerra | 2026-01-07 | PO08584 | SO18495 | 2026-03-06 | SA-567859 | Bearing Assembly, STHM 22-WFR, 1045 Steel Shaft | 1 | Hyperflo | Canada | CA WAREHOUSE | 2026-03-24 | LAND | 2026-03-25 |  | 3304529268 |  |  |  | 2026-03-20 | 2026-03-26 | TRUE | 18 | 78
IN TRANSIT & DELAYED | Ian Trottier | 2026-01-08 | PO08585 | Stock | 2026-03-06 | AC-98-331-595-803 | Stuffing Box Cover, 17", PWO, Frame 2, 317SS | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-03 | SEA | Around June 5 |  | batch number: DYNC-112 / ECU: TAOTOR07006 | was shipped by sea on 3rd April. | ETA Vancouver on May 7 | Email requesting status sent on March 19th | 2026-05-15 |  | FALSE | 28 | -46030
Received | Emilka Guerra | 2026-01-08 | PO08586 | Stock | 2026-02-19 | AC-98-234-808-501 | Gland Assembly, 12x10-25 SRL-C, Cast Iron | 5 | IGH | Mexico | CA WAREHOUSE | 2026-02-27 | LAND | 2026-03-09 |  |  |  | confirmed SHIPMENT ETD FEB 27, 2026 | Email for POs sent on Jan 28th, 2026 Follow up for SHipment date sent on Feb 6th, 2026 | 2026-03-13 | 2026-03-09 | TRUE | 8 | 60
Received | Emilka Guerra | 2026-01-08 | PO08586 | Stock | 2026-02-19 | AC-98-431-651-503 | Impeller (Closed), 8x6-18 SRL-C, Neoprene | 2 | IGH | Mexico | CA WAREHOUSE | 2026-02-27 | LAND | 2026-03-09 |  |  |  | confirmed SHIPMENT ETD FEB 27, 2026 | Email for POs sent on Jan 28th, 2026 Follow up for SHipment date sent on Feb 6th, 2026 | 2026-03-13 | 2026-03-09 | TRUE | 8 | 60
Received | Emilka Guerra | 2026-01-08 | PO08586 | Stock | 2026-02-19 | 5/2/3282 | Impeller, 8x6-18 D-SRL-C, Natural Rubber | 6 | IGH | Mexico | CA WAREHOUSE | 2026-02-27 | LAND | 2026-03-09 |  |  |  | confirmed SHIPMENT ETD FEB 27, 2026 | Email for POs sent on Jan 28th, 2026 Follow up for SHipment date sent on Feb 6th, 2026 | 2026-03-13 | 2026-03-09 | TRUE | 8 | 60
Received | Emilka Guerra | 2026-01-08 | PO08587 | SO18478 | 2026-01-23 | AC-98-233-815-001 | Half Seal Cage, 5x4/5x5/6x6 SRL & SRL-C, Steel | 3 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE |  | LAND | 2026-01-30 | [5 empty] | 2026-02-06 | 2026-01-29 | TRUE | -46045 | 21
Received | Emilka Guerra | 2026-01-08 | PO08587 | SO18478 | 2026-01-23 | SA-567031 | Spacer (Outer), Sala STHM-33WFR. Steel | 6 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE |  | LAND | 2026-01-30 | [5 empty] | 2026-02-06 | 2026-01-29 | TRUE | -46045 | 21
Received | Ian Trottier | 2026-01-08 | PO08589 | SO18182 - Air Shipment to Dynapro Toronto | 2026-03-02 | DU-AY38913AA-TI | Shaft Sleeve, Durco Mark 2 & 3 Group 2, Titanium | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-03-25 | AIR | ETA APRIL 1ST |  | DYNC-111 | Ready to ship on march 25 | The estimated delivery date will be delayed to March 25th |  | 2026-03-16 | 2026-04-02 | TRUE | 23 | 84
Received | Ian Trottier | 2026-01-08 | PO08589 | SO18182 - Air Shipment to Dynapro Toronto | 2026-03-02 | DU-DY21855A/CBS-TI | Rear Cover, 13", Durco Mark 2&3 Group 2, Titanium, Small Bore | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-03-25 | AIR | ETA APRIL 1ST |  | DYNC-111 | Ready to ship on march 25 | The estimated delivery date will be delayed to March 25th |  | 2026-03-16 | 2026-04-02 | TRUE | 23 | 84
Received | Ian Trottier | 2026-01-08 | PO08589 | SO18182 - Air Shipment to Dynapro Toronto | 2026-03-02 | DU-MY36847AA130-TI | Impeller, 4x3-13, Durco Mark 2&3 Group 2, Titanium, Reverse Vane | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-03-25 | AIR | ETA APRIL 1ST |  | DYNC-111 | Ready to ship on march 25 | The estimated delivery date will be delayed to March 25th |  | 2026-03-16 | 2026-04-02 | TRUE | 23 | 84
Received | Ian Trottier | 2026-01-08 | PO08589 | SO18182 - Air Shipment to Dynapro Toronto | 2026-03-02 | DU-CY22344A-TI | Casing, 4x3-13, Durco Mark 2&3 Group 2, Titanium | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-03-25 | AIR | ETA APRIL 1ST |  | DYNC-111 | Ready to ship on march 25 | The estimated delivery date will be delayed to March 25th | This impeller's shell mold was scrapped during the casting process | 2026-03-16 | 2026-04-02 | TRUE | 23 | 84 | 12
In Production | Yannett Yeomans | 2026-01-08 | PO08588 | SO18525 | 2026-04-02 | 10546/0003 | Volute Casing, 12X10, High Chrome | 2 | Super Cast Limited | China | MX WAREHOUSE | 2026-06-11 | SEA | 2026-06-11 |  |  |  | All the 4 pcs are expected to complete packing around Apr 20. |  | 2026-06-11 |  | FALSE
In Production | Yannett Yeomans | 2026-01-08 | PO08588 | SO18525 | 2026-04-02 | 10546/0003 | Volute Casing, 12X10, High Chrome | 2 | Super Cast Limited | China | MX WAREHOUSE | 2026-06-11 | SEA | 2026-06-11 |  |  |  | All the 4 pcs are expected to complete packing around Apr 20. |  | 2026-06-11 |  | FALSE
In Production | Yannett Yeomans | 2026-01-08 | PO08588 | SO18525 | 2026-04-02 | 10546/0003 | Volute Casing, 12X10, High Chrome | v | Super Cast Limited | China | MX WAREHOUSE | 2026-06-11 | SEA | 2026-06-11 |  |  |  | All the 4 pcs are expected to complete packing around Apr 20. |  | 2026-06-11 |  | FALSE
Received | Ian Trottier | 2026-01-13 | PO08591 | SO18506 | 2026-03-13 | DU-MY51086AA100-CD4 | Impeller (Open), 2x1-10A, Durco Mark 2&3 Group 2, CD4MCu | 2 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-03-25 | AIR | ETA APRIL 1ST |  | DYNC-111 | Ready to ship on march 25 | PO08589 and PO8591 ship together by air at the end of march |  | 2026-03-30 | 2026-04-02 | TRUE | 12 | 79 | 11.2857
Received | Emilka Guerra | 2026-01-13 | PO08592 | SO18546 | 2026-02-17 | 10JKH, 7-Vane Impeller, CD4MCu | Impeller, 10JKH, Double Keyed, w/Wear Ring | 3 | Nanjing Wangyang Pumps Co., Ltd | China | BARRICK DIRECT SHIPPING | 2026-03-16 | SEA |  |  | Wrong Impeller to Barrick | ETD Mar 15 from Shanghai to Caucedo, Dominican Republic. | left Shanghai for Caucedo by sea on Mar 16, 2026 |  | 2026-04-28 | 2026-04-28 | TRUE | 27 | 105 | 15
Received | Emilka Guerra | 2026-01-13 | PO08592 | SO18546 | 2026-02-17 | D-2001407-2507 | Bowl Wear Ring, 10JKH/M, 05.50x05.88x0.88, Duplex SS 2507 w/Ion Nitriding | 10 | Nanjing Wangyang Pumps Co., Ltd | China | BARRICK DIRECT SHIPPING | 2026-03-16 | SEA |  |  |  | ETD Mar 15 from Shanghai to Caucedo, Dominican Republic. | left Shanghai for Caucedo by sea on Mar 16, 2026 |  | 2026-04-28 | 2026-04-28 | TRUE | 27 | 105 | 15
Received | Emilka Guerra | 2026-01-13 | PO08593 | SO18035 | 2026-02-24 | DE-504755 | Impeller Closed, 3X3 SRL, Natural Rubber | 2 | IGH | Mexico | CA WAREHOUSE | 2026-04-14 | LAND | ETA Warehouse 29/abril |  | XP Ref. # 088414 |  |  | Supplier delay | 2026-03-24 | 2026-04-29 | TRUE | 49 | 106 | 15.1429
Received | Emilka Guerra | 2026-01-13 | PO08593 | SO18035 | 2026-02-24 | DE-504757 | Suction Side Liner, 4x3 SRL-C, Denver, Rubber | 2 | IGH | Mexico | CA WAREHOUSE | 2026-02-27 | LAND | 2026-03-09 |  |  |  | confirmed SHIPMENT ETD FEB 27, 2026 | Email for POs sent on Jan 28th, 2026 Follow up for SHipment date sent on Feb 6th, 2026 | 2026-03-24 | 2026-03-09 | TRUE | 3 | 55
Received | Emilka Guerra | 2026-01-13 | PO08593 | SO18035 | 2026-02-24 | 504563 | Impeller, 5x5, Denver SRL, Natural Rubber | 1 | IGH | Mexico | CA WAREHOUSE | 2026-02-27 | LAND | 2026-03-09 |  |  |  | confirmed SHIPMENT ETD FEB 27, 2026 | Email for POs sent on Jan 28th, 2026 Follow up for SHipment date sent on Feb 6th, 2026 | 2026-03-24 | 2026-03-09 | TRUE | 3 | 55
Received | Emilka Guerra | 2026-01-13 | PO08593 | SO18035 | 2026-02-24 | 504828 | Impeller, 5x4, Denver SRL, Natural Rubber | 2 | IGH | Mexico | CA WAREHOUSE | 2026-02-27 | LAND | 2026-03-09 |  |  |  | confirmed SHIPMENT ETD FEB 27, 2026 | Email for POs sent on Jan 28th, 2026 Follow up for SHipment date sent on Feb 6th, 2026 | 2026-03-24 | 2026-03-09 | TRUE | 3 | 55
Received | Emilka Guerra | 2026-01-13 | PO08593 | SO18035 | 2026-02-24 | 504830 | Suction Side Liner, 5x4-14, D-SRL-C, Natural Rubber | 2 | IGH | Mexico | CA WAREHOUSE | 2026-02-27 | LAND | 2026-03-09 |  |  |  | confirmed SHIPMENT ETD FEB 27, 2026 | Email for POs sent on Jan 28th, 2026 Follow up for SHipment date sent on Feb 6th, 2026 | 2026-03-24 | 2026-03-09 | TRUE | 3 | 55
Received | Emilka Guerra | 2026-01-13 | PO08593 | SO18035 | 2026-02-24 | 504826 | Gland Side Liner, 5x4-14, D-SRL-C, Natural Rubber | 2 | IGH | Mexico | CA WAREHOUSE | 2026-02-27 | LAND | 2026-03-09 |  |  |  | confirmed SHIPMENT ETD FEB 27, 2026 | Email for POs sent on Jan 28th, 2026 Follow up for SHipment date sent on Feb 6th, 2026 | 2026-03-24 | 2026-03-09 | TRUE | 3 | 55
Received | Emilka Guerra | 2026-01-13 | PO08594 | SO18475 | 2026-03-11 | GA-23972 | Impeller, G-Series 2.5" VSP, 1000 Series, Natural Rubber | 1 | IGH | Mexico | CA WAREHOUSE | 2026-04-14 | LAND | ETA Warehouse 29/abril |  | XP Ref. # 088414 |  |  | Received on April 29th | 2026-04-08 | 2026-04-29 | TRUE | 34 | 106 | 15.1429
Received | Emilka Guerra | 2026-01-13 | PO08594 | SO18475 | 2026-03-11 | GA-24059 | Flinger, 2.5", G-Series VSP, 2.5" 1000 Series or 1.5" 5000 Series, Neoprene | 1 | IGH | Mexico | CA WAREHOUSE | 2026-02-27 | LAND | 2026-03-09 |  |  |  | confirmed SHIPMENT ETD FEB 27, 2026 | Email for POs sent on Jan 28th, 2026 Follow up for SHipment date sent on Feb 6th, 2026 | 2026-04-08 | 2026-03-09 | TRUE | -12 | 55 | 7.8571
IN TRANSIT & DELAYED | Amanda Qiao | 2026-01-13 | PO08595 | SO18485 - Ship direct to Dominican | 2026-02-13 | W-M100KSS-TVB/0507 | Sump Pump, M100KSS-TVB, CD4MCu | 1 | Shijiazhuang Mets Machinery Co., LTD | China | BARRICK DIRECT SHIPPING | 2026-05-06 | SEA |  | Amanda May 6th: This shipment can be shipped to Barrick directly. | EASLINE OSAKA / V.2621E. LS15TJ2605852 | NEW ETD April/30 The new ETD Tianjin is May 22. It departed Tianjin on May 17, 2026. left Tianjin for Caucedo by sea on May 24, 2026 | Peter May 12: Booked the vessel of ETD May 15 from Tianjin to Caucedo. / The cargo is now at Tianjin seaport waiting for boarding. | Although the main pump is now ready, the agitator and the agitator shaft could not come out until end of April. These two parts were scrapped due to quality issue. 05/16: missed the vessel, becasue the actual volume is greater than the booked volume. No enought room to be loaded into the container. | 2026-04-24 |  | FALSE | 82 | -46035
IN TRANSIT & DELAYED | Ian Trottier | 2026-01-13 | PO08596 | SO18551 | 2026-03-06 | G-104-573 1012 | Casing, 1.5x3-8, 3196 STX, Ductile Iron, #300 FF Flanges | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-03 | SEA | Around June 5 |  | batch number: DYNC-112 / ECU: TAOTOR07006 | was shipped by sea on 3rd April. | ETA Vancouver on May 7 |  | 2026-05-08 |  | FALSE | 28 | -46035
Received | Emilka Guerra | 2026-01-14 | PO08597 | Stock | 2026-02-13 | M24X100, W-T45026M/E62 | Liner Stud w/Nut, 450 STL, Metric | 8 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | 2026-02-20 | [5 empty] | 2026-02-20 | 2026-02-02 | TRUE | -46066 | 19
Received | Emilka Guerra | 2026-01-14 | PO08597 | Stock | 2026-02-13 | W-M30A4-70S. Bolt M30x70. Bolt Guard M30-291 | Casing Bolt w/Bolt Guard, 100RV-SPR, 316SS/Neoprene | 3 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | 2026-02-20 | [5 empty] | 2026-02-20 | 2026-02-02 | TRUE | -46066 | 19
Received | Emilka Guerra | 2026-01-14 | PO08598 | SO18150 | 2026-02-13 | PDCH1988 | Inlet Liner, HR150, Natural Rubber | 1 | IGH | Mexico | CA WAREHOUSE | 2026-02-27 | LAND | 2026-03-09 |  |  |  | confirmed SHIPMENT ETD FEB 27, 2026 | Email for POs sent on Jan 28th, 2026 Follow up for SHipment date sent on Feb 6th, 2026 | 2026-03-13 | 2026-03-09 | TRUE | 14 | 54 | 7.7143
Received | Emilka Guerra | 2026-01-14 | PO08598 | SO18150 | 2026-02-13 | PDCH1990 | Case Liner, HR150, Natural Rubber | 1 | IGH | Mexico | CA WAREHOUSE | 2026-02-27 | LAND | 2026-03-09 |  |  |  | confirmed SHIPMENT ETD FEB 27, 2026 | Email for POs sent on Jan 28th, 2026 Follow up for SHipment date sent on Feb 6th, 2026 | 2026-03-13 | 2026-03-09 | TRUE | 14 | 54 | 7.7143
Received | Emilka Guerra | 2026-01-14 | PO08598 | SO18150 | 2026-02-13 | PDCH1973 | Back Liner, HR150, Natural Rubber | 1 | IGH | Mexico | CA WAREHOUSE | 2026-02-27 | LAND | 2026-03-09 |  |  |  | confirmed SHIPMENT ETD FEB 27, 2026 | Email for POs sent on Jan 28th, 2026 Follow up for SHipment date sent on Feb 6th, 2026 | 2026-03-13 | 2026-03-09 | TRUE | 14 | 54
Received | Emilka Guerra | 2026-01-14 | PO08598 | SO18150 | 2026-02-13 | PDCH1960 | Impeller, HR150, Natural Rubber | 1 | IGH | Mexico | CA WAREHOUSE | 2026-02-27 | LAND | 2026-03-09 |  |  |  | confirmed SHIPMENT ETD FEB 27, 2026 | Email for POs sent on Jan 28th, 2026 Follow up for SHipment date sent on Feb 6th, 2026 | 2026-03-13 | 2026-03-09 | TRUE | 14 | 54
Received | Emilka Guerra | 2026-01-14 | PO08599 | Stock | 2026-03-23 | G-249-65 1216 | Casing, 3x4-13, 3196 MTX, CD4MCu | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA | 2026-04-08 |  | BL# TAOTOR06921 |  |  |  | 2026-06-01 | 2026-04-08 | TRUE | -46104 | 84
Received | Emilka Guerra | 2026-01-14 | PO08599 | Stock | 2026-03-23 | DU-CY32768AA-316 | Shaft (Hook Sleeve), Durco Mark 2&3 Group 2, 316SS | 4 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA | 2026-04-08 |  | BL# TAOTOR06921 |  |  |  | 2026-06-01 | 2026-04-08 | TRUE | -46104 | 84
Received | Emilka Guerra | 2026-01-14 | PO08599 | Stock | 2026-03-23 | G-76772X 2229 | Shaft Sleeve, 3196 STX, 316SS | 5 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA | 2026-04-08 |  | BL# TAOTOR06921 |  |  |  | 2026-06-01 | 2026-04-08 | TRUE | -46104 | 84
Received | Emilka Guerra | 2026-01-14 | PO08599 | Stock | 2026-03-23 | DU-DY21855A/CBS-CD4 | Rear Cover, 13", Durco Mark 2&3 Group 2, CD4MCu, Small Bore | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA | 2026-04-08 |  | BL# TAOTOR06921 |  |  |  | 2026-06-01 | 2026-04-08 | TRUE | -46104 | 84 | 12
Received | Emilka Guerra | 2026-01-14 | PO08599 | Stock | 2026-03-23 | OLPWZ011003B, G-A04951A216 | Bearing Isolator (Inboard), 3196 STX/STi, 303SS Rotor / Bronze Stator w/Viton | 15 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-03 | SEA | Around June 5 |  | batch number: DYNC-112 / ECU: TAOTOR07006 | was shipped by sea on 3rd April. | ETA Vancouver on May 7 |  | 2026-06-01 | 2026-05-14 | TRUE | 11 | 120 | 17.1429
Received | Emilka Guerra | 2026-01-14 | PO08599 | Stock | 2026-03-23 | DU-MY36847AA130-CD4 | Impeller, 4x3-13, Durco Mark 2&3 Group 2, CD4MCu, Reverse Vane | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA | 2026-04-08 |  | BL# TAOTOR06921 |  |  |  | 2026-06-01 | 2026-04-08 | TRUE | -46104 | 84
Received | Emilka Guerra | 2026-01-14 | PO08599 | Stock | 2026-03-23 | G-73705X 2229 | Shaft Sleeve, 3196 MTX, 316SS | 15 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA | 2026-04-08 |  | BL# TAOTOR06921 |  |  |  | 2026-06-01 | 2026-04-08 | TRUE | -46104 | 84
Received | Emilka Guerra | 2026-01-14 | PO08599 | Stock | 2026-03-23 | G-P1600M0S00 X050 | Power End, 3196 MTX, Oil Lubed, 4140 Shaft (Sleeved Type), 316SS Shaft Sleeve | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-03 | SEA | Around June 5 |  | batch number: DYNC-112 / ECU: TAOTOR07006 | was shipped by sea on 3rd April. | ETA Vancouver on May 7 |  | 2026-06-01 | 2026-05-14 | TRUE | 11 | 120
Received | Emilka Guerra | 2026-01-14 | PO08599 | Stock | 2026-03-23 | G-B02091A 1001 | Frame Foot, 3196 MTX, 10" Centerline | 3 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA | 2026-04-08 |  | BL# TAOTOR06921 |  |  |  | 2026-06-01 | 2026-04-08 | TRUE | -46104 | 84
Received | Emilka Guerra | 2026-01-14 | PO08600 | Stock | 2026-02-13 | W-E108/G01 | Piston Ring, 6/4 or 8/6 E-AH and 10/8 FF-AH | 15 | Super Cast Limited | China | CA WAREHOUSE | 2026-03-12 | SEA | ETA Warehouse May last week |  | ETD Prince Rupert: Apr 4, 2026 |  | left Tianjin for Toronto by sea on Mar 12, 2026. |  | 2026-04-24 | 2026-04-27 | TRUE | 27 | 103 | 14.7143
Received | Emilka Guerra | 2026-01-14 | PO08600 | Stock | 2026-02-13 | W-E109/S50 | Shaft Sleeve O-Ring, 6/4 E-AH or 8/6 E,R or F-AH, Viton | 30 | Super Cast Limited | China | CA WAREHOUSE | 2026-03-12 | SEA | ETA Warehouse May last week |  | ETD Prince Rupert: Apr 4, 2026 |  | left Tianjin for Toronto by sea on Mar 12, 2026. |  | 2026-04-24 | 2026-04-27 | TRUE | 27 | 103
Received | Emilka Guerra | 2026-01-14 | PO08601 | SO18564 | 2026-02-18 | D-2001407-2507 | Bowl Wear Ring, 10JKH/M, 05.50x05.88x0.88, Duplex SS 2507 w/Ion Nitriding | 16 | Nanjing Wangyang Pumps Co., Ltd | China | BARRICK DIRECT SHIPPING | 2026-03-16 | SEA | 2026-05-06 |  |  | PO08601 and ready for dispatch | left Shanghai for Caucedo by sea on Mar 16, 2026 ✅ | ETD Mar 15 from Shanghai to Caucedo, Dominican Republic. | 2026-05-06 | 2026-04-28 | TRUE | 26 | 104
Received | Emilka Guerra | 2026-01-14 | PO08601 | SO18561 | 2026-02-18 | D-2001412-4PHSS | Hex Cap Screw, 10JKH/M, 0.44-14NCx1.50, 17-4PH SS | 200 | Nanjing Wangyang Pumps Co., Ltd | China | BARRICK DIRECT SHIPPING | 2026-03-16 | SEA | 2026-05-06 |  |  | PO08601 and ready for dispatch | left Shanghai for Caucedo by sea on Mar 16, 2026 ✅ | ETD Mar 15 from Shanghai to Caucedo, Dominican Republic. | 2026-05-06 | 2026-04-28 | TRUE | 26 | 104 | 14.8571
Received | Emilka Guerra | 2026-01-14 | PO08602 | SO18564 | 2026-02-13 | 2001-12-05 | Sleeve Bearing (Bowl), ThorPlas-Blue, HPCW | 16 | Millstream Engineering Inc. | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2026-02-20 | 2026-01-29 | TRUE | -46066 | 15
In Production | Yannett Yeomans | 2026-01-14 | PO08603 | SO18567 | 2026-02-16 | GB/T6172.1 | Nut M20, XS500-710, Carbon Steel | 3 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-13 | SEA | [6 empty] | 2026-04-13 |  | FALSE
In Production | Yannett Yeomans | 2026-01-14 | PO08603 | SO18567 | 2026-02-16 | GB/T85 | Screw M20x5, XS500-710 | 3 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-13 | SEA | [6 empty] | 2026-04-13 |  | FALSE
In Production | Yannett Yeomans | 2026-01-14 | PO08603 | SO18567 | 2026-02-16 | B1205-76-100-02 | Bearing Housing Cover, XS500-710, Cast Iron | 3 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-13 | SEA | [6 empty] | 2026-04-13 |  | FALSE
In Production | Yannett Yeomans | 2026-01-14 | PO08603 | SO18567 | 2026-02-16 | B1205I-76-110 A-01 | Bearing Housing A, XS500-710, HT250 | 2 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-13 | SEA | [6 empty] | 2026-04-13 |  | FALSE
In Production | Yannett Yeomans | 2026-01-14 | PO08603 | SO18567 | 2026-02-16 | GB283 | Cylindrical Roller Bearing NU322, XS500-710 | 2 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-13 | SEA | [6 empty] | 2026-04-13 |  | FALSE
In Production | Yannett Yeomans | 2026-01-14 | PO08603 | SO18567 | 2026-02-16 | 10542/5013 | Fishpaper, 0.25MM, XS500-710 | 3 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-13 | SEA | [6 empty] | 2026-04-13 |  | FALSE
In Production | Yannett Yeomans | 2026-01-14 | PO08603 | SO18567 | 2026-02-16 | 10535/1501 | Screw M16x60, XS500-710, Carbon Steel | 12 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-13 | SEA | [6 empty] | 2026-04-13 |  | FALSE
In Production | Yannett Yeomans | 2026-01-14 | PO08603 | SO18567 | 2026-02-16 | 10534/1501 | Flat Washer M24, XS500-710, Carbon Steel | 12 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-13 | SEA | [6 empty] | 2026-04-13 |  | FALSE
In Production | Yannett Yeomans | 2026-01-14 | PO08603 | SO18567 | 2026-02-16 | 10533/1501 | Spring Washer M24, XS500-710, 1065 Steel | 12 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-13 | SEA | [6 empty] | 2026-04-13 |  | FALSE
In Production | Yannett Yeomans | 2026-01-14 | PO08603 | SO18567 | 2026-02-16 | 10532/0539 | Cap Shape Nut, M24, XS500-710, 201SS | 12 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-13 | SEA | [6 empty] | 2026-04-13 |  | FALSE
In Production | Yannett Yeomans | 2026-01-14 | PO08603 | SO18567 | 2026-02-16 | 10470/1501 | Double Head Bolt M24x140mm, XS500-710, Carbon Steel | 12 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-13 | SEA | [6 empty] | 2026-04-13 |  | FALSE
In Production | Yannett Yeomans | 2026-01-14 | PO08603 | SO18567 | 2026-02-16 | 10469/1501 | Double Head Bolt, M27x110mm, XS500-710, Carbon Steel | 12 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-13 | SEA | [6 empty] | 2026-04-13 |  | FALSE
In Production | Yannett Yeomans | 2026-01-14 | PO08603 | SO18567 | 2026-02-16 | 10468/1501 | Nut M16, XS500-710, Carbon Steel | 6 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-13 | SEA | [6 empty] | 2026-04-13 |  | FALSE
In Production | Yannett Yeomans | 2026-01-14 | PO08603 | SO18567 | 2026-02-16 | 10463/1519 | Spiral Tail Cone Pin 16x100mm, XS500-710, 1035 Steel | 6 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-13 | SEA | [6 empty] | 2026-04-13 |  | FALSE
In Production | Yannett Yeomans | 2026-01-14 | PO08603 | SO18567 | 2026-02-16 | 10461/1501 | Double Head Bolt M27x75mm, XS500-710, Carbon Steel | 114 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-13 | SEA | [6 empty] | 2026-04-13 |  | FALSE
In Production | Yannett Yeomans | 2026-01-14 | PO08603 | SO18567 | 2026-02-16 | 10458/1501 | Cap Shape Nut M27, XS500-710, 201SS | 126 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-13 | SEA | [6 empty] | 2026-04-13 |  | FALSE
In Production | Yannett Yeomans | 2026-01-14 | PO08603 | SO18567 | 2026-02-16 | 10456/0539 | NUT, CAP, M27, XS500-710, 201SS | 126 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-13 | SEA | [6 empty] | 2026-04-13 |  | FALSE
In Production | Yannett Yeomans | 2026-01-14 | PO08603 | SO18567 | 2026-02-16 | 10541/0504 | Plug 0.25", XS500-710, 304SS | 6 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-13 | SEA | [6 empty] | 2026-04-13 |  | FALSE
In Production | Yannett Yeomans | 2026-01-14 | PO08603 | SO18567 | 2026-02-16 | 10453/0504 | Plug 1", XS500-710, 304SS | 15 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-13 | SEA | [6 empty] | 2026-04-13 |  | FALSE
In Production | Yannett Yeomans | 2026-01-14 | PO08603 | SO18567 | 2026-02-16 | GB/T6170 | Nut M24, XS500-710, 304SS | 24 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-13 | SEA | [6 empty] | 2026-04-13 |  | FALSE
IN TRANSIT | Yannett Yeomans | 2026-01-14 | PO08603 | SO18567 | 2026-02-16 | GB/T898 | Double Head Bolt AM24x75, XS500-710, 304SS | 24 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-13 | AIR | ETA Hermosillo: May 20. |  | PEter 05/17: 24 pcs AM24X75 double head bolts in OC00248/PO08603 were shipped out from Shijiazhuang to Hermosillo via DHL on May 16, 2026. |  |  |  | 2026-04-13 |  | FALSE
In Production | Yannett Yeomans | 2026-01-14 | PO08603 | SO18567 | 2026-02-16 | 10538/0536 | Upper & Lower Casing, XS500-710, 416SS | 1 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-13 | SEA | [6 empty] | 2026-04-13 |  | FALSE
Received | Emilka Guerra | 2026-01-15 | PO08604 |  | 2026-01-23 | GB6170-2000 | Nut M24 | 4 | Super Cast Limited | China | CA WAREHOUSE | 2026-01-24 | AIR | 2026-01-30 |  |  | Air shipment for Covia |  |  | 2026-01-30 | 2026-02-02 | TRUE | 1 | 18
Received | Emilka Guerra | 2026-01-15 | PO08604 |  | 2026-01-23 | GB97.1-2002 | Washer 24 | 4 | Super Cast Limited | China | CA WAREHOUSE | 2026-01-24 | AIR | 2026-01-30 |  |  | Air shipment for Covia |  |  | 2026-01-30 | 2026-02-02 | TRUE | 1 | 18
Received | Emilka Guerra | 2026-01-15 | PO08604 |  | 2026-01-23 | GB5782-2000 | Bolt M20x90 | 12 | Super Cast Limited | China | CA WAREHOUSE | 2026-01-24 | AIR | 2026-01-30 |  |  | Air shipment for Covia |  |  | 2026-01-30 | 2026-02-02 | TRUE | 1 | 18
Received | Emilka Guerra | 2026-01-15 | PO08604 |  | 2026-01-23 | Nut M20 | Nut M20 | 10 | Super Cast Limited | China | CA WAREHOUSE | 2026-01-24 | AIR | 2026-01-30 |  |  | Air shipment for Covia |  |  | 2026-01-30 | 2026-02-02 | TRUE | 1 | 18
Received | Emilka Guerra | 2026-01-15 | PO08604 |  | 2026-01-23 | GB5783-2000 | Bolt M20x55 | 2 | Super Cast Limited | China | CA WAREHOUSE | 2026-01-24 | AIR | 2026-01-30 |  |  | Air shipment for Covia |  |  | 2026-01-30 | 2026-02-02 | TRUE | 1 | 18
Received | Yannett Yeomans | 2026-01-16 | PO08606 | SO18543 | 23/01/26 | W-F117/C21 | Shaft Spacer, 8/6 F-AH, 420SS | 1 | Super Cast Limited | China | CA WAREHOUSE |  | AIR |  |  |  | Air shipment for Covia |  | were shipped out from Shijiazhuang to Mississauga via DHL on Jan 31, 2026 | 2026-02-06 | 2026-02-02 | TRUE | #VALUE! | 17
Received | Yannett Yeomans | 2026-01-16 | PO08606 | SO18543 | 23/01/26 | W-F117/C21 | Shaft Spacer, 8/6 F-AH, 420SS | 1 | Super Cast Limited | China | CA WAREHOUSE | 2026-01-29 | AIR | FIRST WEEK OF FEBRUARY |  | DHL waybill (9484911376) | Air shipment for Covia |  | were shipped out from Shijiazhuang to Mississauga via DHL on Jan 31, 2026 | 2026-06-02 | 2026-02-02 | TRUE | #VALUE! | 17
Received | Amanda Qiao | 2026-01-16 | PO08607 | SO18501 | 2026-01-21 | GATES - XPC2240 | V-Belt, Wedge, Gates, SPC 2240mm, Synthetic Rubber | 8 | Wajax Limited - Mississauga | Canada | CA WAREHOUSE | 2026-03-05 | LAND | [6 empty] | 2026-01-23 | 2026-03-05 | TRUE | 43 | 48 | 6.8571
Received | Emilka Guerra | 2026-01-16 | PO08608 | SO18503 - SO18572 | 2026-03-13 | AC-98-5414-HC3 | Suction Side Plate, 5x4-14 SRL-C, High Chrome, 3-Piece Design | 2 | IGH | Mexico | CA WAREHOUSE | 2026-04-14 | LAND | ETA Warehouse 29/abril |  | XP Ref. # 088414 | Supplier will only ship one suction side plate 5×4 HM SRL-C | / | IGH: Currently, we are experiencing a high scrap rate with our present design that uses drilled through holes on the suction plate. Out of three pieces that were machined and drilled, two cracked during the hardening heat treatment. We are in the process of replacing the part, although I am not certain it will be ready by Tuesday. We will do our best to have it completed in time. | 2026-04-10 | 2026-04-29 | TRUE | 32 | 103
Received | Emilka Guerra | 2026-01-16 | PO08608 | SO18503 - SO18572 | 2026-03-13 | AC-98-5414-HC3 | Suction Side Plate, 5x4-14 SRL-C, High Chrome, 3-Piece Design | 1 | IGH | Mexico | CA WAREHOUSE | 2026-02-27 | LAND |  |  |  |  | confirmed SHIPMENT ETD FEB 27, 2026 |  | 2026-04-10 | 2026-03-09 | TRUE | -14 | 52 | 7.4286
Ready to Ship & Delayed | Leriel Reyes | 2026-01-16 | PO08609 | SO17341 | 2026-04-27 | D-XS350-560G | Horizontal Split-Case Pump 20/14 | 1 | Super Cast Limited | China | BARRICK DIRECT SHIPPING |  | SEA | 2026-07-06 | CIF Santo Domingo | CMA CGM DIGNITY / V.1PPSDE1MA | Barrick shipment | Peter 05/16: the performance test was done yesterday (May 15), can be ready to leave factory by next Friday (May 22). Peter 05/29: I already booked the vessel of ETD June 7 from Shanghai to Caucedo. | 04/03: Just confirmed drawings this week. Estimated to be ready for shipment on May 15. June 06/12: It is late. ETD Shanghai: June 18 | 2026-07-06 |  | FALSE | -46139 | -46038 | -6576.8571
Ready to Ship & Delayed | Leriel Reyes | 2026-01-16 | PO08609 | SO17341 | 2026-04-27 | 10652/2001 | Set of Coupling and Coupling Guard XS350-560G, Cast Iron | 1 | Super Cast Limited | China | BARRICK DIRECT SHIPPING |  | SEA | 2026-07-06 | CIF Santo Domingo | CMA CGM DIGNITY / V.1PPSDE1MA | Barrick shipment | Peter 05/16: the performance test was done yesterday (May 15), can be ready to leave factory by next Friday (May 22). Peter 05/29: I already booked the vessel of ETD June 7 from Shanghai to Caucedo. | 04/03: Just confirmed drawings this week. Estimated to be ready for shipment on May 15. June 06/12: It is late. ETD Shanghai: June 18 | 2026-07-06 |  | FALSE | -46139 | -46038 | -6576.8571
Ready to Ship & Delayed | Leriel Reyes | 2026-01-16 | PO08609 | SO17341 | 2026-04-27 | 10653/1501 | Common base XS350-560G, Carbon Steel | 1 | Super Cast Limited | China | BARRICK DIRECT SHIPPING |  | SEA | 2026-07-06 | CIF Santo Domingo | CMA CGM DIGNITY / V.1PPSDE1MA | Barrick shipment | Peter 05/16: the performance test was done yesterday (May 15), can be ready to leave factory by next Friday (May 22). Peter 05/29: I already booked the vessel of ETD June 7 from Shanghai to Caucedo. | 04/03: Just confirmed drawings this week. Estimated to be ready for shipment on May 15. June 06/12: It is late. ETD Shanghai: June 18 | 2026-07-06 |  | FALSE | -46139 | -46038
Received | Ian Trottier | 2026-01-16 | PO08610 | SO18523 | 2026-01-30 | G-00-573-175-293 | Jacking Bolt, 8x6-18/10x8-21 SRL-C, HEX (OEM) Style, c/w Jam Nut | 4 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE | 2026-02-06 | LAND | Monday 9th FEB |  |  |  |  | 02/10/2026 Received | 2026-02-03 | 2026-02-10 | TRUE | 7 | 25
Received | Yannett Yeomans | 2026-01-19 | PO08611 | SO18543 | 2026-01-26 | W-SP15116L/D21 | Lower Strainer, 150 or 200 SV-SP, Ductile Iron | 1 | Super Cast Limited | China | CA WAREHOUSE | 2026-01-30 | SEA | 2026-02-02 | [5 empty] | 2026-02-02 | 2026-02-04 | TRUE | 4 | 16
Received | Emilka Guerra | 2026-01-19 | PO08612 | Stock | 2026-02-27 | G-1.5x2-14-JC-HC | Pump, 1.5x2-14, Dynapro DC, Frame 2J, High Chrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-04-17 | SEA | ETA Warehouse June 10-15 |  | BL 1073610888 | EG: Included in Invoice # 20251212-11A | Betty confirmed shipment | Email requesting status sent on March 19th | 2026-05-08 | 2026-06-01 | TRUE | 49 | 133
Received | Emilka Guerra | 2026-01-19 | PO08613 | SO18571 | 2026-03-16 | SA-567243 | Wear Disc, Sala 6x5 VSP-VF, High Chrome | 2 | Hyperflo | Canada | CA WAREHOUSE | 2026-05-13 | LAND | ETA WAREHOUSE MAY 15-18 |  |  |  | May 8th: supplier will receive the order at their facility by tuesday 12th |  | 2026-03-31 | 2026-05-20 | TRUE | 58 | 121 | 17.2857
Received | Ian Trottier | 2026-01-19 | PO08614 | SO18550 | 23/01/26 | AC-98-236-348-501 | Packing Gland (2 Half/Set), Allis Chalmers PWO, Group 3 & 4, 316SS | 1 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE |  | LAND | 2026-01-29 | [5 empty] | 2026-01-19 | 2026-01-29 | TRUE | #VALUE! | 10 | 1.4286
Received | Ian Trottier | 2026-01-19 | PO08615 | SO18550 | 2026-03-27 | G-RC04060A01 1220 | Stuffing Box Cover, 13", 3196 MTX, Titanium, Big Bore, Non-Jacketed | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-03-25 | SEA | 2026-03-27 |  | DYNC-111 | Ready to ship on march 25 | via air shipment together with PO 08589 at the end of March | Email requesting status sent on March 19th | 2026-01-19 | 2026-03-30 | TRUE | -2 | 70
Received | Ian Trottier | 2026-01-19 | PO08616 | SO8586 | 2026-02-06 | W-E073XLM/E05 | Shaft (X-Large), 6/4 E-AH, 1045 Steel, Metric | 1 | Super Cast Limited | China | CA WAREHOUSE | 2026-02-02 | SEA | first week of april |  |  | left Tianjin for Toronto by sea on Jan 29, 2026 | Expected to arrive first week of april |  | 2026-04-17 | 2026-04-01 | TRUE | -4 | 72
Received | Emilka Guerra | 2026-01-20 | PO08617 | SO18559 | 2026-10-02 | WO-9090150-183 | Impeller Nut, Worthington 6 FRBH-183/223, 316SS | 1 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND | 2026-02-26 | [5 empty] | 2026-03-10 | 2026-02-26 | TRUE | -46297 | 37
Received | Emilka Guerra | 2026-01-21 | PO08618 | SO18540 | 2026-03-18 | DE-503771 | Bushing, Denver, Neoprene | 2 | IGH | Mexico | CA WAREHOUSE | 2026-04-14 | LAND | ETA Warehouse 29/abril |  | XP Ref. # 088414 |  |  |  | 2026-04-15 | 2026-04-29 | TRUE | 27 | 98 | 14
Received | Emilka Guerra | 2026-01-21 | PO08618 | SO18540 | 2026-03-18 | DE-503720 | Ring Seal, 12x10 SRL-C, Denver, Steel | 6 | IGH | Mexico | CA WAREHOUSE | 2026-04-14 | LAND | ETA Warehouse 29/abril |  | XP Ref. # 088414 |  |  |  | 2026-04-15 | 2026-04-29 | TRUE | 27 | 98 | 14
Received | Emilka Guerra | 2026-01-21 | PO08618 | SO18540 | 2026-03-18 | DE-505443 | Stuffing Box, 12x10 SRL, Denver, Cast Iron | 3 | IGH | Mexico | CA WAREHOUSE | 2026-02-27 | LAND | 2026-03-09 |  |  |  | confirmed SHIPMENT ETD FEB 27, 2026 | Email for POs sent on Jan 28th, 2026 Follow up for SHipment date sent on Feb 6th, 2026 | 2026-04-15 | 2026-03-09 | TRUE | -19 | 47 | 6.7143
Received | Emilka Guerra | 2026-01-21 | PO08618 | SO18540 | 2026-03-18 | DE-505455 | Plate Seal, Denver, Steel | 3 | IGH | Mexico | CA WAREHOUSE | 2026-02-27 | LAND | 2026-03-09 |  |  |  | confirmed SHIPMENT ETD FEB 27, 2026 | Email for POs sent on Jan 28th, 2026 Follow up for SHipment date sent on Feb 6th, 2026 | 2026-04-15 | 2026-03-09 | TRUE | -19 | 47 | 6.7143
Received | Emilka Guerra | 2026-01-21 | PO08618 | SO18540 | 2026-03-18 | DU-503695 | Gland Follower, Packing Gland, 12 X 10 SRL FR 5 | 3 | IGH | Mexico | CA WAREHOUSE | 2026-02-27 | LAND | 2026-03-09 |  |  |  | confirmed SHIPMENT ETD FEB 27, 2026 | Email for POs sent on Jan 28th, 2026 Follow up for SHipment date sent on Feb 6th, 2026 | 2026-04-15 | 2026-03-09 | TRUE | -19 | 47 | 6.7143
Received | Emilka Guerra | 2026-01-21 | PO08618 | SO18540 | 2026-03-18 | DE-503678 | Expeller, 12x10-25 SRL-C, Denver, Cast Iron | 6 | IGH | Mexico | CA WAREHOUSE | 2026-02-27 | LAND | 2026-03-09 |  |  |  | confirmed SHIPMENT ETD FEB 27, 2026 | Email for POs sent on Jan 28th, 2026 Follow up for SHipment date sent on Feb 6th, 2026 | 2026-04-15 | 2026-03-09 | TRUE | -19 | 47 | 6.7143
Received | Livan Hernandez | 2026-01-21 | PO08619 | SO17961 | 2026-11-02 | DU-BY38081C | Bearing Housing Drain Plug, Durco Mark 2, Group 2 | 1 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND | 2026-02-26 | [5 empty] | 2026-03-11 | 2026-02-26 | TRUE | -46328 | 36 | 5.1429
Received | Ian Trottier | 2026-01-21 | PO08621 | SO18598 | 2026-02-13 | W-E424M/C23 | Shaft Sleeve (Mechanical Seal), 6/4 or 8/6 E or R-AH, 316SS | 1 | Super Cast Limited | China | CA WAREHOUSE | 2026-03-29 | SEA | ETA Warehouse May last week |  | LS21TJ2603672 | ETA Port of Prince Rupert: Apr 22, 2026 | left Tianjin for Toronto by sea on Mar 29, 2026 |  | 2026-05-01 | 2026-05-20 | TRUE | 44 | 119
Received | Ian Trottier | 2026-01-21 | PO08621 | SO18598 | 2026-02-13 | W-E4147/A49 | Impeller, 6/4 D or E-AH, Ultrachrome, Corrosion Resistant, 5-Vane | 1 | Super Cast Limited | China | CA WAREHOUSE | 2026-03-29 | SEA | ETA Warehouse May last week |  | LS21TJ2603672 | ETA Port of Prince Rupert: Apr 22, 2026 | left Tianjin for Toronto by sea on Mar 29, 2026 |  | 2026-05-01 | 2026-05-20 | TRUE | 44 | 119
IN TRANSIT & DELAYED | Ian Trottier | 2026-01-21 | PO08623 | Stock - SO18744 - | 2026-03-18 | AC-98-330-286-503 | Impeller (Open), 3x3-10 SRL, Neoprene | 2 | Super Cast Limited | China | CA WAREHOUSE | 2026-05-08 | SEA | ETA Prince Rupert: May 30 ETA Warehouse is around Jul. 13 - 17 |  | LS21TJ2604679 |  | Peter 4/30: Already booked the vessel of ETD May 7 from Tianjin to Toronto. Left Tianjin for Toronto by sea on May 8 | Email for follow up sent on April 29th | 2026-05-27 |  | FALSE | 51 | -46043
Received | Ian Trottier | 2026-01-22 | PO08625 | SO18600 | 2026-02-05 | G-R76498 | Lantern Ring, 3175-M, Teflon | 3 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND | 2026-02-26 | [5 empty] | 2026-02-12 | 2026-02-26 | TRUE | -46058 | 35
Received | Ian Trottier | 2026-01-22 | PO08625 | SO18600 | 2026-02-05 | G-B00294A 6956 | Shaft Sleeve, 3175-S, 316SS, Ni-Chrome Boron | 3 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND | 2026-02-26 | [5 empty] | 2026-02-12 | 2026-02-26 | TRUE | -46058 | 35 | 5
Ready to Ship | Emilka Guerra | 2026-01-21 | PO08620 | SO18603 | 2026-06-03 | SZ-9195970141 | Impeller, Sulzer | 6 | Super Cast Limited | China | MX WAREHOUSE | 29/05/26 | SEA | 2026-05-29 |  |  |  | The available vessel is of ETD Tianjin Apr 11, 2026. |  | 2026-05-29 |  | FALSE
Received | Ian Trottier | 2026-01-22 | PO08625 | SO18600 | 2026-02-05 | G-B00295A 6956 | Shaft Sleeve, 3175-M, 316SS, Ni-Chrome Boron | 4 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND | 2026-02-26 | [5 empty] | 2026-02-12 | 2026-02-26 | TRUE | -46058 | 35
Received | Ian Trottier | 2026-01-22 | PO08625 | SO18600 | 2026-02-05 | G-B00296A 6956 | Shaft Sleeve, 3175-L, 316SS, Ni-Chrome Boron | 1 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND | 2026-02-26 | [5 empty] | 2026-02-12 | 2026-02-26 | TRUE | -46058 | 35 | 5
Received | Ian Trottier | 2026-01-23 | PO08626 | SO18182 | 2026-02-06 | DU-AY38411A-GTB | Impeller Gasket, Durco Mark 2 & 3, Group 2, Flat Style, Grafoil. | 10 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND | 2026-02-26 | [5 empty] | 2026-02-13 | 2026-02-26 | TRUE | -46059 | 34 | 4.8571
Received | Ian Trottier | 2026-01-22 | PO08627 | SO18359 | 2026-01-30 | Alternate P/N 114862 | Stud (Casing), Sala, Steel | 24 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE |  | LAND | Monday 9th FEB |  |  |  |  | 02/10/2026 Received | 2026-01-23 | 2026-02-10 | TRUE | -46052 | 19 | 2.7143
Received | Ian Trottier | 2026-01-23 | PO08627 | SO18359 | 2026-01-30 | AC-98-331-958-803 | Shaft Sleeve, 5x4/5x5/6x6 SRL & SRL-C, Steel | 1 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE |  | LAND | Monday 9th FEB |  |  |  |  | 02/10/2026 Received | 2026-01-23 | 2026-02-10 | TRUE | -46052 | 18 | 2.5714
Received | Ian Trottier | 2026-01-23 | PO08628 | SO18582 | 2026-02-16 | DU-DY43289A-CD4 | Casing, (Recessed), 3x3R-10, Durco Mark 2&3, Group 2, CD4 | 1 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND | 2026-02-26 | [5 empty] | 2026-02-27 | 2026-02-26 | TRUE | -46069 | 34 | 4.8571
Received | Livan Hernandez | 2026-01-21 | PO08629 | SO18577 | 2026-03-13 | DU-CY50435A-2205 | Shaft (Solid), Durco Mark 3 Group 3, 2205 Duplex Stainless | 1 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-05-05 | LAND | ETA May 1st week |  |  |  | Hisco May 5th: Quenton Included in list for ready orders / waiting info on shipping date | April 30th: email follow up for orders. | 2026-03-27 | 2026-05-07 | TRUE | 53 | 106
IN TRANSIT & DELAYED | Ian Trottier | 2026-01-21 | PO08630 | Stock | 2026-03-16 | G-R102-871 2238 | Shaft (Sleeve Type), 3175-S, 4140 Steel | 2 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-03 | SEA | Around June 5 |  | batch number: DYNC-112 / ECU: TAOTOR07006 | was shipped by sea on 3rd April. | ETA Vancouver on May 7 |  | 2026-05-25 |  | FALSE | 18 | -46043 | -6577.5714
Received | Ian Trottier | 2026-01-23 | PO08631 | SO18359 | 2026-05-25 | AC-98-332-794-501 | Suction Side Plate, 10x10-28 SRL-XT, Natural Rubber | 12 | Super Cast Limited | China | CA WAREHOUSE | 2026-03-12 | SEA | ETA Warehouse May last week |  | ETD Prince Rupert: Apr 4, 2026. | LS21TJ2603571 | 6 pcs in transit |  | 2026-03-19 | 2026-04-27 | TRUE | -74 | 94 | 13.4286
Received | Ian Trottier | 2026-01-23 | PO08632 | SO18359 | 2026-05-15 | SA-128214-1 | Inlet, Sala VS150, High Chrome | 5 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | Around Week of Apr. 30 - May 1 |  | TCLU8795637 |  | Naipu: confirmed shipped out |  | 2026-03-06 | 2026-04-28 | TRUE | -46157 | 95 | 13.5714
Received | Emilka Guerra | 2026-01-26 | PO08633 | SO18560 | 2026-03-23 | SA-567895 | O-ring, Sala, ,STGVA-65W | 2 | Hyperflo | Canada | CA WAREHOUSE | 2026-05-13 | LAND | ETA WAREHOUSE MAY 15-18 |  |  |  | May 8th: supplier will receive the order at their facility by tuesday 12th |  | 2026-04-06 | 2026-05-20 | TRUE | 51 | 114 | 16.2857
Received | Emilka Guerra | 2026-01-26 | PO08633 | SO18560 | 2026-03-23 | SA-567243 | Wear Disc, Sala 6x5 VSP-VF, High Chrome | 2 | Hyperflo | Canada | CA WAREHOUSE | 2026-05-13 | LAND | ETA WAREHOUSE MAY 15-18 |  |  |  | May 8th: supplier will receive the order at their facility by tuesday 12th |  | 2026-04-06 | 2026-05-20 | TRUE | 51 | 114 | 16.2857
Received | Emilka Guerra | 2026-01-26 | PO08633 | SO18560 | 2026-03-23 | SA-572855 | Impeller, Sala, STGVA-65W | 2 | Hyperflo | Canada | CA WAREHOUSE | 2026-05-13 | LAND | ETA WAREHOUSE MAY 15-18 |  |  |  | May 8th: supplier will receive the order at their facility by tuesday 12th | Hyperflo: there is currently a production delay for part 100851-2 | 2026-04-06 | 2026-05-20 | TRUE | 51 | 114 | 16.2857
Received | Ian Trottier | 2026-01-27 | PO08634 | SO18615 | 2026-02-04 | DU-DY21855A/CBS-CD4 | Rear Cover, 13", Durco Mark 2&3 Group 2, CD4MCu, Small Bore | 1 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND | 2026-02-26 | [5 empty] | 2026-02-09 | 2026-02-26 | TRUE | -46057 | 30 | 4.2857
Received | Ian Trottier | 2026-01-23 | PO08635 | SO18414 | 2026-01-27 | 102-863 1001 | Thrust Bearing Housing, 3175-M, Cast Iron, Oil Lubricated | 1 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND | 2026-02-26 | [5 empty] | 2026-01-28 | 2026-02-26 | TRUE | -46049 | 34
Received | Emilka Guerra | 2026-01-27 | PO08636 | SO18359 | 2026-01-30 | AC-98-431-743-501 | Shaft Assembly, 10x8-21 SRL-C, 1045 Steel | 4 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2026-02-10 | 2026-02-10 | TRUE | -46052 | 14 | 2
Received | Emilka Guerra | 2026-01-28 | PO08637 | SO18627 - Stock | 2026-04-08 | GA-25223 | Shaft, 60", G-Series 2.5" VSP, 1000 Series, Natural Rubber Lined | 1 | IGH | Mexico | CA WAREHOUSE | 2026-04-14 | LAND | ETA Warehouse 29/abril |  | XP Ref. # 088414 |  |  |  | 2026-04-13 | 2026-04-29 | TRUE | 6 | 91 | 13
Received | Emilka Guerra | 2026-01-28 | PO08637 | SO18627 - Stock | 2026-04-08 | AC-98-431-775-001 | Suction Side Casing, 8x6-18 SRL-C, Cast Iron | 1 | IGH | Mexico | CA WAREHOUSE | 2026-02-27 | LAND | 2026-03-09 |  |  |  | confirmed SHIPMENT ETD FEB 27, 2026 | Email for POs sent on Jan 28th, 2026 Follow up for SHipment date sent on Feb 6th, 2026 | 2026-05-13 | 2026-03-06 | TRUE | -40 | 37 | 5.2857
Received | Emilka Guerra | 2026-01-28 | PO08638 | Stock | 2026-03-13 | AC-98-331-606-808 | Suction Side Plate, 8x4(5)(6)-17, PWO, CD4MCu | 3 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-20 | SEA | ETA Warehouse Mid June |  | DYNC-113 SEA // BL# HHSE6042268, Container # CAAU5246660 | ETA Vancouver on May 5 |  |  | 2026-05-29 | 2026-05-26 | TRUE | 38 | 118 | 16.8571
IN TRANSIT & DELAYED | Emilka Guerra | 2026-01-28 | PO08638 | Stock | 2026-03-13 | AC-98-431-577-501 | Frame, 14", Allis Chalmers PWO, Frame A1, Oil-Lubed, Cast Iron | 2 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-06-12 | SEA | ETA Warehouse 1st week of august |  | shipped via DYNC-116 SEA. YM COSMOS/190E | ETD Qingdao 12 June ETA Toronto 16 July |  | Email for follow up sent on April 23rd | 2026-05-29 |  | FALSE | 91 | -46050 | -6578.5714
Received | Emilka Guerra | 2026-01-28 | PO08638 | Stock | 2026-03-13 | DU-DY21855A/CBS-CD4 | Rear Cover, 13", Durco Mark 2&3 Group 2, CD4MCu, Small Bore | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-03 | SEA | Around June 5 |  | batch number: DYNC-112 / ECU: TAOTOR07006 | was shipped by sea on 3rd April. | ETA Vancouver on May 7 |  | 2026-05-29 | 2026-05-20 | TRUE | 21 | 112
Received | Emilka Guerra | 2026-01-28 | PO08638 | Stock | 2026-03-13 | G-76772X 2229 | Shaft Sleeve, 3196 STX, 316SS | 9 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-03 | SEA | Around June 5 |  | batch number: DYNC-112 / ECU: TAOTOR07006 | was shipped by sea on 3rd April. | ETA Vancouver on May 7 |  | 2026-05-29 | 2026-05-20 | TRUE | 21 | 112 | 16
Received | Emilka Guerra | 2026-01-28 | PO08638 | Stock | 2026-03-13 | G-76772X 2229 | Shaft Sleeve, 3196 STX, 316SS | 6 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-03-23 | AIR | 2026-05-29 |  |  |  | expected to be transported to Qingdao port on March 23rd |  | 2026-05-29 | 2026-04-02 | TRUE | 10 | 64 | 9.1429
Received | Emilka Guerra | 2026-01-28 | PO08638 | Stock | 2026-03-13 | OLPWZ011004B, G-A04951A217 | Bearing Isolator (Outboard), 3196 STX/STi, 303SS Rotor / Bronze Stator w/Viton | 15 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-03 | SEA | Around June 5 |  | batch number: DYNC-112 / ECU: TAOTOR07006 | was shipped by sea on 3rd April. | ETA Vancouver on May 7 |  | 2026-05-29 | 2026-05-20 | TRUE | 21 | 112 | 16
Received | Emilka Guerra | 2026-01-28 | PO08638 | Stock | 2026-03-13 | G-P1600S0S00 X050 | Power End, 3196 STX, 4140 Shaft (Sleeved Type), Oil Lubed | 2 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-03 | SEA | Around June 5 |  | batch number: DYNC-112 / ECU: TAOTOR07006 | was shipped by sea on 3rd April. | ETA Vancouver on May 7 | Email for follow up sent on April 23rd | 2026-05-29 | 2026-05-15 | TRUE | 21 | 107 | 15.2857
Received | Emilka Guerra | 2026-01-28 | PO08638 | Stock | 2026-03-13 | G-105-202 1012 | Casing, 2x3-6, 3196 STX, Ductile Iron | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-20 | SEA | ETA Warehouse Mid June |  | DYNC-113 SEA // BL# HHSE6042268, Container # CAAU5246660 | ETA Vancouver on May 5 |  |  | 2026-05-29 | 2026-05-26 | TRUE | 38 | 118 | 16.8571
Received | Emilka Guerra | 2026-01-28 | PO08638 | Stock | 2026-03-13 | G-P1600M0S00 X060 | Power End, 3196 MTX, 316SS Shaft (Sleeved Type), Oil Lubed | 2 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-03 | SEA | Around June 5 |  | batch number: DYNC-112 / ECU: TAOTOR07006 | was shipped by sea on 3rd April. | ETA Vancouver on May 7 | Email for follow up sent on April 23rd | 2026-05-29 | 2026-05-15 | TRUE | 21 | 107 | 15.2857
Received | Emilka Guerra | 2026-01-28 | PO08638 | Stock | 2026-03-13 | G-104-556 1216 | Casing, 1x1.5-8, 3196 STX, CD4MCu | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-20 | SEA | ETA Warehouse Mid June |  | DYNC-113 SEA // BL# HHSE6042268, Container # CAAU5246660 | ETA Vancouver on May 5 |  |  | 2026-05-29 | 2026-05-26 | TRUE | 38 | 118 | 16.8571
Ready to Ship & Delayed | Ian Trottier | 2026-01-28 | PO08639 | SO18654 | 2026-04-08 | G-0C01359A 1203 | Flush Gland Assembly, 3196 MTX, Big Bore, 316SS | 2 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-06-16 | LAND | 2026-02-27 |  |  |  | Quenton Hisco 06/16: Ready to ship - Pending Pick up confirmation by logistics | May 5th: Asked for update on this delayed PO. Hisco May5th: Delayed ~ to be shipped Mid-may | 2026-02-27 |  | FALSE | 69 | -46050
Received | Ian Trottier | 2026-01-29 13:30 | PO08640 | SO18651 - RE | 2026-04-23 | AC-52-430-274-501 | Frame, Allis-Chalmers CSO, F4D1, Cast Iron | 2 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND | 2/26/02 | [5 empty] | 2026-04-24 | 2026-02-26 | TRUE | -46135 | 27.4377 | 3.9197
Received | Emilka Guerra | 2026-01-29 | PO08641 | SO18653 | 2026-03-13 | GA-24042 | Casing, G-Series 2.5" VSP, 1000 Series, Natural Rubber | 1 | IGH | Mexico | CA WAREHOUSE | 2026-04-15 | LAND | ETA Warehouse 29/abril |  | XP Ref. # 088414 |  |  |  | 2026-04-10 | 2026-04-29 | TRUE | 33 | 90 | 12.8571
Received | Emilka Guerra | 2026-01-29 | PO08641 | SO18653 | 2026-03-13 | GA-23972 | Impeller, G-Series 2.5" VSP, 1000 Series, Natural Rubber | 1 | IGH | Mexico | CA WAREHOUSE | 2026-04-16 | LAND | ETA Warehouse 29/abril |  | XP Ref. # 088414 |  |  |  | 2026-04-10 | 2026-04-29 | TRUE | 34 | 90 | 12.8571
Received | Emilka Guerra | 2026-01-29 | PO08641 | SO18653 | 2026-03-13 | GA-25232 | Cover Plate, G-Series 2.5" VSP, 1000 Series, Natural Rubber | 1 | IGH | Mexico | CA WAREHOUSE | 2026-04-17 | LAND | ETA Warehouse 29/abril |  | XP Ref. # 088414 |  |  |  | 2026-04-10 | 2026-04-29 | TRUE | 35 | 90 | 12.8571
IN TRANSIT | Emilka Guerra | 2026-01-29 | PO08642 | Stock | 2026-03-20 | 571638 | Casing, Sala VS150, High Chrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-06-19 | SEA | ETA Warehouse Mid-Sept |  |  | Follow email sent for update on June 16th . We already shipped them to Tianjin, but the vessel delayed, it shows that it will depart on June 19. | Betty 5/15: Included in Comercial Invoice / #20260205-11 | Status email sent on April 22nd Status email sent on May 15th | 2026-05-29 |  | FALSE | 91 | -46051 | -6578.7143
IN TRANSIT & DELAYED | Emilka Guerra | 2026-01-29 | PO08642 | Stock | 2026-03-20 | AC-98-431-768-501 | Shaft Assembly, 8x6-18 SRL-C, 1045 Steel | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | 2026-05-29 |  | 20251217-11 Sea Waybill-No. 1074440607 |  | Peter 05/16: the vessel already arrived at Tianjin seaport, will depart Tianjin tomorrow: May 17 | Status email sent on April 22nd Betty 04/23: It is ready, waiting on weight and dimentions, I wILL update later. | 2026-05-29 |  | FALSE | -46101 | -46051 | -6578.7143
IN TRANSIT & DELAYED | Emilka Guerra | 2026-01-29 | PO08642 | Stock | 2026-03-20 | W-G12060/S01 | Intake Joint Ring, EPDM | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | 2026-05-29 |  | 20251217-11 Sea Waybill-No. 1074440607 |  | Peter 05/16: the vessel already arrived at Tianjin seaport, will depart Tianjin tomorrow: May 17 | Status email sent on April 22nd Betty 04/23: It is ready, waiting on weight and dimentions, I wILL update later. | 2026-05-29 |  | FALSE | -46101 | -46051 | -6578.7143
IN TRANSIT | Emilka Guerra | 2026-01-29 | PO08642 | Stock | 2026-03-20 | AC-98-131-246-511 | Deflector (Water Slinger), 5x5/5x4/6x6 SRL & SRL-C, Neoprene/Steel | 20 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-04-17 | SEA | ETA Warehouse June 10-15 |  | BL 1073610888 | EG: Included in Invoice | Betty confirmed shipment |  | 2026-05-29 |  | FALSE | 28 | -46051 | -6578.7143
DELAYED PRODUCTION | Ian Trottier | 2026-01-29 | PO08643 | SO18666 | 2026-03-09 | W-TUL55147DP1/A05 | Impeller, 5 VCG, Duty Point, No Back Vanes, 550 TU-L, High Chrome | 1 | Shijiazhuang Mets Machinery Co., LTD | China | CA WAREHOUSE | 2026-04-30 | SEA | 2026-05-18 |  |  | follow up sent May 14th follow up sent June 1 follow up sent June 16th | and the estimated date ready to leave factory will be by next Thursday (Apr 24). Peter 05/21: The new impeller is under machining, expected to be ready for shipment by May 30. | Due to its own foundry shop will not be put into use until June, 2026, Metslurry had this impeller casted by other foundry factry. But bloced by the local environmental control measures, the rough casting did not come out until last weekend. Now the rough casting is under cleaning, will be sent to Metslurry's machining shop by this Friday. I contacted Metslurry's boss, he promised to put this impeller's machining at the first top, Peter 06/16 Very bad luck. The 3th and 4th rough castings were found defects and rejected by the QC department. The 5th is expected to complete around June 22, if everything goes well. | 2026-05-18 |  | FALSE | 52 | -46051 | -6578.7143
Received | Emilka Guerra | 2026-01-30 | PO08646 | Stock | 2026-03-20 | W-B075/C21 | Shaft Sleeve, 1.5/1 or 2/1.5 B-AH, 420SS Heat Treated, Hardened | 3 | Super Cast Limited | China | CA WAREHOUSE | 2026-03-26 | SEA | ETA Prince Rupert: May 30 ETA Warehouse is around Jul. 13 - 17 |  | LS21TJ2603672 | ETA Port of Prince Rupert: Apr 22, 2026 | (1st batch) is now in Tianjin seaport waiting for the vessel of ETD Mar 26 to Toronto |  | 2026-05-29 | 2026-05-20 | TRUE | 6 | 110 | 15.7143
Received | Emilka Guerra | 2026-01-30 | PO08646 | Stock | 2026-03-20 | AC-98-231-071-501 | Suction Side Liner, 3x3-10 SRL, Natural Rubber | 4 | Super Cast Limited | China | CA WAREHOUSE | 2026-04-10 | SEA | ETA Prince Rupert: May 30 ETA Warehouse is around Jul. 13 - 17 |  | LS21TJ2604576 |  | left Tianjin for Toronto by sea on Apr 10, 2026 ETA Port of Prince Rupert: May 2, 2026 |  | 2026-05-29 | 2026-06-09 | TRUE | 21 | 130 | 18.5714
IN TRANSIT | Emilka Guerra | 2026-01-30 | PO08646 | Stock | 2026-03-20 | AC-98-431-641-501 | Impeller (Closed), 10x8-21 SRL-C, Natural Rubber | 10 | Super Cast Limited | China | CA WAREHOUSE | 2026-05-08 | SEA | ETA Prince Rupert: May 30 ETA Warehouse is around Jul. 13 - 17 |  | LS21TJ2604679 |  | left Tianjin for Toronto by sea on May 8, 2026 ETA Prince Rupert: May 30 |  | 2026-05-29 |  | FALSE | 49 | -46052 | -6578.8571
Received | Emilka Guerra | 2026-01-30 | PO08646 | Stock | 2026-03-20 | W-G118-1/C21 | Lantern Restrictor, 10/8 to 14/12, 420SS | 2 | Super Cast Limited | China | CA WAREHOUSE | 2026-03-26 | SEA | ETA Prince Rupert: May 30 ETA Warehouse is around Jul. 13 - 17 |  | LS21TJ2603672 | ETA Port of Prince Rupert: Apr 22, 2026 | (1st batch) is now in Tianjin seaport waiting for the vessel of ETD Mar 26 to Toronto |  | 2026-05-29 | 2026-05-20 | TRUE | 6 | 110 | 15.7143
IN TRANSIT | Emilka Guerra | 2026-01-30 | PO08646 | Stock | 2026-03-20 | W-RSL30147/A05 | Impeller, 300 RSL, High Chrome, 5-Vane | 1 | Super Cast Limited | China | CA WAREHOUSE | 2026-03-26 | SEA | ETA Prince Rupert: May 30 ETA Warehouse is around Jul. 13 - 17 |  | LS21TJ2603672 | ETA Port of Prince Rupert: Apr 22, 2026 | (1st batch) is now in Tianjin seaport waiting for the vessel of ETD Mar 26 to Toronto |  | 2026-05-29 |  | FALSE | 6 | -46052 | -6578.8571
Received | Emilka Guerra | 2026-01-30 | PO08646 | Stock | 2026-03-20 | AC-98-231-115-501 | Suction Side Liner, 5x4-14 SRL-C, Natural Rubber | 10 | Super Cast Limited | China | CA WAREHOUSE | 2026-04-10 | SEA | ETA Prince Rupert: May 30 ETA Warehouse is around Jul. 13 - 17 |  | LS21TJ2604576 |  | left Tianjin for Toronto by sea on Apr 10, 2026 ETA Port of Prince Rupert: May 2, 2026 |  | 2026-05-29 | 2026-06-09 | TRUE | 21 | 130 | 18.5714
Received | Emilka Guerra | 2026-01-30 | PO08646 | Stock | 2026-03-20 | AC-98-231-116-501 | Gland Side Liner, 5x4-14 SRL-C, Natural Rubber | 9 | Super Cast Limited | China | CA WAREHOUSE | 2026-04-10 | SEA | ETA Prince Rupert: May 30 ETA Warehouse is around Jul. 13 - 17 |  | LS21TJ2604576 |  | left Tianjin for Toronto by sea on Apr 10, 2026 ETA Port of Prince Rupert: May 2, 2026 |  | 2026-05-29 | 2026-06-09 | TRUE | 21 | 130 | 18.5714
Received | Ian Trottier | 2026-01-30 16:41 | PO08647 | SO18670 | 2026-02-06 | G-RD01080A 1216 | Stuffing Box Cover, 12", 3175-S, Standard Bore, CD4MCu | 2 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND | 2/26/02 | [5 empty] | 2026-02-13 | 2026-02-26 | TRUE | -46059 | 26.3052 | 3.7579
Received | Ian Trottier | 2026-01-30 | PO08649 | SO18666 - RE | 2026-03-31 | GA-20442 | Discharge Pipe, 60", G-Series 2.5" VSP, 1000 Series, Rubber Lined Inside | 2 | IGH | Mexico | CA WAREHOUSE | 2026-04-17 | LAND | ETA Warehouse 29/abril |  | XP Ref. # 088414 |  |  |  | 2026-04-14 | 2026-04-29 | TRUE | 17 | 89 | 12.7143
Received | Emilka Guerra | 2026-01-30 | PO08650 | Stock | 2026-03-20 | AC-98-331-958-831 | Shaft Sleeve, 5x4/5x5/6X6 SRL-C & SRL, 420SS Heat Treated, Hardened | 7 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-20 | SEA | ETA Warehouse Mid June |  | DYNC-113 SEA // BL# HHSE6042268, Container # CAAU5246660 | ETA Vancouver on May 5 |  |  | 2026-05-29 | 2026-05-26 | TRUE | 31 | 116 | 16.5714
Received | Emilka Guerra | 2026-01-30 22:45 | PO08651 | SO18669 - Stock | 2026-02-03 | G-RC03132A 2229 | Shaft (Less Sleeve), 3196 LTX, 316SS | 1 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND | 2026-02-26 | [5 empty] | 2026-03-02 | 2026-02-26 | TRUE | -46056 | 26.0524 | 3.7218
Received | Emilka Guerra | 2026-01-30 22:45 | PO08651 | SO18669 - Stock | 2026-02-03 | WO-9070000-012 | Casing Gasket, 18", Worthington FRBH | 10 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND | 2026-02-26 | [5 empty] | 2026-03-02 | 2026-02-26 | TRUE | -46056 | 26.0524 | 3.7218
Received | Amanda Qiao | 2026-01-31 | PO08652 | SO18397 | 2026-04-10 | 15HP-3600-VHS | 15 HP, 3600 RPM, 460/3/60, 254TP Frame, TEFC, NEMA Standard, BMR USA VHS Motor | 1 | Nanjing Wangyang Pumps Co., Ltd | China | CA WAREHOUSE | 2026-04-20 | SEA | 2026-06-10 |  | TN#1073820498 |  | ETD: 4/25 ETA VAN: 5/15 |  | 2026-06-10 | 2026-05-26 | TRUE | 10 | 115 | 16.4286
Received | Amanda Qiao | 2026-01-31 | PO08652 | SO18397 | 2026-04-10 | D-12RJHC-4-BRZ | Pump, Dynapro Vertical Turbine Without Motor, 12RJHC 4-Stages, Cast Iron w/Bronze Impeller | 1 | Nanjing Wangyang Pumps Co., Ltd | China | CA WAREHOUSE | 2026-04-20 | SEA | 2026-06-10 |  | TN#1073820498 |  | ETD: 4/25 ETA VAN: 5/15 |  | 2026-06-10 | 2026-05-26 | TRUE | 10 | 115 | 16.4286
IN TRANSIT & DELAYED | Amanda Qiao | 2026-01-31 | PO08653 | SO18397 | 2026-03-22 | W-100RVSP-900-CD4 | Sump Pump, W-Series, 100RV-SP, CD4MCu, 900mm Column | 2 | Shijiazhuang Mets Machinery Co., LTD | China | CA WAREHOUSE | 2026-05-22 | SEA | 2026-05-30 |  | LS21TJ2605577 | Follow up sent May 14th | 3/31: is in normal process, to be ready by Apr 15.\ 04/20:could not be ready for shipment until May 15. 05/14: already came out. The vessel of ETD May 21 from Tianjin to Toronto was booked yesterday 5/27: left Tianjin for Toronto by sea on May 22, 2026. | Metslurry is unable to cast the CD4MCu parts by themselves. They asked a foundry factory to cast for them. However, this foundry factory's production was delayed by local government's environmental measures. // April23rd: Impeller was rejected due to the impeller itself was damaged during removing the ingates. | 2026-05-30 |  | FALSE | 61 | -46053 | -6579
Received | Amanda Qiao | 2026-02-02 15:26 | PO08654 | SO18728 | 2026-04-02 | VI-GLH-H25-WM | Mag Drive Gear Pump, Micropump GLH-H25, With Motor | 1 | Vissers Sales Corp. | Canada | CA WAREHOUSE |  | LAND | 3/4/02 | [5 empty] | 2026-04-09 | 2026-03-04 | TRUE | -46114 | 29.3566
IN TRANSIT | Emilka Guerra | 2026-02-03 | PO08655 | SO18583 | 2026-04-28 | 9102760141-0 | Impeller, Ahlstrom, MCE 32-4, 2205 Duplex | 1 | Super Cast Limited | China | CA WAREHOUSE | 2026-05-22 | SEA | ETA WAREHOUSE Mid agust |  | LS21TJ2605578 | Long production time | Peter 04/27: I plan to ship it together with PO08697 which will come out by May 15. Peter 05/26: left Tianjin for Toronto by sea on May 22, 2026. | Email for follow up sent on April 23rd | 2026-07-07 |  | FALSE | 24 | -46056 | -6579.4286
Received | Emilka Guerra | 2026-02-03 | PO08656 | Stock | 2026-04-14 | G-104-424 1012 | Casing, 1.5x3-8, 3196 STX, Ductile Iron | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-20 | SEA | ETA Warehouse Mid June |  | DYNC-113 SEA // BL# HHSE6042268, Container # CAAU5246660 | ETA Vancouver on May 5 |  |  | 2026-07-07 | 2026-05-26 | TRUE | 6 | 112 | 16
Received | Emilka Guerra | 2026-02-03 | PO08656 | Stock | 2026-04-14 | G-247-41 1216 | Casing, 2x3-8, 3196 MTX, CD4MCu | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-20 | SEA | ETA Warehouse Mid June |  | DYNC-113 SEA // BL# HHSE6042268, Container # CAAU5246660 | ETA Vancouver on May 5 |  |  | 2026-07-07 | 2026-05-26 | TRUE | 6 | 112 | 16
Received | Emilka Guerra | 2026-02-03 | PO08656 | Stock | 2026-04-14 | G-247-44 1012 | Casing, 3x4-8, 3196 MTX, Ductile Iron | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-20 | SEA | ETA Warehouse Mid June |  | DYNC-113 SEA // BL# HHSE6042268, Container # CAAU5246660 | ETA Vancouver on May 5 |  |  | 2026-07-07 | 2026-05-26 | TRUE | 6 | 112 | 16
Received | Emilka Guerra | 2026-02-03 | PO08656 | Stock | 2026-04-14 | G-249-56 1012 | Casing, 3x4-10, 3196 MTX, Ductile Iron | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-20 | SEA | ETA Warehouse Mid June |  | DYNC-113 SEA // BL# HHSE6042268, Container # CAAU5246660 | ETA Vancouver on May 5 |  |  | 2026-07-07 | 2026-05-26 | TRUE | 6 | 112 | 16
Received | Emilka Guerra | 2026-02-03 | PO08656 | Stock | 2026-04-14 | G-RC04058A02 1012 | Stuffing Box Cover, 7" & 8", 3196 MTX, Ductile Iron, Big Bore, Non-Jacketed | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-20 | SEA | ETA Warehouse Mid June |  | DYNC-113 SEA // BL# HHSE6042268, Container # CAAU5246660 | ETA Vancouver on May 5 |  |  | 2026-07-07 | 2026-05-26 | TRUE | 6 | 112 | 16
Received | Emilka Guerra | 2026-02-03 | PO08656 | Stock | 2026-04-14 | G-RC04047A 1012 | Stuffing Box, 3x4-7, 3196 MTX, Ductile Iron, Taper Bore Plus | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-03 | SEA | Around June 5 |  | batch number: DYNC-112 / ECU: TAOTOR07006 | was shipped by sea on 3rd April. | ETA Vancouver on May 7 |  | 2026-07-07 | 2026-05-20 | TRUE | -11 | 106 | 15.1429
Received | Emilka Guerra | 2026-02-03 | PO08656 | Stock | 2026-04-14 | G-RC04109A01 1216 | Stuffing Box Cover, 7" & 8", 3196 MTX, CD4, Taper Bore Plus | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-03 | SEA | Around June 5 |  | batch number: DYNC-112 / ECU: TAOTOR07006 | was shipped by sea on 3rd April. | ETA Vancouver on May 7 |  | 2026-07-07 | 2026-05-20 | TRUE | -11 | 106 | 15.1429
Received | Emilka Guerra | 2026-02-03 | PO08656 | Stock | 2026-04-14 | G-RC04110A01 1216 | Stuffing Box Cover, 10", 3196 MTX, CD4, Taper Bore Plus | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-20 | SEA | ETA Warehouse Mid June |  | DYNC-113 SEA // BL# HHSE6042268, Container # CAAU5246660 | ETA Vancouver on May 5 |  |  | 2026-07-07 | 2026-05-26 | TRUE | 6 | 112 | 16
Received | Emilka Guerra | 2026-02-03 | PO08656 | Stock | 2026-04-14 | G-RC04048A 1012 | Stuffing Box Cover, 10", 3196 MTX, Ductile Iron, Taper Bore Plus | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-20 | SEA | ETA Warehouse Mid June |  | DYNC-113 SEA // BL# HHSE6042268, Container # CAAU5246660 | ETA Vancouver on May 5 |  |  | 2026-07-07 | 2026-05-26 | TRUE | 6 | 112 | 16
Received | Emilka Guerra | 2026-02-03 | PO08656 | Stock | 2026-04-14 | G-RC04049A 1012 | Stuffing Box Cover, 13", 3196 MTX, Ductile Iron, Taper Bore Plus | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-03 | SEA | Around June 5 |  | batch number: DYNC-112 / ECU: TAOTOR07006 | was shipped by sea on 3rd April. | ETA Vancouver on May 7 |  | 2026-07-07 | 2026-05-20 | TRUE | -11 | 106 | 15.1429
Received | Emilka Guerra | 2026-02-03 | PO08656 | Stock | 2026-04-14 | G-RC04111A01 1216 | Stuffing Box Cover, 13", 3196 MTX, CD4MCu, Taper Bore Plus | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-03 | SEA | Around June 5 |  | batch number: DYNC-112 / ECU: TAOTOR07006 | was shipped by sea on 3rd April. | ETA Vancouver on May 7 |  | 2026-07-07 | 2026-05-20 | TRUE | -11 | 106 | 15.1429
Received | Emilka Guerra | 2026-02-03 | PO08656 | Stock | 2026-04-14 | G-RC04107A01 1216 | Stuffing Box Cover, 6", 3196 STX, CD4MCu, Taper Bore Plus, Non-Jacketed | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-20 | SEA | ETA Warehouse Mid June |  | DYNC-113 SEA // BL# HHSE6042268, Container # CAAU5246660 | ETA Vancouver on May 5 |  |  | 2026-07-07 | 2026-05-26 | TRUE | 6 | 112 | 16
Received | Emilka Guerra | 2026-02-03 | PO08656 | Stock | 2026-04-14 | G-RC04044A 1012 | Stuffing Box Cover, 6", 3196 STX, Ductile Iron, Taper Bore Plus, Non-Jacketed | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-20 | SEA | ETA Warehouse Mid June |  | DYNC-113 SEA // BL# HHSE6042268, Container # CAAU5246660 | ETA Vancouver on May 5 |  |  | 2026-07-07 | 2026-05-26 | TRUE | 6 | 112 | 16
Received | Emilka Guerra | 2026-02-03 | PO08656 | Stock | 2026-04-14 | G-RC04108A01 1216 | Stuffing Box Cover, 8", 3196 STX, CD4MCu, Taper Bore Plus | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-20 | SEA | ETA Warehouse Mid June |  | DYNC-113 SEA // BL# HHSE6042268, Container # CAAU5246660 | ETA Vancouver on May 5 |  |  | 2026-07-07 | 2026-05-26 | TRUE | 6 | 112 | 16
Received | Emilka Guerra | 2026-02-03 | PO08656 | Stock | 2026-04-14 | G-RC04045A 1012 | Stuffing Box Cover, 8", 3196 STX, Ductile Iron, Taper Bore Plus, Non-Jacketed | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-03 | SEA | Around June 5 |  | batch number: DYNC-112 / ECU: TAOTOR07006 | was shipped by sea on 3rd April. | ETA Vancouver on May 7 |  | 2026-07-07 | 2026-05-20 | TRUE | -11 | 106 | 15.1429
Received | Emilka Guerra | 2026-02-04 14:58 | PO08657 | Stock | 2026-02-13 | SKF-34886, G-8690-23660 | Oil Seal (Inboard), 8x6-18 & 10x8-21 SRL-C, Nitrile | 5 | Wajax Limited - Mississauga | Canada | CA WAREHOUSE |  | LAND | 2026-02-17 | [5 empty] | 2026-02-20 | 2026-02-17 | TRUE | -46066 | 12.3761 | 1.768
Received | Emilka Guerra | 2026-02-04 14:58 | PO08657 | Stock | 2026-02-13 | SKF-33700, G-8690-10164 | Oil Seal (Outboard), 8x6-18 & 10x8-21 SRL-C, Nitrile | 5 | Wajax Limited - Mississauga | Canada | CA WAREHOUSE |  | LAND | 2026-02-17 | [5 empty] | 2026-02-20 | 2026-02-17 | TRUE | -46066 | 12.3761 | 1.768
Received | Emilka Guerra | 2026-02-04 14:58 | PO08657 | Stock | 2026-02-13 | NSK-22318EAE4 or FAG 22318 EAS M C3 or SKF 22318CC/W33, AC-00-813-261-541 | Roller Bearing (Outboard), 8x6-18 & 10x8-21 SRL-C | 3 | Wajax Limited - Mississauga | Canada | CA WAREHOUSE |  | LAND | 2026-02-17 | [5 empty] | 2026-02-20 | 2026-02-17 | TRUE | -46066 | 12.3761 | 1.768
Received | Emilka Guerra | 2026-02-04 14:58 | PO08657 | Stock | 2026-02-13 | NSK-22218EAE4, AC-00-813-261-537 | Roller Bearing (Inboard), 8x6-18 & 10x8-21 SRL-C | 3 | Wajax Limited - Mississauga | Canada | CA WAREHOUSE |  | LAND | 2026-02-17 | [5 empty] | 2026-02-20 | 2026-02-17 | TRUE | -46066 | 12.3761 | 1.768
IN TRANSIT | Livan Hernandez | 2026-02-04 | PO08658 | STOCK | 2026-03-25 | AC-98-231-081-501 | Suction Side Liner, 5x5-14 SRL, Natural Rubber | 4 | Super Cast Limited | China | CA WAREHOUSE | 2026-04-10 | SEA | ETA Warehouse May last week |  | ECU: LS21TJ2604576 | ETA Port of Prince Rupert: May 2, 2026 | left Tianjin for Toronto by sea on Apr 10, 2026 |  | 2026-06-17 |  | FALSE | 16 | -46057 | -6579.5714
Received | Livan Hernandez | 2026-02-04 | PO08658 | STOCK | 2026-03-25 | W-SL30110/A05 | Volute Liner, 300 RSL, High Chrome | 1 | Super Cast Limited | China | CA WAREHOUSE | 2026-03-12 | SEA | ETA MAY 1ST WEEK |  | ECU: LS21TJ2603573 | ETD Prince Rupert: Apr 4, 2026. | left Tianjin for Toronto by sea on Mar 12, 2026. |  | 2026-06-17 | 2026-04-27 | TRUE | -13 | 82 | 11.7143
Received | Livan Hernandez | 2026-02-04 | PO08658 | STOCK | 2026-03-25 | 6700SC-16MM | Packing, 16mm x 16mm, Kevlar Fiber w/Silicon Core, 12.5 lbs. Spool | 2 | Super Cast Limited | China | CA WAREHOUSE | 2026-03-29 | SEA | ETA Warehouse May last week |  | ECU: LS21TJ2603672 | ETA Port of Prince Rupert: Apr 22, 2026 | left Tianjin for Toronto by sea on Mar 29, 2026 | (2nd batch) | 2026-06-17 | 2026-04-27 | TRUE | 4 | 82 | 11.7143
Received | Livan Hernandez | 2026-02-04 | PO08658 | STOCK | 2026-03-25 | W-E090SQ/S10 | Lip Seal, 8/6 E-AH, Nitrile | 30 | Super Cast Limited | China | CA WAREHOUSE | 2026-03-29 | SEA | ETA Warehouse May last week |  | ECU: LS21TJ2603672 | ETA Port of Prince Rupert: Apr 22, 2026 | left Tianjin for Toronto by sea on Mar 29, 2026 |  | 2026-06-17 | 2026-04-27 | TRUE | 4 | 82 | 11.7143
IN TRANSIT | Livan Hernandez | 2026-02-04 | PO08658 | STOCK | 2026-03-25 | SA-013733-M1 | Wear Disc, 44 WFR, Sala STGVA-180, Steel, Rubber Lined | 40 | Super Cast Limited | China | CA WAREHOUSE | 2026-04-10 | SEA | ETA Warehouse May last week |  | ECU: LS21TJ2604576 | ETA Port of Prince Rupert: May 2, 2026 | left Tianjin for Toronto by sea on Apr 10, 2026 |  | 2026-06-17 |  | FALSE | 16 | -46057 | -6579.5714
Cancelled | Livan Hernandez | 2026-02-04 | PO08658 | STOCK | 2026-03-25 | W-SPR10206A/S42 | Impeller (Agitator), 100RV-SP, Neoprene | 1 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | 2026-06-17 |  |  |  |  | Discarded by Amanda from original Order | 2026-06-17 |  | FALSE | -46106 | -46057 | -6579.5714
Received | Livan Hernandez | 2026-02-04 | PO08659 | STOCK | 2026-03-25 | AC-98-331-910-801 | Bearing Cylinder, 8x6-18 & 10x8-21 SRL-C, Cast Iron | 5 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-04-17 | SEA | ETA Warehouse June 10-15 | Follow email sent for update on June 16th | BL 1073610888 | EG: Included in Invoice | Betty confirmed shipment |  | 2026-06-17 | 2026-06-01 | TRUE | 23 | 117 | 16.7143
IN TRANSIT | Livan Hernandez | 2026-02-04 | PO08659 | STOCK | 2026-03-25 | AC-98-331-958-822 | Shaft Sleeve, 3x3-10 SRL & SRL-C, 420SS Heat Treated, Hardened | 6 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-06-19 | SEA | ETA Warehouse Mid-Sept |  |  | Follow email sent for update on June 16th . We already shipped them to Tianjin, but the vessel delayed, it shows that it will depart on June 19. | Betty 5/15: Included in Comercial Invoice / #20260205-11 | Status email sent on April 22nd Betty 04/23: 6 shaft sleeve still not ready to ship,it wll ready after the labor day holiday. | 2026-06-17 |  | FALSE | 86 | -46057 | -6579.5714
IN TRANSIT & DELAYED | Livan Hernandez | 2026-02-04 | PO08659 | STOCK | 2026-03-25 | AC-98-331-901-801 | Bearing Cover (Outboard), 8x6-18 & 10x8-21 SRL-C, Cast Iron | 10 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-05-26 | SEA | ETA Warehouse mid-august | the vessel depart on May 26 | 20251217-11 Sea Waybill-No. 1074440607 |  | Betty 4/23: Included in Comercial Invoice #20251217-11 | Status email sent on April 22nd | 2026-06-17 |  | FALSE | 62 | -46057 | -6579.5714
IN TRANSIT & DELAYED | Livan Hernandez | 2026-02-04 | PO08659 | STOCK | 2026-03-25 | AC-98-331-936-801 | Bearing Cover (Inboard), 8x6-18 & 10x8-21 SRL-C, Cast Iron | 10 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-05-26 | SEA | ETA Warehouse mid-august | the vessel depart on May 26 | 20251217-11 Sea Waybill-No. 1074440607 |  | Betty 4/23: Included in Comercial Invoice #20251217-11 | Status email sent on April 22nd | 2026-06-17 |  | FALSE | 62 | -46057 | -6579.5714
IN TRANSIT & DELAYED | Livan Hernandez | 2026-02-04 | PO08659 | STOCK | 2026-03-25 | AC-98-431-858-501 | Shaft Assembly, 3x3-10 SRL & SRL-C, 1045 Steel | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-05-26 | SEA | ETA Warehouse mid-august | the vessel depart on May 26 | 20251217-11 Sea Waybill-No. 1074440607 |  | Betty 4/23: Included in Comercial Invoice #20251217-11 | Status email sent on April 22nd | 2026-06-17 |  | FALSE | 62 | -46057 | -6579.5714
IN TRANSIT & DELAYED | Livan Hernandez | 2026-02-04 | PO08661 | STOCK | 2026-03-25 | DU-DY21806ACP-DI | Adapter (Bearing Housing), 10", Durco Mark 2&3 Group 2, Ductile Iron | 5 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-03 | SEA | Around June 5 |  | batch number: DYNC-112 / ECU: TAOTOR07006 | was shipped by sea on 3rd April. | ETA Vancouver on May 7 |  | 2026-06-17 |  | FALSE | 9 | -46057 | -6579.5714
Received | Emilka Guerra | 2026-02-04 18:19 | PO08662 | Stock | 2026-02-18 | SA-013826-1 | Shaft Sleeve, Sala STGVA-33-WFR, Steel | 3 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2026-02-26 | 2026-02-10 | TRUE | -46071 | 5.2367 | 0.7481
Received | Emilka Guerra | 2026-02-04 18:57 | PO08663 | SO18644 | 2026-03-04 | 52-321-237-100 | Impeller, 2x1-10, Allis-Chalmers CSO, 317SS | 1 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND | 2026-02-26 | [5 empty] | 2026-04-01 | 2026-02-26 | TRUE | -46085 | 21.2108 | 3.0301
Ready to Ship & Delayed | Amanda Qiao | 2026-02-04 | PO08664 | SO18536 | 2026-05-05 | AC-SRL 3x3-10-C | Pump, AC-SRL 3x3-10-C, Natural Rubber Lined, Motor Mounting Plate, Belt Guard | 2 | IGH | Mexico | CA WAREHOUSE |  | LAND | 2026-05-05 |  |  | follow up sent June 16th | Carlos IGH 06/16: List for PO ready to ship ~ destination of shipement confirmed |  | 2026-05-05 |  | FALSE | -46147 | -46057 | -6579.5714
Received | Livan Hernandez | 2026-02-05 14:54 | PO08666 | STOCK | 2026-02-19 | AC-98-232-857-801 | Shim Set, A-C PWO-C Group 1, Plastic | 10 | Renewal Services Inc. | Canada | CA WAREHOUSE |  | LAND | 2026-03-13 | [5 empty] | 2026-03-26 | 2026-03-13 | TRUE | -46072 | 35.3795 | 5.0542
IN TRANSIT & DELAYED | Leriel Reyes | 2026-02-05 | PO08667 | SO17754 | 2026-04-06 | W-400-DSTL-A49-UC | Pump, W-Series 400 ZJD, Ultrachrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | BARRICK DIRECT SHIPPING | 2026-05-17 | SEA | ETA CAUCEDO JUNE 28 | FOB Tianjin | TS6QJ1969800 / BL. ONEYTS6QJ1969800 | Original Lead time for production: 60 days (9 weeks) after payment. Wrong due date in Order + regular sea transit 10 weeks | PEter 05/16: The vessel already arrived at Tianjin seaport, will depart Tianjin tomorrow: May 17. left Tianjin for Caucedo by sea on May 17, 2026 | Naipu: still need 10-14 day to complete. ETD Mar 15 from Shanghai to Caucedo New ETD MAY 8TH May 14th: ETD Tianjin May 16 early morning | 2026-04-27 |  | FALSE | 41 | -46058 | -6579.7143
IN TRANSIT & DELAYED | Leriel Reyes | 2026-02-05 | PO08667 | SO17754 | 2026-04-06 |  | Pulley and belts, 400 ZJD, Ultrachrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | BARRICK DIRECT SHIPPING | 2026-05-17 | SEA | ETA CAUCEDO JUNE 28 | FOB Tianjin | TS6QJ1969800 / BL. ONEYTS6QJ1969800 | Original Lead time for production: 60 days (9 weeks) after payment. Wrong due date in Order + regular sea transit 10 weeks | PEter 05/16: The vessel already arrived at Tianjin seaport, will depart Tianjin tomorrow: May 17. left Tianjin for Caucedo by sea on May 17, 2026 | Naipu: still need 10-14 day to complete. ETD Mar 15 from Shanghai to Caucedo New ETD MAY 8TH May 14th: ETD Tianjin May 16 early morning | 2026-04-27 |  | FALSE | 41 | -46058
IN TRANSIT & DELAYED | Leriel Reyes | 2026-02-05 | PO08667 | SO17754 | 2026-04-06 | W-400-DSTL-A49-UC | Pump, W-Series 400 ZJD, Ultrachrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | BARRICK DIRECT SHIPPING | 2026-05-17 | SEA | ETA CAUCEDO JUNE 28 | FOB Tianjin | TS6QJ1969800 / BL. ONEYTS6QJ1969800 | Original Lead time for production: 60 days (9 weeks) after payment. Wrong due date in Order + regular sea transit 10 weeks | PEter 05/16: The vessel already arrived at Tianjin seaport, will depart Tianjin tomorrow: May 17. left Tianjin for Caucedo by sea on May 17, 2026 | Naipu: still need 10-14 day to complete. ETD Mar 15 from Shanghai to Caucedo New ETD MAY 8TH May 14th: ETD Tianjin May 16 early morning | 2026-04-27 |  | FALSE | 41 | -46058
IN TRANSIT & DELAYED | Leriel Reyes | 2026-02-05 | PO08667 | SO17754 | 2026-04-06 |  | Pulley and belts, 400 ZJD, Ultrachrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | BARRICK DIRECT SHIPPING | 2026-05-17 | SEA | ETA CAUCEDO JUNE 28 | FOB Tianjin | TS6QJ1969800 / BL. ONEYTS6QJ1969800 | Original Lead time for production: 60 days (9 weeks) after payment. Wrong due date in Order + regular sea transit 10 weeks | PEter 05/16: The vessel already arrived at Tianjin seaport, will depart Tianjin tomorrow: May 17. left Tianjin for Caucedo by sea on May 17, 2026 | Naipu: still need 10-14 day to complete. ETD Mar 15 from Shanghai to Caucedo New ETD MAY 8TH May 14th: ETD Tianjin May 16 early morning | 2026-04-27 |  | FALSE | 41 | -46058
Received | Emilka Guerra | 2026-02-05 | PO08668 | SO18667 | 2026-03-26 | B12*95 ET02, W-C070M/E02 | Shaft Key, 3/2 or 4/3 C-AH, Metric | 5 | Super Cast Limited | China | CA WAREHOUSE | 2026-03-12 | SEA | ETA Warehouse May last week |  | ETD Prince Rupert: Apr 4, 2026 |  | left Tianjin for Toronto by sea on Mar 12, 2026. |  | 2026-06-11 | 2026-04-27 | TRUE | -14 | 81
Received | Emilka Guerra | 2026-02-05 | PO08668 | SO18667 | 2026-03-26 | W-C062-10/G01 | Labyrinth, 3/2 or 4/3 C-AH, Cast Iron | 5 | Super Cast Limited | China | CA WAREHOUSE | 2026-03-12 | SEA | ETA Warehouse May last week |  | ETD Prince Rupert: Apr 4, 2026 |  | left Tianjin for Toronto by sea on Mar 12, 2026. |  | 2026-06-11 | 2026-04-27 | TRUE | -14 | 81
Received | Emilka Guerra | 2026-02-05 | PO08668 | SO18667 | 2026-03-26 | W-C108/G01 | Piston Ring, 3/2 or 4/3 C-AH and 40PV-SP, Cast Iron | 10 | Super Cast Limited | China | CA WAREHOUSE | 2026-03-12 | SEA | ETA Warehouse May last week |  | ETD Prince Rupert: Apr 4, 2026 |  | left Tianjin for Toronto by sea on Mar 12, 2026. |  | 2026-06-11 | 2026-04-27 | TRUE | -14 | 81
Received | Amanda Qiao | 2026-02-05 | PO08669 | SO18668 | 2026-03-01 | W-UL55083M/R55 | Throat Bushing, 550 TU-L, Natural Rubber | 2 | Super Cast Limited | China | CA WAREHOUSE | 2026-03-16 | AIR | [5 empty] | 1st batch of PO08669 delivered to Vancouver by air on Mar 16, 2026 | 2026-03-06 | 2026-03-17 | TRUE | 15 | 40
Received | Amanda Qiao | 2026-02-05 | PO08669 | SO18668 | 2026-03-01 | W-T50015M/E66 | Cover Plate Bolt w/2 Nuts Metric, 550 TU-L | 6 | Super Cast Limited | China | CA WAREHOUSE | 2026-03-28 | AIR | 2026-03-06 |  |  |  | left Beijing for Vancouver by air on Mar 28, 2028. | The remaining parts (2 types of cover plate studs) will be shipped in the 2nd batch next week. | 2026-03-06 | 2026-03-17 | TRUE | 27 | 40
Received | Amanda Qiao | 2026-02-05 | PO08669 | SO18668 | 2026-03-01 | W-UL55015M/E66 | Cover Plate BoltW/2 Nuts | 8 | Super Cast Limited | China | CA WAREHOUSE | 2026-03-28 | AIR | 2026-03-06 |  |  |  | left Beijing for Vancouver by air on Mar 28, 2028. | The remaining parts (2 types of cover plate studs) will be shipped in the 2nd batch next week. | 2026-03-06 | 2026-03-17 | TRUE | 27 | 40
IN TRANSIT | Leriel Reyes | 2026-02-06 | PO08671 | SO17754 | 2026-06-26 | PF4506 | 450 HP, 1200 RPM, 460/3/60, 5011B Frame TEFC, Optim TEFC, Teco-Westinghouse Motor | 1 | Teco-Westinghouse Motors (Canada) Inc. | Canada | BARRICK CONSOLIDATED |  | LAND | 2026-06-26 |  |  | Follow up email sent June 11th | May 8th: The 450 HP motor is currently in transit from china to the supplier's warehouse* 8 week to arrive to Dynapro Warehouse. | June 11th; The motor 450 HP is currently on the water ETA into Edmonton in two weeks | 2026-06-26 |  | FALSE | -46199 | -46059 | -6579.8571
Received | Leriel Reyes | 2026-02-06 | PO08671 | SO17754 | 2026-06-26 | PF5006 | 500 HP, 1200 RPM, 460/3/60, 5011B Frame TEFC, Optim TEFC, Teco-Westinghouse Motor | 1 | Teco-Westinghouse Motors (Canada) Inc. | Canada | BARRICK CONSOLIDATED | 2026-05-13 | LAND | 2026-06-26 |  | BOL-5000647727 | Currently in transit to Dynapro warehouse. | follow up email sent on May6th |  | 2026-06-26 | 2026-05-19 | TRUE | -44 | 102 | 14.5714
Received | Emilka Guerra | 2026-02-06 | PO08672 | SO18701 & SO18678 | 2026-03-06 | W-G12147/A05 | Impeller, 14/12 DH, High Chrome, 5-Vane | 1 | Super Cast Limited | China | CA WAREHOUSE | 2026-03-12 | SEA | ETA Warehouse May last week |  |  | ETD Prince Rupert: Apr 4, 2026. | left Tianjin for Toronto by sea on Mar 12, 2026 |  | 2026-06-12 | 2026-04-27 | TRUE | 6 | 80 | 11.4286
Received | Emilka Guerra | 2026-02-06 | PO08672 | SO18701 & SO18678 | 2026-03-06 | W-SH076/C21 | Shaft Sleeve Long, 10/8 to 14/12 ST-AH, 420SS | 5 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | ETA Warehouse May last week |  | LS21TJ2603672 | ETA Port of Prince Rupert: Apr 22, 2026 | left Tianjin for Toronto by sea on Mar 29, 2026 ETA Port of Prince Rupert: Apr 22, 2026 |  | 2026-06-15 | 2026-05-20 | TRUE | -46087 | 103 | 14.7143
Received | Emilka Guerra | 2026-02-06 | PO08673 | SO18703 | 2026-04-03 | AC-98-5414-HC3 | Suction Side Plate, 5x4-14 SRL-C, High Chrome, 3-Piece Design | 1 | IGH | Mexico | CA WAREHOUSE |  | LAND | 2026-05-08 | [5 empty] | 2026-05-08 | 2026-06-09 | TRUE | -46115 | 123 | 17.5714
Received | Emilka Guerra | 2026-02-09 | PO08674 | Stock | 2026-03-30 | W-D3041/A05 | Frame Plate Liner Insert, 4/3 C or D-AH, High Chrome | 2 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | 2026-06-15 |  | LS21TJ2603672 | ETA Port of Prince Rupert: Apr 22, 2026 | left Tianjin for Toronto by sea on Mar 29, 2026 ETA Port of Prince Rupert: Apr 22, 2026 |  | 2026-06-15 | 2026-05-20 | TRUE | -46111 | 100 | 14.2857
IN TRANSIT & DELAYED | Emilka Guerra | 2026-02-09 | PO08674 | Stock | 2026-03-30 | AC-98-330-286-503 | Impeller (Open), 3x3-10 SRL, Neoprene | 8 | Super Cast Limited | China | CA WAREHOUSE | 2026-05-08 | SEA | ETA Prince Rupert: May 30 ETA Warehouse is around Jul. 13 - 17 |  | LS21TJ2604679 |  | Peter 4/30: Already booked the vessel of ETD May 7 from Tianjin to Toronto. left Tianjin for Toronto by sea on May 8, 2026 |  | 2026-06-15 |  | FALSE | 39 | -46062 | -6580.2857
Received | Yannett Yeomans | 2026-02-05 | PO08670 | SO18712 | 16/02/26 | 10654/6007 | Oli Seal, 150FY-40, Natural Rubber | 3 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE | 23/02/26 | AIR |  |  |  | DHL to Hermosillo. | to consolidate with Hongya's OC00237/PO08495, OC00249/PO08605 and OC00269/PO08746 |  | 2026-02-23 | 2026-04-13 | TRUE
Received | Yannett Yeomans | 2026-02-05 | PO08670 | SO18712 | 16/02/26 | 10655/0512 | Spacer, 150FY-40, 316LSS | 3 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE | 23/02/26 | AIR |  |  |  | DHL to Hermosillo. | to consolidate with Hongya's OC00237/PO08495, OC00249/PO08605 and OC00269/PO08746 |  | 2026-02-23 | 2026-04-13 | TRUE
Received | Emilka Guerra | 2026-02-09 | PO08674 | Stock | 2026-03-30 | SA-138413-M1 | Casing, Sala 2", SPV, Rubber Lined | 4 | Super Cast Limited | China | CA WAREHOUSE | 2026-03-29 | SEA | 2026-06-15 |  | LS21TJ2603672 | ETA Port of Prince Rupert: Apr 22, 2026 | left Tianjin for Toronto by sea on Mar 29, 2026 ETA Port of Prince Rupert: Apr 22, 2026 |  | 2026-06-15 | 2026-05-20 | TRUE | -1 | 100
IN TRANSIT | Emilka Guerra | 2026-02-09 | PO08674 | Stock | 2026-03-30 | W-SP15092/A05 | Casing w/Flange, 150SV-SP, High Chrome | 4 | Super Cast Limited | China | CA WAREHOUSE | 2026-04-16 | SEA | 2026-06-15 |  | LS21TJ2604675 | ETA Prince Rupert: May 9, 2026 | left Tianjin for Toronto by sea on Apr 16, 2026 |  | 2026-06-15 |  | FALSE | 17 | -46062 | -6580.2857
IN TRANSIT | Emilka Guerra | 2026-02-09 | PO08674 | Stock | 2026-03-30 | W-SP15206A/A05 | Impeller, 150SV-SP, 5-Vane, High Chrome | 5 | Super Cast Limited | China | CA WAREHOUSE | 2026-04-16 | SEA | 2026-06-15 |  | LS21TJ2604675 | ETA Prince Rupert: May 9, 2026 | left Tianjin for Toronto by sea on Apr 16, 2026 |  | 2026-06-15 |  | FALSE | 17 | -46062 | -6580.2857
Received | Emilka Guerra | 2026-02-09 | PO08674 | Stock | 2026-03-30 | W-SH076/C21 | Shaft Sleeve Long, 10/8 to 14/12 ST-AH, 420SS | 4 | Super Cast Limited | China | CA WAREHOUSE | 2026-03-29 | SEA | 2026-06-15 |  | LS21TJ2603672 | ETA Port of Prince Rupert: Apr 22, 2026 | left Tianjin for Toronto by sea on Mar 29, 2026 ETA Port of Prince Rupert: Apr 22, 2026 |  | 2026-06-15 | 2026-05-20 | TRUE | -1 | 100 | 14.2857
Received | Livan Hernandez | 2026-02-10 | PO08676 | SO18724 | 2026-03-10 | 37231 | Sleeve Bearing (Suction Bell), ThorPlas-Blue, HPCW | 10 | Millstream Engineering Inc. | Canada | BARRICK CONSOLIDATED |  | LAND | 2026-03-24 | [5 empty] | 2026-03-24 | 2026-03-24 | TRUE | -46091 | 42 | 6
Received | Amanda Qiao | 2026-02-11 | PO08677 |  | 2026-04-09 |  | Mag Drive Gear Pump, Micropump GLH-H25, With Motor | 1 | Vissers Sales Corp. | Canada | BARRICK CONSOLIDATED |  | LAND | 2026-04-16 | [5 empty] | 2026-04-16 | 2026-03-19 | TRUE | -46121 | 36 | 5.1429
Received | Emilka Guerra | 2026-02-11 | PO08678 | SO18732 | 2026-03-11 | WO-390078-00 | Seal Ring, Worthington FRBH, Frame Size 5, Rubber | 1 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-04-09 | LAND | 2026-04-15 | [5 empty] | 2026-04-15 | 2026-04-14 | TRUE | 29 | 62 | 8.8571
Received | Ian Trottier | 2026-02-11 | PO08679 | SO18725 | 2026-04-22 | AC-52-224-289-005 | Shaft Sleeve, Allis-Chalmers CSO, Frame F4B3/F4B5/F4D1, XH-800 | 2 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-05-05 | LAND | ETA May 1st week |  |  |  | Hisco May 5th: Quenton Included in list for ready orders / waiting info on shipping date | April 30th: email follow up for orders. | 2026-01-05 | 2026-05-07 | TRUE | 13 | 85 | 12.1429
Received | Emilka Guerra | 2026-02-13 | PO08680 | SO18717 | 2026-03-27 | GA-24042 | Casing, G-Series 2.5" VSP, 1000 Series, Natural Rubber | 1 | IGH | Mexico | CA WAREHOUSE | 2026-04-17 | LAND | ETA Warehouse 29/abril |  | XP Ref. # 088414 |  |  |  | 2026-05-01 | 2026-04-29 | TRUE | 21 | 75 | 10.7143
Received | Emilka Guerra | 2026-02-13 | PO08681 | SO18726 | 2026-05-08 | AC-98-530-477-005 | Impeller, 10x8-17, PWO, 316SS | 1 | M&N Alloy Cast Products, Inc. | US | CA WAREHOUSE | 2026-05-15 | LAND | M&N: to ship on May 15th |  |  |  |  | Email for follow up sent on April 23rd | 6/1/26 | 6/1/26 | TRUE | 7 | -292086 | -41726.5714
Received | Yannett Yeomans | 2026-02-16 | PO08682 | SO18754 | 2026-03-16 | D-2001408-2507 | Impeller Wear Ring, 10JKH/M, 5.12x5.48x0.88, Duplex SS 2507 w/Ion Nitriding | 27 | Nanjing Wangyang Pumps Co., Ltd | China | BARRICK CONSOLIDATED | 2026-04-21 | AIR | ETA Mississauga: Apr 23 |  | DHL waybill (5270923545) | left Shanghai for Mississauga via DHL on Apr 21, 2026 | April 17 / PO08682 was originally planned to ship together with PO08715 by sea to Toronto. Now we can add it to the DHL shipment of PO08794 to Toronto. |  | 2026-05-20 | 2026-04-30 | TRUE | 36 | 73 | 10.4286
Received | Emilka Guerra | 2026-02-18 | PO08683 | SO18779 | 2026-05-06 | GA-20291 | Discharge Pipe, 48", G-Series 3.5" VSP, 1000 Series, Natural Rubber Lined | 1 | IGH | Mexico | CA WAREHOUSE | 2026-04-14 | LAND | ETA Warehouse 29/abril |  | XP Ref. # 088414 | on time |  |  | 2026-04-29 | 2026-04-29 | TRUE | -22 | 70 | 10
DELAYED PRODUCTION | Yannett Yeomans | 2026-02-09 | PO08675 | SO18722 | 2026-09-03 | 10640/0534 | Gland Packing Kit for A22-65 | 2 | Super Cast Limited | China | MX WAREHOUSE | 2026-09-02 | SEA | 2026-05-14 |  |  |  | the expected completed date is Apr 25, 2026. | hONGYA~ We planned to get all the parts ready by Apr 11. | 2026-05-14 |  | FALSE
Received | Ian Trottier | 2026-02-19 | PO08684 | Stock | 2026-02-01 | 046692G161-2229 | Shaft Sleeve (Mechanical Seal), Goulds JC Frame 2J, 316SS | 2 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE | 2026-02-27 | LAND | 2026-03-12 |  |  |  | confirmed SHIPMENT |  | 2026-02-19 | 2026-03-12 | TRUE | 26 | 21
IN TRANSIT | Emilka Guerra | 2026-02-20 | PO08685 | SO18775 | 2026-03-25 | W-SP15092/A05 | Casing w/Flange, 150SV-SP, High Chrome | 2 | Super Cast Limited | China | CA WAREHOUSE | 2026-04-16 | SEA | 2026-05-05 |  | LS21TJ2604675 | ETA Prince Rupert: May 9, 2026 | left Tianjin for Toronto by sea on Apr 16, 2026 |  | 2026-05-05 |  | FALSE | 22 | -46073
IN TRANSIT | Emilka Guerra | 2026-02-20 | PO08685 | SO18775 | 2026-03-25 | W-SP15206A/A05 | Impeller, 150SV-SP, 5-Vane, High Chrome | 1 | Super Cast Limited | China | CA WAREHOUSE | 2026-04-16 | SEA | 2026-06-03 |  | LS21TJ2604675 | ETA Prince Rupert: May 9, 2026 | left Tianjin for Toronto by sea on Apr 16, 2026 |  | 2026-06-03 |  | FALSE | 22 | -46073
IN TRANSIT | Emilka Guerra | 2026-02-20 | PO08685 | SO18775 | 2026-03-25 | W-SP25092/A05 | Casing, 250SV-SP, High Chrome | 1 | Super Cast Limited | China | BARRICK DIRECT SHIPPING | 2026-04-16 | SEA | 2026-05-05 | CIF CAUCEDO PORT | LS15TJ2604798 |  | shipped out from Tianjin to Caucedo, Dominincan Republic on Apr 16, 2026. ✅ |  | 2026-05-05 |  | FALSE | 22 | -46073 | -6581.8571
Received | Emilka Guerra | 2026-02-20 | PO08686 | Stock D-196 Parts - SO18793 | 2026-02-25 | 28VSMS3-04C4VS4 | Single Cartridge Seal, 1 3/4", VSMS, Standard Bore, Carbon vs Silicon Carbide / TFEP | 2 | Flexaseal Engineered Seals and Systems, LLC | Canada | CA WAREHOUSE |  | LAND | 2026-03-27 | [5 empty] | 2026-03-27 | 2026-03-26 | TRUE | -46078 | 34 | 4.8571
Ready to Ship & Delayed | Carlos Leon | 2026-02-20 | PO08688 | SO18785 | 2026-04-03 | WO-9090140-183 | Impeller Nut, Worthington, 8FRBH152 316SS | 1 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-06-16 | LAND | 2026-04-17 |  |  | follow up sent June 16th | Quenton Hisco 06/16: Ready to ship - Pending Pick up confirmation by logistics | May 5th: Asked for update on this delayed PO. Hisco May5th: Delayed ~ to be shipped Mid-may | 2026-04-17 |  | FALSE | 74 | -46073 | -6581.8571
IN TRANSIT & DELAYED | Emilka Guerra | 2026-02-20 | PO08689 | Stock | 2026-04-06 | D-1J2311-2 | Casing, 2x3-11, Goulds JC, Frame 1J, High Chrome, OEM# 055891G0001228 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-05-26 | SEA | ETA Warehouse mid-august | the vessel depart on May 26 | 20251217-11 Sea Waybill-No. 1074440607 | EG: email follow up on this item sent april 14 | Betty 4/23: Included in Comercial Invoice ONLY 3 PCS READY / #20251217-11 | EG: email follow up on this item sent april 14 | 2026-06-22 |  | FALSE | 50 | -46073 | -6581.8571
IN TRANSIT | Emilka Guerra | 2026-02-20 | PO08689 | Stock | 2026-04-06 | D-1J2311-2 | Casing, 2x3-11, Goulds JC, Frame 1J, High Chrome, OEM# 055891G0001228 | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-06-19 | SEA | ETA Warehouse Mid-Sept |  |  | Follow email sent for update on June 16th . We already shipped them to Tianjin, but the vessel delayed, it shows that it will depart on June 19. | Betty 5/15: Included in Comercial Invoice 4 PCS remaining / #20260205-11 | EG: email follow up on this item sent MAy 15 | 2026-06-22 |  | FALSE | 74 | -46073 | -6581.8571
Received | Emilka Guerra | 2026-02-20 | PO08689 | Stock | 2026-04-06 | G-1.5x2-14-JC-HC | Pump, 1.5x2-14, Dynapro DC, Frame 2J, High Chrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-04-17 | SEA | ETA Warehouse June 10-15 |  | BL 1073610888 | EG: Included in Invoice | Betty confirmed shipment |  | 2026-06-22 | 2026-06-01 | TRUE | 11 | 101
Received | Emilka Guerra | 2026-02-20 | PO08689 | Stock | 2026-04-06 | AC-98-331-983-801 | Bearing Cylinder, 3x3-10 SRL & SRL-C, Cast Iron | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-04-17 | SEA | ETA Warehouse June 10-15 |  | BL 1073610888 | EG: Included in Invoice | Betty confirmed shipment |  | 2026-06-22 | 2026-05-29 | TRUE | 11 | 98
IN TRANSIT & DELAYED | Ian Trottier | 2026-02-20 | PO08690 | SO18457 | 2026-04-10 | D-PE4J-400-316 | Power End, Goulds JC, Frame 4J, Grease-Lubed, SKF Bearings, 316SS Steel Shaft | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-05-26 | SEA | ETA Warehouse mid-august | the vessel depart on May 26 | 20251217-11 Sea Waybill-No. 1074440607 |  | Betty 4/23: Included in Comercial Invoice #20251217-11 | Status email sent on April 22nd | 2026-06-12 |  | FALSE | 46 | -46073 | -6581.8571
Received | Ian Trottier | 2026-02-23 | PO08691 | SO18737 | 2026-06-01 | AC-98-331-596-801 | Stuffing Box Cover, 21", PWO, Frame 3, Cast Iron | 1 | Emnor Mechanical Inc. | Canada | CA WAREHOUSE |  | LAND | 2026-02-24 | [5 empty] | 2026-02-24 | 2026-04-15 | TRUE | -46174 | 51 | 7.2857
Received | Emilka Guerra | 2026-02-23 | PO08692 | SO18720 | 18/05/26 | WO-2114552-317 | Impeller, Worthington 6-FRBH-223, 317SS | 1 | M&N Alloy Cast Products, Inc. | US | CA WAREHOUSE |  | LAND | 2026-03-18 | [5 empty] | 2026-06-22 | 2026-03-18 | TRUE | #VALUE! | 23 | 3.2857
Received | Amanda Qiao | 2026-02-24 | PO08695 | SO18803 | 2026-02-03 | GATES - XPC2240 | V-Belt, Wedge, Gates, SPC 2240mm, Synthetic Rubber | 10 | Wajax Limited - Mississauga | Canada | CA WAREHOUSE |  | LAND | 2026-03-02 | [5 empty] | 2026-03-06 | 3/2/02 | TRUE | -46056 | -666197 | -95171
IN TRANSIT | Emilka Guerra | 2026-02-24 | PO08697 | SO18719 | 2026-05-08 | 5340900141 | Casing, Ahlstrom, MCE 32-4, 2205 Duplex | 1 | Super Cast Limited | China | CA WAREHOUSE | 2026-05-22 | SEA | ETA WAREHOUSE Mid agust |  | LS21TJ2605578 | Long production time | Peter 04/27: will come out by May 15. Peter 05/26: left Tianjin for Toronto by sea on May 22, 2026. | Email for follow up sent on April 23rd | 2026-08-07 |  | FALSE | 14 | -46077 | -6582.4286
DELAYED PRODUCTION | Ian Trottier | 2026-02-25 | PO08698 | Stock | 2026-04-08 | SF-PE2 | Baseplate, JC, 2J/3J Frame, Steel Fabricated, Adjustable Over-Head Motor Mount & Belt Guard | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | 2026-06-24 |  |  |  |  | Waiting on Ian confirmation to Naipu for the attached drawings | 2026-06-24 |  | FALSE | -46120 | -46078 | -6582.5714
DELAYED PRODUCTION | Ian Trottier | 2026-02-25 | PO08698 | Stock | 2026-04-08 | SF-PE3 | Baseplate, JC, 3J Frame, Steel Fabricated, Adjustable Over-Head Motor Mount & Belt Guard | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | 2026-06-24 |  |  |  |  | Waiting on Ian confirmation to Naipu for the attached drawings | 2026-06-24 |  | FALSE | -46120 | -46078 | -6582.5714
DELAYED PRODUCTION | Ian Trottier | 2026-02-25 | PO08698 | Stock | 2026-04-08 | SF-PE4 | Baseplate, JC, 4J Frame, Steel Fabricated, Adjustable Over-Head Motor Mount & Belt Guard | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | 2026-06-24 |  |  |  |  | Waiting on Ian confirmation to Naipu for the attached drawings | 2026-06-24 |  | FALSE | -46120 | -46078 | -6582.5714
Received | Emilka Guerra | 2026-02-26 | PO08699 | Stock for HPCW - SO18843 | 2026-06-03 | 2-432V700 (black) | O-Ring, 10JKH/M, 5.38IDx0.25RD, Viton | 1 | Wajax Limited - Mississauga | Canada | CA WAREHOUSE |  | LAND | 2026-03-04 |  |  |  |  | Stock for HPCW - SO18843 | 2026-03-13 | 2026-03-04 | TRUE | -46176 | 6 | 0.85714
Received | Emilka Guerra | 2026-02-26 | PO08699 | Stock for HPCW - SO18843 | 2026-06-03 | 2-461V70B (brown) | O-Ring, 10JKH/M, 16.00IDx0.25RD, Viton | 1 | Wajax Limited - Mississauga | Canada | CA WAREHOUSE |  | LAND | 2026-03-04 |  |  |  |  | Stock for HPCW - SO18843 | 2026-03-13 | 2026-03-04 | TRUE | -46176 | 6
Received | Ian Trottier | 2026-02-27 | PO08701 | SO18805 | 2026-05-01 | G-113-47 1220 | Casing, 3196 STX, 1x1.5-8, Titanium | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-03 | AIR | 2026-05-15 |  | DYNC-114 The AIR waybill# is 006-5139 2703 |  |  | Email for follow up sent on April 23rd | 2026-05-15 | 2026-05-12 | TRUE | -28 | 74
Received | Emilka Guerra | 2026-02-27 | PO08705 | SO18821 & Stock | 2026-04-10 | G-R104-562 1216 | Stuffing Box Cover, 6", 3196 STX, CD4MCu, Standard Bore, Non-Jacketed | 2 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-03 | SEA | Around June 5 |  | batch number: DYNC-112 / ECU: TAOTOR07006 | was shipped by sea on 3rd April. | ETA Vancouver on May 7 |  | 2026-06-19 | 2026-05-20 | TRUE | -7 | 82
Received | Emilka Guerra | 2026-02-27 | PO08705 | SO18821 & Stock | 2026-04-10 | DU-AY38913AA-316 | Shaft Sleeve, Durco Mark 2&3 Group 2, 316SS | 10 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-03 | SEA | Around June 5 |  | batch number: DYNC-112 / ECU: TAOTOR07006 | was shipped by sea on 3rd April. | ETA Vancouver on May 7 |  | 2026-06-19 | 2026-05-20 | TRUE | -7 | 82 | 11.7143
Received | Emilka Guerra | 2026-02-27 | PO08705 | SO18821 & Stock | 2026-04-10 | G-73705X 2229 | Shaft Sleeve, 3196 MTX, 316SS | 12 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-03 | SEA | Around June 5 |  | batch number: DYNC-112 / ECU: TAOTOR07006 | was shipped by sea on 3rd April. | ETA Vancouver on May 7 |  | 2026-06-19 | 2026-05-20 | TRUE | -7 | 82 | 11.7143
Received | Emilka Guerra | 2026-02-27 | PO08705 | SO18821 & Stock | 2026-04-10 | G-76772X 2229 | Shaft Sleeve, 3196 STX, 316SS | 10 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-03 | SEA | Around June 5 |  | batch number: DYNC-112 / ECU: TAOTOR07006 | was shipped by sea on 3rd April. | ETA Vancouver on May 7 |  | 2026-06-19 | 2026-05-20 | TRUE | -7 | 82 | 11.7143
Received | Emilka Guerra | 2026-02-27 | PO08705 | SO18821 & Stock | 2026-04-10 | AC-98-130-367-008 | Shaft Sleeve, PWO Frame 2, 317SS | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-20 | SEA | ETA Warehouse Mid June |  | DYNC-113 SEA // BL# HHSE6042268, Container # CAAU5246660 | ETA Vancouver on May 5 |  |  | 2026-06-19 | 2026-05-26 | TRUE | 10 | 88 | 12.5714
Received | Emilka Guerra | 2026-02-27 | PO08705 | SO18821 & Stock | 2026-04-10 | G-0100-165 1216 | Impeller, 3x4-8G, 3196 MTX, CD4MCu, 5-Vane | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-03 | SEA | Around June 5 |  | batch number: DYNC-112 / ECU: TAOTOR07006 | was shipped by sea on 3rd April. | ETA Vancouver on May 7 |  | 2026-06-19 | 2026-05-20 | TRUE | -7 | 82
Received | Emilka Guerra | 2026-02-27 | PO08705 | SO18821 & Stock | 2026-04-10 | OLPWZ011214B, DU-AY55122A-BZV | Bearing Isolator (Inboard), Durco Mark 3 Group 1, 303SS Rotor / Bronze Stator w/Viton | 5 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-03 | SEA | Around June 5 |  | batch number: DYNC-112 / ECU: TAOTOR07006 | was shipped by sea on 3rd April. | ETA Vancouver on May 7 |  | 2026-06-19 | 2026-05-20 | TRUE | -7 | 82
IN TRANSIT | Ian Trottier | 2026-02-27 | PO08706 | Stock | 2026-04-03 | DU-PE2YRB-LHS-4140-H | Power End, Durco Mark 3 Group 2, 4140 Steel Shaft (Hook Sleeve), 316SS Sleeve, (Power End Only - Less Adapter & Foot) | 2 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA | 2026-06-12 |  | batch number: DYNC-112 / ECU: TAOTOR07006 | was shipped by sea on 3rd April. | ETA Vancouver on May 7 | Email for follow up sent on April 23rd | 2026-06-12 |  | FALSE | -46115 | -46080 | -6582.8571
Ready to Ship & Delayed | Ian Trottier | 2026-02-27 | PO08707 | SO18631 | 2026-05-31 | AC-SRL 5x5-14 | Pump, AC-SRL 5x5-14, Natural Rubber Lined, Motor Mounting Plate, Belt Guard | 1 | IGH | Mexico | CA WAREHOUSE |  | LAND | 2026-07-06 |  |  |  | Carlos IGH 06/16: List for PO ready to ship ~ destination of shipement confirmed |  | 2026-07-06 |  | FALSE | -46173 | -46080 | -6582.8571
Received | Emilka Guerra | 2026-02-03 | PO08708 | SO18574 & Stock | 2026-05-15 | GA-20DELSLV | Valve (Sleeve), 2" G-Series VSP, Delta Series, Natural Rubber | 6 | IGH | Mexico | CA WAREHOUSE | 2026-04-17 | LAND | ETA Warehouse 29/abril |  | XP Ref. # 088414 | on time |  |  | 2026-06-12 | 2026-04-29 | TRUE | -28 | 85 | 12.1429
Received | Emilka Guerra | 2026-02-03 | PO08708 | SO18574 & Stock | 2026-05-15 | AC-98-330-289-503 | Impeller (Open), 5x5-14 SRL, Neoprene | 1 | IGH | Mexico | CA WAREHOUSE | 2026-04-17 | LAND | ETA Warehouse 29/abril |  | XP Ref. # 088414 | on time |  |  | 2026-06-12 | 2026-04-29 | TRUE | -28 | 85 | 12.1429
Received | Emilka Guerra | 2026-02-03 | PO08708 | SO18574 & Stock | 2026-05-15 | AC-98-331-932-503 | Shaft, 5x4-14 SRL-C & 5x5-14 SRL, 316SS | 1 | IGH | Mexico | CA WAREHOUSE | 2026-04-17 | LAND | ETA Warehouse 29/abril |  | XP Ref. # 088414 | on time |  |  | 2026-05-07 | 2026-04-29 | TRUE | -28 | 85 | 12.1429
Received | Emilka Guerra | 2026-02-03 | PO08708 | SO18574 & Stock | 2026-05-15 | AC-98-231-081-503 | Suction Side Liner, 5x5-14 SRL, Neoprene | 1 | IGH | Mexico | CA WAREHOUSE | 2026-04-17 | LAND | ETA Warehouse 29/abril |  | XP Ref. # 088414 | on time |  |  | 2026-06-12 | 2026-04-29 | TRUE | -28 | 85 | 12.1429
Received | Emilka Guerra | 2026-02-03 | PO08708 | SO18574 & Stock | 2026-05-15 | AC-98-231-079-503 | Gland Side Liner, 5x5-14 SRL, Neoprene | 1 | IGH | Mexico | CA WAREHOUSE | 2026-04-17 | LAND | ETA Warehouse 29/abril |  | XP Ref. # 088414 | on time |  |  | 2026-06-12 | 2026-04-29 | TRUE | -28 | 85 | 12.1429
Received | Ian Trottier | 2026-02-03 | PO08711 | SO18527 | 2026-04-05 | GA-23974 | Impeller, G-Series 2.5" VSP, 1000 Series, Neoprene | 4 | IGH | Mexico | CA WAREHOUSE | 2026-04-17 | LAND | ETA Warehouse 29/abril |  | XP Ref. # 088414 |  |  |  | 2026-04-06 | 2026-04-29 | TRUE | 12 | 85 | 12.1429
Received | Ian Trottier | 2026-02-03 | PO08712 | SO18863 | 2026-03-30 | E11H439392 | O-Ring, Sideplate, Ahlstrom, APT 51-10, EPDM | 1 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-05-05 | LAND | ETA May 1st week |  |  |  | Hisco May 5th: Quenton Included in list for ready orders / waiting info on shipping date | April 30th: email follow up for orders. | 4/10/26 | 2026-05-07 | TRUE | 36 | 93 | 13.2857
Received | Ian Trottier | 2026-02-03 | PO08712 | SO18863 | 2026-03-30 | E11B064594 | O-Ring, Shaft Sleeve, Ahlstrom, APT 51-10, Teflon | 1 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-05-05 | LAND | ETA May 1st week |  |  |  | Hisco May 5th: Quenton Included in list for ready orders / waiting info on shipping date | April 30th: email follow up for orders. | 4/10/26 | 2026-05-07 | TRUE | 36 | 93 | 13.2857
IN TRANSIT | Yannett Yeomans | 2026-02-27 | PO08703 | SO18851 | 2026-01-05 | DVT-GV8RJHC-2I/0502 | Vertical Turbine Pump, 8RJHC-2, 420SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE | 2026-05-01 | SEA | 2026-07-10 |  |  |  | Peter 05/17: left Shanghai for Ensenada by sea on May 13, 2026 |  | 2026-07-10 |  | FALSE
IN TRANSIT & DELAYED | Emilka Guerra | 2026-03-03 | PO08714 | SO18745 & Stock | 2026-04-07 | W-SP15041/A05 | Back Liner, 150SV-SP, High Chrome | 4 | Super Cast Limited | China | CA WAREHOUSE | 2026-04-16 | SEA | ETA Warehouse Mid-June |  | LS21TJ2604675 | ETA Prince Rupert: May 9, 2026 ETA Vancouver on May 24th Container in the discharge process May 26th | left Tianjin for Toronto by sea on Apr 16, 2026 | ETA Vancouver on May 24 | 2026-06-19 |  | FALSE | 9 | -46084
Received | Emilka Guerra | 2026-03-03 | PO08714 | SO18745 & Stock | 2026-04-07 | W-SP15204/R55 | Discharge Pipe Gasket, 150SV-SP, Natural Rubber | 10 | Super Cast Limited | China | CA WAREHOUSE | 2026-03-29 | SEA | 2026-06-19 |  | LS21TJ2603672 | ETA Port of Prince Rupert: Apr 22, 2026 | left Tianjin for Toronto by sea on Mar 29, 2026 |  | 2026-06-19 | 2026-05-20 | TRUE | -9 | 78 | 11.1429
IN TRANSIT & DELAYED | Emilka Guerra | 2026-03-03 | PO08714 | SO18745 & Stock | 2026-04-07 | AC-98-332-794-501 | Suction Side Plate, 10x10-28 SRL-XT, Natural Rubber | 6 | Super Cast Limited | China | CA WAREHOUSE | 2026-05-08 | SEA | ETA Prince Rupert: May 30 ETA Warehouse is around Jul. 13 - 17 |  | LS21TJ2604679 |  | Peter 4/30: Already booked the vessel of ETD May 7 from Tianjin to Toronto. left Tianjin for Toronto by sea on May 8, 2026 |  | 2026-06-19 |  | FALSE | 31 | -46084 | -6583.4286
Received | Emilka Guerra | 2026-03-03 | PO08714 | SO18745 & Stock | 2026-04-07 | W-E089-10/S10 | Bearing Seal Ring, 6/4 & 8/6 E-AH or 150 to 300 Type L, Natural Rubber | 10 | Super Cast Limited | China | CA WAREHOUSE | 2026-03-29 | SEA | 2026-06-19 |  | LS21TJ2603672 | ETA Port of Prince Rupert: Apr 22, 2026 | left Tianjin for Toronto by sea on Mar 29, 2026 |  | 2026-06-19 | 2026-05-20 | TRUE | -9 | 78 | 11.1429
Received | Emilka Guerra | 2026-03-03 | PO08714 | SO18745 & Stock | 2026-04-07 | W-FAHF6060/S01 | Intake Joint Ring, 6" E, EE or F-AHF, EPDM Rubber | 4 | Super Cast Limited | China | CA WAREHOUSE | 2026-03-29 | SEA | 2026-06-19 |  | LS21TJ2603672 | ETA Port of Prince Rupert: Apr 22, 2026 | left Tianjin for Toronto by sea on Mar 29, 2026 |  | 2026-06-19 | 2026-05-20 | TRUE | -9 | 78 | 11.1429
Received | Emilka Guerra | 2026-03-03 | PO08714 | SO18745 & Stock | 2026-04-07 | W-F6018/R55 | Cover Plate Liner, 8/6 E or F-AH, Natural Rubber | 2 | Super Cast Limited | China | CA WAREHOUSE | 2026-03-29 | SEA | 2026-06-19 |  | LS21TJ2603672 | ETA Port of Prince Rupert: Apr 22, 2026 | left Tianjin for Toronto by sea on Mar 29, 2026 |  | 2026-06-19 | 2026-05-20 | TRUE | -9 | 78 | 11.1429
Received | Emilka Guerra | 2026-03-03 | PO08714 | SO18745 & Stock | 2026-04-07 | W-EAM117/C21 | Shaft Spacer, 8/6 E or R-AH, 420SS | 10 | Super Cast Limited | China | CA WAREHOUSE | 2026-03-29 | SEA | 2026-06-19 |  | LS21TJ2603672 | ETA Port of Prince Rupert: Apr 22, 2026 | left Tianjin for Toronto by sea on Mar 29, 2026 |  | 2026-06-19 | 2026-05-20 | TRUE | -9 | 78 | 11.1429
IN TRANSIT & DELAYED | Emilka Guerra | 2026-03-03 | PO08714 | SO18745 & Stock | 2026-04-07 | W-F8147/A05 | Impeller, 10/8 E-M, High Chrome | 2 | Super Cast Limited | China | CA WAREHOUSE | 2026-04-16 | SEA | ETA Warehouse Mid-June |  | LS21TJ2604675 | ETA Prince Rupert: May 9, 2026 ETA Vancouver on May 24th Container in the discharge process May 26th | left Tianjin for Toronto by sea on Apr 16, 2026 | ETA Vancouver on May 24 | 2026-06-19 |  | FALSE | 9 | -46084 | -6583.4286
IN TRANSIT | Emilka Guerra | 2026-03-03 | PO08715 | Stock | 2026-04-07 | D-2001414-2507 | Key (Square), 10JKH/M, 0.38x1.13LG, Duplex SS 2507 | 40 | Nanjing Wangyang Pumps Co., Ltd | China | CA WAREHOUSE | 2026-05-30 | SEA | 2026-06-16 |  |  | Stock Canada / BALANCE PAYMENT REQUESTED | the ETD is 25th April. We will try to get it ready for dispatch asap. Peter: The vessel of ETD June 7 from Shanghai to Toronto Departed Shanghai and are on sea to Toronto. | Jiansuwin 04/30: All machining job is finished and we are only waiting for the wear ring now, we can get this order ready for dispatch around 10th May. James 05/15: The wear rings are just finished by nitriding treatment yesterday and it is now on the way to us. Hopefully, I will share you with packing list for this order in early next week | 2026-06-16 |  | FALSE | 53 | -46084 | -6583.4286
IN TRANSIT | Emilka Guerra | 2026-03-03 | PO08715 | Stock | 2026-04-07 | D-2001407-2507 | Bowl Wear Ring, 10JKH/M, 05.50x05.88x0.88, Duplex SS 2507 w/Ion Nitriding | 60 | Nanjing Wangyang Pumps Co., Ltd | China | CA WAREHOUSE | 2026-05-30 | SEA | 2026-06-16 |  |  | Stock Canada / BALANCE PAYMENT REQUESTED | the ETD is 25th April. We will try to get it ready for dispatch asap. Peter: The vessel of ETD June 7 from Shanghai to Toronto Departed Shanghai and are on sea to Toronto. | Jiansuwin 04/30: All machining job is finished and we are only waiting for the wear ring now, we can get this order ready for dispatch around 10th May. James 05/15: The wear rings are just finished by nitriding treatment yesterday and it is now on the way to us. Hopefully, I will share you with packing list for this order in early next week | 2026-06-16 |  | FALSE | 53 | -46084 | -6583.4286
IN TRANSIT | Emilka Guerra | 2026-03-03 | PO08715 | Stock | 2026-04-07 | D-2001405-CD4 | Bowl,10JKH/M, BW-INT-STEP-NO-SL-SP, CD4MCu | 16 | Nanjing Wangyang Pumps Co., Ltd | China | CA WAREHOUSE | 2026-05-30 | SEA | 2026-06-16 |  |  | Stock Canada / BALANCE PAYMENT REQUESTED | the ETD is 25th April. We will try to get it ready for dispatch asap. Peter: The vessel of ETD June 7 from Shanghai to Toronto Departed Shanghai and are on sea to Toronto. | Jiansuwin 04/30: All machining job is finished and we are only waiting for the wear ring now, we can get this order ready for dispatch around 10th May. James 05/15: The wear rings are just finished by nitriding treatment yesterday and it is now on the way to us. Hopefully, I will share you with packing list for this order in early next week | 2026-06-16 |  | FALSE | 53 | -46084 | -6583.4286
IN TRANSIT | Emilka Guerra | 2026-03-03 | PO08715 | Stock | 2026-04-07 | D-2001408-2507 | Impeller Wear Ring, 10JKH/M, 5.12x5.48x0.88, Duplex SS 2507 w/Ion Nitriding | 35 | Nanjing Wangyang Pumps Co., Ltd | China | CA WAREHOUSE | 2026-05-30 | SEA | 2026-06-16 |  |  | Stock Canada / BALANCE PAYMENT REQUESTED | the ETD is 25th April. We will try to get it ready for dispatch asap. Peter: The vessel of ETD June 7 from Shanghai to Toronto Departed Shanghai and are on sea to Toronto. | Jiansuwin 04/30: All machining job is finished and we are only waiting for the wear ring now, we can get this order ready for dispatch around 10th May. James 05/15: The wear rings are just finished by nitriding treatment yesterday and it is now on the way to us. Hopefully, I will share you with packing list for this order in early next week | 2026-06-16 |  | FALSE | 53 | -46084 | -6583.4286
IN TRANSIT | Emilka Guerra | 2026-03-03 | PO08715 | Stock | 2026-04-07 | D-2001417-CD4 | Bell,10JKH/M, BW-FLG-STD-STEP-CUT_NR, CD4MCu | 3 | Nanjing Wangyang Pumps Co., Ltd | China | CA WAREHOUSE | 2026-05-30 | SEA | 2026-06-16 |  |  | Stock Canada / BALANCE PAYMENT REQUESTED | the ETD is 25th April. We will try to get it ready for dispatch asap. Peter: The vessel of ETD June 7 from Shanghai to Toronto Departed Shanghai and are on sea to Toronto. | Jiansuwin 04/30: All machining job is finished and we are only waiting for the wear ring now, we can get this order ready for dispatch around 10th May. James 05/15: The wear rings are just finished by nitriding treatment yesterday and it is now on the way to us. Hopefully, I will share you with packing list for this order in early next week | 2026-06-16 |  | FALSE | 53 | -46084 | -6583.4286
IN TRANSIT | Emilka Guerra | 2026-03-03 | PO08715 | SO18991 & Stock | 2026-04-07 | D-2001412-4PHSS | Hex Cap Screw, 10JKH/M, 0.44-14NCx1.50, 17-4PH SS | 180 | Nanjing Wangyang Pumps Co., Ltd | China | CA WAREHOUSE | 2026-05-30 | SEA | 2026-06-16 |  |  | Stock Canada / BALANCE PAYMENT REQUESTED | the ETD is 25th April. We will try to get it ready for dispatch asap. Peter: The vessel of ETD June 7 from Shanghai to Toronto Departed Shanghai and are on sea to Toronto. | Jiansuwin 04/30: All machining job is finished and we are only waiting for the wear ring now, we can get this order ready for dispatch around 10th May. James 05/15: The wear rings are just finished by nitriding treatment yesterday and it is now on the way to us. Hopefully, I will share you with packing list for this order in early next week | 2026-06-16 |  | FALSE | 53 | -46084 | -6583.4286
IN TRANSIT | Emilka Guerra | 2026-03-03 | PO08715 | SO18991 & Stock | 2026-04-07 | D-2001412-4PHSS | Hex Cap Screw, 10JKH/M, 0.44-14NCx1.50, 17-4PH SS | 192 | Nanjing Wangyang Pumps Co., Ltd | China | BARRICK CONSOLIDATED | 2026-05-30 | SEA | 2026-06-16 |  |  | Stock Canada / BALANCE PAYMENT REQUESTED JAmes arranged shipment to SHANGAI PORT | the ETD is 25th April. We will try to get it ready for dispatch asap. Peter: The vessel of ETD June 7 from Shanghai to Toronto Departed Shanghai and are on sea to Toronto. | Jiansuwin 04/30: All machining job is finished and we are only waiting for the wear ring now, we can get this order ready for dispatch around 10th May. James 05/15: The wear rings are just finished by nitriding treatment yesterday and it is now on the way to us. Hopefully, I will share you with packing list for this order in early next week | 2026-06-16 |  | FALSE | 53 | -46084 | -6583.4286
IN TRANSIT | Emilka Guerra | 2026-03-03 | PO08715 | SO18991 & Stock | 2026-04-07 | D-2001416-174PH | Hex-Head Socket Cap Screw, 10JKH/M, 0.31-18NCx0.750, 17-4PH SS | 300 | Nanjing Wangyang Pumps Co., Ltd | China | CA WAREHOUSE |  | SEA | 2026-06-16 |  |  | Stock Canada / BALANCE PAYMENT REQUESTED | the ETD is 25th April. We will try to get it ready for dispatch asap. Peter: The vessel of ETD June 7 from Shanghai to Toronto Departed Shanghai and are on sea to Toronto. | Jiansuwin 04/30: All machining job is finished and we are only waiting for the wear ring now, we can get this order ready for dispatch around 10th May. James 05/15: The wear rings are just finished by nitriding treatment yesterday and it is now on the way to us. Hopefully, I will share you with packing list for this order in early next week | 2026-06-16 |  | FALSE | -46119 | -46084 | -6583.4286
Received | Administrator | 2026-03-03 | PO08717 | SO18473 | 2026-03-24 | G-10x12-22-JC-HC | Pump, 10x12-22, Goulds JC Frame 5J, High Chrome | 1 | Frac Pump Parts | Other | CA WAREHOUSE | 2026-03-17 | LAND | ETA March last week | [5 empty] | 2026-03-31 | 2026-03-25 | TRUE | -7 | 22 | 3.1429
IN TRANSIT & DELAYED | Emilka Guerra | 2026-03-03 | PO08719 | Stock | 2026-04-07 | D-PE2J-200 | Power End, Goulds JC, Frame 2J, Grease-Lubed, SKF Bearings, 4140 Steel Shaft | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-05-26 | SEA | ETA Warehouse mid-august | the vessel depart on May 26 |  | #20251217-11 | Betty 4/23: Included in Comercial Invoice #20251217-11 | Status email sent on April 22nd | 2026-06-16 |  | FALSE | 49 | -46084 | -6583.4286
Received | Ian Trottier | 2026-03-04 | PO08722 | SO18855 | 2026-04-15 | WO-2114552-316 | Impeller, Worthington 6-FRBH-223, 316SS | 1 | M&N Alloy Cast Products, Inc. | US | CA WAREHOUSE | 2026-03-27 | LAND | 2026-04-22 |  |  |  | Ready to be shipped March 27th |  | 2026-04-22 | 2026-04-01 | TRUE | -19 | 28
Ready to Ship | Emilka Guerra | 2026-03-04 | PO08720 | SO18874 | 2026-05-01 | OLPWZ011005B, G-A04951A218 | Bearing Isolator (Inboard), 3196 MTX/MTi, Bronze Rotor/Bronze Stator w/Viton | 2 | Shandong Furkey Pumps Co., Ltd. | China | MX WAREHOUSE | 2026-07-17 | SEA | 2026-07-17 |  | DYNM-029Sea | Furkey: Order will be ready on April 20th. Booking shipping space to the port of Ensenada |  |  | 2026-07-17 |  | FALSE
Ready to Ship | Emilka Guerra | 2026-03-04 | PO08720 | SO18874 | 2026-05-01 | OLPWZ011006B, G-A04951A219 | Bearing Isolator (Outboard), 3196 MTX/MTi, 303SS Rotor / Bronze Stator w/Viton | 4 | Shandong Furkey Pumps Co., Ltd. | China | MX WAREHOUSE | 2026-07-17 | SEA | 2026-07-17 |  | DYNM-029Sea | Furkey: Order will be ready on April 20th. Booking shipping space to the port of Ensenada |  |  | 2026-07-17 |  | FALSE
Ready to Ship | Emilka Guerra | 2026-03-04 | PO08720 | SO18874 | 2026-05-01 | G-R104-733 2238 | Shaft (Sleeve Type), 3196 MTX, 4140 | 3 | Shandong Furkey Pumps Co., Ltd. | China | MX WAREHOUSE | 2026-07-17 | SEA | 2026-07-17 |  | DYNM-029Sea | Furkey: Order will be ready on April 20th. Booking shipping space to the port of Ensenada |  |  | 2026-07-17 |  | FALSE
Ready to Ship | Emilka Guerra | 2026-03-04 | PO08720 | SO18874 | 2026-05-01 | 468421/0507 | Power End, D-196 X17, 316SS Shaft (Sleeved Type), CD4MCu Fra | 2 | Shandong Furkey Pumps Co., Ltd. | China | MX WAREHOUSE | 2026-07-17 | SEA | 2026-07-17 |  | DYNM-029Sea | Furkey: Order will be ready on April 20th. Booking shipping space to the port of Ensenada |  |  | 2026-07-17 |  | FALSE
Ready to Ship | Emilka Guerra | 2026-03-04 | PO08720 | SO18874 | 2026-05-01 | G-0D04563A02 1216 | Impeller, 4x6-17, 3196 X17, CD4MCu, 5-Vane | 1 | Shandong Furkey Pumps Co., Ltd. | China | MX WAREHOUSE | 2026-07-17 | SEA | 2026-07-17 |  | DYNM-029Sea | Furkey: Order will be ready on April 20th. Booking shipping space to the port of Ensenada |  |  | 2026-07-17 |  | FALSE
Ready to Ship | Emilka Guerra | 2026-03-04 | PO08720 | SO18874 | 2026-05-01 | G-249-62 1216 | Casing, 3x4-10, 3196 MTX, CD4MCu | 2 | Shandong Furkey Pumps Co., Ltd. | China | MX WAREHOUSE | 2026-07-17 | SEA | 2026-07-17 |  | DYNM-029Sea | Furkey: Order will be ready on April 20th. Booking shipping space to the port of Ensenada |  |  | 2026-07-17 |  | FALSE
Received | Emilka Guerra | 2026-03-04 | PO08721 | SO18875 | 2026-01-05 | 10046/5001 | Suction Bell Bearing, 12RJHC-8, Teflon | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE | 2026-07-17 | SEA | 2026-07-17 |  |  |  | After Tomb-Sweeping holiday (Apr 4 to 6), OC00248/PO08603 will be ready for shipment. I will arrange the sea freight to Ensenada. |  | 2026-07-17 | 2026-06-09 | TRUE
Received | Emilka Guerra | 2026-03-04 | PO08721 | SO18875 | 2026-01-05 | 10045/5001 | Bowl Bearing, 12RJHC-8, Teflon | 16 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE | 2026-07-17 | SEA | 2026-07-17 |  |  |  | After Tomb-Sweeping holiday (Apr 4 to 6), OC00248/PO08603 will be ready for shipment. I will arrange the sea freight to Ensenada. |  | 2026-07-17 | 2026-06-09 | TRUE
Received | Emilka Guerra | 2026-03-04 | PO08721 | SO18875 | 2026-01-05 | 10049/0505 | Impeller Shaft, 12RJHC-8, 316SS | 2 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE | 2026-07-17 | SEA | 2026-07-17 |  |  |  | After Tomb-Sweeping holiday (Apr 4 to 6), OC00248/PO08603 will be ready for shipment. I will arrange the sea freight to Ensenada. |  | 2026-07-17 | 2026-06-09 | TRUE
Received | Emilka Guerra | 2026-03-04 | PO08721 | SO18875 | 2026-01-05 | 10059/5001 | Suction Bell Bearing, 18BHC-1, Teflon | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE | 2026-07-17 | SEA | 2026-07-17 |  |  |  | After Tomb-Sweeping holiday (Apr 4 to 6), OC00248/PO08603 will be ready for shipment. I will arrange the sea freight to Ensenada. |  | 2026-07-17 | 2026-06-09 | TRUE
Received | Emilka Guerra | 2026-03-04 | PO08721 | SO18875 | 2026-01-05 | 10060/5001 | Suction Box Bearing, 18BHC-1, Teflon | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE | 2026-07-17 | SEA | 2026-07-17 |  |  |  | After Tomb-Sweeping holiday (Apr 4 to 6), OC00248/PO08603 will be ready for shipment. I will arrange the sea freight to Ensenada. |  | 2026-07-17 | 2026-06-09 | TRUE
Received | Emilka Guerra | 2026-03-04 | PO08721 | SO18875 | 2026-01-05 | 10063/1501 | Lineshaft Coupling, 18BHC-1, 316SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE | 2026-07-17 | SEA | 2026-07-17 |  |  |  | After Tomb-Sweeping holiday (Apr 4 to 6), OC00248/PO08603 will be ready for shipment. I will arrange the sea freight to Ensenada. |  | 2026-07-17 | 2026-06-09 | TRUE
Received | Emilka Guerra | 2026-03-04 | PO08721 | SO18875 | 2026-01-05 | 10345/0503 | Head Shaft, 7CHC-9, 420SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE | 2026-07-17 | SEA | 2026-07-17 |  |  |  | After Tomb-Sweeping holiday (Apr 4 to 6), OC00248/PO08603 will be ready for shipment. I will arrange the sea freight to Ensenada. |  | 2026-07-17 | 2026-06-09 | TRUE
Received | Emilka Guerra | 2026-03-04 | PO08721 | SO18875 | 2026-01-05 | DC-MS000021 | Mechanical Seal, Dynapro Vertical Turbine, 12RJHC-8, A20 | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE | 2026-07-17 | SEA | 2026-07-17 |  |  |  | After Tomb-Sweeping holiday (Apr 4 to 6), OC00248/PO08603 will be ready for shipment. I will arrange the sea freight to Ensenada. |  | 2026-07-17 | 2026-06-09 | TRUE
Received | Emilka Guerra | 2026-03-04 | PO08721 | SO18875 | 2026-01-05 | DC-MS000035 | Mechanical Seal, 7CHC-9 | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE | 2026-07-17 | SEA | 2026-07-17 |  |  |  | After Tomb-Sweeping holiday (Apr 4 to 6), OC00248/PO08603 will be ready for shipment. I will arrange the sea freight to Ensenada. |  | 2026-07-17 | 2026-06-09 | TRUE
Received | Ian Trottier | 2026-03-05 | PO08723 | SO18857 | 2026-05-28 | PM# 6246, WO-2114549-001 | Impeller, Worthington 8-FRBH-183, 316SS | 1 | M&N Alloy Cast Products, Inc. | US | CA WAREHOUSE | 2026-04-06 | LAND | 2026-04-06 | [5 empty] | 2026-06-04 | 2026-04-08 | TRUE | -52 | 34 | 4.8571
DELAYED PRODUCTION | Gerardo Hernandez | 2026-03-05 | PO08724 | SO18877 | 2026-06-11 | AC-98-431-615-007 | Impeller, 6x4-14, PWO, 317SS | 1 | Emnor Mechanical Inc. | Canada | CA WAREHOUSE |  | LAND | 2026-12-06 |  |  | Follow up email sent June 16th | Steve 06/16: We are a little behind schedule. We should be able to ship by June 25/2026 |  | 2026-12-06 |  | FALSE | -46184 | -46086
Received | Jeff Bell | 2026-03-05 | PO08726 | Q-250613-N-1DDYFA-42415 | 2026-03-05 | WG-HT350406NPRBW22449T | 350 HP, 1200 RPM, 460/3/60, L447/9T Frame, WEG - TEFC - W22 Severe Duty NEMA Premium Electric Motor | 1 | V.J. Pamensky Canada Inc. | Canada | CA WAREHOUSE |  | LAND | 2026-05-03 | [5 empty] | 2026-05-03 | 2026-06-04 | TRUE | -46086 | 91 | 13
Received | Emilka Guerra | 2026-03-05 | PO08725 | SO18882 | 2026-03-04 | W-F029/A05 | Expeller Ring, 8/6 F-AH, High Chrome | 1 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-21 | SEA | 2026-05-03 |  | LS15TJ2604877 | Expeller Ring for SOMX00746 | After the Tomb-Sweeping holiday (Apr 4 to 6), the 1st batch will be ready for shipment. | ETA ENSENADA: May 14 | 2026-04-02 | 2026-06-09 | TRUE
Received | Emilka Guerra | 2026-03-05 | PO08725 | SO18882 | 2026-03-04 | W-E109/S50 | Shaft Sleeve O-Ring, 6/4 E-AH or 8/6 E,R or F-AH, Viton | 7 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-21 | SEA | 2026-05-03 |  | LS15TJ2604877 |  | After the Tomb-Sweeping holiday (Apr 4 to 6), the 1st batch will be ready for shipment. | ETA ENSENADA: May 14 | 2026-04-02 | 2026-06-09 | TRUE
Received | Emilka Guerra | 2026-03-05 | PO08725 | SO18882 | 2026-03-04 | SZ-E11B104591 | Bearing Cover, O-Ring | 11 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-02 | AIR | 2026-05-03 |  | DHL waybill (2884550826) | DHL TO HERMOSILLO | After the Tomb-Sweeping holiday (Apr 4 to 6), the 1st batch will be ready for shipment. |  | 2026-04-02 | 2026-04-28 | TRUE
Received | Emilka Guerra | 2026-03-05 | PO08725 | SO18882 | 2026-03-04 | SZ-2837900133-1 | Shaft | 2 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-21 | SEA | 2026-06-03 |  | LS15TJ2604877 |  |  | ETA ENSENADA: May 14 | 2026-06-12 | 2026-06-09 | TRUE
Received | Emilka Guerra | 2026-03-05 | PO08725 | SO18882 | 2026-03-04 | W-E075/C21 | Shaft Sleeve, 6/4 or 8/6 E or R-AH, 420SS Heat Treated, Hard | 1 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-21 | SEA | 2026-06-03 |  | LS15TJ2604877 |  | After the Tomb-Sweeping holiday (Apr 4 to 6), the 1st batch will be ready for shipment. | ETA ENSENADA: May 14 | 2026-04-02 | 2026-06-09 | TRUE
Received | Emilka Guerra | 2026-03-05 | PO08725 | SO18882 | 2026-03-04 | SZ-EL1208506M | Deflector | 13 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-02 | AIR | 2026-06-03 |  | DHL waybill (2884550826) | DHL TO HERMOSILLO | After the Tomb-Sweeping holiday (Apr 4 to 6), the 1st batch will be ready for shipment. |  | 2026-04-02 | 2026-04-28 | TRUE
Received | Emilka Guerra | 2026-03-05 | PO08725 | SO18882 | 2026-03-04 | SZ-3822790584 | Static Seal | 5 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-02 | AIR | 2026-06-03 |  | DHL waybill (2884550826) | DHL TO HERMOSILLO | After the Tomb-Sweeping holiday (Apr 4 to 6), the 1st batch will be ready for shipment. |  | 2026-04-02 | 2026-04-28 | TRUE
Received | Emilka Guerra | 2026-03-05 | PO08725 | SO18882 | 2026-03-04 | B1205I-76-110-03 | Bearing Cover, XS500-710, HT250 | 2 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-23 | SEA | 2026-06-03 |  | SHESE26251826G | left Shanghai for Ensenada by sea on Apr 23, 2026 |  | ETA ENSENADA: May 14 | 2026-04-02 | 2026-06-09 | TRUE
DELAYED PRODUCTION | Emilka Guerra | 2026-03-05 | PO08725 | SO18882 | 2026-03-04 | M74-140 | Mechanical Seal, XS500-710 | 3 | Super Cast Limited | China | MX WAREHOUSE | 2026-05-07 | AIR | ETA 2nd week of May | [5 empty] | 2026-04-02 |  | FALSE
IN TRANSIT | Emilka Guerra | 2026-03-05 | PO08725 | SO18882 | 2026-03-04 | JC-SCS-2 1/2-5610-XLT-SB | Single Cartridge Seal, 2 1/2", John Crane, Standard Bore | 3 | Super Cast Limited | China | MX WAREHOUSE | 2026-05-07 | AIR | ETA 2nd week of May |  | DHL waybill 6104171393 | Sent with OC00279 to complete weight |  |  | 2026-04-02 |  | FALSE
Received | Emilka Guerra | 2026-03-05 | PO08725 | SO18882 | 2026-03-04 | B1205I-76-110-06 | Bearing Locating Ring, XS500-710, Carbon Steel | 1 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-23 | SEA | 19/04/26 |  | SHESE26251826G | left Shanghai for Ensenada by sea on Apr 23, 2026 |  | ETA ENSENADA: May 14 | 2026-04-02 | 2026-05-25 | TRUE
Received | Emilka Guerra | 2026-03-05 | PO08725 | SO18882 | 2026-03-04 | B1205I-76-110-06 | Bearing Locating Ring, XS500-710, Carbon Steel | 3 | Super Cast Limited | China | MX WAREHOUSE | 2026-05-11 | SEA | ETA 2nd week of May |  | DHL waybill (7963743782) | left Shijiazhuang for Hermosillo via DHL on May 11, 2026 |  | ETA ENSENADA: May 15 | 2026-04-02 | 2026-06-09 | TRUE
Received | Emilka Guerra | 2026-03-05 | PO08725 | SO18882 | 2026-03-04 | CB22-140 | Mechanical Seal Cover - Bolts & Nuts, XS500-710, 2Cr13 | 3 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-23 | SEA | 19/04/26 |  | SHESE26251826G | left Shanghai for Ensenada by sea on Apr 23, 2026 |  | ETA ENSENADA: May 14 | 2026-04-02 | 2026-06-09 | TRUE
IN TRANSIT | Jeff Bell | 2026-03-05 | PO08728 | SO17350 | 2026-04-17 | W-250-FF-MCU/0011 | Pump, W-Series, 250 FF-MCU, Hyperchrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-06-19 | SEA | ETA Warehouse Mid-Sept | Follow email sent for update on June 16th |  | We already shipped them to Tianjin, but the vessel delayed, it shows that it will depart on June 19. | Betty 5/15: Included in Comercial Invoice / #20260205-11 | 4/13: After several pushing, Naipu finally gave out the ready time of the 250 FF-MCU pump: still need more than half a month. | 2026-06-17 |  | FALSE | 63 | -46086 | -6583.7143
Received | Ian Trottier | 2026-03-06 | PO08729 | SO18889 | 2026-03-27 | G-77-59 1001 | Bearing Housing, 3405-M, Cast Iron | 1 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-05-05 | LAND | ETA May 1st week |  |  |  | Hisco May 5th: Quenton Included in list for ready orders / waiting info on shipping date | April 30th: email follow up for orders. | 2026-04-30 | 2026-05-07 | TRUE | 39 | 62 | 8.8571
Ready to Ship & Delayed | Ian Trottier | 2026-03-06 | PO08730 | SO18872 | 2026-05-01 | WO-9090150-183 | Impeller Nut, Worthington 6 FRBH-183/223, 316SS | 1 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-06-16 | LAND | 2026-06-05 |  |  |  | Quenton Hisco 06/16: Ready to ship - Pending Pick up confirmation by logistics | May 5th: Asked for update on this delayed PO. Hisco May5th: Delayed ~ to be shipped Mid-may | 2026-06-05 |  | FALSE | 46 | -46087 | -6583.8571
DELAYED PRODUCTION | Ian Trottier | 2026-03-06 | PO08731 | SO18872 | 2026-05-29 | PM# 5899, WO-2112700-1 | Wear Plate, Worthington 6-FRBH-223, 316SS | 1 | M&N Alloy Cast Products, Inc. | US | CA WAREHOUSE |  | LAND | 2026-06-26 |  |  | Email for follow up sent on June 16th | Tammy 6/16: will ship on 7/10 |  | 2026-06-26 |  | FALSE | -46171 | -46087
Ready to Ship & Delayed | Emilka Guerra | 2026-03-06 | PO08732 | SO18865 | 2026-05-29 | AC-98-5414-HC1 | Volute Casing, 5x4-14 SRL-C, High Chrome, 3-Piece Design | 1 | IGH | Mexico | CA WAREHOUSE |  | LAND | 2026-07-03 |  |  |  | Carlos IGH 06/16: List for PO ready to ship ~ destination of shipement confirmed |  | 2026-07-03 |  | FALSE | -46171 | -46087 | -6583.8571
Ready to Ship & Delayed | Emilka Guerra | 2026-03-06 | PO08732 | SO18865 | 2026-05-29 | AC-98-5414-HC2 | Impeller (Nesting Design), 5x4-14 SRL-C, High Chrome, 3-Piece Design | 1 | IGH | Mexico | CA WAREHOUSE |  | LAND | 2026-07-03 |  |  |  | Carlos IGH 06/16: List for PO ready to ship ~ destination of shipement confirmed |  | 2026-07-03 |  | FALSE | -46171 | -46087 | -6583.8571
Received | Ian Trottier | 2026-03-06 | PO08733 | SO18763 | 2026-05-01 | G-R102-871 2229 | Shaft (Sleeve Type), 3175-S, 316SS | 1 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND | 2026-05-08 | [5 empty] | 2026-06-05 | 2026-03-17 | TRUE | -46143 | 11 | 1.5714
Received | Ian Trottier | 2026-03-06 | PO08733 | SO18763 | 2026-05-01 | G-B00296A 6956 | Shaft Sleeve, 3175-L, 316SS, Ni-Chrome Boron | 3 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-05-05 | LAND | ETA May 1st week |  |  |  | Hisco May 5th: Quenton Included in list for ready orders / waiting info on shipping date | April 30th: email follow up for orders. | 2026-06-05 | 2026-05-07 | TRUE | 4 | 62 | 8.8571
Ready to Ship & Delayed | Yannett Yeomans | 2026-03-09 | PO08735 | SO17830 | 2026-05-22 | AC-98-530-586-001 | Pedestal, 8x6-18 & 10x8-21 SRL-C, Cast Iron | 1 | IGH | Mexico | CA WAREHOUSE |  | LAND | 2026-06-12 |  |  |  | Carlos IGH 06/16: List for PO ready to ship ~ destination of shipement confirmed |  | 2026-05-18 |  | FALSE | -46164 | -46090 | -6584.2857
Ready to Ship & Delayed | Yannett Yeomans | 2026-03-09 | PO08735 | SO17830 | 2026-05-22 | AC-SRL 10x8-21-C-URE | Pump, AC-SRL 10x8-21-C, Urethane Lined, Motor Mounting Plate, Belt Guard | 1 | IGH | Mexico | CA WAREHOUSE |  | LAND | 2026-06-12 |  |  |  | Carlos IGH 06/16: List for PO ready to ship ~ destination of shipement confirmed |  | 2026-06-26 |  | FALSE | -46164 | -46090 | -6584.2857
Ready to Ship | Emilka Guerra | 2026-03-09 | PO08736 | SO18902 | 20/03/26 | W-D025/P10 | End Cover Shim Set, 4/3 or 6/4 D-AH | 2 | Super Cast Limited | China | MX WAREHOUSE | 2026-03-25 | AIR |  |  | DHL waybill# 4552478464. | shipped out yesterday (Mar 25, 2025). |  |  | 2026-10-04 |  | FALSE
DELAYED PRODUCTION | Emilka Guerra | 2026-03-09 | PO08736 | SO18902 | 20/03/26 | AC-98-231-123-501 | Gland Side Liner, 8x6-18 SRL-C, Natural Rubber | 4 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-10 | AIR | 2026-06-05 |  |  | Email sent for update april 16th 2026 |  | (1st batch) | 2026-04-10 |  | FALSE
IN TRANSIT | Ian Trottier | 2026-03-10 | PO08737 | Stock | 2026-04-29 | D-PE3J-300 | Power End, Goulds JC, Frame 3J, Grease-Lubed, SKF Bearings, 4140 Steel Shaft | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-06-19 | SEA | ETA Warehouse Mid-Sept |  |  | Follow email sent for update on June 16th . We already shipped them to Tianjin, but the vessel delayed, it shows that it will depart on June 19. | Betty 6/9: Included in Comercial Invoice / #20260205-11 | Status email sent on April 22nd | 2026-07-08 |  | FALSE | 51 | -46091 | -6584.4286
DELAYED PRODUCTION | Ian Trottier | 2026-03-10 | PO08738 | SO18849 | 2026-04-10 | AC-98-431-614-007 | Impeller, 6x3-14, PWO, 317SS | 2 | Emnor Mechanical Inc. | Canada | CA WAREHOUSE |  | LAND | 2026-06-19 |  |  | Follow up email sent June 16th | Steve 06/16: We should be able to ship by July 8/2026. Sooner if possible. |  | 2026-06-19 |  | FALSE | -46122 | -46091 | -6584.4286
Ready to Ship | Emilka Guerra | 2026-03-11 | PO08739 | Stock | 2026-05-15 | AC-98-331-954-801 | Bearing Cover (Inboard), 5x4/5x5/6x6 SRL & SRL-C, Cast Iron | 6 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | 2026-07-10 |  |  | Email for update sent June 2nd | Betty: These three parts are ready to ship now. KN told me that the vessel was changed yesterday, I contacted with KN try to add these parts and PO0737 in the shipment. | Betty: We estimate these spare parts need about 40-50 days | 2026-07-10 |  | FALSE | -46157 | -46092
Ready to Ship | Emilka Guerra | 2026-03-11 | PO08739 | Stock | 2026-05-15 | AC-98-236-256-501 | Gland Assembly, 5x4-14 SRL-C, 316SS | 10 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | 2026-07-10 |  |  | Email for update sent June 2nd | Betty: These three parts are ready to ship now. KN told me that the vessel was changed yesterday, I contacted with KN try to add these parts and PO0737 in the shipment. | Betty: We estimate these spare parts need about 40-50 days | 2026-07-10 |  | FALSE | -46157 | -46092
IN TRANSIT | Emilka Guerra | 2026-03-11 | PO08739 | Stock | 2026-05-15 | D-2J3411-2 | Casing, 3x4-11, Goulds JC, Frame 2J, High Chrome, OEM# 056185G4001228 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-06-19 | SEA | ETA Warehouse Mid-Sept |  |  | Follow email sent for update on June 16th . We already shipped them to Tianjin, but the vessel delayed, it shows that it will depart on June 19. | Betty 5/15: Included in Comercial Invoice / #20260205-11 | Betty: We estimate these spare parts need about 40-50 days | 2026-07-10 |  | FALSE | 35 | -46092
IN TRANSIT | Emilka Guerra | 2026-03-11 | PO08739 | Stock | 2026-05-15 | D-2J3411-6 | Suction Cover Liner, 3x4-11, Goulds JC, Frame 2J, High Chrome, OEM# 048824G0001228 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-06-19 | SEA | ETA Warehouse Mid-Sept |  |  | Follow email sent for update on June 16th . We already shipped them to Tianjin, but the vessel delayed, it shows that it will depart on June 19. | Betty 5/15: Included in Comercial Invoice / #20260205-11 | Betty: We estimate these spare parts need about 40-50 days | 2026-07-10 |  | FALSE | 35 | -46092
Ready to Ship | Emilka Guerra | 2026-03-11 | PO08739 | Stock | 2026-05-15 | AC-98-234-268-001-SS | Waterseal Bushing, 5x4/5x5/6x6 SRL, 316SS | 10 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | 2026-07-10 |  |  | Email for update sent June 2nd | Betty: These three parts are ready to ship now. KN told me that the vessel was changed yesterday, I contacted with KN try to add these parts and PO0737 in the shipment. | Betty: We estimate these spare parts need about 40-50 days | 2026-07-10 |  | FALSE | -46157 | -46092
IN TRANSIT & DELAYED | Emilka Guerra | 2026-03-11 | PO08740 | Stock | 2026-04-22 | DU-DY51040A-CD4 | Casing, 3x2-10A, Durco Mark 2&3 Group 2, CD4MCu | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-06-12 | SEA | ETA Warehouse 1st week of august |  | shipped via DYNC-116 SEA. YM COSMOS/190E | ETD Qingdao 12 June ETA Toronto 16 July | Betty 04/24: will be finished around 3rd May & will consolidate shipping with other orders around May 10th. | Status email sent on April 23rd Status email sent on June 8th | 2026-07-10 |  | FALSE | 51 | -46092
Received | Emilka Guerra | 2026-03-11 | PO08740 | Stock | 2026-04-22 | DU-SA3210AA00-TFR | Impeller Gasket, Durco Mark 2&3 Group 2, Teflon/Rubber | 14 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-20 | SEA | ETA Warehouse Mid June |  | DYNC-113 SEA // BL# HHSE6042268, Container # CAAU5246660 | ETA Vancouver on May 5 |  |  | 2026-07-10 | 2026-05-26 | TRUE | -2 | 76 | 10.8571
IN TRANSIT & DELAYED | Emilka Guerra | 2026-03-11 | PO08740 | Stock | 2026-04-22 | DU-MY51049A100-CD4 | Impeller, 3x2-10A, Durco Mark 2&3 Group 2, CD4MCu, Reverse Vane | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-06-12 | SEA | ETA Warehouse 1st week of august |  | shipped via DYNC-116 SEA. YM COSMOS/190E | ETD Qingdao 12 June ETA Toronto 16 July | Betty 04/24: will be finished around 3rd May & will consolidate shipping with other orders around May 10th. | Status email sent on April 23rd Status email sent on June 8th | 2026-07-10 |  | FALSE | 51 | -46092 | -6584.5714
IN TRANSIT & DELAYED | Emilka Guerra | 2026-03-11 | PO08740 | Stock | 2026-04-22 | G-254-50 1216 | Casing, 6x8-13, 3196 XLT, CD4MCu | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-06-12 | SEA | ETA Warehouse 1st week of august |  | shipped via DYNC-116 SEA. YM COSMOS/190E | ETD Qingdao 12 June ETA Toronto 16 July | Betty 04/24: will be finished around 3rd May & will consolidate shipping with other orders around May 10th. | Status email sent on April 23rd Status email sent on June 8th | 2026-07-10 |  | FALSE | 51 | -46092 | -6584.5714
IN TRANSIT & DELAYED | Emilka Guerra | 2026-03-11 | PO08740 | Stock | 2026-04-22 | DU-MY49112A130-CD4 | Impeller, 3x2-13, Durco Mark 2&3 Group 2, CD4MCu, Reverse Vane | 5 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-06-12 | SEA | ETA Warehouse 1st week of august |  | shipped via DYNC-116 SEA. YM COSMOS/190E | ETD Qingdao 12 June ETA Toronto 16 July | Betty 04/24: will be finished around 3rd May & will consolidate shipping with other orders around May 10th. | Status email sent on April 23rd Status email sent on June 8th | 2026-07-10 |  | FALSE | 51 | -46092 | -6584.5714
IN TRANSIT & DELAYED | Emilka Guerra | 2026-03-11 | PO08740 | Stock | 2026-04-22 | G-D04872A 1000 | Thrust Bearing Housing, 3196 MTX, Cast Iron | 2 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-06-12 | SEA | ETA Warehouse 1st week of august |  | shipped via DYNC-116 SEA. YM COSMOS/190E | ETD Qingdao 12 June ETA Toronto 16 July | Betty 04/24: will be finished around 3rd May & will consolidate shipping with other orders around May 10th. | Status email sent on April 23rd Status email sent on June 8th | 2026-07-10 |  | FALSE | 51 | -46092 | -6584.5714
Received | Emilka Guerra | 2026-03-11 | PO08740 | Stock | 2026-04-22 | OLPWZ011005B, G-A04951A218 | Bearing Isolator (Inboard), 3196 MTX/MTi, Bronze Rotor/Bronze Stator w/Viton | 8 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-20 | SEA | ETA Warehouse Mid June |  | DYNC-113 SEA // BL# HHSE6042268, Container # CAAU5246660 | ETA Vancouver on May 5 |  |  | 2026-07-10 | 2026-05-26 | TRUE | -2 | 76 | 10.8571
Received | Emilka Guerra | 2026-03-11 | PO08740 | Stock | 2026-04-22 | OLPWZ011006B, G-A04951A219 | Bearing Isolator (Outboard), 3196 MTX/MTi, 303SS Rotor / Bronze Stator w/Viton | 12 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-20 | SEA | ETA Warehouse Mid June |  | DYNC-113 SEA // BL# HHSE6042268, Container # CAAU5246660 | ETA Vancouver on May 5 |  |  | 2026-07-10 | 2026-05-26 | TRUE | -2 | 76 | 10.8571
Received | Emilka Guerra | 2026-03-11 | PO08740 | Stock | 2026-04-22 | G-R104-733 2238 | Shaft (Sleeve Type), 3196 MTX, 4140 | 6 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-20 | SEA | ETA Warehouse Mid June |  | DYNC-113 SEA // BL# HHSE6042268, Container # CAAU5246660 | ETA Vancouver on May 5 |  |  | 2026-07-10 | 2026-05-26 | TRUE | -2 | 76 | 10.8571
Received | Emilka Guerra | 2026-03-11 | PO08741 | SO18692 | 2026-03-27 | AC-98-5414-HC7 | Suction Side Plate Gasket, 5x4-14 SRL-C, Rubber, 3-Piece Design | 1 | Specialty Gaskets Inc. | Canada | CA WAREHOUSE |  | LAND | 2026-04-10 | [5 empty] | 2026-04-10 | 2026-03-23 | TRUE | -46108 | 12 | 1.7143
Received | Emilka Guerra | 2026-03-11 | PO08742 | Stock | 2026-03-27 | FS58979M4 | Single Cartridge Mechanical Seal, 1 7/8", VBRB3, Big Bore, Carbon vs Silicon Carbide, TFEP, A276 Bellows, 316SS | 3 | Flexaseal Engineered Seals and Systems, LLC | Canada | CA WAREHOUSE | 2026-04-01 | LAND | [6 empty] | 2026-04-03 | 2026-03-27 | TRUE | 5 | 16 | 2.2857
Received | Emilka Guerra | 2026-03-11 | PO08742 | Stock | 2026-03-27 | 28VSMS3-04C4VS4 | Single Cartridge Seal, 1 3/4", VSMS, Standard Bore, Carbon vs Silicon Carbide / TFEP | 2 | Flexaseal Engineered Seals and Systems, LLC | Canada | CA WAREHOUSE | 2026-03-27 | LAND | 2026-03-28 | [5 empty] | 2026-04-03 | 2026-04-01 | TRUE | 0 | 21 | 3
IN TRANSIT & DELAYED | Emilka Guerra | 2026-03-11 | PO08743 | Stock | 2026-04-10 | TSSC-J01-1.375(BIG BORE)-00 | Single Cartridge Seal, 1 3/8", D-196 STX or D-III Group 1, Big Bore, Carbon vs Silicon Carbide w/Aflas Elastomers | 15 | Super Cast Limited | China | CA WAREHOUSE | 2026-05-08 | SEA | ETA Prince Rupert: May 30 ETA Warehouse is around Jul. 13 - 17 |  | LS21TJ2604679 |  | Peter 4/30: Already booked the vessel of ETD May 7 from Tianjin to Toronto. left Tianjin for Toronto by sea on May 8, 2026 | Production time longer 7 weeks, to be ready by april 30th. | 2026-06-26 |  | FALSE | 28 | -46092 | -6584.5714
IN TRANSIT | Emilka Guerra | 2026-03-11 | PO08743 | Stock | 2026-04-10 | AC-98-231-135-501 | Suction Side Plate, 10x8-21 SRL-C, Natural Rubber | 10 | Super Cast Limited | China | CA WAREHOUSE | 2026-06-04 | SEA | ETA Warehouse Mid-end June |  | LS21TJ2605671 |  | Peter 06/12: left Tianjin for Toronto by sea on June 4, 2026. ETA Prince Rupert: June 29. | Production time longer 7 weeks, to be ready by april 30th. | 2026-06-26 |  | FALSE | 55 | -46092 | -6584.5714
IN TRANSIT | Emilka Guerra | 2026-03-11 | PO08743 | Stock | 2026-04-10 | AC-98-431-651-501 | Impeller (Closed), 8x6-18 SRL-C, Natural Rubber | 6 | Super Cast Limited | China | CA WAREHOUSE | 2026-06-04 | SEA | ETA Warehouse Mid-end June |  | LS21TJ2605671 |  | Peter 06/12: left Tianjin for Toronto by sea on June 4, 2026. ETA Prince Rupert: June 29. | Production time longer 7 weeks, to be ready by april 30th. | 2026-06-26 |  | FALSE | 55 | -46092 | -6584.5714
IN TRANSIT & DELAYED | Emilka Guerra | 2026-03-11 | PO08743 | Stock | 2026-04-10 | AC-98-231-120-501 | Suction Side Liner, 8x6-18 SRL-C, Natural Rubber | 5 | Super Cast Limited | China | CA WAREHOUSE | 2026-05-08 | SEA | ETA Prince Rupert: May 30 ETA Warehouse is around Jul. 13 - 17 |  | LS21TJ2604679 |  | Peter 4/30: Already booked the vessel of ETD May 7 from Tianjin to Toronto. left Tianjin for Toronto by sea on May 8, 2026 | Production time longer 7 weeks, to be ready by april 30th. | 2026-06-26 |  | FALSE | 28 | -46092 | -6584.5714
IN TRANSIT | Emilka Guerra | 2026-03-11 | PO08743 | Stock | 2026-04-10 | W-SL30083M/A05 | Throatbush, 300 RSL, High Chrome | 1 | Super Cast Limited | China | CA WAREHOUSE | 2026-04-16 | SEA | 2026-06-26 |  | LS21TJ2604675 | ETA Prince Rupert: May 9, 2026 | left Tianjin for Toronto by sea on Apr 16, 2026 |  | 2026-06-26 |  | FALSE | 6 | -46092 | -6584.5714
Received | Emilka Guerra | 2026-03-11 | PO08744 | SO17830 & SO18886 / Stock | 2026-03-27 | AC-98-331-958-804 | Shaft Sleeve, 3x3-10 SRL, Steel | 3 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE | 2026-03-27 | LAND | 2026-03-28 | [5 empty] | 2026-04-03 | 2026-03-27 | TRUE | 0 | 16 | 2.2857
Received | Emilka Guerra | 2026-03-11 | PO08744 | SO17830 & SO18886 / Stock | 2026-03-27 | AC-98-331-958-810 | Shaft Sleeve, 2x2-10 SRL, 316SS | 1 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE | 2026-03-27 | LAND | 2026-03-28 | [5 empty] | 2026-04-03 | 2026-03-27 | TRUE | 0 | 16 | 2.2857
Received | Emilka Guerra | 2026-03-11 | PO08744 | SO17830 & SO18886 / Stock | 2026-03-27 | G-00-573-175-293 | Jacking Bolt, 8x6-18/10x8-21 SRL-C, HEX (OEM) Style, c/w Jam Nut | 4 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE | 2026-03-27 | LAND | 2026-03-28 | [5 empty] | 2026-04-03 | 2026-03-27 | TRUE | 0 | 16 | 2.2857
Received | Ian Trottier | 2026-03-11 | PO08745 | SO18914 | 2026-05-08 | DU-DY21855A/CBS-C276 | Rear Cover, 13", Durco Mark 2&3 Group 2, Hastelloy-C, Small Bore | 4 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-23 | AIR | 2026-05-26 |  | DYNC-114 The AIR waybill# is 006-5139 2703 |  |  | Status email sent on April 23rd | 2026-05-26 | 2026-05-12 | TRUE | -15 | 62 | 8.8571
Received | Ian Trottier | 2026-03-12 | PO08747 | Stock - Fastener Kits | 2026-03-20 | BSHCCS8114, WLHC38, SA-013733-FAS-KIT | Wear Disc Fastener Kit, 44 WFR, Sala STGVA-180, 4 Studs, & 4 Lock-Washers | 90 | Rastall Mine Supply Limited | Canada | CA WAREHOUSE |  | LAND | 2026-03-13 | [5 empty] | 2026-03-13 | 2026-03-26 | TRUE | -46101 | 14
Received | Emilka Guerra | 2026-03-12 | PO08746 | SO18921 | 2026-03-20 | 17779900159 | Annular Washer, Sulzer A53-250 | 2 | Super Cast Limited | China | MX WAREHOUSE |  | AIR | 2026-04-10 |  |  | SHIP TO GRUPO MEXICO AND ASK FOR THE WRONG PIECE BACK | The shipment left Hongya's factory on Apr 2's afternoon by truck for Guangzhou where it will be delivered to DHL. | due to the Tomb-sweeping holiday (Apr 4 to 6), the DHL does not work. | 2026-04-10 | 2026-04-01 | TRUE
IN TRANSIT | Ian Trottier | 2026-03-13 | PO08748 | Stock | 2026-04-22 | SA-128214-1 | Inlet, Sala VS150, High Chrome | 6 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-06-19 | SEA | ETA Warehouse Mid-Sept |  |  | Follow email sent for update on June 16th . We already shipped them to Tianjin, but the vessel delayed, it shows that it will depart on June 19. | Betty 6/9: Included in Comercial Invoice / #20260205-11 |  | 2026-07-08 |  | FALSE | 58 | -46094
Cancelled | Ian Trottier | 2026-03-13 | PO08749 | Stock | 2026-05-06 | AC-98-231-136-507 | Gland Side Liner, 10x8-21 SRL-C, Urethane | 1 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | 2026-07-22 |  |  | Cancelled by Ian in Odoo |  |  | 2026-07-22 |  | FALSE | -46148 | -46094
Cancelled | Ian Trottier | 2026-03-13 | PO08749 | Stock | 2026-05-06 | AC-98-231-134-507 | Suction Side Liner, 10x8-21 SRL-C, Urethane | 1 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | 2026-07-22 |  |  | Cancelled by Ian in Odoo |  |  | 2026-07-22 |  | FALSE | -46148 | -46094
Cancelled | Ian Trottier | 2026-03-13 | PO08749 | Stock | 2026-05-06 | AC-98-231-135-507 | Suction Side Plate, 10x8-21 SRL-C, Urethane | 1 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | 2026-07-22 |  |  | Cancelled by Ian in Odoo |  |  | 2026-07-22 |  | FALSE | -46148 | -46094
Cancelled | Ian Trottier | 2026-03-13 | PO08749 | Stock | 2026-05-06 | AC-98-431-641-507 | Impeller (Closed), 10x8-21 SRL-C, Urethane | 1 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | 2026-07-22 |  |  | Cancelled by Ian in Odoo |  |  | 2026-07-22 |  | FALSE | -46148 | -46094
Received | Ian Trottier | 2026-03-13 | PO08750 | SO18909 | 2026-03-18 | BG-187260 | Motor Bracket, Bell & Gossett, E-80 4x4-7B, 143-184JM, Cast Iron | 4 | Bramham Bros Limited | Canada | CA WAREHOUSE |  | LAND | 2026-03-17 | [5 empty] | 2026-03-17 | 2026-03-19 | TRUE | -46099 | 6 | 0.85714
IN TRANSIT | Ian Trottier | 2026-03-17 | PO08751 | SO18930 | 2026-06-09 | MY47018A-A20 | Impeller (Recessed), 4x3R-13, Durco Mark 2&3, Group 2, Alloy-20 | 2 | M&N Alloy Cast Products, Inc. | US | CA WAREHOUSE | 2026-06-05 | LAND | 2026-06-16 |  |  |  | will ETA our warehouse 2ndweek June. |  | 2026-06-16 |  | FALSE | -4 | -46098 | -6585.4286
Received | Emilka Guerra | 2026-03-18 | PO08752 | SO18946 | 2026-03-27 | WO-390078-00 | Seal Ring, Worthington FRBH, Frame Size 5, Rubber | 1 | Renewal Services Inc. | Canada | CA WAREHOUSE |  | LAND | 2026-05-01 | [5 empty] | 2026-05-01 | 2026-03-23 | TRUE | -46108 | 5
Received | Ian Trottier | 2026-03-18 | PO08753 | SO18945 | 2026-05-13 | G-270-38 1013 | Bearing Frame, 10 Inch, Goulds 3996 MT, Ductile Iron | 1 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-04-09 | LAND | 2026-05-22 | [5 empty] | 2026-05-22 | 2026-04-14 | TRUE | -34 | 27
Cancelled | Ian Trottier | 2026-03-18 | PO08754 |  | 2026-05-07 | AC-98-231-136-507 | Gland Side Liner, 10x8-21 SRL-C, Urethane | 1 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | 2026-07-16 |  |  | Cancelled by Ian in Odoo |  | Pls be kindly noted: considering the long labor holiday (May 1 to 5), and the coming high-load production season, the supplier required 10 more days for lead time. | 2026-07-16 |  | FALSE | -46149 | -46099 | -6585.5714
Cancelled | Ian Trottier | 2026-03-18 | PO08754 |  | 2026-05-07 | AC-98-231-134-507 | Suction Side Liner, 10x8-21 SRL-C, Urethane | 1 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | 2026-07-16 |  |  | Cancelled by Ian in Odoo |  | Pls be kindly noted: considering the long labor holiday (May 1 to 5), and the coming high-load production season, the supplier required 10 more days for lead time. | 2026-07-16 |  | FALSE | -46149 | -46099 | -6585.5714
Received | Ian Trottier | 2026-03-19 | PO08755 | SO18950 | 2026-04-03 | G-71224-1001 | Casing Wear Ring 3405-M, 4x6-17G, Cast Iron | 2 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-04-09 | LAND | 2026-04-14 | [5 empty] | 2026-04-14 | 2026-04-14 | TRUE | 6 | 26
Received | Emilka Guerra | 2026-03-20 | PO08756 | SO18957 | 27/03/26 | AC-98-234-268-001 | Waterseal Bushing, 5x5/5x4/6x6 SRL & SRL-C, Steel | 2 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE | 2026-03-27 | LAND | 2026-10-04 | [5 empty] | 2026-04-10 | 2026-03-27 | TRUE | #VALUE! | 7
Received | Emilka Guerra | 2026-03-20 | PO08756 | SO18957 | 27/03/26 | AC-98-431-743-501 | Shaft Assembly, 10x8-21 SRL-C, 1045 Steel | 1 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE | 2026-03-27 | LAND | 2026-10-04 | [5 empty] | 2026-04-10 | 2026-03-27 | TRUE | #VALUE! | 7
Received | Emilka Guerra | 2026-03-20 | PO08757 | Stock | 27/03/26 | 029V, G-C02495A029 5304 | Shaft Sleeve O-Ring, 3x3-10 SRL, Viton | 20 | Wajax Limited - Mississauga | Canada | CA WAREHOUSE | 2026-03-27 | LAND | 2026-03-24 | [5 empty] | 2026-04-10 | 2026-03-24 | TRUE | #VALUE! | 4
Received | Emilka Guerra | 2026-03-20 | PO08758 | Stock | 27/03/26 | AC-98-430-807-163 | Casing Gasket, 21", PWO Frame 3 | 12 | NC Industrial | US | CA WAREHOUSE | 2026-03-30 | LAND | 2026-04-10 | [5 empty] | 2026-04-10 | 2026-03-27 | TRUE | #VALUE! | 7
Received | Emilka Guerra | 2026-03-20 | PO08759 | Stock | 2026-05-08 | G-R104-562 1216 | Stuffing Box Cover, 6", 3196 STX, CD4MCu, Standard Bore, Non-Jacketed | 2 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-20 | SEA | ETA Warehouse Mid June |  | DYNC-113 SEA // BL# HHSE6042268, Container # CAAU5246660 | ETA Vancouver on May 5 |  |  | 2026-07-16 | 2026-05-26 | TRUE | -18 | 67 | 9.5714
Received | Emilka Guerra | 2026-03-23 | PO08760 | SO18965 | 2026-04-20 | W-F8147/R55 | Impeller, 10/8 E-M, Natural Rubber | 3 | Super Cast Limited | China | CA WAREHOUSE | 2026-04-10 | SEA | 2026-06-29 |  | LS21TJ2604576 | ETA Port of Prince Rupert: May 2, 2026 | left Tianjin for Toronto by sea on Apr 10, 2026 |  | 2026-06-29 | 2026-06-09 | TRUE | -10 | 78 | 11.1429
Received | Emilka Guerra | 2026-03-23 | PO08761 | Stock | 2026-04-03 | AC-52-108-475-012 | Deflector (Inboard), Allis-Chalmers PWO, Group 2 | 6 | Advanced Engineered Pump Inc. | Canada | CA WAREHOUSE | 2026-05-05 | LAND | 2026-07-24 | [5 empty] | 2026-07-24 | 2026-05-07 | TRUE | 32 | 45 | 6.4286
Ready to Ship & Delayed | Leriel Reyes | 2026-03-24 | PO08762 | SO18978 | 2026-06-16 | AC-SRL 2x2-10 | Pump, AC-SRL 2x2-10, Natural Rubber Lined, Motor Mounting Plate, Belt Guard | 1 | IGH | Mexico | CA WAREHOUSE |  | LAND | 2026-05-05 |  |  |  | Carlos IGH 06/16: List for PO ready to ship ~ destination of shipement confirmed |  | 2026-05-05 |  |  | -46189 | -46105 | -6586.4286
Received | Emilka Guerra | 2026-03-24 | PO08764 | SO18981 | 21/04/26 | G-RPK-ESHM | Repair Kit, E-SH Pump, Goulds | 1 | SUMMIT WATER | Canada | MX WAREHOUSE | 2026-04-09 | LAND | 26/03/26 | [5 empty] | 2026-04-13 |  | TRUE
DELAYED PRODUCTION | Ian Trottier | 2026-03-26 | PO08765 | SO18990 | 2026-06-18 | PM# 510, G-R254-70 1216 | Stuffing Box Cover, 18", 3175-M, CD4MCu, Standard Bore | 2 | M&N Alloy Cast Products, Inc. | US | CA WAREHOUSE |  | LAND | 2026-06-19 |  |  | Email for follow up sent on June 16th | Tammy 6/16: will ship on 6/26 |  | 2026-06-19 |  |  | -46191 | -46107 | -6586.7143
IN TRANSIT | Ian Trottier | 2026-03-26 | PO08766 | SO18967 | 2026-06-18 | PM# 1599, AC-52-425-392-006 | Casing, 2x3-13, Allis Chalmers CSO, 316ss | 1 | M&N Alloy Cast Products, Inc. | US | CA WAREHOUSE | 2026-06-12 | LAND | 2026-06-19 |  |  |  | Christine 06/12: This shipment (1 Pallet) is expected to arrive at our warehouse next week. |  | 2026-06-19 |  | FALSE | -6 | -46107 | -6586.7143
Received | Ian Trottier | 2026-03-27 | PO08767 | SO18999 | 2026-06-19 | 52-321-237-100 | Impeller, 2x1-10, Allis-Chalmers CSO, 317SS | 1 | M&N Alloy Cast Products, Inc. | US | CA WAREHOUSE |  | LAND | 2026-06-25 | [5 empty] | 2026-06-25 | 2026-04-08 | TRUE | -46192 | 12
Ready to Ship | Amanda Qiao | 2026-03-30 | PO08768 | SO18861 | 2026-05-22 | AC-SRL 5x5-14 | Pump, AC-SRL 5x5-14, Natural Rubber Lined, Motor Mounting Plate, Belt Guard | 1 | IGH | Mexico | CA WAREHOUSE |  | LAND | 2026-07-24 |  |  |  | Carlos IGH 06/16: List for PO ready to ship ~ destination of shipement confirmed |  | 2026-07-24 |  | FALSE | -46164 | -46111 | -6587.2857
Received | Ian Trottier | 2026-03-30 | PO08769 |  | 2026-05-25 | DU-DY50172A20 | Casing, 4x3-13HH, Durco Mark 2&3 Group 2, Alloy 20 | 3 | M&N Alloy Cast Products, Inc. | US | CA WAREHOUSE |  | LAND | 2026-06-23 | [5 empty] | 2026-06-23 | 2026-05-13 | TRUE | -46167 | 44 | 6.2857
Received | Ian Trottier | 2026-03-30 | PO08770 | SO18895 | 2026-05-15 | DU-CY21853A-A20 | Casing, 3x1.5-13, Durco Mark 2&3 Group 2, Alloy 20 | 2 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-05-22 | AIR | ETA WAREHOSE June 2nd week |  | DYNC-115 Air | After Ian's approval, will be transported to Qingdao Airport. |  |  | 2026-05-27 | 2026-06-01 | TRUE | 7 | 63 | 9
Received | Ian Trottier | 2026-03-30 | PO08770 | SO18895 | 2026-05-15 | DU-MY36649AA130-A20 | Impeller, 3x1.5-13, Durco Mark 2&3 Group 2, Alloy 20, Reverse Vane | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-05-22 | AIR | ETA WAREHOSE June 2nd week |  | DYNC-115 Air | After Ian's approval, will be transported to Qingdao Airport. |  |  | 2026-05-27 | 2026-06-01 | TRUE | 7 | 63 | 9
Received | Ian Trottier | 2026-03-30 | PO08770 | SO18895 | 2026-05-15 | DU-MY36649AA130-A20 | Impeller, 3x1.5-13, Durco Mark 2&3 Group 2, Alloy 20, Reverse Vane | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-06-05 | AIR | ETA WAREHOSE June 2nd week |  | DYNC-117 AIR | After Ian's approval, will be transported to Qingdao Airport. |  |  | 2026-05-27 | 2026-06-08 | TRUE | 21 | 70 | 10
Received | Ian Trottier | 2026-03-30 | PO08770 | SO18895 | 2026-05-15 | DU-MY36847AA130-A20 | Impeller, 4x3-13, Durco Mark 2&3 Group 2, Alloy 20, Reverse Vane | 2 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-05-22 | AIR | ETA WAREHOSE June 2nd week |  | DYNC-115 Air | After Ian's approval, will be transported to Qingdao Airport. |  |  | 2026-05-27 | 2026-06-01 | TRUE | 7 | 63 | 9
Received | Ian Trottier | 2026-03-30 | PO08770 | SO18895 | 2026-05-15 | DU-MY50171AA130-A20 | Impeller, 4x3-13HH, Durco Mark 2&3 Group 2, Alloy 20, Reverse Vane | 4 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-05-22 | AIR | ETA WAREHOSE June 2nd week |  | DYNC-115 Air | After Ian's approval, will be transported to Qingdao Airport. |  |  | 2026-05-27 | 2026-06-01 | TRUE | 7 | 63 | 9
In Production | Emilka Guerra | 2026-03-30 | PO08771 | SO19012 | 2026-04-27 | W-M120MC076/C21 | Shaft Sleeve, 350 MCR, 420SS | 2 | Super Cast Limited | China | MX WAREHOUSE |  | SEA | 2026-07-06 | [5 empty] | 2026-07-06 |  | FALSE
Ready to Ship & Delayed | Emilka Guerra | 2026-03-30 | PO08772 | SO18353 | 2026-05-18 | AM-HH200C21-13 | Casing Cover (Blackplate), DW-AE8/6-21W, CD4MCu | 1 | AMOS Fluid Technology Co., Ltd | China | BARRICK DIRECT SHIPPING |  | SEA | 2026-07-07 | Peter will take care of the sea shipment -- CIF Caucedo Port | BARRICK ORDER | Follow up email sent on May 7th. Follow up email sent on May 20th. Follow up email sent on May 29th. Follow up email sent on June 2nd Follow up email sent on June 11th Follow up email sent on June 16th | AMOS May 8th: confirmed completition by May 20th ✅ Peter: AMOS confirmed it will be ready to leave factory by May 20 (Wednesday). I will book vessel next Monday. June 5th: will be dispatched to Shanghai seaport | Delayed production: To be completed in the week 25 - 29 The delivery dates of all orders have been affected. This order will be completed by this Friday at the earliest. June 3rd Pump casing is under painting now ~ JUNE 06/11: is already in Shanghai seaport's warehouse waiting for the vessel: CMA CGM UNITY / OPPJCE. original ETD Shanghai: June 14. new ETD Shanghai: June 16 *ETD Shanghai: June 17 | 2026-07-07 |  | FALSE | -46160 | -46111 | -6587.2857
Ready to Ship & Delayed | Emilka Guerra | 2026-03-30 | PO08772 | SO18353 | 2026-05-18 | AM-HH200C21-10-CD4 | Casing, DW-AE8/6-21W, CD4MCu | 1 | AMOS Fluid Technology Co., Ltd | China | BARRICK DIRECT SHIPPING |  | SEA | 2026-07-07 | Peter will take care of the sea shipment -- CIF Caucedo Port | BARRICK ORDER | Follow up email sent on May 7th. Follow up email sent on May 20th. Follow up email sent on May 29th. Follow up email sent on June 2nd Follow up email sent on June 11th Follow up email sent on June 16th | AMOS May 8th: confirmed completition by May 20th ✅ Peter: AMOS confirmed it will be ready to leave factory by May 20 (Wednesday). I will book vessel next Monday. June 5th: will be dispatched to Shanghai seaport | Delayed production: To be completed in the week 25 - 29 The delivery dates of all orders have been affected. This order will be completed by this Friday at the earliest. June 3rd Pump casing is under painting now ~ JUNE 06/11: is already in Shanghai seaport's warehouse waiting for the vessel: CMA CGM UNITY / OPPJCE. original ETD Shanghai: June 14. new ETD Shanghai: June 16 *ETD Shanghai: June 17 | 2026-07-07 |  | FALSE | -46160 | -46111 | -6587.2857
In Production | Emilka Guerra | 2026-03-30 | PO08771 | SO19012 | 27/04/26 | W-M120MC076/C21 | Shaft Sleeve, 350 MCR, 420SS | 2 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-27 | SEA | 2026-07-06 | [5 empty] | 2026-07-06 |  | FALSE
IN TRANSIT | Emilka Guerra | 2026-03-31 | PO08773 | Stock | 2026-05-22 | AC-98-331-983-801 | Bearing Cylinder, 3x3-10 SRL & SRL-C, Cast Iron | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-05-26 | SEA | ETA Warehouse mid-august | the vessel depart on May 26 |  | #20251217-11 | Betty 4/23: Included in Comercial Invoice #20251217-11 |  | 2026-07-31 |  | FALSE | 4 | -46112 | -6587.4286
Received | Ian Trottier | 2026-03-31 | PO08774 | Stock | 2026-04-14 | DU-SA3210AA00-TFR | Impeller Gasket, Durco Mark 2&3 Group 2, Teflon/Rubber | 10 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-04-09 | LAND | 2026-04-24 | [5 empty] | 2026-04-24 | 2026-04-14 | TRUE | -5 | 14
Received | Emilka Guerra | 2026-03-31 | PO08775 | SO19021 | 14/04/26 | AC-98-233-813-001 | Neck Bushing, 5x4/5x5/6x6 SRL & SRL-C | 3 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE | 2026-04-02 | SEA | 2026-04-06 | [5 empty] | 2026-03-31 | 2026-04-06 | TRUE | #VALUE! | 6
Received | Emilka Guerra | 2026-03-31 | PO08775 | SO19021 | 14/04/26 | AC-98-234-108-001 | Half Seal Cage, 2x2-10 SRL, Cast Iron | 2 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE | 2026-04-02 | SEA | 2026-04-06 | [5 empty] | 2026-03-31 | 2026-04-06 | TRUE | #VALUE! | 6
Received | Ian Trottier | 2026-03-31 | PO08776 | SO19015 | 2026-06-23 | MN# 71 | Impeller, 8x4-17, Allis Chalmers PWO, 317SS | 1 | M&N Alloy Cast Products, Inc. | US | CA WAREHOUSE | 2026-05-15 | LAND | 2026-06-30 | [5 empty] | 2026-06-30 | 2026-06-01 | TRUE | -39 | 62 | 8.8571
Received | Ian Trottier | 2026-04-01 | PO08777 | SO19016 | 2026-04-12 | G-0B10588 1216 | Impeller, 2x3-13, 3196 LTX, CD4MCu, 5-Vane | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-23 | AIR | 2026-07-02 |  | DYNC-114 The AIR waybill# is 006-5139 2703 |  |  |  | 2026-07-02 | 2026-05-12 | TRUE | 11 | 41 | 5.8571
Received | Emilka Guerra | 2026-04-01 | PO08778 | SO18893 | 2026-03-04 | W-EH3132L/R55 | Discharge Joint Ring, 4/3 E-HH, Natural Rubber | 2 | Super Cast Limited | China | CA WAREHOUSE | 2026-04-07 | AIR | 2026-04-13 |  | DHL waybill (6357097574) |  | left Shijiazhuang for Mississauga via DHL on Apr 7, 2026 |  | 2026-04-10 | 2026-04-10 | TRUE | 34 | 9
Ready to Ship | Ian Trottier | 2026-04-01 | PO08779 | SO18941 | 2026-06-24 | AC-98-231-134-507 | Suction Side Liner, 10x8-21 SRL-C, Urethane | 1 | IGH | Mexico | CA WAREHOUSE |  | LAND | 2026-07-30 |  |  |  | Carlos IGH 06/16: List for PO ready to ship ~ destination of shipement confirmed |  | 2026-07-30 |  | FALSE | -46197 | -46113 | -6587.5714
Ready to Ship | Ian Trottier | 2026-04-01 | PO08779 | SO18941 | 2026-06-24 | AC-98-231-136-507 | Gland Side Liner, 10x8-21 SRL-C, Urethane | 1 | IGH | Mexico | CA WAREHOUSE |  | LAND | 2026-07-30 |  |  |  | Carlos IGH 06/16: List for PO ready to ship ~ destination of shipement confirmed |  | 2026-07-30 |  | FALSE | -46197 | -46113 | -6587.5714
Received | Leriel Reyes | 2026-04-02 | PO08780 | SO19016 | 2026-04-02 | FS-58984M3 | Single Cartridge Seal, 2 1/8", VSMS, Standard, Carbon vs Silicon Carbide / TFEP | 1 | Flexaseal Engineered Seals and Systems, LLC | Canada | CA WAREHOUSE |  | LAND | 2026-04-14 | [5 empty] | 2026-04-14 | 2026-04-13 | TRUE | -46114 | 11
IN TRANSIT | Yannett Yeomans | 2026-04-06 | PO08781 | Stock | 2026-06-08 | DU-DY55718A-CI | Bearing Housing, Durco Mark 3 Group 2, Cast Iron | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-06-12 | SEA | ETA Warehouse 1st week of august |  | shipped via DYNC-116 SEA. YM COSMOS/190E | ETD Qingdao 12 June ETA Toronto 16 July |  |  | 2026-08-17 |  | FALSE | 4 | -46118 | -6588.2857
IN TRANSIT | Yannett Yeomans | 2026-04-06 | PO08781 | Stock | 2026-06-08 | G-D04872A 1000 | Thrust Bearing Housing, 3196 MTX, Cast Iron | 4 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-06-12 | SEA | ETA Warehouse 1st week of august |  | shipped via DYNC-116 SEA. YM COSMOS/190E | ETD Qingdao 12 June ETA Toronto 16 July |  |  | 2026-08-17 |  | FALSE | 4 | -46118 | -6588.2857
DELAYED PRODUCTION | Yannett Yeomans | 2026-04-06 | PO08781 | Stock | 2026-06-08 | G-R100-586 1012 | Stuffing Box Cover, 10", 3196 MTX, Ductile Iron, Standard Bore, Non-Jacketed | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-20 | SEA | 2026-08-17 |  |  | Follow up email sent on June 5th | Linda 6/6: x1 being re-cast, will be finished around the end of June. |  | 2026-08-17 |  | FALSE | -49 | -46118 | -6588.2857
IN TRANSIT | Yannett Yeomans | 2026-04-06 | PO08781 | Stock | 2026-06-08 | G-R100-586 1012 | Stuffing Box Cover, 10", 3196 MTX, Ductile Iron, Standard Bore, Non-Jacketed | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-04-20 | SEA | ETA Warehouse Mid June |  | DYNC-113 SEA // BL# HHSE6042268, Container # CAAU5246660 | ETA Vancouver on May 5 |  |  | 2026-08-17 |  | FALSE | -49 | -46118 | -6588.2857
IN TRANSIT | Yannett Yeomans | 2026-04-06 | PO08781 | Stock | 2026-06-08 | G-0B10588 1216 | Impeller, 2x3-13, 3196 LTX, CD4MCu, 5-Vane | 2 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA | 2026-08-17 |  | DYNC-116 | Follow up email sent on June 5th |  |  | 2026-08-17 |  | FALSE | -46181 | -46118 | -6588.2857
IN TRANSIT | Emilka Guerra | 2026-04-06 | PO08782 | Stock | 2026-05-25 | AC-98-231-121-501 | Suction Side Plate, 8x6-18 SRL-C, Natural Rubber | 10 | Super Cast Limited | China | CA WAREHOUSE | 2026-06-04 | SEA | ETA Warehouse Mid-end June |  | LS21TJ2605671 |  | Peter 06/12: left Tianjin for Toronto by sea on June 4, 2026. ETA Prince Rupert: June 29. | the lead time will be about 50 days, considering the coming labor holiday (May 1 to May 5). | 2026-08-03 |  | FALSE | 10 | -46118 | -6588.2857
IN TRANSIT | Emilka Guerra | 2026-04-06 | PO08782 | Stock | 2026-05-25 | W-F6018/R55 | Cover Plate Liner, 8/6 E or F-AH, Natural Rubber | 1 | Super Cast Limited | China | CA WAREHOUSE | 2026-05-25 | SEA | ETA Prince Rupert: May 30 ETA Warehouse is around Jul. 13 - 17 |  | LS21TJ2604679 |  | Peter 4/30: Already booked the vessel of ETD May 7 from Tianjin to Toronto. left Tianjin for Toronto by sea on May 8, 2026 |  | 2026-08-03 |  | FALSE | 0 | -46118 | -6588.2857
IN TRANSIT | Emilka Guerra | 2026-04-06 | PO08782 | Stock | 2026-05-25 | W-F6147/R55 | Impeller, 8/6 E, F or R-AH, Natural Rubber | 1 | Super Cast Limited | China | CA WAREHOUSE | 2026-05-25 | SEA | ETA Prince Rupert: May 30 ETA Warehouse is around Jul. 13 - 17 |  | LS21TJ2604679 |  | Peter 4/30: Already booked the vessel of ETD May 7 from Tianjin to Toronto. left Tianjin for Toronto by sea on May 8, 2026 |  | 2026-08-03 |  | FALSE | 0 | -46118 | -6588.2857
Received | Emilka Guerra | 2026-04-06 | PO08783 | SO19033 | 2026-04-10 | W-RS075/C21 | Shaft Sleeve, 300 RSL, 420CSS | 1 | Super Cast Limited | China | CA WAREHOUSE | 2026-04-10 | AIR | 2026-04-26 |  | DHL waybill (3438512136) | ETA Mississauga: May 15 | - Will send out by DHL to Mississauga on Apr 9. - Left Shijiazhuang for Mississauga by DHL on Apr 11, 2026. |  | 2026-04-26 | 2026-04-15 | TRUE | 0 | 9
Received | Emilka Guerra | 2026-04-06 | PO08784 | Stock | 2026-04-10 | AC-98-331-958-803 | Shaft Sleeve, 5x4/5x5/6x6 SRL & SRL-C, Steel | 4 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE | 2026-04-10 | LAND | 2026-04-14 |  | 3304567930 | Manitoulin Transport |  |  | 2026-04-14 | 2026-04-13 | TRUE | 0 | 7
Received | Emilka Guerra | 2026-04-06 | PO08784 | Stock | 2026-04-10 | AC-98-233-979-005 | Sleeve Washer (Impeller), 2x2-10 SRL, Steel | 2 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE | 2026-04-10 | LAND | 2026-04-14 |  | 3304567930 | Manitoulin Transport |  |  | 2026-04-14 | 2026-04-13 | TRUE | 0 | 7
In Production | Emilka Guerra | 2026-04-06 | PO08785 | Stock | 2026-05-26 | D-WE1J-4 | Shaft Sleeve, Goulds JC Frame 1J, 420SS Heat Treated, Hardened | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-05-26 | SEA | 2026-08-11 |  |  | Email for update sent June 2nd |  |  | 2026-08-11 |  | FALSE | 0 | -46118 | -6588.2857
IN TRANSIT | Emilka Guerra | 2026-04-06 | PO08785 | Stock | 2026-05-26 | AC-98-331-932-501 | Shaft Assembly, 5x4-14 SRL-C & 5x5-14 SRL, 1045 Steel | 12 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-06-19 | SEA | ETA Warehouse Mid-Sept |  |  | Follow email sent for update on June 16th . We already shipped them to Tianjin, but the vessel delayed, it shows that it will depart on June 19. | Betty 6/9: Included in Comercial Invoice / #20260205-11 |  | 2026-08-11 |  | FALSE | 24 | -46118 | -6588.2857
IN TRANSIT | Emilka Guerra | 2026-04-06 | PO08786 | Stock | 2026-05-04 | D-2001412-4PHSS | Hex Cap Screw, 10JKH/M, 0.44-14NCx1.50, 17-4PH SS | 300 | Jiangsu Win-win International Trading Co., Ltd. | China | CA WAREHOUSE | 2026-05-30 | SEA | 2026-07-13 |  |  | The packing size and weight is 250*200*160mm and 12KG. 05/15: Asked Peter to consolidate with other orders to Canada | Jiansuwin04/30: It will be ready for dispatch before 10th May. departed Shanghai and are on sea to Toronto. | James MAy 10th: PO08786 is ready for dispatch. I will wait for your further confirmation for shipment. May 15th: asked Peter to consolidate shipment to Canada. | 2026-07-13 |  | FALSE | 26 | -46118 | -6588.2857
IN TRANSIT | Emilka Guerra | 2026-04-07 | PO08789 | SO19037 | 2026-05-19 | D-1J2311-14 | Suction Cover, 2x3-11, Goulds JC, Frame 1J, High Chrome, OEM# 050387G0001228 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-06-19 | SEA | ETA Warehouse Mid-Sept |  |  | Follow email sent for update on June 16th . We already shipped them to Tianjin, but the vessel delayed, it shows that it will depart on June 19. | Betty 5/15: Included in Comercial Invoice / #20260205-11 |  | 2026-07-28 |  | FALSE | 31 | -46119 | -6588.4286
Received | Emilka Guerra | 2026-04-07 | PO08790 | Stock | 2026-04-14 | G-C02495A30 6359 | Impeller O-Ring, 3196 LTX, Teflon | 25 | Wajax Limited - Mississauga | Canada | CA WAREHOUSE | 2026-04-14 | LAND | 2026-04-21 | [5 empty] | 2026-04-21 | 2026-04-13 | TRUE | 0 | 6
Received | Emilka Guerra | 2026-04-07 | PO08790 | Stock | 2026-04-14 | CR16084, G-8690-93760 | Bearing Seal, 3x3-10 SRL & SRL-C (Outboard) & 2x2-10 (Inboard), Neoprene/Steel | 5 | Wajax Limited - Mississauga | Canada | CA WAREHOUSE | 2026-04-14 | LAND | 2026-04-21 | [5 empty] | 2026-04-21 | 2026-04-13 | TRUE | 0 | 6
In Production | Ian Trottier | 2026-04-08 | PO08791 | SO19027 | 2026-07-01 | AC-52-425-753-004 | Stuffing Box Cover, 10", CSO F4B3, Alloy-20 | 1 | M&N Alloy Cast Products, Inc. | US | CA WAREHOUSE | 2026-07-01 | LAND | 2026-04-08 | [5 empty] | 2026-04-08 |  | FALSE | 0 | -46120 | -6588.5714
Received | Jeff Bell | 2026-04-08 | PO08793 | SO18868 | 2026-04-20 | D-KFSC-20MM-12.5 | Packing, 20mm x 20mm, Kevlar Fiber w/Silicon Core, 12.5 lbs. Spool | 1 | Super Cast Limited | China | BARRICK CONSOLIDATED | 2026-04-25 | AIR | ETA Mississauga: Apr 30. |  | DHL waybill (2082414994) | JB: To be shipped via air to Toronto | Peter 04/24: Just received from the packing factory today. Will ship out via DHL to Mississauga Sat 25th | The lead time is 10 days. | 2026-04-30 | 2026-05-01 | TRUE | 5 | 23 | 3.2857
Received | Emilka Guerra | 2026-04-09 | PO08794 | SO18546 | 2026-04-24 | 10JKM, 6-Vane Impeller, CD4 | Impeller, 10JKM, Double Keyed, w/Wear Ring | 3 | Jiangsu Win-win International Trading Co., Ltd. | China | BARRICK CONSOLIDATED | 2026-04-21 | AIR | ETA Mississauga: Apr 23 |  | DHL waybill (5270923545) | left Shanghai for Mississauga via DHL on Apr 21, 2026 | 04/17: Ready to Ship: evaluating shipment mode / dhl to toronto. / Correct Impeller | Received in CA Warehouse, to consolidate Barrick Shipment | 2026-07-16 | 2026-04-23 | TRUE | -3 | 14
Received | Emilka Guerra | 2026-04-09 | PO08795 | SO19032 | 2026-04-16 | SA-021435-M1 | Impeller (Open), Sala VTP 3, High Chrome | 1 | Dexhor | Other | CA WAREHOUSE | 2026-04-10 | LAND | 2026-04-30 | [5 empty] | 2026-04-30 | 2026-04-14 | TRUE | -6 | 5
Received | Ian Trottier | 2026-04-09 | PO08796 | SO18585 | 2026-06-12 | G-0C02528AA 1220 | Impeller, 1.5x3-13, 3196 MTX, Titanium, 5-Vane | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-06-05 | AIR | 2026-04-10 |  | DYNC-117 AIR |  |  |  | 2026-04-10 | 2026-06-08 | TRUE | -7 | 60 | 8.5714
Received | Ian Trottier | 2026-04-10 | PO08797 | SO18837 | 2026-05-25 | DU-CY22344A-A20 | Casing, 4x3-13, Durco Mark 2&3 Group 2, Alloy 20 | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-06-05 | SEA | 2026-05-25 |  | DYNC-117 AIR |  |  |  | 2026-05-25 | 2026-06-08 | TRUE | 11 | 59 | 8.4286
Received | Ian Trottier | 2026-04-10 | PO08797 | SO18837 | 2026-05-25 | DU-DY33074A-A20 | Casing, 6x4-13A, Durco Mark 2&3 Group 2, Alloy 20 | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-06-05 | SEA | 2026-05-25 |  | DYNC-117 AIR |  |  |  | 2026-05-25 | 2026-06-08 | TRUE | 11 | 59 | 8.4286
Received | Ian Trottier | 2026-04-10 | PO08797 | SO18837 | 2026-05-25 | DU-CY21805A/CBS-DC20 | Rear Cover, 10", Durco Mark 2&3 Group 2, Alloy 20, Small Bore | 3 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-06-05 | SEA | 2026-05-25 |  | DYNC-117 AIR |  |  |  | 2026-05-25 | 2026-06-08 | TRUE | 11 | 59 | 8.4286
Received | Ian Trottier | 2026-04-10 | PO08797 | SO18837 | 2026-05-25 | DU-DY21855A/CBS-DC20 | Rear Cover, 13", Durco Mark 2&3 Group 2, Alloy-20, Small Bore | 7 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-06-05 | SEA | 2026-05-25 |  | DYNC-117 AIR |  |  |  | 2026-05-25 | 2026-06-08 | TRUE | 11 | 59 | 8.4286
Received | Ian Trottier | 2026-04-10 | PO08797 | SO18837 | 2026-05-25 | DU-DY32218AA-A20 | Casing, 8x6-14A, Durco Mark 2&3 Group 2, Alloy 20 | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-06-05 | AIR | 2026-05-30 |  | DYNC-117 AIR |  |  |  | 2026-05-30 | 2026-06-08 | TRUE | 11 | 59 | 8.4286
Received | Ian Trottier | 2026-04-10 | PO08797 | SO18837 | 2026-05-25 | DU-MY40103AA140-A20 | Impeller, 8x6-14A, Durco Mark 2&3 Group 3, Alloy 20, Reverse Vane | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-06-05 | SEA | 2026-05-30 |  | DYNC-117 AIR |  |  |  | 2026-05-30 | 2026-06-08 | TRUE | 11 | 59 | 8.4286
Received | Ian Trottier | 2026-04-10 | PO08797 | SO18837 | 2026-05-25 | DU-MY36847AA130-A20 | Impeller, 4x3-13, Durco Mark 2&3 Group 2, Alloy 20, Reverse Vane | 2 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-06-05 | SEA | 2026-05-30 |  | DYNC-117 AIR |  |  |  | 2026-05-30 | 2026-06-08 | TRUE | 11 | 59 | 8.4286
Received | Ian Trottier | 2026-04-10 | PO08797 | SO18837 | 2026-05-25 | DU-MY36846AA130-A20 | Impeller, 6x4-13A, Durco Mark 2&3 Group 2, Alloy 20, Reverse Vane | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-06-05 | SEA | 2026-05-30 |  | DYNC-117 AIR |  |  |  | 2026-05-30 | 2026-06-08 | TRUE | 11 | 59 | 8.4286
Received | Ian Trottier | 2026-04-10 | PO08797 | SO18837 | 2026-05-25 | DU-DY28284AA/CBS-A20 | Rear Cover, 14", Durco Mark 2&3 Group 3, Alloy 20, Small Bore | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-06-05 | SEA | 2026-05-30 |  | DYNC-117 AIR |  |  |  | 2026-05-30 | 2026-06-08 | TRUE | 11 | 59 | 8.4286
Received | Ian Trottier | 2026-04-10 | PO08797 | SO18837 | 2026-06-01 | DU-CY21805A/CBS-DC20 | Rear Cover, 10", Durco Mark 2&3 Group 2, Alloy 20, Small Bore | 3 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-06-07 | AIR | ETA WAREHOUSE 2ND WEEK OF JUNE |  | DYNC-117 AIR | This is a top-priority urgent air shipment (DYNC-117). | It departs from Beijing airport on June 7 and arrives at Toronto airport on June 7. |  | 2026-05-25 | 2026-06-08 | TRUE | 6 | 59 | 8.4286
Received | Ian Trottier | 2026-04-10 | PO08797 | SO18837 | 2026-06-01 | DU-DY21855A/CBS-DC20 | Rear Cover, 13", Durco Mark 2&3 Group 2, Alloy-20, Small Bore | 7 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-06-07 | AIR | ETA WAREHOUSE 2ND WEEK OF JUNE |  | DYNC-117 AIR | This is a top-priority urgent air shipment (DYNC-117). | It departs from Beijing airport on June 7 and arrives at Toronto airport on June 7. |  | 2026-05-25 | 2026-06-08 | TRUE | 6 | 59
Received | Ian Trottier | 2026-04-10 | PO08797 | SO18837 | 2026-06-01 | DU-DY32218AA-A20 | Casing, 8x6-14A, Durco Mark 2&3 Group 2, Alloy 20 | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-06-07 | AIR | ETA WAREHOUSE 2ND WEEK OF JUNE |  | DYNC-117 AIR | This is a top-priority urgent air shipment (DYNC-117). | It departs from Beijing airport on June 7 and arrives at Toronto airport on June 7. |  | 2026-05-30 | 2026-06-08 | TRUE | 6 | 59 | 8.4286
Received | Ian Trottier | 2026-04-10 | PO08797 | SO18837 | 2026-06-01 | DU-MY40103AA140-A20 | Impeller, 8x6-14A, Durco Mark 2&3 Group 3, Alloy 20, Reverse Vane | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-06-07 | AIR | ETA WAREHOUSE 2ND WEEK OF JUNE |  | DYNC-117 AIR | This is a top-priority urgent air shipment (DYNC-117). | It departs from Beijing airport on June 7 and arrives at Toronto airport on June 7. |  | 2026-05-30 | 2026-06-08 | TRUE | 6 | 59 | 8.4286
Received | Ian Trottier | 2026-04-10 | PO08797 | SO18837 | 2026-06-01 | DU-MY36847AA130-A20 | Impeller, 4x3-13, Durco Mark 2&3 Group 2, Alloy 20, Reverse Vane | 2 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-06-07 | AIR | ETA WAREHOUSE 2ND WEEK OF JUNE |  | DYNC-117 AIR | This is a top-priority urgent air shipment (DYNC-117). | It departs from Beijing airport on June 7 and arrives at Toronto airport on June 7. |  | 2026-05-30 | 2026-06-08 | TRUE | 6 | 59 | 8.4286
Received | Ian Trottier | 2026-04-10 | PO08797 | SO18837 | 2026-06-01 | DU-MY36846AA130-A20 | Impeller, 6x4-13A, Durco Mark 2&3 Group 2, Alloy 20, Reverse Vane | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-06-07 | AIR | ETA WAREHOUSE 2ND WEEK OF JUNE |  | DYNC-117 AIR | This is a top-priority urgent air shipment (DYNC-117). | It departs from Beijing airport on June 7 and arrives at Toronto airport on June 7. |  | 2026-05-30 | 2026-06-08 | TRUE | 6 | 59 | 8.4286
Received | Ian Trottier | 2026-04-10 | PO08797 | SO18837 | 2026-06-01 | DU-DY28284AA/CBS-A20 | Rear Cover, 14", Durco Mark 2&3 Group 3, Alloy 20, Small Bore | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-06-07 | AIR | ETA WAREHOUSE 2ND WEEK OF JUNE |  | DYNC-117 AIR | This is a top-priority urgent air shipment (DYNC-117). | It departs from Beijing airport on June 7 and arrives at Toronto airport on June 7. |  | 2026-05-30 | 2026-06-08 | TRUE | 6 | 59 | 8.4286
Received | Ian Trottier | 2026-04-10 | PO08798 | SO18837 | 2026-04-24 | DU-BY50424F-TSSR | Oil Seal (Inboard & Outboard), Durco Mark 2&3 Group 3, Teflon/Stainless Steel/Rubber | 4 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-05-05 | LAND | ETA May 1st week |  |  |  | Hisco May 5th: Quenton Included in list for ready orders / waiting info on shipping date | April 30th: email follow up for orders. | 2026-05-01 | 2026-05-07 | TRUE | 11 | 27 | 3.8571
Received | Emilka Guerra | 2026-04-10 | PO08799 | SO19017 | 2026-04-17 | AC-98-236-104-001 | Shaft Sleeve, 8x6-18 & 10x8-21 SRL-C, Steel | 2 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE | 2026-04-16 | LAND | 2026-04-24 |  |  | This shipment (2 Boxes) will ETA our warehouse this Friday april 17th |  |  | 2026-04-24 | 2026-04-17 | TRUE | -1 | 7 | 1
In Production | Emilka Guerra | 2026-04-10 | PO08800 | Stock | 2026-05-22 | D-2J3411-6 | Suction Cover Liner, 3x4-11, Goulds JC, Frame 2J, High Chrome, OEM# 048824G0001228 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-05-22 | SEA | 2026-07-08 |  |  | Email for update sent June 2nd |  |  | 2026-07-08 |  | FALSE | 0 | -46122 | -6588.8571
IN TRANSIT | Emilka Guerra | 2026-04-10 | PO08800 | Stock | 2026-05-22 | D-1J2311-14 | Suction Cover, 2x3-11, Goulds JC, Frame 1J, High Chrome, OEM# 050387G0001228 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-05-26 | SEA | ETA Warehouse mid-august | the vessel depart on May 26 |  | #20251217-11 | Betty 4/23: Included in Comercial Invoice #20251217-11 |  | 2026-07-08 |  | FALSE | 4 | -46122 | -6588.8571
IN TRANSIT | Ian Trottier | 2026-04-13 | PO08801 | SO18931 | 2026-06-15 | SA-13576-M1 | Casing, Sala STHM, 33-WFR, High Chrome | 5 | Dexhor | Other | CA WAREHOUSE | 2026-06-15 | LAND | ETA WAREHOUSE JUNE 17-18 | Shipped manitoulin | 3304738659 | Requested update status on June16th |  |  | 2026-06-26 |  | FALSE | 0 | -46125 | -6589.2857
Received | Ian Trottier | 2026-04-13 | PO08802 | SO18931 | 2026-05-04 | AC-98-431-743-501 | Shaft Assembly, 10x8-21 SRL-C, 1045 Steel | 4 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE | 2026-05-04 | LAND | 2026-04-14 |  |  | Sent email for follow up June 9th |  | Mario 06/9: So they are almost done need to drill & tap end hole & QA should be shipping to you this week I think there is 8 or 9 of those separate P.O.’s | 2026-05-11 | 2026-06-17 | TRUE | 0 | 65 | 9.2857
Received | Ian Trottier | 2026-04-13 | PO08802 | SO18931 | 2026-05-04 | SA-013826-1 | Shaft Sleeve, Sala STGVA-33-WFR, Steel | 8 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE | 2026-04-16 | LAND | 2026-04-14 | [5 empty] | 2026-05-11 | 2026-04-17 | TRUE | -18 | 4 | 0.57143
Received | Ian Trottier | 2026-04-13 | PO08803 | SO1893 | 2026-04-28 | FAS-10570, FASM-2157 | Mechanical Seal, Ingersoll Dresser, 40-25CPX200 & 65-40CPX160, Sil-Carb vs' Sil-Carb, Viton Bellows | 8 | Flexaseal Engineered Seals and Systems, LLC | Canada | CA WAREHOUSE | 2026-04-28 | LAND | 2026-04-13 | [5 empty] | 2026-04-13 | 2026-04-28 | TRUE | 0 | 15 | 2.1429
Received | Ian Trottier | 2026-04-13 | PO08804 | SO18931 | 2026-04-20 | B8*56 ET02, W-B070M/E02 | Shaft Key, 1.5/1 or 2/1.5 B-AH, Metric | 5 | Super Cast Limited | China | CA WAREHOUSE | 2026-05-06 | AIR | ETA May 2nd week |  | DHL waybill (4463297635) |  |  |  | 2026-07-13 | 2026-05-12 | TRUE | 16 | 29 | 4.1429
Ready to Ship | Emilka Guerra | 2026-04-13 | PO08805 | Stock | 2026-06-10 | G-R100-533 1216 | Stuffing Box Cover, 13", 3196 LTX, CD4MCu, Standard Bore, Non-Jacketed | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA |  |  | DYNC-119 SEA |  |  |  | 2026-08-19 |  | FALSE | -46183 | -46125 | -6589.2857
Ready to Ship | Emilka Guerra | 2026-04-13 | PO08805 | Stock | 2026-06-10 | G-P1600L0S00 X060 | Power End, 3196 LTX, 316SS Shaft (Sleeved Type), Oil Lubed | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA |  |  | DYNC-119 SEA |  |  |  | 2026-08-19 |  | FALSE | -46183 | -46125 | -6589.2857
IN TRANSIT | Emilka Guerra | 2026-04-13 | PO08805 | Stock | 2026-06-10 | DU-MY36847AA130-CD4 | Impeller, 4x3-13, Durco Mark 2&3 Group 2, CD4MCu, Reverse Vane | 2 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-06-12 | SEA | ETA Warehouse 1st week of august |  | shipped via DYNC-116 SEA. YM COSMOS/190E | ETD Qingdao 12 June ETA Toronto 16 July |  |  | 2026-08-19 |  | FALSE | 2 | -46125 | -6589.2857
Ready to Ship | Emilka Guerra | 2026-04-13 | PO08805 | Stock | 2026-06-10 | G-249-65 1216 | Casing, 3x4-13, 3196 MTX, CD4MCu | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA |  |  | DYNC-119 SEA |  |  |  | 2026-08-19 |  | FALSE | -46183 | -46125
IN TRANSIT | Emilka Guerra | 2026-04-13 | PO08806 | Stock | 2026-05-13 | W-F005M | Bearing Assembly w/Shaft, 8/6 F-AH, Metric | 1 | Super Cast Limited | China | CA WAREHOUSE | 2026-06-04 | SEA | ETA Warehouse Mid-end June |  | LS21TJ2605671 |  | Peter 06/12: left Tianjin for Toronto by sea on June 4, 2026. ETA Prince Rupert: June 29. |  | 2026-07-29 |  | FALSE | 22 | -46125
IN TRANSIT | Emilka Guerra | 2026-04-13 | PO08806 | Stock | 2026-05-13 | AC-98-039-047-501 | Impeller (Closed), 5x4-14 SRL-C, Natural Rubber | 4 | Super Cast Limited | China | CA WAREHOUSE | 2026-05-08 | SEA |  |  |  |  | Left Tianjin for Toronto by sea | might need about 10 more days for Item #2 and Item #3, considdering the coming Labor Holiday (May 1 to 5), and the rubber factory is in full production load. | 2026-07-29 |  | FALSE | -5 | -46125 | -6589.2857
DELAYED PRODUCTION | Emilka Guerra | 2026-04-13 | PO08806 | Stock | 2026-05-13 | AC-98-039-047-501 | Impeller (Closed), 5x4-14 SRL-C, Natural Rubber | 8 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [5 empty] | might need about 10 more days for Item #2 and Item #3, considdering the coming Labor Holiday (May 1 to 5), and the rubber factory is in full production load. | 2026-07-29 |  | FALSE | -46155 | -46125 | -6589.2857
DELAYED PRODUCTION | Emilka Guerra | 2026-04-13 | PO08806 | Stock | 2026-05-13 | AC-98-231-116-501 | Gland Side Liner, 5x4-14 SRL-C, Natural Rubber | 9 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [5 empty] | might need about 10 more days for Item #2 and Item #3, considdering the coming Labor Holiday (May 1 to 5), and the rubber factory is in full production load. | 2026-07-29 |  | FALSE | -46155 | -46125 | -6589.2857
IN TRANSIT | Emilka Guerra | 2026-04-13 | PO08806 | Stock | 2026-05-13 | W-F8147/R55 | Impeller, 10/8 E-M, Natural Rubber | 4 | Super Cast Limited | China | CA WAREHOUSE | 2026-05-08 | SEA | ETA Prince Rupert: May 30 ETA Warehouse is around Jul. 13 - 17 |  | LS21TJ2604679 |  | Peter 4/30: Already booked the vessel of ETD May 7 from Tianjin to Toronto. left Tianjin for Toronto by sea on May 8, 2026 |  | 2026-07-29 |  | FALSE | -5 | -46125 | -6589.2857
Received | Emilka Guerra | 2026-04-13 | PO08807 | Stock | 2026-04-22 | SA-567131 | Labyrinth Ring, Sala STHM-33WFR, Steel | 1 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE | 2026-04-16 | LAND | 2026-04-29 | [5 empty] | 2026-04-29 | 2026-04-17 | TRUE | -6 | 4 | 0.57143
Received | Emilka Guerra | 2026-04-13 | PO08808 | Stock | 2026-04-21 | AC-98-131-246-504 AC-52-108-475-009 | Deflector (Water Slinger), 3x3-10 SRL/SRL-C, Neoprene/Steel | 3 | Advanced Engineered Pump Inc. | Canada | CA WAREHOUSE | 2026-05-05 | LAND | ETA May 1st week | [5 empty] | 2026-05-19 | 2026-05-07 | TRUE | 14 | 24 | 3.4286
Received | Emilka Guerra | 2026-04-13 | PO08808 | Stock | 2026-04-21 | AC-52-108-475-010 | Deflector (Inboard), Allis Chalmers CSO, Frame F4D1, Steel | 1 | Advanced Engineered Pump Inc. | Canada | CA WAREHOUSE | 2026-05-05 | LAND | ETA May 1st week | [5 empty] | 2026-05-19 | 2026-05-07 | TRUE | 14 | 24 | 3.4286
Received | Emilka Guerra | 2026-04-13 | PO08808 | Stock | 2026-04-21 | AC-52-108-475-013 | Deflector (Outboard), Allis-Chalmers PWO, Group 2 | 4 | Advanced Engineered Pump Inc. | Canada | CA WAREHOUSE | 2026-05-05 | LAND | ETA May 1st week | [5 empty] | 2026-05-19 | 2026-05-07 | TRUE | 14 | 24 | 3.4286
In Production | Ian Trottier | 2026-04-13 | PO08809 | SO18643 | 2026-06-22 | G-R72360 6956 | Shaft Sleeve, 3405-M, Ni-Chrome Boron On 316SS | 1 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND |  |  |  | April 30th: email follow up for orders. June 16th: Follow up email for inclusion on a second shipment |  |  | 2026-06-29 |  | FALSE | -46195 | -46125 | -6589.2857
Received | Ian Trottier | 2026-04-14 | PO08810 | SO19080, SO19078, SO19079 | 2026-04-24 | G-D08717A04 6241 | Labyrinth Seal (Inboard), 3196 MTX, Carbon Teflon | 2 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-05-05 | LAND | ETA May 1st week |  |  |  | Hisco May 5th: Quenton Included in list for ready orders / waiting info on shipping date | April 30th: email follow up for orders. | 2026-05-01 | 2026-05-07 | TRUE | 11 | 23 | 3.2857
Received | Ian Trottier | 2026-04-14 | PO08810 | SO19080, SO19078, SO19079 | 2026-04-24 | G-D08717A03 6241 | Labyrinth Seal (Outboard), 3196 MTX, Carbon Teflon | 2 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-05-05 | LAND | ETA May 1st week |  |  |  | Hisco May 5th: Quenton Included in list for ready orders / waiting info on shipping date | April 30th: email follow up for orders. | 2026-05-01 | 2026-05-07 | TRUE | 11 | 23 | 3.2857
Received | Emilka Guerra | 2026-04-14 | PO08811 | Stock | 2026-04-21 | 22309EAE4 | Bearing (Outboard), 3x3-10 SRL & SRL-C, Steel | 1 | Wajax Limited - Mississauga | Canada | CA WAREHOUSE | 2026-04-15 | LAND | 2026-04-29 | [5 empty] | 2026-04-29 | 2026-04-16 | TRUE | -6 | 2
Received | Emilka Guerra | 2026-04-14 | PO08811 | Stock | 2026-04-21 | 22209EAE4 | Bearing (Inboard), 3x3-10 SRL & SRL-C, Steel | 1 | Wajax Limited - Mississauga | Canada | CA WAREHOUSE | 2026-04-15 | LAND | 2026-04-29 | [5 empty] | 2026-04-29 | 2026-04-20 | TRUE | -6 | 6 | 0.85714
Ready to Ship | Emilka Guerra | 2026-04-14 | PO08812 | Stock | 2026-06-09 | AC-98-037-796-503 | Impeller (Open), 6x6-15 SRL, Neoprene | 1 | IGH | Mexico | CA WAREHOUSE |  | LAND | 2026-07-07 |  |  |  | Carlos IGH 06/16: List for PO ready to ship ~ destination of shipement confirmed |  | 2026-07-07 |  | FALSE | -46182 | -46126 | -6589.4286
Ready to Ship | Ian Trottier | 2026-04-14 | PO08813 | SO18681 | 2026-05-26 | AC-98-233-212-501 | Slinger Assembly, PWO Frame 3, Oil | 3 | Advanced Engineered Pump Inc. | Canada | CA WAREHOUSE | 2026-05-26 | LAND | 2026-06-09 | [5 empty] | 2026-06-09 |  | FALSE | 0 | -46126 | -6589.4286
Received | Ian Trottier | 2026-04-14 | PO08814 | SO18924 | 2026-04-17 | BSHCCS8114, WLHC38, SA-013733-FAS-KIT | Wear Disc Fastener Kit, 44 WFR, Sala STGVA-180, 4 Studs, & 4 Lock-Washers | 90 | Rastall Mine Supply Limited | Canada | CA WAREHOUSE | 2026-04-21 | LAND | 2026-04-22 |  |  | Confirmed shipment |  |  | 2026-04-15 | 2026-04-23 | TRUE | 4 | 9 | 1.2857
Ready to Ship | Yannett Yeomans | 2026-04-14 | PO08815 | SO19071 | 2026-06-22 | AC-98-432-037-001 | Bearing Cylinder Strap (Set of 2), 8x6/10x8 SRL-C, Cast Iron | 2 | IGH | Mexico | CA WAREHOUSE |  | LAND | 2026-07-06 |  |  |  | Carlos IGH 06/16: List for PO ready to ship ~ destination of shipement confirmed |  | 2026-07-06 |  | FALSE | -46195 | -46126
Received | Ian Trottier | 2026-04-15 | PO08816 | SO19092 | 2026-06-01 | DU-DY32218AA-A20 | Casing, 8x6-14A, Durco Mark 2&3 Group 2, Alloy 20 | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-06-05 | AIR | 2026-06-12 |  | DYNC-117 AIR |  |  |  | 2026-06-12 | 2026-06-08 | TRUE | 4 | 54 | 7.7143
In Production | Ian Trottier | 2026-04-16 | PO08817 | SO19098 | 2026-07-23 | AC-98-331-596-801 | Stuffing Box Cover, 21", PWO, Frame 3, Cast Iron | 1 | Emnor Mechanical Inc. | Canada | CA WAREHOUSE |  | LAND | 2026-07-30 | [5 empty] | 2026-07-30 |  | FALSE | -46226 | -46128 | -6589.7143
In Production | Emilka Guerra | 2026-04-16 | PO08818 | SO19043 | 2026-07-09 | P/N #73, AC-98-431-321-013 | Impeller, 8x6-17, PWO, 3-Vane, CD4MCu | 2 | M&N Alloy Cast Products, Inc. | US | CA WAREHOUSE |  | SEA | 2026-04-17 | [5 empty] | 2026-04-17 |  | FALSE | -46212 | -46128 | -6589.7143
Received | Yannett Yeomans | 2026-04-16 | PO08819 | SO19101 | 2026-06-01 | DU-CY22344A-A20 | Casing, 4x3-13, Durco Mark 2&3 Group 2, Alloy 20 | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-06-05 | AIR | 2026-06-12 |  | DYNC-117 AIR |  |  |  | 2026-06-10 | 2026-06-08 | TRUE | 4 | 53 | 7.5714
Received | Yannett Yeomans | 2026-04-16 | PO08820 | SO19066 | 2026-05-14 | G-090407-4 1203 | Impeller w/Balance Holes, 2x3-10, 3196 MTX, 316SS, 5-Vane | 1 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-05-05 | LAND | ETA May 1st week |  |  |  | Hisco May 5th: Quenton Included in list for ready orders / waiting info on shipping date | April 30th: email follow up for orders. | 2026-06-18 | 2026-05-07 | TRUE | -9 | 21 | 3
Ready to Ship | Yannett Yeomans | 2026-04-16 | PO08821 | Stock | 2026-05-29 | D-1J2311-14 | Suction Cover, 2x3-11, Goulds JC, Frame 1J, High Chrome, OEM# 050387G0001228 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-06-19 | SEA | ETA Warehouse Mid-Sept |  |  | Follow email sent for update on June 16th . We already shipped them to Tianjin, but the vessel delayed, it shows that it will depart on June 19. | Betty 5/15: Included in Comercial Invoice / #20260205-11 |  | 2026-05-26 |  | FALSE | 21 | -46128 | -6589.7143
In Production | Yannett Yeomans | 2026-04-17 | PO08822 | SO19118 | 2026-05-22 | W-F6018TL1/R55 | Cover Plate Liner (Thick), 8/6 F-AH, Natural Rubber | 1 | Super Cast Limited | China | MX WAREHOUSE |  | SEA | 2026-07-17 | [5 empty] | 2026-07-17 |  | FALSE
Received | Yannett Yeomans | 2026-04-17 | PO08823 | SO19111 | 2026-05-15 | G-B00294A 6956 | Shaft Sleeve, 3175-S, 316SS, Ni-Chrome Boron | 4 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-05-05 | LAND | ETA May 1st week |  |  |  | Hisco May 5th: Quenton Included in list for ready orders / waiting info on shipping date | April 30th: email follow up for orders. | 2026-05-22 | 2026-05-07 | TRUE | -10 | 20 | 2.8571
In Production | Yannett Yeomans | 2026-04-17 | PO08822 | SO19118 | 2026-05-22 | 17779900159 | Annular Washer, Sulzer A53-250 | 6 | Super Cast Limited | China | MX WAREHOUSE |  | SEA | 2026-07-17 | [5 empty] | 2026-07-17 |  | FALSE
Received | Yannett Yeomans | 2026-04-17 | PO08823 | SO19111 | 2026-05-15 | G-B00296A 6956 | Shaft Sleeve, 3175-L, 316SS, Ni-Chrome Boron | 4 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-05-05 | LAND | ETA May 1st week |  |  |  | Hisco May 5th: Quenton Included in list for ready orders / waiting info on shipping date | April 30th: email follow up for orders. | 2026-05-22 | 2026-05-07 | TRUE | -10 | 20 | 2.8571
In Production | Taylor Cook | 2026-04-20 | PO08824 | SO19123 | 2026-05-11 | AC-98-432-883-501 | Shaft (Fine Thread), PWO, Frame 3, 1045 Steel | 1 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE | [8 empty] | 2026-04-20 |  | FALSE | -46153 | -46132 | -6590.2857
Received | Emilka Guerra | 2026-04-20 | PO08825 | SO19103 | 2026-04-27 | AC-52-320-812-101 | Impeller, 3x2-13, Allis Chalmers CSO, 316SS | 1 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-05-05 | LAND | ETA May 1st week |  |  |  | Hisco May 5th: Quenton Included in list for ready orders / waiting info on shipping date | April 30th: email follow up for orders. | 2026-05-25 | 2026-05-07 | TRUE | 8 | 17 | 2.4286
Ready to Ship | Emilka Guerra | 2026-04-20 | PO08826 | SO18757 | 2026-06-22 | DE-560229 | Housing Packing Gland, 10x8 SRL, Denver, Cast Iron | 2 | IGH | Mexico | CA WAREHOUSE |  | LAND |  |  |  |  | Carlos IGH 06/16: List for PO ready to ship ~ destination of shipement confirmed |  | 2026-07-13 |  | FALSE | -46195 | -46132 | -6590.2857
Ready to Ship | Emilka Guerra | 2026-04-20 | PO08826 | SO18757 | 2026-06-22 | DE-503397 | Lantern Ring, 10x8 SRL, Denver, Carbon Steel | 2 | IGH | Mexico | CA WAREHOUSE |  | LAND |  |  |  |  | Carlos IGH 06/16: List for PO ready to ship ~ destination of shipement confirmed |  | 2026-07-13 |  | FALSE | -46195 | -46132 | -6590.2857
Ready to Ship | Emilka Guerra | 2026-04-20 | PO08826 | SO18757 | 2026-06-22 | DE-503539 | Shaft Sleeve, 10x8 SRL, Denver, Carbon Steel | 2 | IGH | Mexico | CA WAREHOUSE |  | LAND |  |  |  |  | Carlos IGH 06/16: List for PO ready to ship ~ destination of shipement confirmed |  | 2026-07-13 |  | FALSE | -46195 | -46132 | -6590.2857
Ready to Ship | Emilka Guerra | 2026-04-20 | PO08826 | SO18757 | 2026-06-22 | DE-560227 | Split Gland, 10x8 SRL, Denver, Cast Iron | 2 | IGH | Mexico | CA WAREHOUSE |  | LAND |  |  |  |  | Carlos IGH 06/16: List for PO ready to ship ~ destination of shipement confirmed |  | 2026-07-13 |  | FALSE | -46195 | -46132 | -6590.2857
In Production | Emilka Guerra | 2026-04-20 | PO08827 | Stock | 2026-05-25 | AC-98-234-000-801 | Bearing Cover (Outboard), 3x3-10 SRL & SRL-C, Cast Iron | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA |  |  |  | Email for update sent June 2nd |  |  | 2026-08-10 |  | FALSE | -46167 | -46132 | -6590.2857
IN TRANSIT | Emilka Guerra | 2026-04-20 | PO08827 | Stock | 2026-05-25 | AC-98-431-858-501 | Shaft Assembly, 3x3-10 SRL & SRL-C, 1045 Steel | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-06-19 | SEA | ETA Warehouse Mid-Sept |  |  | Follow email sent for update on June 16th . We already shipped them to Tianjin, but the vessel delayed, it shows that it will depart on June 19. | Betty 6/9: Included in Comercial Invoice / #20260205-11 |  | 2026-08-10 |  | FALSE | 25 | -46132 | -6590.2857
IN TRANSIT | Emilka Guerra | 2026-04-20 | PO08827 | Stock | 2026-05-25 | AC-98-331-983-801 | Bearing Cylinder, 3x3-10 SRL & SRL-C, Cast Iron | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-06-19 | SEA | ETA Warehouse Mid-Sept |  |  | Follow email sent for update on June 16th . We already shipped them to Tianjin, but the vessel delayed, it shows that it will depart on June 19. | Betty 5/15: Included in Comercial Invoice / #20260205-11 |  | 2026-08-10 |  | FALSE | 25 | -46132 | -6590.2857
IN TRANSIT | Emilka Guerra | 2026-04-20 | PO08827 | Stock | 2026-05-25 | D-1J2311-10 | Impeller, 2x3-11, Goulds JC, Frame 1J, High Chrome, OEM# 056189G2601228 | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-06-19 | SEA | ETA Warehouse Mid-Sept |  |  | Follow email sent for update on June 16th . We already shipped them to Tianjin, but the vessel delayed, it shows that it will depart on June 19. | Betty 5/15: Included in Comercial Invoice / #20260205-11 |  | 2026-08-10 |  | FALSE | 25 | -46132 | -6590.2857
In Production | Emilka Guerra | 2026-04-20 | PO08827 | Stock | 2026-05-25 | D-2J3411-6 | Suction Cover Liner, 3x4-11, Goulds JC, Frame 2J, High Chrome, OEM# 048824G0001228 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA |  |  |  | Email for update sent June 2nd |  |  | 2026-08-10 |  | FALSE | -46167 | -46132 | -6590.2857
In Production | Emilka Guerra | 2026-04-20 | PO08827 | Stock | 2026-05-25 | D-WE2J-8 | Stuffing Box Cover, Goulds JC, Frame 2J, High Chrome, OEM# 048877G0001228 | 5 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA |  |  |  | Email for update sent June 2nd |  |  | 2026-08-10 |  | FALSE | -46167 | -46132 | -6590.2857
IN TRANSIT | Emilka Guerra | 2026-04-20 | PO08827 | Stock | 2026-05-25 | D-2J3411-1 | Casing, 3x4-11, Goulds JC, Frame 2J, Cast Iron, OEM#056185G4011002 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-06-19 | SEA | ETA Warehouse Mid-Sept |  |  | Follow email sent for update on June 16th . We already shipped them to Tianjin, but the vessel delayed, it shows that it will depart on June 19. | Betty 5/15: Included in Comercial Invoice / #20260205-11 |  | 2026-08-10 |  | FALSE | 25 | -46132 | -6590.2857
Received | Emilka Guerra | 2026-04-20 | PO08828 | Stock | 2026-06-15 | DU-CY21805A/CBS-DC20 | Rear Cover, 10", Durco Mark 2&3 Group 2, Alloy 20, Small Bore | 2 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-06-05 | AIR | 2026-06-12 |  | DYNC-117 AIR |  |  |  | 2026-08-25 | 2026-06-08 | TRUE | -10 | 49 | 7
Ready to Ship | Emilka Guerra | 2026-04-20 | PO08828 | Stock | 2026-06-15 | DU-DY21855A/CBS-DC20 | Rear Cover, 13", Durco Mark 2&3 Group 2, Alloy-20, Small Bore | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA |  |  | DYNC-119 SEA |  |  |  | 2026-08-25 |  | FALSE | -46188 | -46132 | -6590.2857
IN TRANSIT | Emilka Guerra | 2026-04-20 | PO08828 | Stock | 2026-06-15 | DU-MY36846AA130-CD4 | Impeller, 6x4-13A, Durco Mark 2&3 Group 2, CD4MCu, Reverse Vane | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-06-12 | SEA | ETA Warehouse 1st week of august |  | shipped via DYNC-116 SEA. YM COSMOS/190E | ETD Qingdao 12 June ETA Toronto 16 July |  |  | 2026-08-25 |  | FALSE | -3 | -46132 | -6590.2857
Ready to Ship | Emilka Guerra | 2026-04-20 | PO08828 | Stock | 2026-06-15 | DU-MY36847AA130-CD4 | Impeller, 4x3-13, Durco Mark 2&3 Group 2, CD4MCu, Reverse Vane | 3 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA |  |  | DYNC-119 SEA |  |  |  | 2026-08-25 |  | FALSE | -46188 | -46132 | -6590.2857
In Production | Emilka Guerra | 2026-04-20 | PO08828 | Stock | 2026-06-15 | DU-MY49112A130-CD4 | Impeller, 3x2-13, Durco Mark 2&3 Group 2, CD4MCu, Reverse Vane | 4 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-25 |  | FALSE | -46188 | -46132 | -6590.2857
Ready to Ship | Emilka Guerra | 2026-04-20 | PO08828 | Stock | 2026-06-15 | G-75748X 2229 | Shaft Sleeve, 3175-S, 316SS | 2 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA |  |  | DYNC-119 SEA |  |  |  | 2026-08-25 |  | FALSE | -46188 | -46132 | -6590.2857
IN TRANSIT | Emilka Guerra | 2026-04-20 | PO08828 | Stock | 2026-06-15 | DU-AY38913AA-316 | Shaft Sleeve, Durco Mark 2&3 Group 2, 316SS | 5 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-06-12 | SEA | ETA Warehouse 1st week of august |  | shipped via DYNC-116 SEA. YM COSMOS/190E | ETD Qingdao 12 June ETA Toronto 16 July |  |  | 2026-08-25 |  | FALSE | -3 | -46132 | -6590.2857
Received | Emilka Guerra | 2026-04-20 | PO08829 | SO18821 & Stock | 2026-05-06 | AC-98-431-743-501 | Shaft Assembly, 10x8-21 SRL-C, 1045 Steel | 3 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE | 2026-05-14 | LAND | ETA WAREHOUSE MAY 15-18 | [5 empty] | 2026-05-13 | 2026-06-17 | TRUE | 8 | 58 | 8.2857
Received | Emilka Guerra | 2026-04-20 | PO08829 | SO18821 & Stock | 2026-05-06 | AC-52-109-320-001 | Oil Filler Cap, 1" NPT, SRL, SRL-C & SRL-XT | 10 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE | 2026-05-14 | LAND | ETA WAREHOUSE MAY 15-18 | [5 empty] | 2026-05-13 | 2026-05-19 | TRUE | 8 | 29 | 4.1429
Received | Emilka Guerra | 2026-04-20 | PO08829 | SO18821 & Stock | 2026-05-06 | AC-98-130-367-008 | Shaft Sleeve, PWO Frame 2, 317SS | 1 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE | 2026-05-14 | LAND | ETA WAREHOUSE MAY 15-18 | [5 empty] | 2026-05-13 | 2026-05-19 | TRUE | 8 | 29 | 4.1429
Received | Emilka Guerra | 2026-04-20 | PO08830 | Stock | 2026-04-24 | 22209EAE4 | Bearing (Inboard), 3x3-10 SRL/SRL-C, Steel | 2 | Wajax Limited - Mississauga | Canada | CA WAREHOUSE | 2026-04-24 | LAND | [6 empty] | 2026-04-27 | 2026-04-28 | TRUE | 0 | 8 | 1.1429
Received | Emilka Guerra | 2026-04-20 | PO08830 | Stock | 2026-04-24 | 22309EAE4 | Bearing (Outboard), 3x3-10 SRL & SRL-C, Steel | 2 | Wajax Limited - Mississauga | Canada | CA WAREHOUSE | 2026-04-24 | LAND | [6 empty] | 2026-04-27 | 2026-04-28 | TRUE | 0 | 8 | 1.1429
Received | Emilka Guerra | 2026-04-21 | PO08831 | SO19055 | 2026-04-23 | G-10L38 | Mechanical Seal, Goulds E-SV, Type 0, Carbon vs Silicon-Carbide w/Viton Elastomers | 1 | SUMMIT WATER | Canada | CA WAREHOUSE | 2026-04-23 | LAND | ETA APRIL234-24TH |  | Ship Thursday Truck route |  |  |  | 2026-04-28 | 2026-04-23 | TRUE | 0 | 2
Received | Emilka Guerra | 2026-04-21 | PO08832 | SO19136 & Stock | 2026-04-28 | AC-52-431-816-011 | Casing Gasket, 8x6-13, Allis Chalmers CSO | 3 | Advanced Engineered Pump Inc. | Canada | CA WAREHOUSE | 2026-05-05 | LAND | [6 empty] | 2026-05-12 | 2026-05-07 | TRUE | 7 | 16 | 2.2857
Received | Emilka Guerra | 2026-04-21 | PO08832 | SO19136 & Stock | 2026-04-28 | 52-108-475-015 | Deflector (Inboard), Allis-Chalmers PWO, Group 3 | 6 | Advanced Engineered Pump Inc. | Canada | CA WAREHOUSE | 2026-05-05 | LAND | [6 empty] | 2026-05-12 | 2026-05-07 | TRUE | 7 | 16 | 2.2857
Received | Emilka Guerra | 2026-04-21 | PO08833 | Stock | 2026-04-28 | G-00-737-851-110 | Sight Glass (Press-In), PWO Frame 2 | 15 | Bijur Delimon International | Other | CA WAREHOUSE |  | LAND | [6 empty] | 2026-05-12 | 2026-06-01 | TRUE | -46140 | 41 | 5.8571
IN TRANSIT | Ian Trottier | 2026-04-21 | PO08834 | SO19031 | 2026-05-18 | W-F8036-19M/R55 | Frame Plate Liner (Mechanical Seal), 10/8 E-M or 200 Type L, Natural Rubber | 1 | Super Cast Limited | China | CA WAREHOUSE | 2026-06-04 | SEA | ETA Warehouse Mid-end June |  | LS21TJ2605671 |  | Peter 06/12: left Tianjin for Toronto by sea on June 4, 2026. ETA Prince Rupert: June 29. |  | 2026-08-10 |  | FALSE | 17 | -46133 | -6590.4286
Received | Ian Trottier | 2026-04-21 | PO08835 | SO19143 | 2026-05-12 | AC-98-130-367-008 | Shaft Sleeve, PWO Frame 2, 317SS | 1 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE | 2026-05-14 | LAND | ETA WAREHOUSE MAY 15-18 | [5 empty] | 2026-05-11 | 2026-05-19 | TRUE | 2 | 28 | 4
Received | Ian Trottier | 2026-04-21 | PO08835 | SO19143 | 2026-05-12 | AC-98-233-017-004 | Shaft Sleeve, PWO Frame 3 & 4, 317SS | 1 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE | 2026-05-14 | LAND | ETA WAREHOUSE MAY 15-18 | [5 empty] | 2026-05-11 | 2026-05-19 | TRUE | 2 | 28 | 4
Received | Ian Trottier | 2026-04-21 | PO08836 | SO19144 | 2026-05-01 | AH-484682-0133 | Shaft Sleeve (Mechanical Seal), Ahlstrom APT Frame 4, 316SS | 1 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-05-05 | LAND | ETA May 1st week |  |  |  | Hisco May 5th: Quenton Included in list for ready orders / waiting info on shipping date | April 30th: email follow up for orders. | 2026-05-04 | 2026-05-07 | TRUE | 4 | 16 | 2.2857
Received | Ian Trottier | 2026-04-21 | PO08836 | SO19144 | 2026-05-01 | AH-E11B044294 | Shaft Sleeve O-Ring, Ahlstrom APT Frame 4, Teflon | 5 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-05-05 | LAND | ETA May 1st week |  |  |  | Hisco May 5th: Quenton Included in list for ready orders / waiting info on shipping date | April 30th: email follow up for orders. | 2026-05-04 | 2026-05-07 | TRUE | 4 | 16 | 2.2857
Received | Ian Trottier | 2026-04-21 | PO08837 | SO19145 | 2026-06-02 | DU-CY46072A/CBS-DC20 | Rear Cover, 8", Durco Mark 2&3 Group 2, Alloy-20, Small Bore | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-06-05 | AIR | 2026-06-12 |  | DYNC-117 AIR |  |  |  | 2026-06-12 | 2026-06-08 | TRUE | 3 | 48 | 6.8571
Received | Emilka Guerra | 2026-04-22 | PO08838 | SO17669 | 2026-04-29 | ML2225-7/8 | Packing 7/8" x 7/8", Synthetic Filament w/PTFE Lubricant, 10 lbs. | 1 | Sealing Equipment Products Co., Inc. (SEPCO) | Other | CA WAREHOUSE |  | LAND | [6 empty] | 2026-05-06 | 2026-04-29 | TRUE | -46141 | 7 | 1
Received | Ian Trottier | 2026-04-22 | PO08839 | SO19157 | 2026-05-08 | DU-SA3210AA00-TFR | Impeller Gasket, Durco Mark 2&3 Group 2, Teflon/Rubber | 30 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-05-05 | LAND | ETA May 1st week |  |  |  | Hisco May 5th: Quenton Included in list for ready orders / waiting info on shipping date | April 30th: email follow up for orders. | 2026-05-19 | 2026-05-07 | TRUE | -3 | 15 | 2.1429
Received | Ian Trottier | 2026-04-23 | PO08840 | Stock | 2026-05-01 | G-B00295A 6956 | Shaft Sleeve, 3175-M, 316SS, Ni-Chrome Boron | 2 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-05-05 | LAND | ETA May 1st week |  |  |  | Hisco May 5th: Quenton Included in list for ready orders / waiting info on shipping date | April 30th: email follow up for orders. | 2026-05-12 | 2026-05-07 | TRUE | 4 | 14 | 2
Received | Taylor Cook | 2026-04-23 | PO08841 | SO19081 | 2026-05-07 | G-70782 178 5127 | Casing Gasket, 25", 3180-XL | 2 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-05-05 | LAND | ETA May 1st week |  |  |  | Hisco May 5th: Quenton Included in list for ready orders / waiting info on shipping date | April 30th: email follow up for orders. | 2026-04-23 | 2026-05-07 | TRUE | -2 | 14 | 2
Received | Emilka Guerra | 2026-04-23 | PO08842 | SO19170 | 2026-05-14 | D-500S-98B-18/E05 | Left Round Nut, 500S-98B, M105x2 LH, 1045 Steel | 12 | Super Cast Limited | China | MX WAREHOUSE | 2026-05-07 | SEA | ETA May 2nd week | [5 empty] | 2026-05-21 | 2026-05-12 | TRUE |  | 19 | 2.7143
IN TRANSIT | Yannett Yeomans | 2026-04-23 | PO08843 | SO19177 | 2026-04-27 | W-FMC15145EL1/A05 | Impeller, 150 MCU, High Chrome | 1 | Super Cast Limited | China | MX WAREHOUSE | 2026-05-24 | SEA | ETA Ensenada June 30. |  |  |  | left Tianjin for Ensenada by sea on May 24, 2026 |  | 2026-06-25 |  | FALSE |  | -46135 | -6590.7143
Ready to Ship & Delayed | Emilka Guerra | 2026-04-24 | PO08844 | SO19176 & stock | 2026-06-05 | AC-98-231-079-503 | Gland Side Liner, 5x5-14 SRL, Neoprene | 1 | IGH | Mexico | CA WAREHOUSE |  | LAND |  |  |  |  | Carlos IGH 06/16: List for PO ready to ship ~ destination of shipement confirmed |  | 2026-07-03 |  | FALSE | -46178 | -46136 | -6590.8571
Ready to Ship & Delayed | Emilka Guerra | 2026-04-24 | PO08844 | SO19176 & stock | 2026-06-05 | AC-98-231-081-503 | Suction Side Liner, 5x5-14 SRL, Neoprene | 1 | IGH | Mexico | CA WAREHOUSE |  | LAND |  |  |  |  | Carlos IGH 06/16: List for PO ready to ship ~ destination of shipement confirmed |  | 2026-07-03 |  | FALSE | -46178 | -46136 | -6590.8571
Ready to Ship & Delayed | Emilka Guerra | 2026-04-24 | PO08844 | SO19176 & stock | 2026-06-05 | AC-98-432-037-001 | Bearing Cylinder Strap (Set of 2), 8x6/10x8 SRL-C, Cast Iron | 3 | IGH | Mexico | CA WAREHOUSE |  | LAND |  |  |  |  | Carlos IGH 06/16: List for PO ready to ship ~ destination of shipement confirmed |  | 2026-07-03 |  | FALSE | -46178 | -46136 | -6590.8571
Received | Emilka Guerra | 2026-04-24 | PO08845 | SO19109 & Stock | 2026-05-15 | AC-98-233-979-003 | Sleeve Washer (Impeller), 5x5/5x4/6x6 SRL & SRL-C | 10 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE | 2026-05-14 | LAND | ETA WAREHOUSE MAY 15-18 | [5 empty] | 2026-05-22 | 2026-05-19 | TRUE |  | 25 | 3.5714
Received | Emilka Guerra | 2026-04-24 | PO08845 | SO19109 & Stock | 2026-05-15 | AC-98-331-963-501 | Shaft Assembly, 6x6-15 SRL | 1 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE | 2026-05-14 | LAND | ETA WAREHOUSE MAY 15-18 | [5 empty] | 2026-05-22 | 2026-05-19 | TRUE |  | 25 | 3.5714
Ready to Ship | Emilka Guerra | 2026-04-24 | PO08846 | Stock | 2026-05-25 | G-73705X 2229 | Shaft Sleeve, 3196 MTX, 316SS | 10 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA |  |  | DYNC-119 SEA |  |  |  | 2026-08-03 |  | FALSE |  | -46136 | -6590.8571
Ready to Ship | Emilka Guerra | 2026-04-24 | PO08846 | Stock | 2026-05-25 | G-RC04110A01 1216 | Stuffing Box Cover, 10", 3196 MTX, CD4, Taper Bore Plus | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA |  |  | DYNC-119 SEA |  |  |  | 2026-08-03 |  | FALSE |  | -46136 | -6590.8571
Ready to Ship | Emilka Guerra | 2026-04-24 | PO08846 | Stock | 2026-05-25 | G-249-61 1216 | Casing, 2x3-10, 3196 MTX, CD4MCu | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA |  |  | DYNC-119 SEA |  |  |  | 2026-08-03 |  | FALSE |  | -46136 | -6590.8571
In Production | Amanda Qiao | 2026-04-26 | PO08847 | SO18070 | 2026-05-26 | W-50ZJLF-QV | Froth Pump, 2" QV-AF, W-Series, Rubber Lined Tank | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA |  | get approval from Amanda before shipping |  | SEND FOLLOW UP ON FRIDAY TO NAIPU |  |  | 2026-04-26 |  | FALSE |  | -46138 | -6591.1429
In Production | Amanda Qiao | 2026-04-26 | PO08847 | SO18070 | 2026-05-26 |  | Paint | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA |  | get approval from Amanda before shipping |  | SEND FOLLOW UP ON FRIDAY TO NAIPU |  |  | 2026-04-26 |  | FALSE |  | -46138 | -6591.1429
In Production | Amanda Qiao | 2026-04-26 | PO08847 | SO18070 | 2026-05-26 | W-50ZJLF-QV-BELT | Belts, W-50ZJLF-QV | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA |  | get approval from Amanda before shipping |  | SEND FOLLOW UP ON FRIDAY TO NAIPU |  |  | 2026-04-26 |  | FALSE |  | -46138 | -6591.1429
In Production | Amanda Qiao | 2026-04-26 | PO08847 | SO18070 | 2026-05-26 | W-QV008/E05 | Bearing Sleeve, QV008 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA |  | get approval from Amanda before shipping |  | SEND FOLLOW UP ON FRIDAY TO NAIPU |  |  | 2026-04-26 |  | FALSE |  | -46138 | -6591.1429
In Production | Amanda Qiao | 2026-04-26 | PO08847 | SO18070 | 2026-05-26 | W-BAF2127/A05 | Impeller, 50ZJLF-QV, High Chrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA |  | get approval from Amanda before shipping |  | SEND FOLLOW UP ON FRIDAY TO NAIPU |  |  | 2026-04-27 |  | FALSE |  | -46138 | -6591.1429
In Production | Amanda Qiao | 2026-04-26 | PO08847 | SO18070 | 2026-05-26 | W-BAF4041/A05 | Throat Bushing, 50ZJLF-QV, High Chrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA |  | get approval from Amanda before shipping |  | SEND FOLLOW UP ON FRIDAY TO NAIPU |  |  | 2026-04-27 |  | FALSE |  | -46138 | -6591.1429
In Production | Amanda Qiao | 2026-04-26 | PO08847 | SO18070 | 2026-05-26 | W-QVAF005 | Bearing Assembly, 50ZJLF-QV | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA |  | get approval from Amanda before shipping |  | SEND FOLLOW UP ON FRIDAY TO NAIPU |  |  | 2026-04-27 |  | FALSE |  | -46138 | -6591.1429
Received | Emilka Guerra | 2026-04-27 | PO08849 | SO19151 & Stock | 2026-05-26 | W-SP10116L/D21 | Lower Strainer, 100RV-SP, Ductile Iron | 1 | Super Cast Limited | China | CA WAREHOUSE | 2026-05-06 | AIR |  |  | DHL waybill (4463297635) | Shipped without confirming the date. |  |  | 2026-04-28 | 2026-05-11 | TRUE |  | 14 | 2
IN TRANSIT | Emilka Guerra | 2026-04-27 | PO08849 | SO19151 & Stock | 2026-05-26 | W-F062-10/D81 | Labyrinth, 8/6 to 14/12 F-AH, Zinc Plated | 3 | Super Cast Limited | China | CA WAREHOUSE | 2026-06-04 | SEA | ETA Warehouse Mid-end June |  | LS21TJ2605671 |  | Peter 06/12: left Tianjin for Toronto by sea on June 4, 2026. ETA Prince Rupert: June 29. |  | 2026-08-04 |  | FALSE |  | -46139 | -6591.2857
IN TRANSIT | Emilka Guerra | 2026-04-27 | PO08849 | SO19151 & Stock | 2026-05-26 | W-F108H/D21 | Piston Ring, Ductile Iron | 5 | Super Cast Limited | China | CA WAREHOUSE | 2026-06-04 | SEA | ETA Warehouse Mid-end June |  | LS21TJ2605671 |  | Peter 06/12: left Tianjin for Toronto by sea on June 4, 2026. ETA Prince Rupert: June 29. |  | 2026-08-04 |  | FALSE |  | -46139 | -6591.2857
In Production | Emilka Guerra | 2026-04-27 | PO08851 | Stock | 2026-06-01 | W-RV10005L/0512 | Bearing Assembly (Agitator), 100ZJL-RV, 316L-SS Bearing Cylinder, 1800mm, tapped 316SS Shaft | 1 | Shijiazhuang Mets Machinery Co., LTD | China | CA WAREHOUSE |  | SEA |  |  |  | Production time 5 weeks |  |  | 2026-08-11 |  | FALSE |  | -46139 | -6591.2857
In Production | Emilka Guerra | 2026-04-27 | PO08852 | SO19195 | 2026-06-09 | JC-SCS-1 3/4-4610-MT-BB | Single Cartridge Seal, 1 3/4", D-196 MT, Big Bore, Carbon vs | 1 | Super Cast Limited | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-08-18 |  | FALSE |  | -46139 | -6591.2857
Received | Emilka Guerra | 2026-04-28 | PO08853 | SO19200 | 2026-06-01 | 37230 | Sleeve Bearing (Bowl), ThorPlas-Blue, HPCW | 16 | Millstream Engineering Inc. | Canada | BARRICK CONSOLIDATED | 2026-06-01 | LAND |  |  |  | Ship to Barrick on June 24 | Millstream: the expected ship date is June 1st |  | 2026-06-08 | 2026-06-11 | TRUE |  | 44 | 6.2857
Received | Emilka Guerra | 2026-04-28 | PO08853 | SO19200 | 2026-06-01 | 37229 | Sleeve Bearing (Stuffing Box), ThorPlas-Blue, HPCW | 1 | Millstream Engineering Inc. | Canada | BARRICK CONSOLIDATED | 2026-06-01 | LAND |  |  |  | Ship to Barrick on June 24 | Millstream: the expected ship date is June 1st |  | 2026-06-08 | 2026-06-11 | TRUE |  | 44 | 6.2857
Ready to Ship | Emilka Guerra | 2026-04-28 | PO08854 | SO19200 | 2026-06-10 | D-2001434-CD4 | Bowl (Top),10JKH/M, w/"O" Ring, CD4MCu | 2 | Jiangsu Win-win International Trading Co., Ltd. | China | BARRICK CONSOLIDATED |  | AIR |  | @Peter Please consider PO08854 (Bowl (Top),10JKH/M, CD4MCu 2 pcs) as priority, as soon as it is ready, arrange DHL shipment to Canada. |  | Ship to Barrick on June 24 | Follow up ameil sent June 5th | James 06/05: PO08854 & PO08859 These two orders will be ready for dispatch before the end of next week. James 06/10: Orders ready ✅ | 2026-06-17 |  | FALSE |  | -46140 | -6591.4286
In Production | Yannett Yeomans | 2026-04-28 | PO08855 | SO19186 | 2026-08-04 | AC-52-053-163-000 | Frame Assembly, F4D1, Allis-Chalmers CSO, c/w 316SS Shaft | 1 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND |  |  |  | April 30th: email follow up for orders. June 16th: Follow up email for inclusion on a second shipment |  |  | 2026-08-14 |  | FALSE | -46238 | -46140 | -6591.4286
In Production | Yannett Yeomans | 2026-04-28 | PO08856 | SO19209 | 2026-08-11 | XS500-710 | Horizontal Split Case Pump 24/20, 420SS | 2 | Super Cast Limited | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-10-06 |  | FALSE |  | -46140 | -6591.4286
In Production | Yannett Yeomans | 2026-04-28 | PO08856 | SO19209 | 2026-08-11 | 10364/2001 | Set of Coupling and Coupling Guard XS500-710, Cast Iron | 2 | Super Cast Limited | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-10-06 |  | FALSE |  | -46140 | -6591.4286
In Production | Yannett Yeomans | 2026-04-28 | PO08856 | SO19209 | 2026-08-11 | 10365/1501 | Common base XS500-710, Carbon Steel | 2 | Super Cast Limited | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-10-06 |  | FALSE |  | -46140 | -6591.4286
Received | Emilka Guerra | 2026-04-29 | PO08857 | SO19204 | 2026-05-20 | AC-98-331-932-503 | Shaft, 5x4-14 SRL-C & 5x5-14 SRL, 316SS | 1 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2026-05-27 | 2026-06-09 | TRUE |  | 41 | 5.8571
IN TRANSIT | Ian Trottier | 2026-04-29 | PO08858 | SO19093 | 2026-06-19 | G-0D02490A03 1220 | Impeller, 8x10-13, 3196 XLT, Titanium, 5-Vane | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | AIR |  |  | DYNC-118 DHL# 1279093830 |  |  |  | 2026-07-03 |  | FALSE |  | -46141 | -6591.5714
Ready to Ship | Emilka Guerra | 2026-04-29 | PO08859 | Stock | 2026-06-10 | D-2001434-CD4 | Bowl (Top),10JKH/M, w/"O" Ring, CD4MCu | 3 | Jiangsu Win-win International Trading Co., Ltd. | China | CA WAREHOUSE |  | SEA |  | The PO08859 can be shipped by sea. |  |  | Follow up ameil sent June 5th | James 06/05: PO08854 & PO08859 These two orders will be ready for dispatch before the end of next week. James 06/10: Orders ready ✅ | 2026-08-19 |  | FALSE |  | -46141 | -6591.5714
Received | Emilka Guerra | 2026-04-29 | PO08860 | SO19140 | 2026-07-22 | WO-2104711-121 | Impeller (Open), 11", Worthington 3M111, High Chrome | 1 | M&N Alloy Cast Products, Inc. | US | CA WAREHOUSE |  | LAND | [6 empty] | 2026-08-05 | 2026-05-13 | TRUE |  | 14 | 2
IN TRANSIT | Emilka Guerra | 2026-04-29 | PO08861 | SO19156 | 2026-05-28 | W-F6036TL1HS1/R55 | Frame Plate Liner (Hi-Seal), 8/6 E-AH, Natural Rubber | 1 | Super Cast Limited | China | CA WAREHOUSE | 2026-06-04 | SEA | ETA Warehouse Mid-end June |  | LS21TJ2605671 |  | Peter 06/12: left Tianjin for Toronto by sea on June 4, 2026. ETA Prince Rupert: June 29. |  | 2026-08-06 |  | FALSE |  | -46141 | -6591.5714
Ready to Ship | Ian Trottier | 2026-04-29 | PO08862 | SO19199 | 2026-06-19 | DU-CY21853A-CD4 | Casing, 3x1.5-13, Durco Mark 2&3 Group 2, CD4MCu , #300 Flat Face Flanges | 2 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA |  |  | DYNC-119 SEA |  |  |  | 2026-09-04 |  | FALSE |  | -46141 | -6591.5714
Ready to Ship | Ian Trottier | 2026-04-29 | PO08863 | SO19184 | 2026-07-07 | AC-98-330-289-503 | Impeller (Open), 5x5-14 SRL, Neoprene | 2 | IGH | Mexico | CA WAREHOUSE |  | LAND |  |  |  |  | Carlos IGH 06/16: List for PO ready to ship ~ destination of shipement confirmed |  | 2026-07-21 |  | FALSE | -46210 | -46141 | -6591.5714
Ready to Ship & Delayed | Ian Trottier | 2026-04-30 | PO08864 | SO19125 | 2026-06-04 | G-73705X 1605 | Shaft Sleeve, 3196 MTX, Alloy 254 SMO | 1 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-06-16 | LAND | ETA WAREHOUSE 3rd week of JUNE |  |  |  | Quenton Hisco 06/16: Ready to ship - Pending Pick up confirmation by logistics | April 30th: email follow up for orders. | 2026-06-04 |  | FALSE | 12 | -46142 | -6591.7143
Received | Emilka Guerra | 2026-04-30 | PO08865 | SO19202 | 2026-05-07 | G-70782 28 5117 | Casing Gasket, 13", 3196 MTX, Teflon | 1 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-05-05 | LAND | ETA May 1st week |  |  |  | Hisco May 5th: Quenton Included in list for ready orders / waiting info on shipping date | April 30th: email follow up for orders. | 2026-05-28 | 2026-05-07 | TRUE | -2 | 7 | 1
In Production | Emilka Guerra | 2026-04-30 | PO08866 | SO19221 | 2026-07-23 | SA-572855 | Impeller, Sala, STGVA-65W | 1 | Dexhor | Other | CA WAREHOUSE |  | LAND |  |  |  | Production Time updated to 12 weeks. |  |  | 2026-08-13 |  | FALSE |  | -46142 | -6591.7143
In Production | Ian Trottier | 2026-04-30 | PO08867 | SO19147 | 2026-06-19 | AC-98-231-054-503 | Suction Side Liner, 2x2-10 SRL, Neoprene | 4 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-21 |  | FALSE |  | -46142 | -6591.7143
In Production | Ian Trottier | 2026-04-30 | PO08868 | Stock | 2026-06-19 | AC-98-330-289-503 | Impeller (Open), 5x5-14 SRL, Neoprene | 1 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-21 |  | FALSE |  | -46142 | -6591.7143
In Production | Ian Trottier | 2026-04-30 | PO08869 | SO19232 | 2026-07-23 | G-D09563A 1203 | Impeller, 12x14-22, 3175-L, 316SS, 4-Vane | 1 | M&N Alloy Cast Products, Inc. | US | CA WAREHOUSE |  | LAND | [6 empty] | 2026-07-24 |  | FALSE |  | -46142 | -6591.7143
Ready to Ship | Emilka Guerra | 2026-05-04 | PO08870 | SO18007 | 2026-06-30 | AC-98-5414-HC5 | Stuffing Box, 5x4-14 SRL-C, Cast Iron, 3-Piece Design | 2 | IGH | Mexico | CA WAREHOUSE |  | LAND |  |  |  | 10 weeks originally reduced to 8 by supplier | Carlos IGH 06/16: List for PO ready to ship ~ destination of shipement confirmed |  | 2026-07-21 |  | FALSE | -46203 | -46146 | -6592.2857
Received | Emilka Guerra | 2026-05-04 | PO08871 | SO19194 | 2026-06-01 | G-R175MKM18 | Maintenance Kit, 18", 3175-M | 1 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-05-05 | LAND | ETA May 1st week |  |  |  | Hisco May 5th: Quenton Included in list for ready orders / waiting info on shipping date | April 30th: email follow up for orders. | 2026-06-29 | 2026-05-07 | TRUE | -27 | 3 | 0.42857
IN TRANSIT | Emilka Guerra | 2026-05-04 | PO08872 | Stock | 2026-06-01 | OLPWZ011009B, G-A04951A222 | Bearing Isolator (Inboard), 3196 XLT/XLTi, 303SS Rotor / Bronze Stator w/Viton | 8 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-06-12 | SEA | ETA Warehouse 1st week of august |  | shipped via DYNC-116 SEA. YM COSMOS/190E | ETD Qingdao 12 June ETA Toronto 16 July |  |  | 2026-08-10 |  | FALSE |  | -46146 | -6592.2857
Ready to Ship | Emilka Guerra | 2026-05-04 | PO08872 | Stock | 2026-06-01 | G-70782 28 5117 | Casing Gasket, 13", 3196 MTX, Teflon | 30 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA |  |  | DYNC-119 SEA |  |  |  | 2026-08-10 |  | FALSE |  | -46146 | -6592.2857
In Production | Yannett Yeomans | 2026-04-28 | PO08856 | SO19209 | 2026-07-13 | XS500-710 | Horizontal Split Case Pump 24/20, 420SS | 2 | Super Cast Limited | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-08-31 |  | FALSE |  | -46140 | -6591.4286
In Production | Yannett Yeomans | 2026-04-28 | PO08856 | SO19209 | 2026-07-13 | 10364/2001 | Set of Coupling and Coupling Guard XS500-710, Cast Iron | 2 | Super Cast Limited | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-08-31 |  | FALSE |  | -46140 | -6591.4286
In Production | Yannett Yeomans | 2026-04-28 | PO08856 | SO19209 | 2026-07-13 | 10365/1501 | Common base XS500-710, Carbon Steel | 2 | Super Cast Limited | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-08-31 |  | FALSE |  | -46140 | -6591.4286
In Production | Emilka Guerra | 2026-05-04 | PO08873 | Stock | 2026-05-18 | AC-52-108-475-013 | Deflector (Outboard), Allis-Chalmers PWO, Group 2 | 5 | Advanced Engineered Pump Inc. | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2026-06-01 |  | FALSE |  | -46146 | -6592.2857
In Production | Emilka Guerra | 2026-05-04 | PO08873 | Stock | 2026-05-18 | AC-52-050-313-000 | Shim Kit, Allis Chalmers CSO, Frame F4D1/F4B5 | 6 | Advanced Engineered Pump Inc. | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2026-06-01 |  | FALSE |  | -46146 | -6592.2857
Ready to Ship | Emilka Guerra | 2026-05-04 | PO08874 | SO19250 & Stock | 2026-07-15 | AC-98-037-796-503 | Impeller (Open), 6x6-15 SRL, Neoprene | 2 | IGH | Mexico | CA WAREHOUSE |  | LAND |  |  |  |  | Carlos IGH 06/16: List for PO ready to ship ~ destination of shipement confirmed |  | 2026-08-05 |  | FALSE |  | -46146 | -6592.2857
Ready to Ship | Emilka Guerra | 2026-05-04 | PO08874 | SO19250 & Stock | 2026-07-15 | AC-98-530-586-001 | Pedestal, 8x6-18 & 10x8-21 SRL-C, Cast Iron | 1 | IGH | Mexico | CA WAREHOUSE |  | LAND |  |  |  |  | Carlos IGH 06/16: List for PO ready to ship ~ destination of shipement confirmed |  | 2026-08-05 |  | FALSE |  | -46146 | -6592.2857
In Production | Yannett Yeomans | 2026-05-04 | PO08875 | SO19243 | 2026-06-05 | 150SV-SP | Vertical Sump Pump, 150SV-SP, High Chrome | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-06-03 |  | FALSE |  | -46146 | -6592.2857
Received | Emilka Guerra | 2026-05-04 | PO08876 | Stock | 2026-05-08 | SKF 6306, G-8050-30660 | Bearing (Inboard & Outboard), 2X2-10 SRL, Steel | 4 | Wajax Limited - Mississauga | Canada | CA WAREHOUSE | 2026-05-25 | LAND | [6 empty] | 2026-05-12 | 2026-05-27 | TRUE |  | 23 | 3.2857
Received | Emilka Guerra | 2026-05-04 | PO08876 | Stock | 2026-05-08 | CR16084, G-8690-93760 | Bearing Seal, 3x3-10 SRL & SRL-C (Outboard) & 2x2-10 (Inboard), Neoprene/Steel | 4 | Wajax Limited - Mississauga | Canada | CA WAREHOUSE | 2026-05-25 | LAND | [6 empty] | 2026-05-12 | 2026-05-27 | TRUE |  | 23 | 3.2857
Received | Emilka Guerra | 2026-05-05 | PO08877 | Stock | 2026-05-12 | AC-98-331-958-805 | Shaft Sleeve, 2x2-10 SRL, Steel | 2 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE | 2026-05-14 | LAND | ETA WAREHOUSE MAY 15-18 | [5 empty] | 2026-05-19 | 2026-05-19 | TRUE |  | 14 | 2
Received | Emilka Guerra | 2026-05-05 | PO08877 | Stock | 2026-05-12 | AC-98-234-108-001 | Half Seal Cage, 2x2-10 SRL, Cast Iron | 2 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE | 2026-05-14 | LAND | ETA WAREHOUSE MAY 15-18 | [5 empty] | 2026-05-19 | 2026-05-19 | TRUE |  | 14 | 2
Received | Emilka Guerra | 2026-05-05 | PO08877 | Stock | 2026-05-12 | AC-98-234-104-001 | Waterseal Bushing, 2x2-10 SRL, Cast Iron | 1 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE | 2026-05-14 | LAND | ETA WAREHOUSE MAY 15-18 | [5 empty] | 2026-05-19 | 2026-05-19 | TRUE |  | 14 | 2
In Production | Leriel Reyes | 2026-05-06 | PO08878 | Stock | 2026-06-27 | AC-98-234-036-801 | Overhead Motor Mount, 5x4/6x6, Cast Steel Plate, Steel Jacking Bolt | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-05 |  | FALSE |  | -46148 | -6592.5714
In Production | Leriel Reyes | 2026-05-06 | PO08878 | Stock | 2026-06-27 | AC-98-234-082-801 | Overhead Motor Mount, 3x3-10 SRL/SRL-C, Cast Steel Plate, Steel Bolt | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-05 |  | FALSE |  | -46148 | -6592.5714
In Production | Ian Trottier | 2026-05-06 | PO08879 | Reverse Engineer 6x6-14LS Project | 2026-08-05 | D-WE3J-12 | Stuffing Box Cover, Goulds JC, Frame 3J, 6x6-14LS, High Chrome, OEM# 050294GG0001228 | 1 | M&N Alloy Cast Products, Inc. | US | CA WAREHOUSE |  | LAND | [6 empty] | 2026-05-06 |  | FALSE |  | -46148 | -6592.5714
In Production | Ian Trottier | 2026-05-06 | PO08879 | Reverse Engineer 6x6-14LS Project | 2026-08-05 | D-3J6614-10 | Impeller, 6x6-14, Dynapro DC, Frame 3J, High Chrome, OEM# 056191G3101228 | 1 | M&N Alloy Cast Products, Inc. | US | CA WAREHOUSE |  | LAND | [6 empty] | 2026-05-07 |  | FALSE |  | -46148 | -6592.5714
In Production | Ian Trottier | 2026-05-06 | PO08879 | Reverse Engineer 6x6-14LS Project | 2026-08-05 | D-3J6614-2 | Casing, 6x6-14, Dynapro DC, Frame 3J, High Chrome, OEM# 056191G0701228 | 1 | M&N Alloy Cast Products, Inc. | US | CA WAREHOUSE |  | LAND | [6 empty] | 2026-05-07 |  | FALSE |  | -46148 | -6592.5714
In Production | Ian Trottier | 2026-05-06 | PO08880 | Reverse Engineer 6x6-14LS Project | 2026-06-05 | D-WE3J-18 | Gasket (Casing to Stuffing Box), Goulds JC, Frame 3J, 6x6-14LS, Neoprene | 1 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND |  |  |  | June 16th: Follow up email for inclusion on a second shipment |  |  | 2026-06-19 |  | FALSE |  | -46148 | -6592.5714
In Production | Ian Trottier | 2026-05-07 | PO08882 | SO19241 | 2026-06-26 | DU-MY36862A100-A20 | Impeller, 3x2-10, Durco Mark 2 Group 2, Alloy 20, Reverse Vane | 3 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-08 |  | FALSE |  | -46149 | -6592.7143
In Production | Amanda Qiao | 2026-05-07 | PO08883 | SO18295 | 2026-07-14 | AC-98-530-757-001 | Suction Side Casing, 3x3-10 SRL-C HD, Carbon Steel | 1 | IGH | Mexico | CA WAREHOUSE |  | LAND | [6 empty] | 2026-07-29 |  | FALSE |  | -46149 | -6592.7143
IN TRANSIT | Ian Trottier | 2026-05-07 | PO08884 | SO18994 - SO18242 | 2026-07-13 | AC-52-430-274-501 | Frame, Allis-Chalmers CSO, F4D1, Cast Iron | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-06-12 | SEA | ETA Warehouse 1st week of august |  | shipped via DYNC-116 SEA. YM COSMOS/190E | ETD Qingdao 12 June ETA Toronto 16 July |  |  | 2026-07-31 |  | FALSE |  | -46149 | -6592.7143
In Production | Ian Trottier | 2026-05-07 | PO08884 | SO18994 - SO18242 | 2026-07-13 | AC-52-430-274-501 | Frame, Allis-Chalmers CSO, F4D1, Cast Iron | 3 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-07-31 |  | FALSE |  | -46149 | -6592.7143
IN TRANSIT | Ian Trottier | 2026-05-07 | PO08884 | SO18994 - SO18242 | 2026-07-13 | AC-52-319-380-001 | Frame Foot, Allis Chalmers CSO, Frame F4D1, fits 11" and 13" pumps, Cast Iron | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-06-12 | SEA | ETA Warehouse 1st week of august |  | shipped via DYNC-116 SEA. YM COSMOS/190E | ETD Qingdao 12 June ETA Toronto 16 July |  |  | 2026-07-31 |  | FALSE |  | -46149 | -6592.7143
In Production | Ian Trottier | 2026-05-07 | PO08884 | SO18994 - SO18242 | 2026-07-13 | AC-52-319-380-001 | Frame Foot, Allis Chalmers CSO, Frame F4D1, fits 11" and 13" pumps, Cast Iron | 10 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-07-31 |  | FALSE |  | -46149 | -6592.7143
In Production | Ian Trottier | 2026-05-08 | PO08885 | SO19276 | 2026-06-19 | AC-98-432-883-504 | Shaft (Fine Thread), PWO, Frame 3, 317SS | 1 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2026-06-22 |  | FALSE |  | -46150 | -6592.8571
In Production | Ian Trottier | 2026-05-08 | PO08885 | SO19276 | 2026-06-19 | AC-98-432-881-504 | Shaft, PWO, Frame 1, 317SS | 1 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2026-06-22 |  | FALSE |  | -46150 | -6592.8571
In Production | Emilka Guerra | 2026-05-08 | PO08886 | SO19248 | 2026-07-31 | WO-2104511-004 | Wear Plate, Worthington 6-FRBH-142, 317SS | 1 | M&N Alloy Cast Products, Inc. | US | CA WAREHOUSE |  | LAND | [6 empty] | 2026-08-21 |  | FALSE |  | -46150 | -6592.8571
IN TRANSIT | Emilka Guerra | 2026-05-08 | PO08887 | SO19275 | 2026-06-19 | W-SP25092/A05 | Casing, 250SV-SP, High Chrome | 1 | Super Cast Limited | China | BARRICK DIRECT SHIPPING | 2026-06-01 | SEA |  | CIF CAUCEDO | LS15TJ2605952 |  | June 2nd: left Tianjin for Caucedo by sea on June 1, 2026. |  | 2026-08-07 |  | FALSE |  | -46150 | -6592.8571
Ready to Ship | Emilka Guerra | 2026-05-11 | PO08888 | Stock | 2026-06-12 | W-E4110/A05 | Volute Liner, 6/4 D or E-AH, High Chrome | 2 | Super Cast Limited | China | CA WAREHOUSE | 2026-06-21 | SEA |  |  |  | Follow up email sent May June 10th | Peter 06/10: ready, and will catch the vessel of the Sunday after next (June 21) |  | 2026-08-21 |  | FALSE |  | -46153 | -6593.2857
Ready to Ship | Emilka Guerra | 2026-05-11 | PO08888 | Stock | 2026-06-12 | SA-138413-M1 | Casing, Sala 2", SPV, Rubber Lined | 4 | Super Cast Limited | China | CA WAREHOUSE | 2026-06-21 | SEA |  |  |  | Follow up email sent May June 10th | Peter 06/10: ready, and will catch the vessel of the Sunday after next (June 21) |  | 2026-08-21 |  | FALSE |  | -46153 | -6593.2857
Ready to Ship | Emilka Guerra | 2026-05-11 | PO08888 | Stock | 2026-06-12 | SA-234602-M1 | Impeller, VT50, Natural Rubber | 3 | Super Cast Limited | China | CA WAREHOUSE | 2026-06-21 | SEA |  |  |  | Follow up email sent May June 10th | Peter 06/10: ready, and will catch the vessel of the Sunday after next (June 21) |  | 2026-08-21 |  | FALSE |  | -46153 | -6593.2857
DELAYED PRODUCTION | Emilka Guerra | 2026-05-11 | PO08888 | Stock | 2026-06-12 | SA-138414-M1 | Inlet Door, Sala VT50, Natural Rubber | 3 | Super Cast Limited | China | CA WAREHOUSE |  | SEA |  |  |  | Follow up email sent May June 10th | Peter 06/10: still need about 10 to 15 days to come out. |  | 2026-08-21 |  | FALSE |  | -46153 | -6593.2857
DELAYED PRODUCTION | Emilka Guerra | 2026-05-11 | PO08888 | Stock | 2026-06-12 | W-SP25092/A05 | Casing, 250SV-SP, High Chrome | 2 | Super Cast Limited | China | CA WAREHOUSE |  | SEA |  |  |  | Follow up email sent May June 10th | Peter 06/10: still need about 10 to 15 days to come out. |  | 2026-08-21 |  | FALSE |  | -46153 | -6593.2857
DELAYED PRODUCTION | Emilka Guerra | 2026-05-11 | PO08888 | Stock | 2026-06-12 | W-SP25041/A05 | Back Liner, 250SV-SP, High Chrome | 1 | Super Cast Limited | China | CA WAREHOUSE |  | SEA |  |  |  | Follow up email sent May June 10th | Peter 06/10: still need about 10 to 15 days to come out. |  | 2026-08-21 |  | FALSE |  | -46153 | -6593.2857
Ready to Ship | Emilka Guerra | 2026-05-11 | PO08888 | Stock | 2026-06-12 | W-F8147/R55 | Impeller, 10/8 E-M, Natural Rubber | 5 | Super Cast Limited | China | CA WAREHOUSE | 2026-06-21 | SEA |  |  |  | Follow up email sent May June 10th | Peter 06/10: ready, and will catch the vessel of the Sunday after next (June 21) |  | 2026-08-21 |  | FALSE |  | -46153 | -6593.2857
DELAYED PRODUCTION | Emilka Guerra | 2026-05-11 | PO08888 | Stock | 2026-06-12 | SA-016628-M1 | Casing, 44 WFR, Sala ST, Rubber Lined | 50 | Super Cast Limited | China | CA WAREHOUSE |  | SEA |  |  |  | Follow up email sent May June 10th | Peter 06/10: still need about 10 to 15 days to come out. |  | 2026-08-21 |  | FALSE |  | -46153 | -6593.2857
Ready to Ship | Emilka Guerra | 2026-05-11 | PO08889 | Stock | 2026-07-22 | AC-98-234-113-801 | Bearing Housing, 2x2-10-SRL, Cast Iron | 1 | IGH | Mexico | CA WAREHOUSE |  | LAND |  |  |  |  | Carlos IGH 06/16: List for PO ready to ship ~ destination of shipement confirmed |  | 2026-08-12 |  | FALSE |  | -46153 | -6593.2857
Ready to Ship | Emilka Guerra | 2026-05-11 | PO08889 | Stock | 2026-07-22 | AC-98-431-857-501 | Gland Side Casing, 3x3-10 SRL-C, Cast Iron | 1 | IGH | Mexico | CA WAREHOUSE |  | LAND |  |  |  |  | Carlos IGH 06/16: List for PO ready to ship ~ destination of shipement confirmed |  | 2026-08-12 |  | FALSE |  | -46153 | -6593.2857
Ready to Ship | Emilka Guerra | 2026-05-11 | PO08889 | Stock | 2026-07-22 | AC-98-431-766-501 | Gland Side Casing, 8x6-18 SRL-C, Cast Iron | 1 | IGH | Mexico | CA WAREHOUSE |  | LAND |  |  |  |  | Carlos IGH 06/16: List for PO ready to ship ~ destination of shipement confirmed |  | 2026-08-12 |  | FALSE |  | -46153 | -6593.2857
Ready to Ship | Emilka Guerra | 2026-05-11 | PO08889 | Stock | 2026-07-22 | AC-98-431-775-001 | Suction Side Casing, 8x6-18 SRL-C, Cast Iron | 1 | IGH | Mexico | CA WAREHOUSE |  | LAND |  |  |  |  | Carlos IGH 06/16: List for PO ready to ship ~ destination of shipement confirmed |  | 2026-08-12 |  | FALSE |  | -46153 | -6593.2857
Ready to Ship | Emilka Guerra | 2026-05-11 | PO08889 | Stock | 2026-07-22 | AC-98-432-037-001 | Bearing Cylinder Strap (Set of 2), 8x6/10x8 SRL-C, Cast Iron | 3 | IGH | Mexico | CA WAREHOUSE |  | LAND |  |  |  |  | Carlos IGH 06/16: List for PO ready to ship ~ destination of shipement confirmed |  | 2026-08-12 |  | FALSE |  | -46153 | -6593.2857
Ready to Ship | Emilka Guerra | 2026-05-11 | PO08889 | Stock | 2026-07-22 | AC-98-037-796-503 | Impeller (Open), 6x6-15 SRL, Neoprene | 2 | IGH | Mexico | CA WAREHOUSE |  | LAND |  |  |  |  | Carlos IGH 06/16: List for PO ready to ship ~ destination of shipement confirmed |  | 2026-08-12 |  | FALSE |  | -46153 | -6593.2857
Ready to Ship | Emilka Guerra | 2026-05-11 | PO08889 | Stock | 2026-07-22 | AC-98-231-084-503 | Gland Side Liner, 6x6-15 SRL, Neoprene | 1 | IGH | Mexico | CA WAREHOUSE |  | LAND |  |  |  |  | Carlos IGH 06/16: List for PO ready to ship ~ destination of shipement confirmed |  | 2026-08-12 |  | FALSE |  | -46153 | -6593.2857
Received | Emilka Guerra | 2026-05-11 | PO08890 | Stock | 2026-05-20 | AC-98-233-700-003 | Bearing End Cover Gasket, 3x3-10 SRL & SRL-C | 10 | NC Industrial | US | CA WAREHOUSE | 2026-05-25 | LAND | 2026-05-26 | [5 empty] | 2026-05-27 | 2026-06-01 | TRUE |  | 21 | 3
IN TRANSIT | Emilka Guerra | 2026-05-11 | PO08891 | Stock | 2026-06-24 | T-034, G-C02495A34 6359 | Impeller O-Ring, 3196 XLT, Teflon | 10 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE | 2026-06-12 | SEA | ETA Warehouse 1st week of august |  | shipped via DYNC-116 SEA. YM COSMOS/190E | ETD Qingdao 12 June ETA Toronto 16 July |  |  | 2026-09-02 |  | FALSE |  | -46153 | -6593.2857
In Production | Emilka Guerra | 2026-05-11 | PO08891 | Stock | 2026-06-24 | G-0B10588 1216 | Impeller, 2x3-13, 3196 LTX, CD4MCu, 5-Vane | 2 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-02 |  | FALSE |  | -46153 | -6593.2857
Ready to Ship | Emilka Guerra | 2026-05-11 | PO08891 | Stock | 2026-06-24 | AC-98-431-577-501 | Frame, 14", Allis Chalmers PWO, Frame A1, Oil-Lubed, Cast Iron | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA |  |  | DYNC-119 SEA |  |  |  | 2026-09-02 |  | FALSE |  | -46153 | -6593.2857
In Production | Emilka Guerra | 2026-05-11 | PO08892 | Stock | 2026-06-24 | AC-98-233-998-801 | Bearing Cover (Inboard), 3x3-10 SRL & SRL-C | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-02 |  | FALSE |  | -46153 | -6593.2857
In Production | Emilka Guerra | 2026-05-11 | PO08892 | Stock | 2026-06-24 | AC-98-234-000-801 | Bearing Cover (Outboard), 3x3-10 SRL & SRL-C, Cast Iron | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-02 |  | FALSE |  | -46153 | -6593.2857
In Production | Emilka Guerra | 2026-05-11 | PO08892 | Stock | 2026-06-24 | AC-98-332-173-001 | Bearing Cylinder Strap, 3x3-10 SRL-C | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-02 |  | FALSE |  | -46153 | -6593.2857
In Production | Emilka Guerra | 2026-05-11 | PO08892 | Stock | 2026-06-24 | AC-98-331-910-801 | Bearing Cylinder, 8x6-18 & 10x8-21 SRL-C, Cast Iron | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-02 |  | FALSE |  | -46153 | -6593.2857
Ready to Ship & Delayed | Emilka Guerra | 2026-05-11 | PO08893 | SO19267 | 2026-05-18 | AC-52-231-827-009 | Shaft (Sleeve Type), Allis-Chalmers CSO, Frame F4D1, 4140 Steel | 1 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-06-16 | LAND | ETA WAREHOUSE 3rd week of JUNE |  |  |  | Quenton Hisco 06/16: Ready to ship - Pending Pick up confirmation by logistics |  | 2026-06-01 |  | FALSE |  | -46153 | -6593.2857
Ready to Ship & Delayed | Ian Trottier | 2026-05-11 | PO08894 | SO19264 | 2026-05-26 | DU-BY50424B-TSSR | Oil Seal (Outboard), Durco Mark 2&3 Group 1, Teflon/Stainless Steel/Rubber | 3 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-06-16 | LAND | ETA WAREHOUSE 3rd week of JUNE |  |  |  | Quenton Hisco 06/16: Ready to ship - Pending Pick up confirmation by logistics |  | 2026-06-05 |  | FALSE |  | -46153 | -6593.2857
Ready to Ship & Delayed | Ian Trottier | 2026-05-11 | PO08894 | SO19264 | 2026-05-26 | DU-BY50424G-TSSR | Oil Seal (Inboard), Durco Mark 3 Group 1, Teflon/Stainless Steel/Rubber | 5 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-06-16 | LAND | ETA WAREHOUSE 3rd week of JUNE |  |  |  | Quenton Hisco 06/16: Ready to ship - Pending Pick up confirmation by logistics |  | 2026-06-05 |  | FALSE |  | -46153 | -6593.2857
In Production | Ian Trottier | 2026-05-11 | PO08895 | SO19214 | 2026-06-29 | GA-21630 | Impeller, G-Series 2.5" VSP, 1000 Series, Cast Iron | 1 | IGH | Mexico | CA WAREHOUSE |  | LAND | [6 empty] | 2026-06-30 |  | FALSE |  | -46153 | -6593.2857
In Production | Ian Trottier | 2026-05-12 | PO08896 | SO19292 | 2026-06-10 | DU-CY21805A/CBS-DC20 | Rear Cover, 10", Durco Mark 2&3 Group 2, Alloy 20, Small Bore | 2 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-06-22 |  | FALSE |  | -46154 | -6593.4286
In Production | Emilka Guerra | 2026-05-12 | PO08897 | SO19060 | 2026-05-29 | W-M12Z3-135Z | Frame Plate Liner Stud, 8/6 AH | 10 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-04 |  | FALSE |  | -46154 | -6593.4286
Received | Emilka Guerra | 2026-05-12 | PO08898 | SO19286 | 2026-05-15 | AC-98-­236-­426-­001 | Waterseal Bushing, 6x6-21 SRL-XT, Steel | 1 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE | 2026-05-14 | LAND | ETA WAREHOUSE MAY 15-18 | [5 empty] | 2026-05-19 | 2026-05-25 | TRUE |  | 13 | 1.8571
Received | Emilka Guerra | 2026-05-12 | PO08899 | SO19297 | 2026-05-19 | ML2225-7/8 | Packing 7/8" x 7/8", Synthetic Filament w/PTFE Lubricant, 10 lbs. | 1 | Sealing Equipment Products Co., Inc. (SEPCO) | Other | CA WAREHOUSE | 2026-05-14 | LAND | ETA WAREHOUSE MAY 15-18 | [5 empty] | 2026-05-26 | 2026-05-20 | TRUE |  | 8 | 1.1429
Ready to Ship & Delayed | Emilka Guerra | 2026-05-13 | PO08900 | SO19300 & Stock | 2026-06-03 | DU-BY50424D-TSSR | Oil Seal (Inboard), Durco Mark 3 Group 2, Teflon/Stainless Steel/Rubber | 2 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-06-16 | LAND | ETA WAREHOUSE 3rd week of JUNE |  |  |  | Quenton Hisco 06/16: Ready to ship - Pending Pick up confirmation by logistics |  | 2026-06-24 |  | FALSE |  | -46155 | -6593.5714
Received | Emilka Guerra | 2026-05-14 | PO08901 | Stock | 2026-06-18 | 37230 | Sleeve Bearing (Bowl), ThorPlas-Blue, HPCW | 32 | Millstream Engineering Inc. | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2026-06-25 | 2026-06-11 | TRUE |  | 28 | 4
Received | Emilka Guerra | 2026-05-14 | PO08901 | Stock | 2026-06-18 | 37229 | Sleeve Bearing (Stuffing Box), ThorPlas-Blue, HPCW | 2 | Millstream Engineering Inc. | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2026-06-25 | 2026-06-11 | TRUE |  | 28 | 4
Received | Emilka Guerra | 2026-05-14 | PO08902 | Stock | 2026-05-21 | AC-98-233-731-001 | Half Seal Cage, 8x6-18 & 10x8-21 SRL-C, Steel | 4 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE | 2026-05-14 | LAND | ETA WAREHOUSE MAY 15-18 | [5 empty] | 2026-05-29 | 2026-05-19 | TRUE |  | 5 | 0.71429
Received | Emilka Guerra | 2026-05-14 | PO08903 | Stock | 2026-05-21 | SKF-22340 | Bearing Seal (Inboard & Outboard), 5x4-14 SRL/SRL-C, 6x6-15 SRL | 6 | Wajax Limited - Mississauga | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2026-05-28 | 2026-05-20 | TRUE |  | 6 | 0.85714
In Production | Emilka Guerra | 2026-05-14 | PO08904 | SO19320 | 2026-06-11 | G-D04628A 1000 | Thrust Bearing Housing, 3196 LTX, Cast Iron | 2 | Shandong Furkey Pumps Co., Ltd. | China | MX WAREHOUSE |  | AIR | [6 empty] | 2026-06-25 |  | FALSE |  | -46156 | -6593.7143
In Production | Emilka Guerra | 2026-05-14 | PO08904 | SO19320 | 2026-06-11 | G-B02194A 2210 | Bearing Clamp Ring, LTX | 2 | Shandong Furkey Pumps Co., Ltd. | China | MX WAREHOUSE |  | AIR | [6 empty] | 2026-06-25 |  | FALSE |  | -46156 | -6593.7143
Ready to Ship & Delayed | Emilka Guerra | 2026-05-14 | PO08905 | SO19271 | 2026-06-11 | AC-52-231-716-001 | Shaft, Allis-Chalmers CSO, Frame F4C1, 4140 Steel | 1 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-06-16 | LAND | ETA WAREHOUSE 3rd week of JUNE |  |  |  | Quenton Hisco 06/16: Ready to ship - Pending Pick up confirmation by logistics |  | 2026-07-02 |  | FALSE |  | -46156 | -6593.7143
In Production | Ian Trottier | 2026-05-14 | PO08906 | Stock | 2026-06-05 | G-67868-211-212 5108 | Gasket Material (2 Piece Set), Armstrong Syntheseal N-8090, 16" x 17 3/4" | 100 | Vellumoid Inc. | Other | CA WAREHOUSE |  | LAND | [6 empty] | 2026-06-16 |  | FALSE |  | -46156 | -6593.7143
Received | Emilka Guerra | 2026-05-14 | PO08907 | SO19301 | 2026-06-02 | P398 | Baseplate, PoxyBase Plus Black Polymer Base, Size 398 | 1 | BaseTek, LLC | US | CA WAREHOUSE | 2026-06-12 | LAND | [6 empty] | 2026-06-16 | 2026-06-15 | TRUE |  | 32 | 4.5714
Received | Emilka Guerra | 2026-05-14 | PO08907 | SO19301 | 2026-06-02 | MBK400350-S625 | PoxyBlock Motor Mounting Blocks, ANSI: A90, A100, A110, A120, 14.50" Centerline | 1 | BaseTek, LLC | US | CA WAREHOUSE | 2026-06-12 | LAND | [6 empty] | 2026-06-16 | 2026-06-15 | TRUE |  | 32 | 4.5714
Received | Emilka Guerra | 2026-05-14 | PO08908 | SO19301 - WH/MO/00196 | 2026-05-28 | FS-61407M25 | Single Cartridge Seal, 2 1/2", VBSMSX3, Big/Taper Bore w/Shaft Sleeve, Silicon vs Silicon Carbide / FKM | 1 | Flexaseal Engineered Seals and Systems, LLC | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2026-06-04 | 2026-06-01 | TRUE |  | 18 | 2.5714
Received | Emilka Guerra | 2026-05-15 | PO08909 | SO19279 & Stock | 2026-06-12 | M48x200MM 8.8GR | Throatbush Set Screw - Pusher, 650 MCR | 10 | Super Cast Limited | China | CA WAREHOUSE | 2026-05-23 | AIR | ETA Missisauga: May 27, 2026. |  | DHL waybill (1890189921) |  | left Shijiazhuang for Mississauga via DHL on May 23, 2026 |  | 2026-06-26 | 2026-06-01 | TRUE |  | 17 | 2.4286
DELAYED PRODUCTION | Emilka Guerra | 2026-05-15 | PO08910 | SO19279 | 2026-06-15 | G-090407-4 1203 | Impeller w/Balance Holes, 2x3-10, 3196 MTX, 316SS, 5-Vane | 1 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND |  |  |  | June 16th: Follow up email for inclusion on a second shipment |  |  | 2026-06-30 |  | FALSE |  | -46157 | -6593.8571
DELAYED PRODUCTION | Emilka Guerra | 2026-05-15 | PO08910 | SO19279 | 2026-06-15 | G-090407-4-1013 | Impeller w/Balance Holes, 2x3-10, 3196 MTX, Ductile Iron, 5-Vane | 1 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND |  |  |  | June 16th: Follow up email for inclusion on a second shipment |  |  | 2026-06-30 |  | FALSE |  | -46157 | -6593.8571
In Production | Carlos Leon | 2026-05-15 | PO08911 | SO19322 | 2026-07-03 | W-T076/C21 | Shaft Sleeve Long, 20/18 TU-AH or 550/650 Type L, 420SS | 1 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-11 |  | FALSE |  | -46157 | -6593.8571
In Production | Carlos Leon | 2026-05-15 | PO08911 | SO19322 | 2026-07-03 | W-UL55018M/R55 | Cover Plate Liner, 550 TU-L, Natural Rubber | 1 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-11 |  | FALSE |  | -46157 | -6593.8571
In Production | Carlos Leon | 2026-05-15 | PO08911 | SO19322 | 2026-07-03 | W-U55041M/R55 | Frame Plate Liner Insert, 550 TU-L, Natural Rubber | 1 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-11 |  | FALSE |  | -46157 | -6593.8571
In Production | Carlos Leon | 2026-05-15 | PO08911 | SO19322 | 2026-07-03 | W-UL55083M/R55 | Throat Bushing, 550 TU-L, Natural Rubber | 1 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-11 |  | FALSE |  | -46157 | -6593.8571
In Production | Carlos Leon | 2026-05-15 | PO08911 | SO19322 | 2026-07-03 | W-UL55043M/R55 | Frame Plate Liner, 550 TU-L, Natural Rubber | 1 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-11 |  | FALSE |  | -46157 | -6593.8571
In Production | Emilka Guerra | 2026-05-15 | PO08912 | SO19326 | 2026-06-12 | 10009/0512 | Shaft, 150FY-40, 316LSS | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-08-28 |  | FALSE |  | -46157 | -6593.8571
In Production | Ian Trottier | 2026-05-15 | PO08913 | SO19322 | 2026-07-22 | W-TUL55147DP1/A05 | Impeller, 5 VCG, Duty Point, No Back Vanes, 550 TU-L, High Chrome | 1 | Shijiazhuang Mets Machinery Co., LTD | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-30 |  | FALSE |  | -46157 | -6593.8571
In Production | Emilka Guerra | 2026-05-18 | PO08914 | SO19327 | 2026-08-10 | G-243-90 1203 | Impeller, 6x8-13, 3171-L, 316SS | 1 | M&N Alloy Cast Products, Inc. | US | MX WAREHOUSE |  | LAND | [6 empty] | 2026-08-24 |  | FALSE |  | -46160 | -6594.2857
In Production | Emilka Guerra | 2026-05-18 | PO08915 | SO19329 | 2026-06-29 | SZ-2837900133-1 | Shaft, Sulzer | 5 | Super Cast Limited | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-07 |  | FALSE |  | -46160 | -6594.2857
In Production | Emilka Guerra | 2026-05-18 | PO08915 | SO19329 | 2026-06-29 | SZ-9321480153 | Bearing Housing, Sulzer | 2 | Super Cast Limited | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-07 |  | FALSE |  | -46160 | -6594.2857
In Production | Emilka Guerra | 2026-05-18 | PO08915 | SO19329 | 2026-06-29 | SZ-EL1208506M | Deflector, Sulzer | 20 | Super Cast Limited | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-07 |  | FALSE |  | -46160 | -6594.2857
In Production | Emilka Guerra | 2026-05-18 | PO08915 | SO19329 | 2026-06-29 | SZ-9268290131 | Labyrinth Ring, Sulzer | 10 | Super Cast Limited | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-07 |  | FALSE |  | -46160 | -6594.2857
In Production | Emilka Guerra | 2026-05-18 | PO08916 | SO19331 | 2026-07-06 | DC-MS000021 | Mechanical Seal, Dynapro Vertical Turbine, 12RJHC-8, A20 | 10 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-07 |  | FALSE |  | -46160 | -6594.2857
In Production | Emilka Guerra | 2026-05-18 | PO08916 | SO19331 | 2026-07-06 | 10061/0505 | Impeller Shaft, 18BHC-1, 316SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-07 |  | FALSE |  | -46160 | -6594.2857
In Production | Emilka Guerra | 2026-05-18 | PO08916 | SO19331 | 2026-07-06 | 10062/0505 | Impeller Collect, 18BHC-1, 316SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-07 |  | FALSE |  | -46160 | -6594.2857
In Production | Emilka Guerra | 2026-05-18 | PO08916 | SO19331 | 2026-07-06 | 10009/0512 | Shaft, 150FY-40, 316LSS | 2 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-07 |  | FALSE |  | -46160 | -6594.2857
In Production | Ian Trottier | 2026-05-19 | PO08917 |  | 2026-07-06 | AC-98-211-426-503 | Impeller, 2x2-10 SRL, Neoprene | 1 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-28 |  | FALSE |  | -46161 | -6594.4286
In Production | Ian Trottier | 2026-05-19 | PO08917 |  | 2026-07-06 | AC-98-231-055-503 | Gland Side Liner, 2x2-10 SRL, Neoprene | 1 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-28 |  | FALSE |  | -46161 | -6594.4286
In Production | Emilka Guerra | 2026-05-20 | PO08918 | SO19288 | 2026-06-24 | W-G10018M/R55 | Cover Plate Liner, 12/10 F or ST-AH, Natural Rubber | 1 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-09 |  | FALSE |  | -46162 | -6594.5714
In Production | Emilka Guerra | 2026-05-20 | PO08918 | SO19288 | 2026-06-24 | W-G10036M/R55 | Frame Plate Liner, 12/10 ST-AH, Natural Rubber | 1 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-09 |  | FALSE |  | -46162 | -6594.5714
In Production | Ian Trottier | 2026-05-20 | PO08919 | SO19342 | 2026-06-01 | W-T044/C02 | Gland Split w/Bolt & Nut, 20/18 TU-AH, Ni-Resist | 2 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-24 |  | FALSE |  | -46162 | -6594.5714
In Production | Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10671/0504 | Cartridge Mechanical Seal, 16DMC-4, 304SS | 2 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-01 |  | FALSE |  | -46163 | -6594.7143
In Production | Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10672/0526 | Coupling, 16DMC-4, 416SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-01 |  | FALSE |  | -46163 | -6594.7143
In Production | Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10673/2001 | Adjusting Nut, 16DMC-4, Cast Iron | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-01 |  | FALSE |  | -46163 | -6594.7143
In Production | Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10674/0526 | Motor Shaft, 16DMC-4, 416SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-01 |  | FALSE |  | -46163 | -6594.7143
In Production | Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10675/0504 | Stuffing Box Hex Bolts and Spring Washers, 16DMC-4, 304SS | 6 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-01 |  | FALSE |  | -46163 | -6594.7143
In Production | Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10676/0504 | Stuffing Box Bearing Retaining Ring, 16DMC-4, 304SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-01 |  | FALSE |  | -46163 | -6594.7143
In Production | Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10677/5001 | Stuffing Box Bearing,16DMC-4, Teflon | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-01 |  | FALSE |  | -46163 | -6594.7143
In Production | Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10680/0504 | Discharge Head Hex Bolts and Spring Washers, 16DMC-4, 304SS | 12 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-01 |  | FALSE |  | -46163 | -6594.7143
In Production | Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10681/5010 | Inlet Flange Paper Gasket, 16DMC-4, - | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-01 |  | FALSE |  | -46163 | -6594.7143
In Production | Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10683/0526 | Lineshaft, 16DMC-4, 416SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-01 |  | FALSE |  | -46163 | -6594.7143
In Production | Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10684/0504 | Spider Bearing Retaining Ring, 16DMC-4, 304SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-01 |  | FALSE |  | -46163 | -6594.7143
In Production | Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10685/5001 | Spider Bearing, 16DMC-4, Teflon | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-01 |  | FALSE |  | -46163 | -6594.7143
In Production | Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10687/0526 | Coupling, 16DMC-4, 416SS | 2 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-01 |  | FALSE |  | -46163 | -6594.7143
In Production | Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10688/0526 | Lower Lineshaft, 16DMC-4, 416SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-01 |  | FALSE |  | -46163 | -6594.7143
In Production | Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10690/0504 | Discharge Bowl Hex Bolts, Spring Washers and Nuts, 16DMC-4, 304SS | 8 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-01 |  | FALSE |  | -46163 | -6594.7143
In Production | Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10691/0504 | Intermediate Bowl Hex Bolts and Spring Washers, 16DMC-4, 304SS | 32 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-01 |  | FALSE |  | -46163 | -6594.7143
In Production | Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10692/0526 | Impeller Shaft, 16DMC-4, 416SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-01 |  | FALSE |  | -46163 | -6594.7143
In Production | Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10693/0504 | Discharge Bowl Bearing Retaining Ring, 16DMC-4, 304SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-01 |  | FALSE |  | -46163 | -6594.7143
In Production | Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10694/5001 | Discharge Bowl Bearing, 16DMC-4, Teflon | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-01 |  | FALSE |  | -46163 | -6594.7143
In Production | Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10696/0504 | Impeller Collect Hex Bolts and Spring Washers, 16DMC-4, 304SS | 16 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-01 |  | FALSE |  | -46163 | -6594.7143
In Production | Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10697/0505 | Impeller Collect, 16DMC-4, 316SS | 4 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-01 |  | FALSE |  | -46163 | -6594.7143
In Production | Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10698/0505 | Impeller, 16DMC-4, 316SS | 4 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-01 |  | FALSE |  | -46163 | -6594.7143
In Production | Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10699/0504 | Intermediate Bowl Bearing Retaining Ring, 16DMC-4, 304SS | 3 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-01 |  | FALSE |  | -46163 | -6594.7143
In Production | Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10700/5001 | Intermediate Bowl Bearing, 16DMC-4, Teflon | 3 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-01 |  | FALSE |  | -46163 | -6594.7143
In Production | Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10702/3002 | Sand Collar, 16DMC-4, Bronze | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-01 |  | FALSE |  | -46163 | -6594.7143
In Production | Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10703/0504 | Suction Bell Hex Bolts and Spring Washers, 16DMC-4, 304SS | 6 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-01 |  | FALSE |  | -46163 | -6594.7143
In Production | Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10704/0504 | Suction Bell Bearing Retaining Ring, 16DMC-4, 304SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-01 |  | FALSE |  | -46163 | -6594.7143
In Production | Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10705/5001 | Suction Bowl Bearing, 16DMC-4, Teflon | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-01 |  | FALSE |  | -46163 | -6594.7143
In Production | Ian Trottier | 2026-05-21 | PO08921 | SO19347 | 2026-07-02 | AC-98-432-882-504 | Shaft, PWO, Frame 2, 317SS | 1 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2026-05-22 |  | FALSE |  | -46163 | -6594.7143
In Production | Ian Trottier | 2026-05-21 | PO08921 | SO19347 | 2026-07-02 | AC-98-130-366-012 | Shaft Sleeve, PWO Frame 1, 317SS | 1 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2026-05-22 |  | FALSE |  | -46163 | -6594.7143
In Production | Emilka Guerra | 2026-05-21 | PO08922 | SO19345 | 2026-08-13 | SA-572855 | Impeller, Sala, STGVA-65W, High Chrome | 2 | Dexhor | Other | CA WAREHOUSE |  | LAND | [6 empty] | 2026-08-27 |  | FALSE |  | -46163 | -6594.7143
In Production | Emilka Guerra | 2026-05-21 | PO08923 | Stock | 2026-07-03 | AC-98-330-286-501 | Impeller (Open), 3x3-10 SRL, Natural Rubber | 12 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-11 |  | FALSE |  | -46163 | -6594.7143
In Production | Emilka Guerra | 2026-05-21 | PO08923 | Stock | 2026-07-03 | AC-98-231-071-501 | Suction Side Liner, 3x3-10 SRL, Natural Rubber | 6 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-11 |  | FALSE |  | -46163 | -6594.7143
In Production | Emilka Guerra | 2026-05-21 | PO08923 | Stock | 2026-07-03 | AC-98-231-070-501 | Gland Side Liner, 3x3-10 SRL, Natural Rubber | 3 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-11 |  | FALSE |  | -46163 | -6594.7143
In Production | Emilka Guerra | 2026-05-21 | PO08923 | Stock | 2026-07-03 | M16x55, W-E045M/C23 | Gland Bolt w/Nut & Washer, 6/4 or 8/6 E-AH and 8/6 R-AH, 316SS | 11 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-11 |  | FALSE |  | -46163 | -6594.7143
In Production | Emilka Guerra | 2026-05-21 | PO08923 | Stock | 2026-07-03 | AC-98-234-265-001 | Waterseal Bushing, 8x6-18 & 10x8-21 SRL-C, 316SS | 5 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-11 |  | FALSE |  | -46163 | -6594.7143
In Production | Emilka Guerra | 2026-05-21 | PO08923 | Stock | 2026-07-03 | AC-98-431-651-501 | Impeller (Closed), 8x6-18 SRL-C, Natural Rubber | 6 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-11 |  | FALSE |  | -46163 | -6594.7143
In Production | Emilka Guerra | 2026-05-21 | PO08923 | Stock | 2026-07-03 | AC-98-331-926-801 | Bearing Cover (Outboard), 5x4/5x5/6x6 SRL & SRL-C, Cast Iron | 2 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-11 |  | FALSE |  | -46163 | -6594.7143
In Production | Emilka Guerra | 2026-05-21 | PO08923 | Stock | 2026-07-03 | AC-98-231-134-501 | Suction Side Liner, 10x8-21 SRL-C, Natural Rubber | 6 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-11 |  | FALSE |  | -46163 | -6594.7143
In Production | Emilka Guerra | 2026-05-21 | PO08923 | Stock | 2026-07-03 | SA-013733-M1 | Wear Disc, 44 WFR, Sala STGVA-180, Steel, Rubber Lined | 70 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-11 |  | FALSE |  | -46163 | -6594.7143
In Production | Emilka Guerra | 2026-05-21 | PO08923 | Stock | 2026-07-03 | W-SL30083M/A05 | Throatbush, 300 RSL, High Chrome | 2 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-11 |  | FALSE |  | -46163 | -6594.7143
In Production | Emilka Guerra | 2026-05-21 | PO08923 | Stock | 2026-07-03 | W-SP10116L/D21 | Lower Strainer, 100RV-SP, Ductile Iron | 1 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-11 |  | FALSE |  | -46163 | -6594.7143
Ready to Ship | Emilka Guerra | 2026-05-21 | PO08924 | Stock | 2026-07-03 | G-R102-814 1013 | Frame Adapter, 15", 3196 XLT, Ductile Iron | 2 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA |  |  | DYNC-119 SEA |  |  |  | 2026-09-11 |  | FALSE |  | -46163 | -6594.7143
In Production | Emilka Guerra | 2026-05-21 | PO08924 | Stock | 2026-07-03 | RC04064A01 1216 | Stuffing Box Cover, 15", 3196 XLT, CD4MCu, Big Bore, Non-Jacketed | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-11 |  | FALSE |  | -46163 | -6594.7143
Ready to Ship | Emilka Guerra | 2026-05-21 | PO08924 | Stock | 2026-07-03 | G-0256-122 1216 | Impeller, 8x10-15G, 3196 XLT, CD4MCu | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA |  |  | DYNC-119 SEA |  |  |  | 2026-09-11 |  | FALSE |  | -46163 | -6594.7143
In Production | Emilka Guerra | 2026-05-21 | PO08924 | Stock | 2026-07-03 | G-256-65 1216 | Casing, 8x10-15G, 3196 XLT, CD4MCu | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-11 |  | FALSE |  | -46163 | -6594.7143
Ready to Ship | Emilka Guerra | 2026-05-21 | PO08924 | Stock | 2026-07-03 | G-102-913 1001 | Frame Foot, 3196 XLT, Cast Iron | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA |  |  | DYNC-119 SEA |  |  |  | 2026-09-11 |  | FALSE |  | -46163 | -6594.7143
Ready to Ship | Emilka Guerra | 2026-05-21 | PO08924 | Stock | 2026-07-03 | DU-MY36862A100-CD4 | Impeller, 3x2-10, Durco Mark 2 Group 2, CD4MCu, Reverse Vane | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA |  |  | DYNC-119 SEA |  |  |  | 2026-09-11 |  | FALSE |  | -46163 | -6594.7143
In Production | Emilka Guerra | 2026-05-21 | PO08924 | Stock | 2026-07-03 | DU-DY33074A-CD4 | Casing, 6x4-13A, Durco Mark 2&3 Group 2, CD4MCu | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-11 |  | FALSE |  | -46163 | -6594.7143
In Production | Emilka Guerra | 2026-05-21 | PO08925 | Stock | 2026-07-03 | AC-98-431-849-001 | Suction Side Casing, 3x3-10 SRL, Cast Iron | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-11 |  | FALSE |  | -46163 | -6594.7143
In Production | Emilka Guerra | 2026-05-21 | PO08925 | Stock | 2026-07-03 | W-SP10041/A05 | Back Liner, 100RV-SP, High Chrome | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-11 |  | FALSE |  | -46163 | -6594.7143
In Production | Emilka Guerra | 2026-05-21 | PO08926 | Stock | 2026-08-14 | AC-98-431-676-501 | Gland Side Casing, 10x8-21 SRL-C, Cast Iron | 1 | IGH | Mexico | CA WAREHOUSE |  | LAND | [6 empty] | 2026-09-11 |  | FALSE |  | -46163 | -6594.7143
Ready to Ship & Delayed | Emilka Guerra | 2026-05-21 | PO08927 | Stock | 2026-05-29 | G-73078 5130 | Frame Adapter Gasket, 3196 MTX, LTX, & XLT Vellumoid | 6 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-06-16 | LAND | ETA WAREHOUSE 3rd week of JUNE |  |  |  | Quenton Hisco 06/16: Ready to ship - Pending Pick up confirmation by logistics |  | 2026-06-12 |  | FALSE |  | -46163 | -6594.7143
Ready to Ship & Delayed | Emilka Guerra | 2026-05-21 | PO08927 | Stock | 2026-05-29 | GO351-9607-NSN, G-70782 49 5127 | Casing Gasket, 15", 3196 XLT | 5 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-06-16 | LAND | ETA WAREHOUSE 3rd week of JUNE |  |  |  | Quenton Hisco 06/16: Ready to ship - Pending Pick up confirmation by logistics |  | 2026-06-12 |  | FALSE |  | -46163 | -6594.7143
Ready to Ship & Delayed | Ian Trottier | 2026-05-22 | PO08928 | SO19350 | 2026-06-03 | AH-283794-0133 | Shaft, Ahlstrom APT, Frame 4, 17-4 PH | 1 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-06-16 | LAND | ETA WAREHOUSE 3rd week of JUNE |  |  |  | Quenton Hisco 06/16: Ready to ship - Pending Pick up confirmation by logistics |  | 2026-06-10 |  | FALSE |  | -46164 | -6594.8571
In Production | Amanda Qiao | 2026-05-22 | PO08929 | SO19068 | 2026-07-22 | VI-GLH-H25-WM | Mag Drive Gear Pump, Micropump GLH-H25, With Motor | 2 | Vissers Sales Corp. | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2026-07-24 |  | FALSE |  | -46164 | -6594.8571
DELAYED PRODUCTION | Emilka Guerra | 2026-05-25 | PO08930 | SO19332 | 2026-06-08 | G-B02188A04 6308 | Lantern Ring, 3180 XL, Teflon | 1 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND |  |  |  | June 16th: Follow up email for inclusion on a second shipment |  |  | 2026-06-29 |  | FALSE |  | -46167 | -6595.2857
DELAYED PRODUCTION | Emilka Guerra | 2026-05-25 | PO08930 | SO19332 | 2026-06-08 | G-C03241A 1226 | Shaft Sleeve, 3180-XL, 316SS, Packed Box | 1 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND |  |  |  | June 16th: Follow up email for inclusion on a second shipment |  |  | 2026-06-29 |  | FALSE |  | -46167 | -6595.2857
DELAYED PRODUCTION | Emilka Guerra | 2026-05-25 | PO08930 | SO19332 | 2026-06-08 | 383 Viton | Suction Side Plate O-Ring, 3180-XL, Viton | 1 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND |  |  |  | June 16th: Follow up email for inclusion on a second shipment |  |  | 2026-06-29 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-1J2311-1 | Casing, 2x3-11, Goulds JC, Frame 1J, Cast Iron, OEM# 055891G0001002 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-1J2311-4 | Casing, 2x3-11, Goulds JC, Frame 1J, CD4MCu, OEM# 055891G0001247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-1J2311-5 | Suction Cover Liner, 2x3-11, Goulds JC, Frame 1J, Cast Iron, OEM# 048940G0001002 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D1J2311-6 | Suction Cover Liner, 2x3-11, Goulds JC, Frame 1J, High Chrome, OEM# 048940G0001228 | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-1J2311-8 | Suction Cover Liner, 2x3-11, Goulds JC, Frame 1J, CD4MCu, OEM# 048940G0001247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-1J2311-9 | Impeller, 2x3-11, Goulds JC, Frame 1J, Cast Iron, OEM# 056189G2601002 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-1J2311-10 | Impeller, 2x3-11, Goulds JC, Frame 1J, High Chrome, OEM# 056189G2601228 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-1J2311-12 | Impeller, 2x3-11, Goulds JC, Frame 1J, CD4MCu, OEM# 056189G2601247 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-1J2311-13 | Suction Cover, 2x3-11, Goulds JC, Frame 1J, Cast Iron, OEM# 050387G0001002 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-1J2311-14 | Suction Cover, 2x3-11, Goulds JC, Frame 1J, High Chrome, OEM# 050387G0001228 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-1J2311-16 | Suction Cover, 2x3-11, Goulds JC, Frame 1J, CD4MCu, OEM# 050387G0001247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-1J11511-6 | Suction Cover Liner, 1x1.5-11, Goulds JC, Frame 1J, High Chrome, OEM# 048935G0001228 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-1J11511-10 | Impeller, 1x1.5-11, Goulds JC, Frame 1J, High Chrome, OEM# 056185G4701228 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-1J11511-14 | Suction Cover, 1x1.5-11, Goulds JC, Frame 1J, High Chrome, OEM# 050385G0001228 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-WE1J-7 | Stuffing Box Cover, Goulds JC, Frame 1J, Cast Iron, OEM# 048945G0001002 | 6 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-WE1J-8 | Stuffing Box Cover, Goulds JC, Frame 1J, High Chrome, OEM# 048945G0001228 | 6 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-WE1J-10 | Stuffing Box Cover, Goulds JC, Frame 1J, CD4MCu, OEM# 048945G0001247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J15214-4 | Casing, 1.5x2-14, Goulds JC, Frame 2J, CD4MCu, OEM# 055892G0001247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J15214-5 | Suction Cover Liner, 1.5x2-14, Goulds JC Frame 2J, Cast Iron, OEM# 048938G0001002 | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J15214-6 | Suction Cover Liner, 1.5x2-14, Goulds JC Frame 2J, High Chrome, OEM# 048938G0001228 | 9 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J15214-8 | Suction Cover Liner, 1.5x2-14, Goulds JC Frame 2J, CD4MCu, OEM# 048938G0001247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J15214-9 | Impeller, 1.5x2-14, Goulds JC, Frame 2J, Cast Iron, OEM# 056189G2501002 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J15214-10 | Impeller, 1.5x2-14, Goulds JC, Frame 2J, High Chrome, OEM# 056189G2501228 | 6 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J15214-13 | Suction Cover, 1.5x2-14, Goulds JC Frame 2J, Cast Iron, OEM# 050049G0001002 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J15214-14 | Suction Cover, 1.5x2-14, Goulds JC Frame 2J, High Chrome, OEM# 050049G0001228 | 9 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J15214-16 | Suction Cover, 1.5x2-14, Goulds JC Frame 2J, CD4MCu, OEM# 050049G0001247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J2314-4 | Casing, 2x3-14, Goulds JC, Frame 2J, CD4MCu, OEM# 056190G6601247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J2314-5 | Suction Cover Liner, 2x3-14, Goulds JC, Frame 2J, Cast Iron, OEM# 048941G0001002 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J2314-6 | Suction Cover Liner, 2x3-14, Goulds JC, Frame 2J, High Chrome, OEM# 048941G0001228 | 14 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J2314-8 | Suction Cover Liner, 2x3-14, Goulds JC, Frame 2J, CD4MCu, OEM# 048941G0001247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J2314-9 | Impeller, 2x3-14, Goulds JC, Frame 2J, Cast Iron, OEM# 056189G6701002 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J2314-10 | Impeller, 2x3-14, Goulds JC, Frame 2J, High Chrome, OEM# 056189G6701228 | 7 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J2314-13 | Suction Cover, 2x3-14, Goulds JC, Frame 2J, Cast Iron, OEM# 050388G0001002 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J2314-14 | Suction Cover, 2x3-14, Goulds JC, Frame 2J, High Chrome, OEM# 050388G0001228 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J3411-1 | Casing, 3x4-11, Goulds JC, Frame 2J, Cast Iron, OEM#056185G4011002 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J3411-6 | Suction Cover Liner, 3x4-11, Goulds JC, Frame 2J, High Chrome, OEM# 048824G0001228 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J3411-12 | Impeller, 3x4-11, Goulds JC, Frame 2J, CD4MCu, OEM# 056185G4201247 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J3411-14 | Suction Cover, 3x4-11, Goulds JC, Frame 2J, High Chrome, OEM# 048825G0001228 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-WE2J-7 | Stuffing Box Cover, Goulds JC, Frame 2J, Cast Iron, OEM# 048877G0001002 | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-WE2J-8 | Stuffing Box Cover, Goulds JC, Frame 2J, High Chrome, OEM# 048877G0001228 | 8 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-WE2J-10 | Stuffing Box Cover, Goulds JC, Frame 2J, CD4MCu, OEM# 048877G0001247 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J4614-1 | Casing, 4x6-14, Goulds JC, Frame 3J, Cast Iron, OEM# 056185G1801002 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J4614-4 | Casing, 4x6-14, Goulds JC, Frame 3J, CD4MCu, OEM# 056185G1801247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J4614-5 | Suction Cover Liner, 4x6-14, Goulds JC, Frame 3J, Cast Iron, OEM# 048944G0001002 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J4614-6 | Suction Cover Liner, 4x6-14, Goulds JC, Frame 3J, High Chrome, OEM# 048944G0001228 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J4614-10 | Impeller, 4x6-14, Goulds JC, Frame 3J, High Chrome, OEM# 056185G1401228 | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J4614-13 | Suction Cover, 4x6-14, Goulds JC, Frame 3J, Cast Iron, OEM# 048933G0001002 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J4614-14 | Suction Cover, 4x6-14, Goulds JC, Frame 3J, High Chrome, OEM# 048933G0001228 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J4614-16 | Suction Cover, 4x6-14, Goulds JC, Frame 3J, CD4MCu, OEM# 048933G0001247 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J3414-1 | Casing, 3x4-14, Goulds JC, Frame 3J, Cast Iron, OEM# 056190G7801002 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J3414-2 | Casing, 3x4-14, Goulds JC, Frame 3J, High Chrome, OEM# 056190G7801228 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J3414-4 | Casing, 3x4-14, Goulds JC, Frame 3J, CD4MCu, OEM# 056190G7801247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J3414-5 | Suction Cover Liner, 3x4-14, Goulds JC, Frame 3j, Cast Iron, OEM# 048943G0001002 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J3414-6 | Suction Cover Liner, 3x4-14, Goulds JC, Frame 3J, High Chrome, OEM# 048943G0001228 | 8 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J3414-8 | Suction Cover Liner, 3x4-14, Goulds JC, Frame 3J, CD4MCu, OEM# 048943G0001247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J3414-10 | Impeller, 3x4-14, Goulds JC, Frame 3J, High Chrome, OEM# 056190G7901228 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J3414-12 | Impeller, 3x4-14, Goulds JC, Frame 3J, CD4MCu, OEM# 056190G7901247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J3414-13 | Suction Cover, 3x4-14, Goulds JC, Frame 3J, Cast Iron, OEM# 048932G0001002 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J3414-14 | Suction Cover, 3x4-14, Goulds JC, Frame 3J, High Chrome, OEM# 048932G0001228 | 10 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J3414-16 | Suction Cover, 3x4-14, Goulds JC, Frame 3J, CD4MCu, OEM# 048932G0001247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-WE3J-7 | Stuffing Box Cover, Goulds JC, Frame 3J, Cast Iron, OEM# 048946G0001002 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-WE3J-8 | Stuffing Box Cover, Goulds JC, Frame 3J, High Chrome, OEM# 048946G0001228 | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-WE3J-10 | Stuffing Box Cover, Goulds JC, Frame 3J, CD4MCu, OEM# 048946G0001247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-4J81018-6 | Suction Cover Liner, 8x10-18, Goulds JC, Frame 4J, High Chrome | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-4J81018-10 | Impeller, 8x10-18, Goulds JC, Frame 4J, High Chrome, OEM #056185G8601228 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Ian Trottier | 2026-05-26 | PO08932 | SO19365 | 2026-07-21 | AC-52-224-289-005 | Shaft Sleeve, Allis-Chalmers CSO, Frame F4B3/F4B5/F4D1, XH-800 | 2 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND |  |  |  | Follow up for status first week of July |  |  | 2026-07-25 |  | FALSE |  | -46168 | -6595.4286
In Production | Emilka Guerra | 2026-05-26 | PO08933 | SO19374 | 2026-06-30 | D-500S-98B-16/C21 | Bearing Baffle, 500S-98B, 420SS | 6 | Super Cast Limited | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-07-21 |  | FALSE |  | -46168 | -6595.4286
Ready to Ship & Delayed | Emilka Guerra | 2026-05-27 | PO08935 | SO19319 | 2026-06-03 | WO-2103740-1 | Wear Plate, Worthington 4FRBH-141 | 1 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-06-16 | LAND | ETA WAREHOUSE 3rd week of JUNE |  |  |  | Quenton Hisco 06/16: Ready to ship - Pending Pick up confirmation by logistics |  | 2026-06-10 |  | FALSE |  | -46169 | -6595.5714
Received | Emilka Guerra | 2026-05-28 | PO08936 | Stock | 2026-06-11 | AC-98-234-802-001 | Water Seal Bushing, 12x10-25 SRL-C, One-Piece, Steel | 1 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2026-06-18 | 2026-06-09 | TRUE |  | 12 | 1.7143
Received | Emilka Guerra | 2026-05-28 | PO08936 | Stock | 2026-06-11 | AC-98-236-104-001 | Shaft Sleeve, 8x6-18 & 10x8-21 SRL-C, Steel | 1 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2026-06-18 | 2026-06-09 | TRUE |  | 12 | 1.7143
In Production | Emilka Guerra | 2026-05-28 | PO08936 | Stock | 2026-06-11 | AC-98-236-104-001 | Shaft Sleeve, 8x6-18 & 10x8-21 SRL-C, Steel | 1 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2026-06-18 |  | FALSE |  | -46170 | -6595.7143
Received | Emilka Guerra | 2026-05-28 | PO08937 | Stock | 2026-06-11 | 28VSMS3-04C4VS4 | Single Cartridge Seal, 1 3/4", VSMS, Standard Bore, Carbon vs Silicon Carbide / TFEP | 2 | Flexaseal Engineered Seals and Systems, LLC | Canada | CA WAREHOUSE | 2026-06-12 | LAND |  |  | 1ZAC76466631821670 |  |  |  | 2026-06-25 | 2026-06-15 | TRUE |  | 18 | 2.5714
In Production | Emilka Guerra | 2026-05-28 | PO08938 | Stock | 2026-07-09 | AC-98-231-115-501 | Suction Side Liner, 5x4-14 SRL-C, Natural Rubber | 8 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-17 |  | FALSE |  | -46170 | -6595.7143
In Production | Emilka Guerra | 2026-05-28 | PO08939 | Stock | 2026-07-09 | AC-98-431-851-501 | Gland Side Casing, 3x3-10 SRL, Cast Iron | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-17 |  | FALSE |  | -46170 | -6595.7143
In Production | Emilka Guerra | 2026-05-28 | PO08939 | Stock | 2026-07-09 | AC-98-431-768-501 | Shaft Assembly, 8x6-18 SRL-C, 1045 Steel | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-17 |  | FALSE |  | -46170 | -6595.7143
Received | Emilka Guerra | 2026-05-28 | PO08940 | Stock | 2026-06-18 | AC-98-233-700-002 | Bearing Cover Gasket (Inboard & Outboard), 5x4/5x5/6x6 SRL & SRL-C | 20 | NC Industrial | US | CA WAREHOUSE | 2026-06-03 | LAND | [6 empty] | 2026-06-25 | 2026-06-11 | TRUE |  | 14 | 2
In Production | Emilka Guerra | 2026-05-28 | PO08941 | SO19384 & Stock | 2026-07-09 | AC-98-331-958-809 | Shaft Sleeve, 3x3-10 SRL & SRL-C, 316SS | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-17 |  | FALSE |  | -46170 | -6595.7143
Ready to Ship | Emilka Guerra | 2026-05-28 | PO08941 | SO19384 & Stock | 2026-07-09 | DU-DY21806ACP-DI | Adapter (Bearing Housing), 10", Durco Mark 2&3 Group 2, Ductile Iron | 2 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA |  |  | DYNC-119 SEA |  |  |  | 2026-09-17 |  | FALSE |  | -46170 | -6595.7143
In Production | Emilka Guerra | 2026-05-28 | PO08942 | Stock | 2026-07-23 | DE-504978 | Impeller, 10x8-21, Denver SRL-C, Natural Rubber | 2 | IGH | Mexico | CA WAREHOUSE |  | LAND | [6 empty] | 2026-08-20 |  | FALSE |  | -46170 | -6595.7143
Received | Emilka Guerra | 2026-05-28 | PO08943 | SO19378 | 2026-06-18 | AC-98-331-958-810 | Shaft Sleeve, 2x2-10 SRL, 316SS | 3 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2026-06-25 | 2026-06-09 | TRUE |  | 12 | 1.7143
Received | Emilka Guerra | 2026-05-28 | PO08943 | SO19378 | 2026-06-18 | AC-98-331-958-804 | Shaft Sleeve, 3x3-10 SRL, Steel | 3 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2026-06-25 | 2026-06-09 | TRUE |  | 12 | 1.7143
In Production | Emilka Guerra | 2026-05-28 | PO08943 | SO19378 | 2026-06-18 | AC-98-331-958-804 | Shaft Sleeve, 3x3-10 SRL, Steel | 5 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2026-06-25 |  | FALSE |  | -46170 | -6595.7143
Received | Emilka Guerra | 2026-05-28 | PO08943 | SO19378 | 2026-06-18 | AC-98-233-813-001 | Neck Bushing, 5x4/5x5/6x6 SRL & SRL-C | 4 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2026-06-25 | 2026-06-09 | TRUE |  | 12 | 1.7143
In Production | Emilka Guerra | 2026-05-28 | PO08943 | SO19378 | 2026-06-18 | AC-98-331-958-804 | Shaft Sleeve, 3x3-10 SRL, Steel | 3 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2026-06-25 |  | FALSE |  | -46170 | -6595.7143
In Production | Ian Trottier | 2026-05-28 | PO08944 | SO19372 | 2026-09-03 | AC-52-222-350-503 | Stuffing Box Cover, Jacketed, 10", CSO F4B3, Cast Iron | 1 | Advanced Engineered Pump Inc. | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2026-05-29 |  | FALSE |  | -46170 | -6595.7143
In Production | Ian Trottier | 2026-05-29 | PO08945 | Stock | 2026-07-14 | AC-SRL 5x4-14-C | Pump, AC-SRL 5x4-14-C, Natural Rubber Lined, Motor Mounting Plate, Belt Guard | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-10-06 |  | FALSE |  | -46171 | -6595.8571
In Production | Ian Trottier | 2026-05-29 | PO08946 | SO19365 | 2026-06-12 | AC-52-109-019-018 | Shaft Sleeve, Allis-Chalmers CSO, Frame F4B3/F4B5/F4D1, Monel | 1 | Renewal Services Inc. | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2026-06-26 |  | FALSE |  | -46171 | -6595.8571
In Production | Ian Trottier | 2026-05-29 | PO08947 | SO19365 | 2026-07-24 | AC-52-224-289-005 | Shaft Sleeve, Allis-Chalmers CSO, Frame F4B3/F4B5/F4D1, XH-800 | 2 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND |  |  |  | Follow up for status first week of July |  |  | 2026-08-04 |  | FALSE |  | -46171 | -6595.8571
Received | Emilka Guerra | 2026-06-01 | PO08948 | SO19378 | 2026-06-16 | AC-98-231-116-504 | Gland Side Liner, 5x4-14 SRL-C, Hypalon | 4 | Seal X Supply Inc. | Canada | CA WAREHOUSE | 2026-06-10 | LAND |  |  | Manitoulin 3304720919 |  | Christine: his shipment (1 Skid) will ETA our warehouse this week. 2nd week of June |  | 2026-06-30 | 2026-06-12 | TRUE |  | 11 | 1.5714
In Production | Emilka Guerra | 2026-06-01 | PO08949 | SO19378 | 2026-08-10 | AC-98-231-055-508 | Gland Side Liner, 2x2-10 SRL, Urethane | 3 | IGH | Mexico | CA WAREHOUSE |  | LAND | [6 empty] | 2026-09-07 |  | FALSE |  | -46174 | -6596.2857
In Production | Emilka Guerra | 2026-06-01 | PO08949 | SO19378 | 2026-08-10 | AC-98-231-054-508 | Suction Side Liner, 2x2-10 SRL, Urethane | 3 | IGH | Mexico | CA WAREHOUSE |  | LAND | [6 empty] | 2026-09-07 |  | FALSE |  | -46174 | -6596.2857
In Production | Emilka Guerra | 2026-06-01 | PO08949 | SO19378 | 2026-08-10 | AC-98-211-426-508 | Impeller, 2x2-10 SRL, Urethane | 3 | IGH | Mexico | CA WAREHOUSE |  | LAND | [6 empty] | 2026-09-07 |  | FALSE |  | -46174 | -6596.2857
In Production | Emilka Guerra | 2026-06-01 | PO08949 | SO19378 | 2026-08-10 | AC-98-330-286-508 | Impeller (Open), 3x3-10 SRL, Urethane | 6 | IGH | Mexico | CA WAREHOUSE |  | LAND | [6 empty] | 2026-09-07 |  | FALSE |  | -46174 | -6596.2857
In Production | Emilka Guerra | 2026-06-01 | PO08949 | SO19378 | 2026-08-10 | AC-98-231-109-506 | Gland Side Liner, 3x3-10 SRL-C, Urethane | 3 | IGH | Mexico | CA WAREHOUSE |  | LAND | [6 empty] | 2026-09-07 |  | FALSE |  | -46174 | -6596.2857
In Production | Emilka Guerra | 2026-06-01 | PO08949 | SO19378 | 2026-08-10 | AC-98-231-070-507 | Gland Side Liner, 3x3-10 SRL, Urethane | 7 | IGH | Mexico | CA WAREHOUSE |  | LAND | [6 empty] | 2026-09-07 |  | FALSE |  | -46174 | -6596.2857
In Production | Emilka Guerra | 2026-06-01 | PO08949 | SO19378 | 2026-08-10 | AC-98-231-071-507 | Suction Side Liner, 3x3-10 SRL, Urethane | 6 | IGH | Mexico | CA WAREHOUSE |  | LAND | [6 empty] | 2026-09-07 |  | FALSE |  | -46174 | -6596.2857
In Production | Emilka Guerra | 2026-06-01 | PO08949 | SO19378 | 2026-08-10 | AC-98-231-108-506 | Suction Side Liner, 3x3-10 SRL-C, Urethane | 3 | IGH | Mexico | CA WAREHOUSE |  | LAND | [6 empty] | 2026-09-07 |  | FALSE |  | -46174 | -6596.2857
In Production | Emilka Guerra | 2026-06-01 | PO08949 | SO19378 | 2026-08-10 | AC-98-330-307-506 | Impeller (Closed), 3x3-10 SRL-C, Urethane | 2 | IGH | Mexico | CA WAREHOUSE |  | LAND | [6 empty] | 2026-09-07 |  | FALSE |  | -46174 | -6596.2857
In Production | Emilka Guerra | 2026-06-01 | PO08950 | To be used in the building of the pumps on PO08945 | 2026-06-30 | AC-98-231-115-501 | Suction Side Liner, 5x4-14 SRL-C, Natural Rubber | 2 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-07-07 |  | FALSE |  | -46174 | -6596.2857
In Production | Emilka Guerra | 2026-06-01 | PO08950 | To be used in the building of the pumps on PO08945 | 2026-06-30 | AC-98-231-116-501 | Gland Side Liner, 5x4-14 SRL-C, Natural Rubber | 2 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-07-07 |  | FALSE |  | -46174 | -6596.2857
In Production | Emilka Guerra | 2026-06-01 | PO08950 | To be used in the building of the pumps on PO08945 | 2026-06-30 | AC-98-039-047-501 | Impeller (Closed), 5x4-14 SRL-C, Natural Rubber | 2 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-07-07 |  | FALSE |  | -46174 | -6596.2857
Received | Taylor Cook | 2026-06-01 | PO08952 | SO19180 | 2025-07-14 | AN18 | Bearing Lock Nut, 8x6-18 & 10x8-21 SRL-C, Steel | 6 | BDI Canada Inc. | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2026-06-01 | 2026-06-15 | TRUE |  | 14 | 2
Ready to Ship | Emilka Guerra | 2026-06-01 | PO08953 | SO19385 & Stock | 2026-06-22 | AC-98-234-128-001 | Bearing Gasket Cover (Inboard), 2x2-10 SRL | 5 | Specialty Gaskets Inc. | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2026-06-30 |  | FALSE |  | -46174 | -6596.2857
Ready to Ship | Emilka Guerra | 2026-06-01 | PO08953 | SO19385 & Stock | 2026-06-22 | AC-98-5414-HC7 | Suction Side Plate Gasket, 5x4-14 SRL-C, Rubber, 3-Piece Design | 1 | Specialty Gaskets Inc. | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2026-06-30 |  | FALSE |  | -46174 | -6596.2857
In Production | Emilka Guerra | 2026-06-01 | PO08954 | SO19385 | 2026-07-27 | AC-98-5414-HC3 | Suction Side Plate, 5x4-14 SRL-C, High Chrome, 3-Piece Design | 1 | IGH | Mexico | CA WAREHOUSE |  | LAND | [6 empty] | 2026-08-24 |  | FALSE |  | -46174 | -6596.2857
In Production | Emilka Guerra | 2026-06-01 | PO08955 | SO19378 | 2026-06-15 | AC-98-236-104-001 | Shaft Sleeve, 8x6-18 & 10x8-21 SRL-C, Steel | 5 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2026-06-29 |  | FALSE |  | -46174 | -6596.2857
In Production | Emilka Guerra | 2026-06-02 | PO08956 | SO19403 | 2026-08-11 | AC-98-5414-HC5 | Stuffing Box, 5x4-14 SRL-C, Cast Iron, 3-Piece Design | 1 | IGH | Mexico | CA WAREHOUSE |  | LAND | [6 empty] | 2026-09-01 |  | FALSE |  | -46175 | -6596.4286
Received | Emilka Guerra | 2026-06-02 | PO08957 | SO19391 | 2026-06-05 | AC-98-233-815-001 | Half Seal Cage, 5x4/5x5/6x6 SRL & SRL-C, Steel | 3 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2026-06-09 | 2026-06-09 | TRUE |  | 7 | 1
In Production | Ian Trottier | 2026-06-02 | PO08958 | SO19397 | 2026-06-17 | G-R238-21 2238 | Shaft, 3405-M, 4140 Steel, Grease-Lube | 1 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND |  |  |  | June 16th: Follow up email for inclusion on a second shipment |  |  | 2026-07-01 |  | FALSE |  | -46175 | -6596.4286
In Production | Ian Trottier | 2026-06-02 | PO08958 | SO19397 | 2026-06-17 | G-77-59 1001 | Bearing Housing, 3405-M, Cast Iron | 2 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND |  |  |  | June 16th: Follow up email for inclusion on a second shipment |  |  | 2026-07-01 |  | FALSE |  | -46175 | -6596.4286
In Production | Ian Trottier | 2026-06-02 | PO08958 | SO19397 | 2026-06-17 | G-74812 01 | Deflector, 3405-M, Plastic | 2 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND |  |  |  | June 16th: Follow up email for inclusion on a second shipment |  |  | 2026-07-01 |  | FALSE |  | -46175 | -6596.4286
In Production | Ian Trottier | 2026-06-02 | PO08958 | SO19397 | 2026-06-17 | G-90285-1203 | Stuffing Box Bushing, 3405-L & 3316-L, 316SS | 2 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND |  |  |  | June 16th: Follow up email for inclusion on a second shipment |  |  | 2026-07-01 |  | FALSE |  | -46175 | -6596.4286
In Production | Ian Trottier | 2026-06-02 | PO08958 | SO19397 | 2026-06-17 | G-R70048X 2229 | Shaft Sleeve, 2x3-11, 3316-M, 316SS | 1 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND |  |  |  | June 16th: Follow up email for inclusion on a second shipment |  |  | 2026-07-01 |  | FALSE |  | -46175 | -6596.4286
In Production | Ian Trottier | 2026-06-02 | PO08958 | SO19397 | 2026-06-17 | G-R70047X 2229 | Shaft Sleeve, 3405-M, 316SS, Locking | 1 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND |  |  |  | June 16th: Follow up email for inclusion on a second shipment |  |  | 2026-07-01 |  | FALSE |  | -46175 | -6596.4286
In Production | Ian Trottier | 2026-06-02 | PO08959 | SO18178 | 2026-07-31 | DU-CY22235A-Ni | Casing, 4x3-10, Durco Mark 2&3 Group 2, Nickel 200 | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-10-09 |  | FALSE |  | -46175 | -6596.4286
In Production | Emilka Guerra | 2026-06-02 | PO08960 | SO19378 & stock | 2026-06-23 | AC-98-233-813-001 | Neck Bushing, 5x4/5x5/6x6 SRL & SRL-C | 4 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2026-07-07 |  | FALSE |  | -46175 | -6596.4286
In Production | Emilka Guerra | 2026-06-03 | PO08961 | SO19425 | 2026-07-22 | OLPWZ011006B, G-A04951A219 | Bearing Isolator (Outboard), 3196 MTX/MTi, 303SS Rotor / Bronze Stator w/Viton | 10 | Shandong Furkey Pumps Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-30 |  | FALSE |  | -46176 | -6596.5714
In Production | Emilka Guerra | 2026-06-03 | PO08962 | SO19427 | 2026-07-22 | JC-SCS-1 3/4-4610-MT-BB | Single Cartridge Seal, 1 3/4", D-196 MT, Big Bore, Carbon vs | 2 | Super Cast Limited | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-30 |  | FALSE |  | -46176 | -6596.5714
In Production | Emilka Guerra | 2026-06-03 | PO08962 | SO19427 | 2026-07-22 | W-E028/A05 | Expeller, 6/4 E-AH, High Chrome | 5 | Super Cast Limited | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-30 |  | FALSE |  | -46176 | -6596.5714
In Production | Emilka Guerra | 2026-06-03 | PO08962 | SO19427 | 2026-07-22 | W-E029/A05 | Expeller Ring, 6/4 E-AH, High Chrome | 4 | Super Cast Limited | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-30 |  | FALSE |  | -46176 | -6596.5714
In Production | Emilka Guerra | 2026-06-03 | PO08963 | SO19428 | 2026-07-22 | 10673/2001 | Adjusting Nut, 16DMC-4, Cast Iron | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-30 |  | FALSE |  | -46176 | -6596.5714
In Production | Emilka Guerra | 2026-06-03 | PO08963 | SO19428 | 2026-07-22 | 10674/0526 | Motor Shaft, 16DMC-4, 416SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-30 |  | FALSE |  | -46176 | -6596.5714
In Production | Emilka Guerra | 2026-06-03 | PO08963 | SO19428 | 2026-07-22 | 10677/5001 | Stuffing Box Bearing,16DMC-4, Teflon | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-30 |  | FALSE |  | -46176 | -6596.5714
In Production | Emilka Guerra | 2026-06-03 | PO08963 | SO19428 | 2026-07-22 | 10672/0526 | Coupling, 16DMC-4, 416SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-30 |  | FALSE |  | -46176 | -6596.5714
In Production | Emilka Guerra | 2026-06-03 | PO08963 | SO19428 | 2026-07-22 | 10671/0504 | Cartridge Mechanical Seal, 16DMC-4, 304SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-30 |  | FALSE |  | -46176 | -6596.5714
In Production | Emilka Guerra | 2026-06-03 | PO08963 | SO19428 | 2026-07-22 | 10685/5001 | Spider Bearing, 16DMC-4, Teflon | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-30 |  | FALSE |  | -46176 | -6596.5714
In Production | Emilka Guerra | 2026-06-03 | PO08963 | SO19428 | 2026-07-22 | 10694/5001 | Discharge Bowl Bearing, 16DMC-4, Teflon | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-30 |  | FALSE |  | -46176 | -6596.5714
In Production | Emilka Guerra | 2026-06-03 | PO08963 | SO19428 | 2026-07-22 | 10700/5001 | Intermediate Bowl Bearing, 16DMC-4, Teflon | 3 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-30 |  | FALSE |  | -46176 | -6596.5714
In Production | Emilka Guerra | 2026-06-03 | PO08963 | SO19428 | 2026-07-22 | 10705/5001 | Suction Bowl Bearing, 16DMC-4, Teflon | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-30 |  | FALSE |  | -46176 | -6596.5714
In Production | Ian Trottier | 2026-06-03 | PO08964 | SO19376 | 2026-08-26 | AC-52-321-473-251 | Impeller (Open), 4x3-13, Allis Chalmers CSO, 6-Vanes, CD4MCu | 1 | M&N Alloy Cast Products, Inc. | US | CA WAREHOUSE |  | LAND | [6 empty] | 2026-09-03 |  | FALSE |  | -46176 | -6596.5714
In Production | Emilka Guerra | 2026-06-03 | PO08965 | SO18697 & Stock | 2026-08-12 | AC-98-5414-HC5 | Stuffing Box, 5x4-14 SRL-C, Cast Iron, 3-Piece Design | 3 | IGH | Mexico | CA WAREHOUSE |  | LAND | [6 empty] | 2026-09-09 |  | FALSE |  | -46176 | -6596.5714
In Production | Ian Trottier | 2026-06-04 | PO08966 | SO19440 | 2026-07-29 | DU-CY21853A-CD4 | Casing, 3x1.5-13, Durco Mark 2&3 Group 2, CD4MCu , #300 Flat Face Flanges | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-10-09 |  | FALSE |  | -46177 | -6596.7143
IN TRANSIT | Ian Trottier | 2026-06-04 | PO08967 | SO19038 | 2026-06-10 | 22VSMS3-04C4VS4 | Single Cartridge Seal, 1 3/8", VSMS, Standard Bore, Carbon vs Silicon Carbide / TFEP | 1 | Flexaseal Engineered Seals and Systems, LLC | Canada | CA WAREHOUSE | 2026-06-10 | LAND | [6 empty] | 2026-06-05 |  | FALSE |  | -46177 | -6596.7143
In Production | Emilka Guerra | 2026-06-04 | PO08968 | SO19448 - SOPN00015 | 2026-07-09 | GA-556540 | Impeller, G-Series 6" VSP, 8100 Series, High Chrome | 3 | IGH | Mexico | CA WAREHOUSE |  | LAND | [6 empty] | 2026-08-06 |  | FALSE |  | -46177 | -6596.7143
In Production | Emilka Guerra | 2026-06-04 | PO08969 | Stock | 2026-07-23 | AC-98-231-070-501 | Gland Side Liner, 3x3-10 SRL, Natural Rubber | 6 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-10-01 |  | FALSE |  | -46177 | -6596.7143
In Production | Emilka Guerra | 2026-06-04 | PO08969 | Stock | 2026-07-23 | AC-98-231-071-501 | Suction Side Liner, 3x3-10 SRL, Natural Rubber | 6 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-10-01 |  | FALSE |  | -46177 | -6596.7143
In Production | Emilka Guerra | 2026-06-04 | PO08969 | Stock | 2026-07-23 | AC-98-330-307-501 | Impeller (Closed), 3x3-10 SRL-C, Natural Rubber | 7 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-10-01 |  | FALSE |  | -46177 | -6596.7143
In Production | Emilka Guerra | 2026-06-04 | PO08969 | Stock | 2026-07-23 | AC-98-231-079-501 | Gland Side Liner, 5x5-14 SRL, Natural Rubber | 7 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-10-01 |  | FALSE |  | -46177 | -6596.7143
In Production | Emilka Guerra | 2026-06-04 | PO08969 | Stock | 2026-07-23 | AC-98-231-120-501 | Suction Side Liner, 8x6-18 SRL-C, Natural Rubber | 9 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-10-01 |  | FALSE |  | -46177 | -6596.7143
In Production | Emilka Guerra | 2026-06-04 | PO08969 | Stock | 2026-07-23 | AC-98-431-651-501 | Impeller (Closed), 8x6-18 SRL-C, Natural Rubber | 16 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-10-01 |  | FALSE |  | -46177 | -6596.7143
In Production | Emilka Guerra | 2026-06-04 | PO08969 | Stock | 2026-07-23 | AC-98-231-136-501 | Gland Side Liner, 10x8-21 SRL-C, Natural Rubber | 7 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-10-01 |  | FALSE |  | -46177 | -6596.7143
In Production | Emilka Guerra | 2026-06-04 | PO08969 | Stock | 2026-07-23 | AC-98-039-047-501 | Impeller (Closed), 5x4-14 SRL-C, Natural Rubber | 20 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-10-01 |  | FALSE |  | -46177 | -6596.7143
In Production | Emilka Guerra | 2026-06-04 | PO08969 | Stock | 2026-07-23 | AC-98-231-115-501 | Suction Side Liner, 5x4-14 SRL-C, Natural Rubber | 5 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-10-01 |  | FALSE |  | -46177 | -6596.7143
In Production | Emilka Guerra | 2026-06-04 | PO08969 | Stock | 2026-07-23 | AC-98-231-116-501 | Gland Side Liner, 5x4-14 SRL-C, Natural Rubber | 11 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-10-01 |  | FALSE |  | -46177 | -6596.7143
In Production | Emilka Guerra | 2026-06-04 | PO08969 | Stock | 2026-07-23 | AC-98-330-286-501 | Impeller (Open), 3x3-10 SRL, Natural Rubber | 6 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-10-01 |  | FALSE |  | -46177 | -6596.7143
In Production | Emilka Guerra | 2026-06-04 | PO08969 | Stock | 2026-07-23 | AC-98-231-121-501 | Suction Side Plate, 8x6-18 SRL-C, Natural Rubber | 9 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-10-01 |  | FALSE |  | -46177 | -6596.7143
In Production | Emilka Guerra | 2026-06-04 | PO08969 | Stock | 2026-07-23 | AC-98-231-134-501 | Suction Side Liner, 10x8-21 SRL-C, Natural Rubber | 6 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-10-01 |  | FALSE |  | -46177 | -6596.7143
In Production | Emilka Guerra | 2026-06-04 | PO08969 | Stock | 2026-07-23 | AC-98-231-135-501 | Suction Side Plate, 10x8-21 SRL-C, Natural Rubber | 5 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-10-01 |  | FALSE |  | -46177 | -6596.7143
In Production | Emilka Guerra | 2026-06-04 | PO08969 | Stock | 2026-07-23 | AC-98-231-071-501 | Suction Side Liner, 3x3-10 SRL, Natural Rubber | 6 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-10-01 |  | FALSE |  | -46177 | -6596.7143
In Production | Emilka Guerra | 2026-06-04 | PO08969 | Stock | 2026-07-23 | W-C2017/U38 | Cover Plate Liner, 3/2 C-AH, Urethane | 6 | Super Cast Limited | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-10-01 |  | FALSE |  | -46177 | -6596.7143
In Production | Emilka Guerra | 2026-06-04 | PO08970 | Stock | 2026-07-23 | W-SP10092/A05 | Casing w/Flange, 100RV-SP, High Chrome | 5 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-10-01 |  | FALSE |  | -46177 | -6596.7143
In Production | Emilka Guerra | 2026-06-04 | PO08970 | Stock | 2026-07-23 | W-SP10206A70800, W-SP10206B/A05 | Impeller (Agitator), 100RV-SP, High Chrome | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-10-01 |  | FALSE |  | -46177 | -6596.7143
In Production | Emilka Guerra | 2026-06-04 | PO08970 | Stock | 2026-07-23 | W-ZAG65482/A05 | Agitator, 100 to 200 SP, High Chrome | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-10-01 |  | FALSE |  | -46177 | -6596.7143
In Production | Emilka Guerra | 2026-06-04 | PO08970 | Stock | 2026-07-23 | AC-98-234-268-001-SS | Waterseal Bushing, 5x4/5x5/6x6 SRL, 316SS | 10 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-10-01 |  | FALSE |  | -46177 | -6596.7143
In Production | Emilka Guerra | 2026-06-04 | PO08970 | Stock | 2026-07-23 | W-ZAG65482/A05 | Agitator, 100 to 200 SP, High Chrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-10-01 |  | FALSE |  | -46177 | -6596.7143
In Production | Emilka Guerra | 2026-06-04 | PO08970 | Stock | 2026-07-23 | AC-98-236-256-501 | Gland Assembly, 5x4-14 SRL-C, 316SS | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-10-01 |  | FALSE |  | -46177 | -6596.7143
Ready to Ship | Emilka Guerra | 2026-06-04 | PO08971 | Stock | 2026-07-24 | AC-98-331-958-831 | Shaft Sleeve, 5x4/5x5/6X6 SRL-C & SRL, 420SS Heat Treated, Hardened | 2 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA |  |  | DYNC-119 SEA |  |  |  | 2026-10-01 |  | FALSE |  | -46177 | -6596.7143
In Production | Emilka Guerra | 2026-06-04 | PO08971 | Stock | 2026-07-24 | AC-98-331-958-831 | Shaft Sleeve, 5x4/5x5/6X6 SRL-C & SRL, 420SS Heat Treated, Hardened | 13 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-10-01 |  | FALSE |  | -46177 | -6596.7143
In Production | Emilka Guerra | 2026-06-04 | PO08971 | Stock | 2026-07-24 | DU-CY21805A/CBS-DC20 | Rear Cover, 10", Durco Mark 2&3 Group 2, Alloy 20, Small Bore | 4 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-10-01 |  | FALSE |  | -46177 | -6596.7143
Ready to Ship | Emilka Guerra | 2026-06-04 | PO08971 | Stock | 2026-07-24 | AC-98-236-104-004 | Shaft Sleeve, 8x6-18 & 10x8-21 SRL-C, 420SS Heat Treated, Hardened | 2 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA |  |  | DYNC-119 SEA |  |  |  | 2026-10-01 |  | FALSE |  | -46177 | -6596.7143
In Production | Emilka Guerra | 2026-06-04 | PO08971 | Stock | 2026-07-24 | AC-98-236-104-004 | Shaft Sleeve, 8x6-18 & 10x8-21 SRL-C, 420SS Heat Treated, Hardened | 28 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-10-01 |  | FALSE |  | -46177 | -6596.7143
In Production | Emilka Guerra | 2026-06-04 | PO08971 | Stock | 2026-07-24 | G-249-55 1012 | Casing, 2x3-10, 3196 MTX, Ductile Iron | 1 | Shandong Furkey Pumps Co., Ltd. | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-10-01 |  | FALSE |  | -46177 | -6596.7143
In Production | Yannett Yeomans | 2026-06-04 | PO08972 | SO19444 | 2026-07-06 | D-SH645 | Submersible Sewage Pump, SH645, Ductile Iron w/Impeller in High Chrome | 1 | Super Cast Limited | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-08-31 |  | FALSE |  | -46177 | -6596.7143
Ready to Ship & Delayed | Emilka Guerra | 2026-06-04 | PO08973 | Stock | 2026-06-11 | AC-52-430-298-007 | Seal Cage (Lantern Ring), Allis Chalmers PWO, Group 3 | 2 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-06-16 | LAND | ETA WAREHOUSE 3rd week of JUNE |  |  |  | Quenton Hisco 06/16: Ready to ship - Pending Pick up confirmation by logistics |  | 2026-06-25 |  | FALSE |  | -46177 | -6596.7143
In Production | Emilka Guerra | 2026-06-04 | PO08974 | SO19378 & stock | 2026-06-25 | AC-98-331-963-501 | Shaft Assembly, 6x6-15 SRL | 2 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2026-07-02 |  | FALSE |  | -46177 | -6596.7143
In Production | Emilka Guerra | 2026-06-05 | PO08975 | Stock | 2026-07-31 | AC-98-037-796-501 | Impeller (Open), 6x6-15 AC SRL, Natural Rubber | 3 | IGH | Mexico | CA WAREHOUSE |  | LAND | [6 empty] | 2026-08-28 |  | FALSE |  | -46178 | -6596.8571
In Production | Emilka Guerra | 2026-06-05 | PO08976 | SO19449 | 2026-07-10 | SZ-3822790584 | Static Seal, Sulzer | 10 | Super Cast Limited | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-04 |  | FALSE |  | -46178 | -6596.8571
In Production | Emilka Guerra | 2026-06-05 | PO08976 | SO19449 | 2026-07-10 | D-500S-98B-03/C21 | Wear Ring, 500S-98B, 420SS | 4 | Super Cast Limited | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-04 |  | FALSE |  | -46178 | -6596.8571
Ready to Ship & Delayed | Amanda Qiao | 2026-06-08 | PO08977 | Urgent WH/MO/00200 | 2026-06-15 | DU-DY53443A/FML-316SS | Rear Cover, 13", Durco Mark 2&3 Group 2, 316SS, Flow Modifier Large Bore | 2 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-06-16 | LAND | ETA WAREHOUSE 3rd week of JUNE |  |  |  | Quenton Hisco 06/16: Ready to ship - Pending Pick up confirmation by logistics |  | 2026-06-19 |  | FALSE |  | -46181 | -6597.2857
Ready to Ship & Delayed | Amanda Qiao | 2026-06-08 | PO08977 | Urgent WH/MO/00200 | 2026-06-15 | DU-MY49112A130-316 | Impeller, 3x2-13, Durco Mark 2&3 Group 2, 316SS, Reverse Vane | 2 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-06-16 | LAND | ETA WAREHOUSE 3rd week of JUNE |  |  |  | Quenton Hisco 06/16: Ready to ship - Pending Pick up confirmation by logistics |  | 2026-06-19 |  | FALSE |  | -46181 | -6597.2857
Ready to Ship & Delayed | Amanda Qiao | 2026-06-08 | PO08977 | Urgent WH/MO/00200 | 2026-06-15 | DU-GUARD-M3G2 | Coupling Guard, Durco Mark 3 Group 2, Steel Fabricated, Drum Style | 2 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-06-16 | LAND | ETA WAREHOUSE 3rd week of JUNE |  |  |  | Quenton Hisco 06/16: Ready to ship - Pending Pick up confirmation by logistics |  | 2026-06-19 |  | FALSE |  | -46181 | -6597.2857
In Production | Amanda Qiao | 2026-06-08 | PO08978 | Urgent WH/MO/00200 | 2026-06-15 |  | Coupling, Raptor ES2 Full Spcr Ext Kit | 2 | Mosherflo Pumps, LLC. | Other | CA WAREHOUSE |  | LAND | [6 empty] | 2026-06-18 |  | FALSE |  | -46181 | -6597.2857
In Production | Amanda Qiao | 2026-06-08 | PO08979 | Rush WH/MO/00200 | 2026-06-19 | PDH0026 | 2 HP, 1200 RPM, 460/3/60, Premium Efficiency TEFC, Teco-Westinghouse Motor | 2 | Teco-Westinghouse Motors (Canada) Inc. | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2026-06-22 |  | FALSE |  | -46181 | -6597.2857
In Production | Emilka Guerra | 2026-06-08 | PO08980 | SO18891 | 2026-08-31 | G-243-90 1216 | Impeller, 6x8-13, 3171-L, CD4MCu | 1 | M&N Alloy Cast Products, Inc. | US | CA WAREHOUSE |  | LAND | [6 empty] | 2026-09-21 |  | FALSE |  | -46181 | -6597.2857
In Production | Emilka Guerra | 2026-06-08 | PO08980 | SO18891 | 2026-08-31 | G-101-26 1216 | Suction Cover, 6x8-13, 3171-L, CD4MCu | 1 | M&N Alloy Cast Products, Inc. | US | CA WAREHOUSE |  | LAND | [6 empty] | 2026-09-21 |  | FALSE |  | -46181 | -6597.2857
Ready to Ship & Delayed | Emilka Guerra | 2026-06-08 | PO08981 | SO19438 | 2026-06-15 | AC125-CS02-3SS, AC-52-108-789-004 | Packing Base Ring, Allis Chalmers CSO, Frame F4B3/F4B5/F4D1, 316SS | 1 | Hisco Pump Inc. | US | CA WAREHOUSE | 2026-06-16 | LAND | ETA WAREHOUSE 3rd week of JUNE |  |  |  | Quenton Hisco 06/16: Ready to ship - Pending Pick up confirmation by logistics |  | 2026-06-29 |  | FALSE |  | -46181 | -6597.2857
In Production | Emilka Guerra | 2026-06-08 | PO08982 | SO19438 | 2026-08-31 | AC-52-425-753-005 | Stuffing Box Cover, 10", CSO F4B3, Cast Iron | 1 | M&N Alloy Cast Products, Inc. | US | CA WAREHOUSE |  | LAND | [6 empty] | 2026-09-21 |  | FALSE |  | -46181 | -6597.2857
In Production | Emilka Guerra | 2026-06-08 | PO08983 | SO19405 | 2026-08-17 | AC-98-231-115-506 | Suction Side Liner, 5X4-14 SRL-C, Urethane | 1 | IGH | Mexico | CA WAREHOUSE |  | LAND | [6 empty] | 2026-09-14 |  | FALSE |  | -46181 | -6597.2857
In Production | Emilka Guerra | 2026-06-09 | PO08984 | SO19430 | 2026-07-07 | AC-98-331-931-801 | Bearing Cylinder, 5x4-14 SRL-C, Cast Iron | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-04 |  | FALSE |  | -46182 | -6597.4286
In Production | Emilka Guerra | 2026-06-09 | PO08984 | SO19430 | 2026-07-07 | AC-98-331-926-801 | Bearing Cover (Outboard), 5x4/5x5/6x6 SRL & SRL-C, Cast Iron | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-04 |  | FALSE |  | -46182 | -6597.4286
Received | Emilka Guerra | 2026-06-09 | PO08985 | SO19430 | 2026-06-16 | 22212 EAE4C3, G-8061-22212 | Bearing (Inboard), 5x4-14 SRL/SRL-C & 6x6-15 SRL, Steel | 3 | Wajax Limited - Mississauga | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2026-06-30 | 2026-06-15 | TRUE |  | 6 | 0.85714
Received | Emilka Guerra | 2026-06-09 | PO08985 | SO19430 | 2026-06-16 | 22312 EAE4C3, G-8061-62312 | Bearing (Outboard), 5x4-14 SRL/SRL-C & 6x6-15 SRL, Steel | 3 | Wajax Limited - Mississauga | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2026-06-30 | 2026-06-15 | TRUE |  | 6 | 0.85714
In Production | Yannett Yeomans | 2026-06-10 | PO08986 | SO19464 | 2026-08-03 | DA-D1961.5/3-13MT/1516/0507 | ANSI Pump, D-196 1.5x3-13 MT, Ductile Iron, Impeller CD4MCu | 2 | Shandong Furkey Pumps Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-29 |  | FALSE |  | -46183 | -6597.5714
In Production | Yannett Yeomans | 2026-06-10 | PO08986 | SO19464 | 2026-08-03 | JC-SCS-1 3/4-4610-MT-BB | Single Cartridge Seal, 1 3/4", D-196 MT, Big Bore, Carbon vs | 2 | Shandong Furkey Pumps Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-29 |  | FALSE |  | -46183 | -6597.5714
In Production | Yannett Yeomans | 2026-06-10 | PO08986 | SO19464 | 2026-08-03 | G-R196-MKM13 | Maintenance Kit, 13", 3196 MTX | 4 | Shandong Furkey Pumps Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-29 |  | FALSE |  | -46183 | -6597.5714
In Production | Yannett Yeomans | 2026-06-10 | PO08986 | SO19464 | 2026-08-03 | G-249-63 1216 | Casing, 1.5x3-13, 3196 MTX, CD4MCu | 2 | Shandong Furkey Pumps Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-29 |  | FALSE |  | -46183 | -6597.5714
In Production | Yannett Yeomans | 2026-06-10 | PO08986 | SO19464 | 2026-08-03 | G-0100-537 1216 | Impeller, 1.5x3-13, 3196 MTX, CD4MCu, 5-Vane | 2 | Shandong Furkey Pumps Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-29 |  | FALSE |  | -46183 | -6597.5714
In Production | Yannett Yeomans | 2026-06-10 | PO08986 | SO19464 | 2026-08-03 | G-C04677A 3201 | Coupling Guard, 3196 MTX, Fabricated Steel, Drum Style | 2 | Shandong Furkey Pumps Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-29 |  | FALSE |  | -46183 | -6597.5714
In Production | Yannett Yeomans | 2026-06-10 | PO08986 | SO19464 | 2026-08-03 | RX-ES30 | Coupling, Rexnord ES30, MT/LT | 2 | Shandong Furkey Pumps Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-29 |  | FALSE |  | -46183 | -6597.5714
In Production | Yannett Yeomans | 2026-06-10 | PO08986 | SO19464 | 2026-08-03 | G-D07086A | G-D07086A | 1 | Shandong Furkey Pumps Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-29 |  | FALSE |  | -46183 | -6597.5714
In Production | Leriel Reyes | 2026-06-10 | PO08987 | SO19049 | 2026-09-16 | GA-2.5*1100x60-CI | Sump Pump, G-Series 2.5" VSP, 1000 Series, 60" Column, Cast Iron | 1 | IGH | Mexico | CA WAREHOUSE |  | LAND | [6 empty] | 2026-10-14 |  | FALSE |  | -46183 | -6597.5714
In Production | Ian Trottier | 2026-06-10 | PO08988 | SO19443 | 2026-06-15 | SKF-22340 | Bearing Seal (Inboard & Outboard), 5x4-14 SRL/SRL-C, 6x6-15 SRL | 12 | Wajax Limited - Mississauga | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2026-06-17 |  | FALSE |  | -46183 | -6597.5714
In Production | Emilka Guerra | 2026-06-10 | PO08989 | SO19387 & SO19455 | 2026-07-08 | NUP-317-ECP, G-8060-17317 | Radial Bearing (Inboard), 3180-XL, Steel | 1 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND |  |  |  | June 16th: Follow up email for inclusion on a second shipment |  |  | 2026-07-15 |  | FALSE |  | -46183 | -6597.5714
In Production | Emilka Guerra | 2026-06-10 | PO08989 | SO19387 & SO19455 | 2026-07-08 | G-RD04859A 2249 | Shaft, 3180 XL, AISI, 4340 Alloy Steel HT | 1 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND |  |  |  | June 16th: Follow up email for inclusion on a second shipment |  |  | 2026-07-15 |  | FALSE |  | -46183 | -6597.5714
In Production | Emilka Guerra | 2026-06-10 | PO08989 | SO19387 & SO19455 | 2026-07-08 | G-B02191A04 3211 | Throttle Bushing, Goulds 3180-XL | 1 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND |  |  |  | June 16th: Follow up email for inclusion on a second shipment |  |  | 2026-07-15 |  | FALSE |  | -46183 | -6597.5714
In Production | Emilka Guerra | 2026-06-10 | PO08989 | SO19387 & SO19455 | 2026-07-08 | G-A03189A06 5127 | Side Plate Gasket, 3180-XL | 1 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND |  |  |  | June 16th: Follow up email for inclusion on a second shipment |  |  | 2026-07-15 |  | FALSE |  | -46183 | -6597.5714
In Production | Emilka Guerra | 2026-06-10 | PO08989 | SO19387 & SO19455 | 2026-07-08 | G-9008-31365 | Breather, 3196 MTX, Carbon Steel | 1 | Hisco Pump Inc. | US | CA WAREHOUSE |  | LAND |  |  |  | June 16th: Follow up email for inclusion on a second shipment |  |  | 2026-07-15 |  | FALSE |  | -46183 | -6597.5714
Received | Emilka Guerra | 2026-06-10 | PO08990 | SO19387 | 2026-06-17 | AC-98-233-992-001 | Half Seal Cage, 3x3-10 SRL & SRL-C, Cast Iron | 3 | Mid-Canada Manufacturing | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2026-06-24 | 2026-06-17 | TRUE |  | 7 | 1
In Production | Emilka Guerra | 2026-06-11 | PO08991 | SO19311 | 2026-07-23 | SA-138412-M1 | Impeller, (Keyed), Sala VT50, Natural Rubber | 2 | Dexhor | Other | CA WAREHOUSE |  | LAND | [6 empty] | 2026-08-07 |  | FALSE |  | -46184 | -6597.7143
IN TRANSIT | Ian Trottier | 2026-06-11 | PO08992 | VT40 Project | 2026-06-15 | SA-VT40-NR | Tank Pump, Sala VT40, Rubber Lined Tank & Wet End, Motor Mount, and Belt Guard. | 1 | NRI Industrial | Other | CA WAREHOUSE | 2026-06-12 | LAND |  |  |  |  | Christine 06/12: This shipment (1 Skid) is expected to arrive at our warehouse by the early next week. |  | 2026-06-11 |  | FALSE |  | -46184 | -6597.7143
In Production | Emilka Guerra | 2026-06-12 | PO08993 |  | 2026-07-17 | AC-98-039-047-504 | Impeller (Closed), 5x4-14 SRL-C, Hypalon | 1 | Seal X Supply Inc. | Canada | CA WAREHOUSE |  | LAND | [6 empty] | 2026-07-24 |  | FALSE |  | -46185 | -6597.8571
In Production | Emilka Guerra | 2026-06-12 | PO08994 | SO19290 | 2026-07-24 | AC-98-231-081-503 | Suction Side Liner, 5x5-14 SRL, Neoprene | 3 | IGH | Mexico | CA WAREHOUSE |  | LAND | [6 empty] | 2026-08-21 |  | FALSE |  | -46185 | -6597.8571
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
[22 empty] | FALSE |  | 0 | 0
Formulas:
SUPPLIER DELIVERY = [SHIPPING DATE SUPPLIER]-[DUE DATE FACTORY]
Total LT in weeks = [TOTAL REAL LEAD TIME]/7

## MX
STATUS | CREATED BY | ISSUE DATE | PO NUMBER | REFERENCE | DUE DATE FACTORY | SKU | PRODUCT NAME | INCOMING STOCK | SUPPLIER | ORIGIN | SHIP TO | SHIPPING DATE SUPPLIER | TRANSIT | ETA WAREHOUSE | SHIPPING INSTRUCTIONS | TRACKING NUMBER / UPDATES | IMPORTANT NOTE | PETER UPDATES | DELAY ISSUES | EST RECEIPT DATE ODOO | RECEPTION DATE WAREHOUSE | COMPLETED
IN TRANSIT & DELAYED | Yannett Yeomans | 2025-11-18 | OC00228/PO08442 | SOMX00659 | 2026-02-08 | 10548/0003 | Suction Liner 6x8, High Chrome | 5 | Super Cast Limited | China | MX WAREHOUSE | 2026-03-22 | SEA | 2026-03-30 |  | LS15TJ2603790 | "ETA Ensenada Abr/20" | left Tianjin for Ensenada by sea on Mar 22, 2026. |  | 2026-03-30 |  | FALSE
IN TRANSIT & DELAYED | Yannett Yeomans | 2025-11-18 | OC00228/PO08442 | SOMX00659 | 2026-02-08 | 10547/0003 | Impeller 6x8, High Chrome | 4 | Super Cast Limited | China | MX WAREHOUSE | 2026-03-22 | SEA | 2026-03-30 |  | LS15TJ2603790 | "ETA Ensenada Abr/20" | left Tianjin for Ensenada by sea on Mar 22, 2026. |  | 2026-03-30 |  | FALSE
IN TRANSIT & DELAYED | Yannett Yeomans | 2025-11-18 | OC00228/PO08442 | SOMX00659 | 2026-02-08 | 10544/0003 | Suction Liner 10x12, High Chrome | 4 | Super Cast Limited | China | MX WAREHOUSE | 2026-03-22 | SEA | 2026-03-30 |  | LS15TJ2603790 | "ETA Ensenada Abr/20" | left Tianjin for Ensenada by sea on Mar 22, 2026. |  | 2026-03-30 |  | FALSE
Received | Yannett Yeomans | 2025-12-04 | OC00236/PO08494 | Stock 6x8 Volutes | 2026-01-22 | 6254C-00-0028G | Pump Casing, Dynapro 6X8 MDX-025, High Chrome | 4 | Super Cast Limited | China | MX WAREHOUSE | 2026-02-11 | SEA | 2026-03-20 |  | LS15TJ2602851 |  | eft Tianjin for Ensenada by sea on Feb 11, 2026. |  | 2026-03-19 | 2026-04-01 | TRUE
Received | Yannett Yeomans | 2025-12-04 | OC00237/PO08495 | SOMX00633 | 2025-03-12 | 610471MP41 | Impeller, CPT 24-3, Sulzer | 1 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-09 | AIR | 2026-02-02 |  | DHL waybill (2884550826) | DHL TO HERMOSILLO |  |  | 2026-02-02 | 2026-04-24 | TRUE
IN TRANSIT & DELAYED | Yannett Yeomans | 2025-12-05 | OC00239/PO08503 | SOMX00685 | 19/03/26 | DSC-JHS20/16-560/0503 | Horizontal Split Case Pump, XS400-560, 420SS | 1 | Super Cast Limited | China | MX WAREHOUSE | 2026-05-17 | SEA | 2026-01-05 |  | SHESE26252889H | URGENT!! DELAY W/CUSTOMER left Shanghai for Ensenada by sea on May 17, 2026 | The new ETD is May 6 | The new vessel / Voyage is POSORJA EXPRESS 2620E, ETD Tianjin May 18 | 2026-05-01 |  | FALSE
IN TRANSIT & DELAYED | Yannett Yeomans | 2025-12-05 | OC00239/PO08503 | SOMX00685 | 19/03/26 | 10637/2001 | Set of Coupling and Coupling Guard XS400-560, Cast Iron | 1 | Super Cast Limited | China | MX WAREHOUSE | 2026-05-17 | SEA | 2026-01-05 |  | SHESE26252889H | URGENT!! DELAY W/CUSTOMER left Shanghai for Ensenada by sea on May 17, 2026 | The new ETD is May 6 | The new vessel / Voyage is POSORJA EXPRESS 2620E, ETD Tianjin May 18 | 2026-05-01 |  | FALSE
IN TRANSIT & DELAYED | Yannett Yeomans | 2025-12-05 | OC00239/PO08503 | SOMX00685 | 19/03/26 | 10638/1501 | Common base XS400-560I, Carbon Steel | 1 | Super Cast Limited | China | MX WAREHOUSE | 2026-05-17 | SEA | 2026-01-05 |  | SHESE26252889H | URGENT!! DELAY W/CUSTOMER left Shanghai for Ensenada by sea on May 17, 2026 | The new ETD is May 6 | The new vessel / Voyage is POSORJA EXPRESS 2620E, ETD Tianjin May 18 | 2026-05-01 |  | FALSE
IN TRANSIT & DELAYED | Yannett Yeomans | 2025-12-10 | OC00240 | SOMX00685 | 2026-04-05 | KPF17504 | Common base XS400-560I, Carbon Steel | 1 | BOMBAS Y MOTORES HMG | Mexico | MX WAREHOUSE | 2026-05-14 | SEA | ETA MAYO 15 |  |  |  | José: Salida 16/abril, contamos con ETA tentativa para el 08/Mayo / De igual manera en base a estas fechas la pronosticada por Cristina sigue en pie con una posible mejora a embarcar el próximo 20-25 de Mayo. | ETA Manzanillo 4 de Mayo 2026 | 2026-05-04 |  | FALSE
IN TRANSIT | Yannett Yeomans | 2025-12-19 | OC00242/PO08560 | SOMX00696 | 19/12/25 | Dynapro Vertical Turbine Pump, 16DMC-4 | Dynapro Vertical Turbine Pump, 16DMC-4 | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE | 2026-03-21 | SEA | 2025-12-20 |  |  |  | "Vessel shipped Shanghai Mar/21 ETA Ensenada Apr/06" |  | 2025-12-20 | 2026-03-31 | TRUE
Received | Emilka Guerra | 2026-01-05 | OC00243/PO08577 | SOMX00697 | 2026-10-02 | 10527/1501 | Coupling, 7CHC-9, Carbon Steel | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | 2026-04-21 |  | SHESE26247790M |  | left Shanghai for Ensenada by sea on Feb 11, 2026 |  | 2026-04-21 | 2026-04-10 | TRUE
Received | Emilka Guerra | 2026-01-05 | OC00243/PO08577 | SOMX00697 | 2026-10-02 | 10522/5001 | Intermediate Bowl Bearing, 7CHC-9, Teflon | 9 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | 2026-04-21 |  | SHESE26247790M |  | left Shanghai for Ensenada by sea on Feb 11, 2026 |  | 2026-04-21 | 2026-04-10 | TRUE
Received | Emilka Guerra | 2026-01-05 | OC00243/PO08577 | SOMX00697 | 2026-10-02 | 10524/5001 | Discharge Bowl Bearing, 7CHC-9, Teflon | 2 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | 2026-04-21 |  | SHESE26247790M |  | left Shanghai for Ensenada by sea on Feb 11, 2026 |  | 2026-04-21 | 2026-04-10 | TRUE
Received | Emilka Guerra | 2026-01-05 | OC00243/PO08577 | SOMX00697 | 2026-10-02 | 10531/0504 | Hex Bolts and Spring Washers for Adjustment, 7CHC-9, 304SS | 4 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | 2026-04-21 |  | SHESE26247790M |  | left Shanghai for Ensenada by sea on Feb 11, 2026 |  | 2026-04-21 | 2026-04-10 | TRUE
Received | Emilka Guerra | 2026-01-05 | OC00243/PO08577 | SOMX00697 | 2026-10-02 | 10341/2001 | Stuffing Box, 7CHC-9, Cast Iron | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | 2026-04-21 |  | SHESE26247790M |  | left Shanghai for Ensenada by sea on Feb 11, 2026 |  | 2026-04-21 | 2026-04-10 | TRUE
Received | Emilka Guerra | 2026-01-05 | OC00243/PO08577 | SOMX00697 | 2026-10-02 | 10335/0504 | Impeller Collect, 7CHC-9, 304SS | 9 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | 2026-04-21 |  | SHESE26247790M |  | left Shanghai for Ensenada by sea on Feb 11, 2026 |  | 2026-04-21 | 2026-04-10 | TRUE
Received | Emilka Guerra | 2026-01-05 | OC00243/PO08577 | SOMX00697 | 2026-10-02 | 10530/2001 | Adjustment Nut, 7CHC-9, Cast Iron | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | 2026-04-21 |  | SHESE26247790M |  | left Shanghai for Ensenada by sea on Feb 11, 2026 |  | 2026-04-21 | 2026-04-10 | TRUE
Received | Emilka Guerra | 2026-01-05 | OC00243/PO08577 | SOMX00697 | 2026-10-02 | 10332/2001 | Suction Bell, 7CHC-9, Cast Iron | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | 2026-04-21 |  | SHESE26247790M |  | left Shanghai for Ensenada by sea on Feb 11, 2026 |  | 2026-04-21 | 2026-04-10 | TRUE
Received | Emilka Guerra | 2026-01-05 | OC00243/PO08577 | SOMX00697 | 2026-10-02 | 10521/2001 | Intermediate Bowl, 7CHC-9, Cast Iron | 6 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | 2026-04-21 |  | SHESE26247790M |  | left Shanghai for Ensenada by sea on Feb 11, 2026 |  | 2026-04-21 | 2026-04-10 | TRUE
Received | Emilka Guerra | 2026-01-05 | OC00243/PO08577 | SOMX00697 | 2026-10-02 | 10523/2001 | Discharge Bowl, 7CHC-9, Cast Iron | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | 2026-04-21 |  | SHESE26247790M |  | left Shanghai for Ensenada by sea on Feb 11, 2026 |  | 2026-04-21 | 2026-04-10 | TRUE
Received | Emilka Guerra | 2026-01-05 | OC00243/PO08577 | SOMX00697 | 2026-10-02 | 10051/1501 | Lineshaft Coupling, 12RJHC-8, 316SS | 3 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | 2026-04-21 |  | SHESE26247790M |  | left Shanghai for Ensenada by sea on Feb 11, 2026 |  | 2026-04-21 | 2026-04-10 | TRUE
Received | Emilka Guerra | 2026-01-05 | OC00243/PO08577 | SOMX00697 | 2026-10-02 | 10063/1501 | Lineshaft Coupling, 18BHC-1, 316SS | 3 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | 2026-04-21 |  | SHESE26247790M |  | left Shanghai for Ensenada by sea on Feb 11, 2026 |  | 2026-04-21 | 2026-04-10 | TRUE
Received | Emilka Guerra | 2026-01-05 | OC00243/PO08577 | SOMX00697 | 2026-10-02 | 10374/0505 | Lineshaft, 316SS, 45MM, 12RJHC-8 | 3 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | 2026-04-21 |  | SHESE26247790M |  | left Shanghai for Ensenada by sea on Feb 11, 2026 |  | 2026-04-21 | 2026-04-10 | TRUE
IN TRANSIT | Yannett Yeomans | 2026-01-08 | OC00244/PO08588 | 12X10 Volutes | 31/03/26 | 10546/0003 | Volute Casing, 12X10, High Chrome | 2 | Super Cast Limited | China | MX WAREHOUSE | 2026-05-07 | SEA | 2026-05-25 |  |  |  | left Tianjin for Ensenada by sea on May 7, 2026 |  | 2026-05-25 |  | FALSE
IN TRANSIT & DELAYED | Yannett Yeomans | 2026-01-14 | OC00248/PO08603 | SOMX00706 | 18/03/26 | GB/T6172.1 | Nut M20, XS500-710, Carbon Steel | 2 | Super Cast Limited | China | MX WAREHOUSE | 2026-05-24 | AIR |  |  |  | left Tianjin for Ensenada by sea on May 24, 2026 |  |  |  |  | FALSE
IN TRANSIT & DELAYED | Yannett Yeomans | 2026-01-14 | OC00248/PO08603 | SOMX00706 | 18/03/26 | GB/T6172.1 | Nut M20, XS500-710, Carbon Steel | 1 | Super Cast Limited | China | MX WAREHOUSE | 2026-05-11 | AIR | ETA MAY 15 | ship DHL parts for the SOMX | DHL waybill (7963743782) |  | As per Emilka's instructions, the 1st batch remaining fasteners in OC00248/PO08603 were shipped out via DHL from Shijiazhuang for Hermosillo on May 11, 2026. |  |  |  | FALSE
IN TRANSIT & DELAYED | Yannett Yeomans | 2026-01-14 | OC00248/PO08603 | SOMX00706 | 18/03/26 | GB/T85 | Screw M20x5, XS500-710 | 3 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-23 | SEA | 2026-05-13 |  | SHESE26251826G | left Shanghai for Ensenada by sea on Apr 23, 2026 | After Tomb-Sweeping holiday (Apr 4 to 6), OC00248/PO08603 will be ready for shipment. Already booked the vessel of ETD Apr 20 from Shanghai to Ensenada. | ETA ENSENADA: May 14 |  |  | FALSE
IN TRANSIT & DELAYED | Yannett Yeomans | 2026-01-14 | OC00248/PO08603 | SOMX00706 | 18/03/26 | B1205-76-100-02 | Bearing Housing Cover, XS500-710, Cast Iron | 3 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-23 | SEA | 2026-05-13 |  | SHESE26251826G | left Shanghai for Ensenada by sea on Apr 23, 2026 | After Tomb-Sweeping holiday (Apr 4 to 6), OC00248/PO08603 will be ready for shipment. Already booked the vessel of ETD Apr 20 from Shanghai to Ensenada. | ETA ENSENADA: May 14 |  |  | FALSE
IN TRANSIT & DELAYED | Yannett Yeomans | 2026-01-14 | OC00248/PO08603 | SOMX00706 | 18/03/26 | B12051-76-110z-01 | Bearing Housing A, XS500-710, HT250 | 2 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-23 | SEA | 2026-05-13 |  | SHESE26251826G | left Shanghai for Ensenada by sea on Apr 23, 2026 | After Tomb-Sweeping holiday (Apr 4 to 6), OC00248/PO08603 will be ready for shipment. Already booked the vessel of ETD Apr 20 from Shanghai to Ensenada. | ETA ENSENADA: May 14 |  |  | FALSE
IN TRANSIT & DELAYED | Yannett Yeomans | 2026-01-14 | OC00248/PO08603 | SOMX00706 | 18/03/26 | GB283 | Cylindrical Roller Bearing NU322, XS500-710 | 2 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-23 | SEA | 2026-05-13 |  | SHESE26251826G | left Shanghai for Ensenada by sea on Apr 23, 2026 | After Tomb-Sweeping holiday (Apr 4 to 6), OC00248/PO08603 will be ready for shipment. Already booked the vessel of ETD Apr 20 from Shanghai to Ensenada. | ETA ENSENADA: May 14 |  |  | FALSE
IN TRANSIT & DELAYED | Yannett Yeomans | 2026-01-14 | OC00248/PO08603 | SOMX00706 | 18/03/26 | 10542/5013 | Fishpaper, 0.25MM, XS500-710 | 3 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-23 | SEA | 2026-05-13 |  | SHESE26251826G | left Shanghai for Ensenada by sea on Apr 23, 2026 | After Tomb-Sweeping holiday (Apr 4 to 6), OC00248/PO08603 will be ready for shipment. Already booked the vessel of ETD Apr 20 from Shanghai to Ensenada. | ETA ENSENADA: May 14 |  |  | FALSE
IN TRANSIT & DELAYED | Yannett Yeomans | 2026-01-14 | OC00248/PO08603 | SOMX00706 | 18/03/26 | 10535/1501 | Screw M16x60, XS500-710, Carbon Steel | 12 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-23 | SEA | 2026-05-13 |  | SHESE26251826G | left Shanghai for Ensenada by sea on Apr 23, 2026 | After Tomb-Sweeping holiday (Apr 4 to 6), OC00248/PO08603 will be ready for shipment. Already booked the vessel of ETD Apr 20 from Shanghai to Ensenada. | ETA ENSENADA: May 14 |  |  | FALSE
IN TRANSIT & DELAYED | Yannett Yeomans | 2026-01-14 | OC00248/PO08603 | SOMX00706 | 18/03/26 | 10534/1501 | Flat Washer M24, XS500-710, Carbon Steel | 12 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-23 | SEA | 2026-05-13 |  | SHESE26251826G | left Shanghai for Ensenada by sea on Apr 23, 2026 | After Tomb-Sweeping holiday (Apr 4 to 6), OC00248/PO08603 will be ready for shipment. Already booked the vessel of ETD Apr 20 from Shanghai to Ensenada. | ETA ENSENADA: May 14 |  |  | FALSE
IN TRANSIT & DELAYED | Yannett Yeomans | 2026-01-14 | OC00248/PO08603 | SOMX00706 | 18/03/26 | 10533/1501 | Spring Washer M24, XS500-710, 1065 Steel | 12 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-23 | SEA | 2026-05-13 |  | SHESE26251826G | left Shanghai for Ensenada by sea on Apr 23, 2026 | After Tomb-Sweeping holiday (Apr 4 to 6), OC00248/PO08603 will be ready for shipment. Already booked the vessel of ETD Apr 20 from Shanghai to Ensenada. | ETA ENSENADA: May 14 |  |  | FALSE
IN TRANSIT & DELAYED | Yannett Yeomans | 2026-01-14 | OC00248/PO08603 | SOMX00706 | 18/03/26 | 10532/0539 | Cap Shape Nut, M24, XS500-710, 201SS | 8 | Super Cast Limited | China | MX WAREHOUSE | 2026-05-24 | AIR |  |  |  | left Tianjin for Ensenada by sea on May 24, 2026 |  |  |  |  | FALSE
IN TRANSIT & DELAYED | Yannett Yeomans | 2026-01-14 | OC00248/PO08603 | SOMX00706 | 18/03/26 | 10532/0539 | Cap Shape Nut, M24, XS500-710, 201SS | 4 | Super Cast Limited | China | MX WAREHOUSE | 2026-05-11 | AIR | ETA MAY 15 | ship DHL parts for the SOMX | DHL waybill (7963743782) |  | As per Emilka's instructions, the 1st batch remaining fasteners in OC00248/PO08603 were shipped out via DHL from Shijiazhuang for Hermosillo on May 11, 2026. |  |  |  | FALSE
IN TRANSIT & DELAYED | Yannett Yeomans | 2026-01-14 | OC00248/PO08603 | SOMX00706 | 18/03/26 | 10470/1501 | Double Head Bolt M24x140mm, XS500-710, Carbon Steel | 8 | Super Cast Limited | China | MX WAREHOUSE | 2026-05-24 | AIR |  |  |  | left Tianjin for Ensenada by sea on May 24, 2026 |  |  |  |  | FALSE
IN TRANSIT & DELAYED | Yannett Yeomans | 2026-01-14 | OC00248/PO08603 | SOMX00706 | 18/03/26 | 10470/1501 | Double Head Bolt M24x140mm, XS500-710, Carbon Steel | 4 | Super Cast Limited | China | MX WAREHOUSE | 2026-05-11 | AIR | ETA MAY 15 | ship DHL parts for the SOMX | DHL waybill (7963743782) |  | As per Emilka's instructions, the 1st batch remaining fasteners in OC00248/PO08603 were shipped out via DHL from Shijiazhuang for Hermosillo on May 11, 2026. |  |  |  | FALSE
IN TRANSIT & DELAYED | Yannett Yeomans | 2026-01-14 | OC00248/PO08603 | SOMX00706 | 18/03/26 | 10469/1501 | Double Head Bolt, M27x110mm, XS500-710, Carbon Steel | 8 | Super Cast Limited | China | MX WAREHOUSE | 2026-05-24 | AIR |  |  |  | left Tianjin for Ensenada by sea on May 24, 2026 |  |  |  |  | FALSE
IN TRANSIT & DELAYED | Yannett Yeomans | 2026-01-14 | OC00248/PO08603 | SOMX00706 | 18/03/26 | 10469/1501 | Double Head Bolt, M27x110mm, XS500-710, Carbon Steel | 4 | Super Cast Limited | China | MX WAREHOUSE | 2026-05-11 | AIR | ETA MAY 15 | ship DHL parts for the SOMX | DHL waybill (7963743782) |  | As per Emilka's instructions, the 1st batch remaining fasteners in OC00248/PO08603 were shipped out via DHL from Shijiazhuang for Hermosillo on May 11, 2026. |  |  |  | FALSE
IN TRANSIT & DELAYED | Yannett Yeomans | 2026-01-14 | OC00248/PO08603 | SOMX00706 | 18/03/26 | 10468/1501 | Nut M16, XS500-710, Carbon Steel | 4 | Super Cast Limited | China | MX WAREHOUSE | 2026-05-24 | AIR |  |  |  | left Tianjin for Ensenada by sea on May 24, 2026 |  |  |  |  | FALSE
IN TRANSIT & DELAYED | Yannett Yeomans | 2026-01-14 | OC00248/PO08603 | SOMX00706 | 18/03/26 | 10468/1501 | Nut M16, XS500-710, Carbon Steel | 2 | Super Cast Limited | China | MX WAREHOUSE | 2026-05-11 | AIR | ETA MAY 15 | ship DHL parts for the SOMX | DHL waybill (7963743782) |  | As per Emilka's instructions, the 1st batch remaining fasteners in OC00248/PO08603 were shipped out via DHL from Shijiazhuang for Hermosillo on May 11, 2026. |  |  |  | FALSE
IN TRANSIT & DELAYED | Yannett Yeomans | 2026-01-14 | OC00248/PO08603 | SOMX00706 | 18/03/26 | 10463/1519 | Spiral Tail Cone Pin 16x100mm, XS500-710, 1035 Steel | 6 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-23 | SEA | 2026-05-13 |  | SHESE26251826G | left Shanghai for Ensenada by sea on Apr 23, 2026 | After Tomb-Sweeping holiday (Apr 4 to 6), OC00248/PO08603 will be ready for shipment. Already booked the vessel of ETD Apr 20 from Shanghai to Ensenada. | ETA ENSENADA: May 14 |  |  | FALSE
IN TRANSIT & DELAYED | Yannett Yeomans | 2026-01-14 | OC00248/PO08603 | SOMX00706 | 18/03/26 | 10461/1501 | Double Head Bolt M27x75mm, XS500-710, Carbon Steel | 74 | Super Cast Limited | China | MX WAREHOUSE | 2026-05-24 | AIR |  |  |  | left Tianjin for Ensenada by sea on May 24, 2026 |  |  |  |  | FALSE
DELAYED PRODUCTION | Yannett Yeomans | 2026-01-14 | OC00248/PO08603 | SOMX00706 | 18/03/26 | 10461/1501 | Double Head Bolt M27x75mm, XS500-710, Carbon Steel | 2 | Super Cast Limited | China | MX WAREHOUSE |  | SEA | [8 empty] | FALSE
IN TRANSIT & DELAYED | Yannett Yeomans | 2026-01-14 | OC00248/PO08603 | SOMX00706 | 18/03/26 | 10461/1501 | Double Head Bolt M27x75mm, XS500-710, Carbon Steel | 38 | Super Cast Limited | China | MX WAREHOUSE | 2026-05-11 | AIR | ETA MAY 15 | ship DHL parts for the SOMX | DHL waybill (7963743782) |  | As per Emilka's instructions, the 1st batch remaining fasteners in OC00248/PO08603 were shipped out via DHL from Shijiazhuang for Hermosillo on May 11, 2026. |  |  |  | FALSE
IN TRANSIT & DELAYED | Yannett Yeomans | 2026-01-14 | OC00248/PO08603 | SOMX00706 | 18/03/26 | 10458/1501 | Cap Shape Nut M27, XS500-710, 201SS | 126 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-23 | SEA | 2026-05-13 |  | SHESE26251826G | left Shanghai for Ensenada by sea on Apr 23, 2026 | After Tomb-Sweeping holiday (Apr 4 to 6), OC00248/PO08603 will be ready for shipment. Already booked the vessel of ETD Apr 20 from Shanghai to Ensenada. | ETA ENSENADA: May 14 |  |  | FALSE
IN TRANSIT & DELAYED | Yannett Yeomans | 2026-01-14 | OC00248/PO08603 | SOMX00706 | 18/03/26 | 10456/0539 | FLAT WASHER, M27, XS500-710, 201SS | 84 | Super Cast Limited | China | MX WAREHOUSE | 2026-05-24 | AIR |  |  |  | left Tianjin for Ensenada by sea on May 24, 2026 |  |  |  |  | FALSE
IN TRANSIT & DELAYED | Yannett Yeomans | 2026-01-14 | OC00248/PO08603 | SOMX00706 | 18/03/26 | 10456/0539 | FLAT WASHER, M27, XS500-710, 201SS | 42 | Super Cast Limited | China | MX WAREHOUSE | 2026-05-11 | AIR | ETA MAY 15 | ship DHL parts for the SOMX | DHL waybill (7963743782) |  | As per Emilka's instructions, the 1st batch remaining fasteners in OC00248/PO08603 were shipped out via DHL from Shijiazhuang for Hermosillo on May 11, 2026. |  |  |  | FALSE
IN TRANSIT & DELAYED | Yannett Yeomans | 2026-01-14 | OC00248/PO08603 | SOMX00706 | 18/03/26 | 10541/0504 | Plug 0.25", XS500-710, 304SS | 6 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-23 | SEA | 2026-05-13 |  | SHESE26251826G | left Shanghai for Ensenada by sea on Apr 23, 2026 | After Tomb-Sweeping holiday (Apr 4 to 6), OC00248/PO08603 will be ready for shipment. Already booked the vessel of ETD Apr 20 from Shanghai to Ensenada. | ETA ENSENADA: May 14 |  |  | FALSE
IN TRANSIT & DELAYED | Yannett Yeomans | 2026-01-14 | OC00248/PO08603 | SOMX00706 | 18/03/26 | 10453/0504 | Plug 1", XS500-710, 304SS | 15 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-23 | SEA | 2026-05-13 |  | SHESE26251826G | left Shanghai for Ensenada by sea on Apr 23, 2026 | After Tomb-Sweeping holiday (Apr 4 to 6), OC00248/PO08603 will be ready for shipment. Already booked the vessel of ETD Apr 20 from Shanghai to Ensenada. | ETA ENSENADA: May 14 |  |  | FALSE
IN TRANSIT & DELAYED | Yannett Yeomans | 2026-01-14 | OC00248/PO08603 | SOMX00706 | 18/03/26 | GB/T6170 | Nut M24, XS500-710, 304SS | 16 | Super Cast Limited | China | MX WAREHOUSE | 2026-05-24 | SEA |  |  |  |  | were shipped out by sea from Tianjin to Ensenada on May 24, 2026 |  |  |  | FALSE
IN TRANSIT & DELAYED | Yannett Yeomans | 2026-01-14 | OC00248/PO08603 | SOMX00706 | 18/03/26 | GB/T6170 | Nut M24, XS500-710, 304SS | 8 | Super Cast Limited | China | MX WAREHOUSE | 2026-05-11 | AIR | ETA MAY 15 | ship DHL parts for the SOMX | DHL waybill (7963743782) |  | As per Emilka's instructions, the 1st batch remaining fasteners in OC00248/PO08603 were shipped out via DHL from Shijiazhuang for Hermosillo on May 11, 2026. |  |  |  | FALSE
IN TRANSIT & DELAYED | Yannett Yeomans | 2026-01-14 | OC00248/PO08603 | SOMX00706 | 18/03/26 | GB/T898 | Double Head Bolt AM24x75, XS500-710, 304SS | 16 | Super Cast Limited | China | MX WAREHOUSE |  | SEA | ETA Hermosillo: May 20. |  |  |  | PEter 05/17: 24 pcs AM24X75 double head bolts in OC00248/PO08603 were shipped out from Shijiazhuang to Hermosillo via DHL on May 16, 2026. |  |  |  | FALSE
IN TRANSIT & DELAYED | Yannett Yeomans | 2026-01-14 | OC00248/PO08603 | SOMX00706 | 18/03/26 | GB/T898 | Double Head Bolt AM24x75, XS500-710, 304SS | 8 | Super Cast Limited | China | MX WAREHOUSE | 2026-05-11 | AIR | ETA MAY 15 | ship DHL parts for the SOMX | DHL waybill (7963743782) |  | PEter 05/17: 24 pcs AM24X75 double head bolts in OC00248/PO08603 were shipped out from Shijiazhuang to Hermosillo via DHL on May 16, 2026. | As per Emilka's instructions, the 1st batch remaining fasteners in OC00248/PO08603 were shipped out via DHL from Shijiazhuang for Hermosillo on May 11, 2026. |  |  | FALSE
IN TRANSIT & DELAYED | Yannett Yeomans | 2026-01-14 | OC00248/PO08603 | SOMX00706 | 18/03/26 | 10538/0536 | Upper & Lower Casing, XS500-710, 416SS | 1 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-23 | SEA | ETA ENSENADA: May 14 |  | SHESE26251826G |  | left Shanghai for Ensenada by sea on Apr 23, 2026 |  |  |  | FALSE
Received | Yannett Yeomans | 2026-01-15 | OC00249/PO08605 | SOMX00713 | 31/03/26 | NS 100290241 | Dynamic Seal Kit, WPP 23-50 | 1 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-02 | AIR | 2026-05-19 |  | DHL waybill (2884550826) | DHL TO HERMOSILLO |  |  | 2026-05-19 | 2026-04-24 | TRUE
Received | Emilka Guerra | 2026-01-21 | OC00250/PO08620 | Stock | 2026-06-03 | SZ-9195970141 | Impeller | 6 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-21 | SEA | 2026-05-29 |  | LS15TJ2604877 | The available vessel is of ETD Tianjin Apr 11, 2026. | Now it is in Tianjin seaport waiting to board the vessel of ETD Apr 21 to Ensenada, together with OC00264/PO08725 (Warman parts) and OC00274/PO08771. | left Tianjin for Ensenada by sea on Apr 21, 2026 | 2026-05-29 | 2026-06-08 | TRUE
IN TRANSIT | Yannett Yeomans | 2026-02-05 | OC00255/PO08670 | Stock | 16/02/26 | 10654/6007 | Oli Seal, 150FY-40, Natural Rubber | 3 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | 2026-06-02 |  |  | DHL TO HERMOSILLO | to consolidate with Hongya's OC00237/PO08495, OC00249/PO08605 and OC00269/PO08746 |  |  |  | FALSE
IN TRANSIT | Yannett Yeomans | 2026-02-05 | OC00255/PO08670 | Stock | 16/02/26 | 10655/0512 | Spacer, 150FY-40, 316LSS | 3 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | 2026-06-02 |  |  | DHL TO HERMOSILLO | to consolidate with Hongya's OC00237/PO08495, OC00249/PO08605 and OC00269/PO08746 |  |  |  | FALSE
IN TRANSIT | Yannett Yeomans | 2026-02-09 | OC00256/PO08675 | SOMX00733 | 19/03/26 | 10640/0534 | Gland Packing Kit for A22-65 | 2 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-15 | SEA | 2026-05-14 |  |  | was shipped out from Dalian for Hermosillo via DHL on Apr 15, 2026. | the expected completed date is Apr 25, 2026. | hONGYA~ We planned to get all the parts ready by Apr 11. |  | 2026-05-14 | FALSE
In Production | Yannett Yeomans | 2026-02-27 | OC00260/PO08703 | SOMX00748 | 2026-01-05 | DVT-GV8RJHC-2I/0502 | Vertical Turbine Pump, 8RJHC-2, 420SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | 2026-06-26 | [7 empty] | FALSE
Received | Yannett Yeomans | 2026-03-04 | OC00261/PO08736 | SOMX00743 & SOMX00729 | 20/03/26 | W-D025/P10 | End Cover Shim Set, 4/3 or 6/4 D-AH | 2 | Super Cast Limited | China | MX WAREHOUSE |  | AIR | 2026-04-10 |  | DHL waybill# 4552478464. |  | left Shijiazhuang for Hermosillo via DHL on Mar 25, 2026 |  |  |  | FALSE
IN TRANSIT & DELAYED | Yannett Yeomans | 2026-03-04 | OC00261/PO08736 | SOMX00743 & SOMX00729 | 20/03/26 | AC-98-231-123-501 | Gland Side Liner, 8x6-18 SRL-C, Natural Rubber | 4 | Super Cast Limited | China | MX WAREHOUSE |  | SEA | ETA Ensenada: June 2 |  | LS15TJ2604891 | ETD Busan: May 18 | Will book the vessel of ETD Apr 28 from Tianjin to Ensenada. |  |  |  | FALSE
Received | Emilka Guerra | 2026-03-04 | OC00262/PO08720 | Stock | 2026-01-05 | OLPWZ011005B | Bearing Isolator (Inboard), D-196 MT/MTi, 303SS Rotor / Bronze | 2 | Shandong Furkey Pumps Co., Ltd. | China | MX WAREHOUSE | 2026-05-06 | SEA | 17/07/26 |  | DYNM-029 (OC00262/PO08720) | Furkey: Order will be ready on April 20th. Booking shipping space to the port of Ensenada | Furkey 04/23: has been transported to Shanghai seaport. It is estimated to be shipped around the end of month | The vessel sailed from Shanghai seaport on 6th May. | 2026-07-17 | 2026-06-17 | TRUE
Received | Emilka Guerra | 2026-03-04 | OC00262/PO08720 | Stock | 2026-01-05 | OLPWZ011006B | Bearing Isolator (Outboard), D-196 MT/MTi, 303SS Rotor / Bronze | 4 | Shandong Furkey Pumps Co., Ltd. | China | MX WAREHOUSE | 2026-05-06 | SEA | 17/07/26 |  | DYNM-029 (OC00262/PO08720) | Furkey: Order will be ready on April 20th. Booking shipping space to the port of Ensenada | Furkey 04/23: has been transported to Shanghai seaport. It is estimated to be shipped around the end of month | The vessel sailed from Shanghai seaport on 6th May. | 2026-07-17 | 2026-06-17 | TRUE
Received | Emilka Guerra | 2026-03-04 | OC00262/PO08720 | Stock | 2026-01-05 | G-R104-733 2238 | Shaft Kit (Sleeve Type), D-196 MT, 4140 Steel, with Nut, Washer, and Key | 3 | Shandong Furkey Pumps Co., Ltd. | China | MX WAREHOUSE | 2026-05-06 | SEA | 17/07/26 |  | DYNM-029 (OC00262/PO08720) | Furkey: Order will be ready on April 20th. Booking shipping space to the port of Ensenada | Furkey 04/23: has been transported to Shanghai seaport. It is estimated to be shipped around the end of month | The vessel sailed from Shanghai seaport on 6th May. | 2026-07-17 | 2026-06-17 | TRUE
Received | Emilka Guerra | 2026-03-04 | OC00262/PO08720 | Stock | 2026-01-05 | 468421/0507 | Power End, D-196 X17, 316SS Shaft (Sleeved Type), CD4MCu Fra | 2 | Shandong Furkey Pumps Co., Ltd. | China | MX WAREHOUSE | 2026-05-06 | SEA | 17/07/26 |  | DYNM-029 (OC00262/PO08720) | Furkey: Order will be ready on April 20th. Booking shipping space to the port of Ensenada | Furkey 04/23: has been transported to Shanghai seaport. It is estimated to be shipped around the end of month | The vessel sailed from Shanghai seaport on 6th May. | 2026-07-17 | 2026-06-17 | TRUE
Received | Emilka Guerra | 2026-03-04 | OC00262/PO08720 | Stock | 2026-01-05 | G-0D04563A02 1216 | Impeller, 4x6-17, D-196 X17, CD4MCu, 5-Vane | 1 | Shandong Furkey Pumps Co., Ltd. | China | MX WAREHOUSE | 2026-05-06 | SEA | 17/07/26 |  | DYNM-029 (OC00262/PO08720) | Furkey: Order will be ready on April 20th. Booking shipping space to the port of Ensenada | Furkey 04/23: has been transported to Shanghai seaport. It is estimated to be shipped around the end of month | The vessel sailed from Shanghai seaport on 6th May. | 2026-07-17 | 2026-06-17 | TRUE
Received | Emilka Guerra | 2026-03-04 | OC00262/PO08720 | Stock | 2026-01-05 | G-249-62 1216 | Casing, 3x4-10, D-196 MT, CD4MCu | 2 | Shandong Furkey Pumps Co., Ltd. | China | MX WAREHOUSE | 2026-05-06 | SEA | 17/07/26 |  | DYNM-029 (OC00262/PO08720) | Furkey: Order will be ready on April 20th. Booking shipping space to the port of Ensenada | Furkey 04/23: has been transported to Shanghai seaport. It is estimated to be shipped around the end of month | The vessel sailed from Shanghai seaport on 6th May. | 2026-07-17 | 2026-06-17 | TRUE
Received | Emilka Guerra | 2026-03-05 | OC00263/PO08721 | Stock | 2026-05-01 | 10046/5001 | Suction Bell Bearing, 12RJHC-8, Teflon | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE | 2026-04-23 | SEA | 2026-07-17 |  | SHESE26251826G | left Shanghai for Ensenada by sea on Apr 23, 2026 | After Tomb-Sweeping holiday (Apr 4 to 6), OC00248/PO08603 will be ready for shipment. I will arrange the sea freight to Ensenada. | ETA ENSENADA: May 14 | 2026-07-17 | 2026-06-09 | TRUE
Received | Emilka Guerra | 2026-03-05 | OC00263/PO08721 | Stock | 2026-05-01 | 10045/5001 | Bowl Bearing, 12RJHC-8, Teflon | 16 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE | 2026-04-23 | SEA | 2026-07-17 |  | SHESE26251826G | left Shanghai for Ensenada by sea on Apr 23, 2026 | After Tomb-Sweeping holiday (Apr 4 to 6), OC00248/PO08603 will be ready for shipment. I will arrange the sea freight to Ensenada. | ETA ENSENADA: May 14 | 2026-07-17 | 2026-06-09 | TRUE
Received | Emilka Guerra | 2026-03-05 | OC00263/PO08721 | Stock | 2026-05-01 | 10049/0505 | Impeller Shaft, 12RJHC-8, 316SS | 2 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE | 2026-04-23 | SEA | 2026-07-17 |  | SHESE26251826G | left Shanghai for Ensenada by sea on Apr 23, 2026 | After Tomb-Sweeping holiday (Apr 4 to 6), OC00248/PO08603 will be ready for shipment. I will arrange the sea freight to Ensenada. | ETA ENSENADA: May 14 | 2026-07-17 | 2026-06-09 | TRUE
Received | Emilka Guerra | 2026-03-05 | OC00263/PO08721 | Stock | 2026-05-01 | 10059/5001 | Suction Bell Bearing, 18BHC-1, Teflon | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE | 2026-04-23 | SEA | 2026-07-17 |  | SHESE26251826G | left Shanghai for Ensenada by sea on Apr 23, 2026 | After Tomb-Sweeping holiday (Apr 4 to 6), OC00248/PO08603 will be ready for shipment. I will arrange the sea freight to Ensenada. | ETA ENSENADA: May 14 | 2026-07-17 | 2026-06-09 | TRUE
Received | Emilka Guerra | 2026-03-05 | OC00263/PO08721 | Stock | 2026-05-01 | 10060/5001 | Stuffing Box Bearing, 18BHC-1, Teflon | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE | 2026-04-23 | SEA | 2026-07-17 |  | SHESE26251826G | left Shanghai for Ensenada by sea on Apr 23, 2026 | After Tomb-Sweeping holiday (Apr 4 to 6), OC00248/PO08603 will be ready for shipment. I will arrange the sea freight to Ensenada. | ETA ENSENADA: May 14 | 2026-07-17 | 2026-06-09 | TRUE
Received | Emilka Guerra | 2026-03-05 | OC00263/PO08721 | Stock | 2026-05-01 | 10063/1501 | Lineshaft Coupling, 18BHC-1, 316SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE | 2026-04-23 | SEA | 2026-07-17 |  | SHESE26251826G | left Shanghai for Ensenada by sea on Apr 23, 2026 | After Tomb-Sweeping holiday (Apr 4 to 6), OC00248/PO08603 will be ready for shipment. I will arrange the sea freight to Ensenada. | ETA ENSENADA: May 14 | 2026-07-17 | 2026-06-09 | TRUE
Received | Emilka Guerra | 2026-03-05 | OC00263/PO08721 | Stock | 2026-05-01 | 10345/0503 | Head Shaft, 7CHC-9, 420SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE | 2026-04-23 | SEA | 2026-07-17 |  | SHESE26251826G | left Shanghai for Ensenada by sea on Apr 23, 2026 | After Tomb-Sweeping holiday (Apr 4 to 6), OC00248/PO08603 will be ready for shipment. I will arrange the sea freight to Ensenada. | ETA ENSENADA: May 14 | 2026-07-17 | 2026-06-09 | TRUE
Received | Emilka Guerra | 2026-03-05 | OC00263/PO08721 | Stock | 2026-05-01 | DC-MS000021 | Mechanical Seal, Dynapro Vertical Turbine, 12RJHC-8, A20 | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE | 2026-04-23 | SEA | 2026-07-17 |  | SHESE26251826G | left Shanghai for Ensenada by sea on Apr 23, 2026 | After Tomb-Sweeping holiday (Apr 4 to 6), OC00248/PO08603 will be ready for shipment. I will arrange the sea freight to Ensenada. | ETA ENSENADA: May 14 | 2026-07-17 | 2026-06-09 | TRUE
Received | Emilka Guerra | 2026-03-05 | OC00263/PO08721 | Stock | 2026-05-01 | DC-MS000035 | Mechanical Seal, 7CHC-9 | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE | 2026-04-23 | SEA | 2026-07-17 |  | SHESE26251826G | left Shanghai for Ensenada by sea on Apr 23, 2026 | After Tomb-Sweeping holiday (Apr 4 to 6), OC00248/PO08603 will be ready for shipment. I will arrange the sea freight to Ensenada. | ETA ENSENADA: May 14 | 2026-07-17 | 2026-06-09 | TRUE
Received | Emilka Guerra | 2026-03-05 | OC00264/PO08725 | SOMX00746 & Stock | 2026-02-04 | W-F029/A05 | Expeller Ring, 8/6 F-AH, High Chrome | 1 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-21 | SEA | 2026-05-03 |  | LS15TJ2604877 | Expeller Ring for SOMX00746 | After the Tomb-Sweeping holiday (Apr 4 to 6), the 1st batch will be ready for shipment. | ETA ENSENADA: May 14 | 2026-03-05 | 2026-06-09 | TRUE
Received | Emilka Guerra | 2026-03-05 | OC00264/PO08725 | SOMX00746 & Stock | 2026-02-04 | W-E109/S50 | Shaft Sleeve O-Ring, 6/4 E-AH or 8/6 E,R or F-AH, Viton | 7 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-21 | SEA | 2026-05-03 |  | LS15TJ2604877 |  | After the Tomb-Sweeping holiday (Apr 4 to 6), the 1st batch will be ready for shipment. | ETA ENSENADA: May 14 | 2026-03-05 | 2026-06-09 | TRUE
Received | Emilka Guerra | 2026-03-05 | OC00264/PO08725 | SOMX00746 & Stock | 2026-02-04 | SZ-E11B104591 | Bearing Cover, O-Ring | 11 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-02 | AIR | 2026-05-03 |  | DHL waybill (2884550826) | DHL TO HERMOSILLO | After the Tomb-Sweeping holiday (Apr 4 to 6), the 1st batch will be ready for shipment. |  | 2026-03-05 | 2026-04-27 | TRUE
Received | Emilka Guerra | 2026-03-05 | OC00264/PO08725 | SOMX00746 & Stock | 2026-02-04 | SZ-2837900133-1 | Shaft | 2 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-21 | SEA | 2026-06-03 |  | LS15TJ2604877 |  |  | ETA ENSENADA: May 14 | 2026-03-05 | 2026-06-09 | TRUE
Received | Emilka Guerra | 2026-03-05 | OC00264/PO08725 | SOMX00746 & Stock | 2026-02-04 | W-E075/C21 | Shaft Sleeve, 6/4 or 8/6 E or R-AH, 420SS Heat Treated, Hard | 1 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-21 | SEA | 2026-06-03 |  | LS15TJ2604877 |  | After the Tomb-Sweeping holiday (Apr 4 to 6), the 1st batch will be ready for shipment. | ETA ENSENADA: May 14 | 2026-03-05 | 2026-06-09 | TRUE
Received | Emilka Guerra | 2026-03-05 | OC00264/PO08725 | SOMX00746 & Stock | 2026-02-04 | SZ-EL1208506M | Deflector | 13 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-02 | AIR | 2026-06-03 |  | DHL waybill (2884550826) | DHL TO HERMOSILLO | After the Tomb-Sweeping holiday (Apr 4 to 6), the 1st batch will be ready for shipment. |  | 2026-03-05 | 2026-04-27 | TRUE
Received | Emilka Guerra | 2026-03-05 | OC00264/PO08725 | SOMX00746 & Stock | 2026-02-04 | SZ-3822790584 | Static Seal | 5 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-02 | AIR | 2026-06-03 |  | DHL waybill (2884550826) | DHL TO HERMOSILLO | After the Tomb-Sweeping holiday (Apr 4 to 6), the 1st batch will be ready for shipment. |  | 2026-03-05 | 2026-04-27 | TRUE
Received | Emilka Guerra | 2026-03-05 | OC00264/PO08725 | SOMX00746 & Stock | 2026-02-04 | B12051-76-110-03 | Bearing Cover, XS500-710, HT250 | 2 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-23 | SEA | 2026-06-03 |  | SHESE26251826G | left Shanghai for Ensenada by sea on Apr 23, 2026 |  | ETA ENSENADA: May 14 | 2026-03-05 | 2026-06-09 | TRUE
Received | Emilka Guerra | 2026-03-05 | OC00264/PO08725 | SOMX00746 & Stock | 2026-02-04 | M74-140 | Mechanical Seal, XS500-710 | 3 | Super Cast Limited | China | MX WAREHOUSE | 2026-05-25 | AIR | ETA Hermosillo: May 28. |  | DHL waybill (1970113983) | (3 pcs M74-140 mechanical seal) | left Shijiazhuang for Hermosillo via DHL on May 25, 2026: |  | 2026-03-05 | 2026-06-09 | TRUE
IN TRANSIT | Emilka Guerra | 2026-03-05 | OC00264/PO08725 | SOMX00746 & Stock | 2026-02-04 | JC-SCS-2 1/2-5610-XLT-SB | Single Cartridge Seal, 2 1/2", John Crane, Standard Bore | 3 | Super Cast Limited | China | MX WAREHOUSE | 2026-05-07 | AIR | ETA 2nd week of May |  | DHL waybill 6104171393 | Sent with OC00279 to complete weight |  |  | 2026-03-05 |  | FALSE
Received | Emilka Guerra | 2026-03-05 | OC00264/PO08725 | SOMX00746 & Stock | 2026-02-04 | B12051-76-110-06 | Bearing Locating Ring, XS500-710, Carbon Steel | 1 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-23 | SEA | 19/04/26 |  | SHESE26251826G | left Shanghai for Ensenada by sea on Apr 23, 2026 |  | ETA ENSENADA: May 14 | 2026-03-05 | 2026-05-25 | TRUE
Received | Emilka Guerra | 2026-03-05 | OC00264/PO08725 | SOMX00746 & Stock | 2026-02-04 | B12051-76-110-06 | Bearing Locating Ring, XS500-710, Carbon Steel | 3 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-23 | SEA | 19/04/26 |  | SHESE26251826G | left Shanghai for Ensenada by sea on Apr 23, 2026 |  | ETA ENSENADA: May 14 | 2026-03-05 | 2026-06-09 | TRUE
Received | Emilka Guerra | 2026-03-05 | OC00264/PO08725 | SOMX00746 & Stock | 2026-02-04 | B12051-76-110-06 | Bearing Locating Ring, XS500-710, Carbon Steel | 1 | Super Cast Limited | China | MX WAREHOUSE | 2026-05-11 | SEA | ETA 2nd week of May |  | DHL waybill (7963743782) | left Shijiazhuang for Hermosillo via DHL on May 11, 2026 |  | ETA ENSENADA: May 15 | 2026-03-05 | 2026-05-26 | PO08595
Received | Emilka Guerra | 2026-03-05 | OC00264/PO08725 | SOMX00746 & Stock | 2026-02-04 | CB22-140 | Mechanical Seal Cover - Bolts & Nuts, XS500-710, 2Cr13 | 3 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-23 | SEA | 19/04/26 |  | SHESE26251826G | left Shanghai for Ensenada by sea on Apr 23, 2026 |  | ETA ENSENADA: May 14 | 2026-03-05 | 2026-06-09 | TRUE
Received | Yannett Yeomans | 2026-03-09 | OC00265 | SOMX00729 | 13/03/26 | AC-98-039-047-501 | Impeller (Closed), 5x4-14 SRL-C, Natural Rubber | 9 | DYNAPRO EQUIPMENT LIMITED | Canada | MX WAREHOUSE | 2026-03-19 | LAND | 2026-09-03 |  |  | SO18901 |  |  |  |  | FALSE
Received | Yannett Yeomans | 2026-03-09 | OC00265 | SOMX00729 | 13/03/26 | AC-98-231-115-501 | Suction Side Liner, 5x4-14 SRL-C, Natural Rubber | 8 | DYNAPRO EQUIPMENT LIMITED | Canada | MX WAREHOUSE | 2026-03-19 | LAND | 2026-09-03 |  |  | SO18901 |  |  |  |  | FALSE
Received | Yannett Yeomans | 2026-03-09 | OC00265 | SOMX00729 | 13/03/26 | AC-98-231-116-501 | Gland Side Liner, 5x4-14 SRL-C, Natural Rubber | 11 | DYNAPRO EQUIPMENT LIMITED | Canada | MX WAREHOUSE | 2026-03-19 | LAND | 2026-09-03 |  |  | SO18901 |  |  |  |  | FALSE
Received | Yannett Yeomans | 2026-03-09 | OC00265 | SOMX00729 | 13/03/26 | AC-98-231-120-501 | Suction Side Liner, 8x6-18 SRL-C, Natural Rubber | 4 | DYNAPRO EQUIPMENT LIMITED | Canada | MX WAREHOUSE | 2026-03-19 | LAND | 2026-09-03 |  |  | SO18901 |  |  |  |  | FALSE
Received | Yannett Yeomans | 2026-03-09 | OC00265 | SOMX00729 | 13/03/26 | AC-98-231-121-501 | Suction Side Plate, 8x6-18 SRL-C, Natural Rubber | 4 | DYNAPRO EQUIPMENT LIMITED | Canada | MX WAREHOUSE | 2026-03-19 | LAND | 2026-09-03 |  |  | SO18901 |  |  |  |  | FALSE
Received | Yannett Yeomans | 2026-03-09 | OC00265 | SOMX00729 | 13/03/26 | AC-98-431-641-501 | Impeller (Closed), 10x8-21 SRL-C, Natural Rubber | 1 | DYNAPRO EQUIPMENT LIMITED | Canada | MX WAREHOUSE | 2026-03-19 | LAND | 2026-09-03 |  |  | SO18901 |  |  |  |  | FALSE
Received | Yannett Yeomans | 2026-03-09 | OC00265 | SOMX00729 | 13/03/26 | AC-98-231-136-501 | Gland Side Liner, 10x8-21 SRL-C, Natural Rubber | 4 | DYNAPRO EQUIPMENT LIMITED | Canada | MX WAREHOUSE | 2026-03-19 | LAND | 2026-09-03 |  |  | SO18901 |  |  |  |  | FALSE
Received | Yannett Yeomans | 2026-03-09 | OC00265 | SOMX00729 | 13/03/26 | AC-98-231-134-501 | Suction Side Liner, DSH-DV3/6007 | 2 | DYNAPRO EQUIPMENT LIMITED | Canada | MX WAREHOUSE | 2026-03-19 | LAND | 2026-09-03 |  |  | SO18901 |  |  |  |  | FALSE
Received | Yannett Yeomans | 2026-03-09 | OC00265 | SOMX00729 | 13/03/26 | AC-98-231-135-501 | Suction Side Plate, 10x8-21 SRL-C, Natural Rubber | 8 | DYNAPRO EQUIPMENT LIMITED | Canada | MX WAREHOUSE | 2026-03-19 | LAND | 2026-09-03 |  |  | SO18901 |  |  |  |  | FALSE
Received | Yannett Yeomans | 2026-03-09 | OC00265 | SOMX00729 | 13/03/26 | AC-98-431-651-501 | Impeller (Closed), 8x6-18 SRL-C, Natural Rubber | 2 | DYNAPRO EQUIPMENT LIMITED | Canada | MX WAREHOUSE | 2026-03-19 | LAND | 2026-10-03 |  |  | SO18901 |  |  |  |  | FALSE
DELAYED PRODUCTION | Yannett Yeomans | 2026-03-10 | OC00267 | SOMX00752 | 27/04/26 | 100MMRKCMS-03G2AS2 | Sello Mecanico Tipo Cartucho Grased Lubricated Multiresortes estacionarios Shaft 100 mm | 2 | FLEXASEAL INGENIERIA | Mexico | MX WAREHOUSE |  | LAND | 2026-05-05 |  |  |  |  | Flexaseal: Supplier will receive on April 30 | 2026-05-05 |  | FALSE
Received | Emilka Guerra | 2026-03-12 | OC00269/PO08746 | SOMX00715 | 20/03/26 | 17779900159 | Annular Washer, Sulzer A53-250 | 2 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-09 | AIR | 2026-10-04 |  | DHL waybill (2884550826) | SHIP TO GRUPO MEXICO AND ASK FOR THE WRONG PIECE BACK | The shipment left Hongya's factory on Apr 2's afternoon by truck for Guangzhou where it will be delivered to DHL. | due to the Tomb-sweeping holiday (Apr 4 to 6), the DHL does not work. | 2026-04-10 | 24/24/2026 | TRUE
Received | Emilka Guerra | 2026-03-24 | OC00270 | SOMX00751 | 14/04/26 | DC-MS000040 | Mechanical Seal 2", Type JC-C, TG/SiC/FKM/304SS, | 4 | FLEXASEAL INGENIERIA | Mexico | MX WAREHOUSE | 2026-04-23 | LAND | 28/04/26 |  |  |  | / | Este material ya se encuentra en liberación aduanal por lo que esperamos tenerlo más tardar a inicios de la siguiente semana en nuestras instalaciones listo para ser enviado. | 2026-04-28 | 2026-04-28 | TRUE
Received | Emilka Guerra | 2026-03-24 | OC00271/PO08764 | SOMX00766 | 21/04/26 | G-RPK-ESHM | Repair Kit, E-SH Pump, Goulds | 1 | SUMMIT WATER | Canada | MX WAREHOUSE |  | LAND | [6 empty] | 2026-05-12 | 2026-05-04 | TRUE
Received | Emilka Guerra | 2026-03-26 | OC00272 | SOMX00758 | 2026-03-26 | WG-4013 | [WG-4013] WEG MOTOR | 1 | BOMBAS Y MOTORES HMG | Mexico | MX WAREHOUSE | 2026-03-26 | LAND | 2026-03-26 |  |  |  | in stock |  | 2026-04-08 | 2026-03-26 | TRUE
Received | Emilka Guerra | 2026-03-26 | OC00273 | SOMX00758 | 2026-02-04 | G-C04674A | Baseplate, ST, 148 Carbon Steel | 1 | METALES Y ALEACIONES DE SONORA | Mexico | MX WAREHOUSE | 2026-04-13 | LAND | 2026-04-09 |  |  |  | / | STILL IN PRODUCTION: Aplicación de pintura. MASON: Esperamos poder entregar el proximo viernes mas tardar el dia lunes |  | 2026-04-14 | TRUE
Received | Emilka Guerra | 2026-03-30 | OC00274/PO08771 | SOMX00762 | 2026-04-28 | W-M120MC076/C21 | Shaft Sleeve, 350 MCR, 420SS | 2 | Super Cast Limited | China | MX WAREHOUSE | 2026-04-21 | AIR | 2026-07-06 |  | LS15TJ2604877 | OC00274/PO08771/SO19012 |  |  | 2026-07-06 | 2026-06-08 | TRUE
Received | Emilka Guerra | 2026-04-08 | OC00276 | SOMX00748 | 2026-04-28 | US-4642 | 7.5HP, 1800 RPM, FRAME H213TP, TIPO RUS, 230/460, US MOTORS | 1 | MCB MOTORES SA DE CV - MXN | Mexico | MX WAREHOUSE |  | LAND | [6 empty] | 2026-05-05 | 2026-05-07 | TRUE
DELAYED PRODUCTION | Yannett Yeomans | 2026-04-16 | OC00277 | SOMX00784 | 2026-04-24 | 17742003151 | Roller Bearing, SM203-640 | 3 | APPLIED MEXICO SA DE CV | Mexico | MX WAREHOUSE |  | LAND | [5 empty] | hubo un retraso con el envío desde el proveedor. | 2026-04-20 |  | FALSE
Ready to Ship | Emilka Guerra | 2026-04-17 | OC00278/PO08822 | SOMX00784 | 2026-05-22 | W-F6018TL1/R55 | Cover Plate Liner (Thick), 8/6 F-AH, Natural Rubber | 1 | DYNAPRO EQUIPMENT LIMITED | Canada | MX WAREHOUSE |  | SEA | [6 empty] | 2026-07-17 |  | FALSE
Received | Emilka Guerra | 2026-04-17 | OC00278/PO08822 | SOMX00784 | 2026-05-22 | 17779900159 | Annular Washer, Sulzer A53-250 | 6 | DYNAPRO EQUIPMENT LIMITED | Canada | MX WAREHOUSE | 2026-05-25 | AIR | ETA Hermosillo: May 28. |  | DHL waybill (1970113983) | (6 pcs annular washer) | left Shijiazhuang for Hermosillo via DHL on May 25, 2026: | Manufacturing defect | 2026-07-17 | 2026-06-09 | TRUE
IN TRANSIT | Emilka Guerra | 2026-04-23 | OC00279 | SOMX00791 | 2026-05-14 | D-500S-98B-18/E05 | Left Round Nut, 500S-98B, M105x2 LH, 1045 Steel | 12 | DYNAPRO EQUIPMENT LIMITED | Canada | MX WAREHOUSE | 2026-05-07 | AIR | ETA MAY 2nd Week |  | DHL waybill 6104171393 | Sent with a batch of OC00264 |  |  | 2026-05-21 |  | FALSE
IN TRANSIT | Yannett Yeomans | 2026-04-23 | OC00280/PO08843 | SOMX00658 | 2026-04-30 | W-FMC15145EL1/A05 | Impeller, 150 MCU, High Chrome | 1 | DYNAPRO EQUIPMENT LIMITED | Canada | MX WAREHOUSE | 2026-05-24 | SEA | ETA 1ST WEEK June |  | The 2nd vessel is SEASPAN BRAVO / 0103E LS15TJ2605877 |  | left Tianjin for Ensenada by sea on May 24, 2026 |  | 2026-06-25 |  | FALSE
In Production | Emilka Guerra | 2026-04-27 | OC00281 | SOMX00734 | 2026-06-09 | JC-SCS-1 3/4-4610-MT-BB | Single Cartridge Seal, 1 3/4", D-196 MT, Big Bore, Carbon vs | 1 | DYNAPRO EQUIPMENT LIMITED | Canada | MX WAREHOUSE |  | SEA | [6 empty] | 2026-08-18 |  | FALSE
In Production | Yannett Yeomans | 2026-04-28 | OC00282 | SOMX00800 | 2026-08-11 | XS500-710 | Dynapro Horizontal Split Case Pump 24/20, 420SS | 2 | DYNAPRO EQUIPMENT LIMITED | Canada | MX WAREHOUSE |  | SEA | [6 empty] | 2026-10-06 |  | FALSE
In Production | Yannett Yeomans | 2026-04-28 | OC00282 | SOMX00800 | 2026-08-11 | 10364/2001 | Set of Coupling and Coupling Guard XS500-10, Cast Iron | 2 | DYNAPRO EQUIPMENT LIMITED | Canada | MX WAREHOUSE |  | SEA | [6 empty] | 2026-10-06 |  | FALSE
In Production | Yannett Yeomans | 2026-04-28 | OC00282 | SOMX00800 | 2026-08-11 | 10365/1501 | Common base XS500-10, Carbon Steel | 2 | DYNAPRO EQUIPMENT LIMITED | Canada | MX WAREHOUSE |  | SEA | [6 empty] | 2026-10-06 |  | FALSE
Received | Yannett Yeomans | 2026-04-29 | OC00283 | SOMX00795 | 2026-05-07 | AC-98-231-134-501 | Suction Side Liner, DSH-DV3/6007 | 3 | DYNAPRO EQUIPMENT LIMITED | Canada | MX WAREHOUSE |  | LAND |  |  |  | Purchase from warehouse CA |  |  | 2026-05-15 | 2026-05-25 | TRUE
In Production | Yannett Yeomans | 2026-04-30 | OC00284 | SOMX00801 | 2026-05-30 | DSV-WS240/150/0003 | [150SV-SP] Vertical Sump Pump, 150SV-SP, High Chrome | 2 | DYNAPRO EQUIPMENT LIMITED | Canada | MX WAREHOUSE |  | SEA |  |  |  |  | Betty 06/10: We plan to assemble this pump next week. so it can ship out in about 10-15 days. |  |  |  | FALSE
Received | Emilka Guerra | 2026-05-14 | OC00285/PO08904 | SOMX00805 & Stock | 2026-06-11 | G-D04628A 1000 | Thrust Bearing Housing, D-196 LT, Cast Iron | 2 | Shandong Furkey Pumps Co., Ltd. | China | MX WAREHOUSE | 2026-05-25 | AIR | ETA Hermosillo: May 28. |  | SF1535462687299 / DHL waybill (1970113983) | DYNM-030 | left Shijiazhuang for Hermosillo via DHL on May 25, 2026: |  | 2026-06-25 | 2026-06-09 | TRUE
Received | Emilka Guerra | 2026-05-14 | OC00285/PO08904 | SOMX00805 & Stock | 2026-06-11 | G-B02194A 2210 | Bearing Clamp Ring, LTX | 2 | Shandong Furkey Pumps Co., Ltd. | China | MX WAREHOUSE | 2026-05-25 | AIR | ETA Hermosillo: May 28. |  | SF1535462687299 / DHL waybill (1970113983) | DYNM-030 | left Shijiazhuang for Hermosillo via DHL on May 25, 2026: |  | 2026-06-25 | 2026-06-09 | TRUE
In Production | Emilka Guerra | 2026-05-15 | OC00286 | SOMX00807 | 2026-06-12 | 10009/0512 | Shaft, 150FY-40, 316LSS | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [8 empty] | FALSE
In Production | Emilka Guerra | 2026-05-18 | OC00287 | SOMX00730 | 2026-08-10 | G-243-90 1203 | Impeller, 6x8-13, 3171-L, 316SS | 1 | M&N Alloy Cast Products, Inc. | US | MX WAREHOUSE |  | LAND | [8 empty] | FALSE
In Production | Emilka Guerra | 2026-05-18 | OC00288 | Stock | 2026-06-29 | SZ-2837900133-1 | Shaft | 5 | Super Cast Limited | China | MX WAREHOUSE |  | SEA | [8 empty] | FALSE
In Production | Emilka Guerra | 2026-05-18 | OC00288 | Stock | 2026-06-29 | SZ-9321480153 | Bearing Housing | 2 | Super Cast Limited | China | MX WAREHOUSE |  | SEA | [8 empty] | FALSE
In Production | Emilka Guerra | 2026-05-18 | OC00288 | Stock | 2026-06-29 | SZ-EL1208506M | Deflector | 20 | Super Cast Limited | China | MX WAREHOUSE |  | SEA | [8 empty] | FALSE
In Production | Emilka Guerra | 2026-05-18 | OC00288 | Stock | 2026-06-29 | SZ-9268290131 | Labyrinth Ring | 10 | Super Cast Limited | China | MX WAREHOUSE |  | SEA | [8 empty] | FALSE
In Production | Emilka Guerra | 2026-05-18 | OC00289 | Stock | 2026-07-06 | DC-MS000021 | Mechanical Seal, Dynapro Vertical Turbine, 12RJHC-8, A20 | 10 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [8 empty] | FALSE
In Production | Emilka Guerra | 2026-05-18 | OC00289 | Stock | 2026-07-06 | 10061/0505 | Impeller Shaft, 18BHC-1, 316SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [8 empty] | FALSE
In Production | Emilka Guerra | 2026-05-18 | OC00289 | Stock | 2026-07-06 | 10062/0505 | Impeller Collect, 18BHC-1, 316SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [8 empty] | FALSE
In Production | Emilka Guerra | 2026-05-18 | OC00289 | Stock | 2026-07-06 | 10009/0512 | Shaft, 150FY-40, 316LSS | 2 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [8 empty] | FALSE
In Production | Yannett Yeomans | 2026-05-19 | OC00290 | Stock 16DMC-4 | 2026-07-07 | 10671/0504 | Cartridge Mechanical Seal, 16DMC-4, 304SS | 2 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [8 empty] | FALSE
In Production | Yannett Yeomans | 2026-05-19 | OC00290 | Stock 16DMC-4 | 2026-07-07 | 10672/0526 | Coupling, 16DMC-4, 416SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [8 empty] | FALSE
In Production | Yannett Yeomans | 2026-05-19 | OC00290 | Stock 16DMC-4 | 2026-07-07 | 10673/2001 | Adjusting Nut, 16DMC-4, Cast Iron | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [8 empty] | FALSE
In Production | Yannett Yeomans | 2026-05-19 | OC00290 | Stock 16DMC-4 | 2026-07-07 | 10674/0526 | Motor Shaft, 16DMC-4, 416SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [8 empty] | FALSE
In Production | Yannett Yeomans | 2026-05-19 | OC00290 | Stock 16DMC-4 | 2026-07-07 | 10675/0504 | Stuffing Box Hex Bolts and Spring Washers, 16DMC-4, 304SS | 6 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [8 empty] | FALSE
In Production | Yannett Yeomans | 2026-05-19 | OC00290 | Stock 16DMC-4 | 2026-07-07 | 10676/0504 | Stuffing Box Bearing Retaining Ring, 16DMC-4, 304SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [8 empty] | FALSE
In Production | Yannett Yeomans | 2026-05-19 | OC00290 | Stock 16DMC-4 | 2026-07-07 | 10677/5001 | Stuffing Box Bearing,16DMC-4, Teflon | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [8 empty] | FALSE
In Production | Yannett Yeomans | 2026-05-19 | OC00290 | Stock 16DMC-4 | 2026-07-07 | 10680/0504 | Discharge Head Hex Bolts and Spring Washers, 16DMC-4, 304SS | 12 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [8 empty] | FALSE
In Production | Yannett Yeomans | 2026-05-19 | OC00290 | Stock 16DMC-4 | 2026-07-07 | 10681/5010 | Inlet Flange Paper Gasket, 16DMC-4, - | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [8 empty] | FALSE
In Production | Yannett Yeomans | 2026-05-19 | OC00290 | Stock 16DMC-4 | 2026-07-07 | 10683/0526 | Lineshaft, 16DMC-4, 416SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [8 empty] | FALSE
In Production | Yannett Yeomans | 2026-05-19 | OC00290 | Stock 16DMC-4 | 2026-07-07 | 10684/0504 | Spider Bearing Retaining Ring, 16DMC-4, 304SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [8 empty] | FALSE
In Production | Yannett Yeomans | 2026-05-19 | OC00290 | Stock 16DMC-4 | 2026-07-07 | 10685/5001 | Spider Bearing, 16DMC-4, Teflon | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [8 empty] | FALSE
In Production | Yannett Yeomans | 2026-05-19 | OC00290 | Stock 16DMC-4 | 2026-07-07 | 10687/0526 | Coupling, 16DMC-4, 416SS | 2 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [8 empty] | FALSE
In Production | Yannett Yeomans | 2026-05-19 | OC00290 | Stock 16DMC-4 | 2026-07-07 | 10688/0526 | Lower Lineshaft, 16DMC-4, 416SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [8 empty] | FALSE
In Production | Yannett Yeomans | 2026-05-19 | OC00290 | Stock 16DMC-4 | 2026-07-07 | 10690/0504 | Discharge Bowl Hex Bolts, Spring Washers and Nuts, 16DMC-4, 304SS | 8 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [8 empty] | FALSE
In Production | Yannett Yeomans | 2026-05-19 | OC00290 | Stock 16DMC-4 | 2026-07-07 | 10691/0504 | Intermediate Bowl Hex Bolts and Spring Washers, 16DMC-4, 304SS | 32 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [8 empty] | FALSE
In Production | Yannett Yeomans | 2026-05-19 | OC00290 | Stock 16DMC-4 | 2026-07-07 | 10692/0526 | Impeller Shaft, 16DMC-4, 416SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [8 empty] | FALSE
In Production | Yannett Yeomans | 2026-05-19 | OC00290 | Stock 16DMC-4 | 2026-07-07 | 10693/0504 | Discharge Bowl Bearing Retaining Ring, 16DMC-4, 304SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [8 empty] | FALSE
In Production | Yannett Yeomans | 2026-05-19 | OC00290 | Stock 16DMC-4 | 2026-07-07 | 10694/5001 | Discharge Bowl Bearing, 16DMC-4, Teflon | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [8 empty] | FALSE
In Production | Yannett Yeomans | 2026-05-19 | OC00290 | Stock 16DMC-4 | 2026-07-07 | 10696/0504 | Impeller Collect Hex Bolts and Spring Washers, 16DMC-4, 304SS | 16 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [8 empty] | FALSE
In Production | Yannett Yeomans | 2026-05-19 | OC00290 | Stock 16DMC-4 | 2026-07-07 | 10697/0505 | Impeller Collect, 16DMC-4, 316SS | 4 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [8 empty] | FALSE
In Production | Yannett Yeomans | 2026-05-19 | OC00290 | Stock 16DMC-4 | 2026-07-07 | 10698/0505 | Impeller, 16DMC-4, 316SS | 4 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [8 empty] | FALSE
In Production | Yannett Yeomans | 2026-05-19 | OC00290 | Stock 16DMC-4 | 2026-07-07 | 10699/0504 | Intermediate Bowl Bearing Retaining Ring, 16DMC-4, 304SS | 3 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [8 empty] | FALSE
In Production | Yannett Yeomans | 2026-05-19 | OC00290 | Stock 16DMC-4 | 2026-07-07 | 10700/5001 | Intermediate Bowl Bearing, 16DMC-4, Teflon | 3 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [8 empty] | FALSE
In Production | Yannett Yeomans | 2026-05-19 | OC00290 | Stock 16DMC-4 | 2026-07-07 | 10702/3002 | Sand Collar, 16DMC-4, Bronze | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [8 empty] | FALSE
In Production | Yannett Yeomans | 2026-05-19 | OC00290 | Stock 16DMC-4 | 2026-07-07 | 10703/0504 | Suction Bell Hex Bolts and Spring Washers, 16DMC-4, 304SS | 6 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [8 empty] | FALSE
In Production | Yannett Yeomans | 2026-05-19 | OC00290 | Stock 16DMC-4 | 2026-07-07 | 10704/0504 | Suction Bell Bearing Retaining Ring, 16DMC-4, 304SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [8 empty] | FALSE
In Production | Yannett Yeomans | 2026-05-19 | OC00290 | Stock 16DMC-4 | 2026-07-07 | 10705/5001 | Suction Bowl Bearing, 16DMC-4, Teflon | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [8 empty] | FALSE
In Production | Emilka Guerra | 2026-05-26 | OC00291 | SOMX00810 | 2026-06-30 | D-500S-98B-16/C21 | Bearing Baffler, 500S-98B, 420SS | 6 | Super Cast Limited | China | MX WAREHOUSE |  | AIR |  | DHL SHIPMENT |  |  |  |  | 2026-07-21 |  | FALSE
In Production | Emilka Guerra | 2026-06-03 | OC00292 | Stock | 2026-07-22 | OLPWZ011006B | Bearing Isolator (Outboard), D-196 MT/MTi, 303SS Rotor / Bronze | 10 | Shandong Furkey Pumps Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-30 |  | FALSE
In Production | Emilka Guerra | 2026-06-03 | OC00293 | Stock | 2026-07-22 | JC-SCS-1 3/4-4610-MT-BB | Single Cartridge Seal, 1 3/4", D-196 MT, Big Bore, Carbon vs | 2 | Super Cast Limited | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-30 |  | FALSE
In Production | Emilka Guerra | 2026-06-03 | OC00293 | Stock | 2026-07-22 | W-E028/A05 | Expeller, 6/4 E-AH, High Chrome | 5 | Super Cast Limited | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-30 |  | FALSE
In Production | Emilka Guerra | 2026-06-03 | OC00293 | Stock | 2026-07-22 | W-E029/A05 | Expeller Ring, 6/4 E-AH, High Chrome | 4 | Super Cast Limited | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-30 |  | FALSE
In Production | Emilka Guerra | 2026-06-03 | OC00294 | Stock | 2026-07-22 | 10673/2001 | Adjusting Nut, 16DMC-4, Cast Iron | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-30 |  | FALSE
In Production | Emilka Guerra | 2026-06-03 | OC00294 | Stock | 2026-07-22 | 10674/0526 | Motor Shaft, 16DMC-4, 416SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-30 |  | FALSE
In Production | Emilka Guerra | 2026-06-03 | OC00294 | Stock | 2026-07-22 | 10677/5001 | Stuffing Box Bearing,16DMC-4, Teflon | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-30 |  | FALSE
In Production | Emilka Guerra | 2026-06-03 | OC00294 | Stock | 2026-07-22 | 10672/0526 | Coupling, 16DMC-4, 416SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-30 |  | FALSE
In Production | Emilka Guerra | 2026-06-03 | OC00294 | Stock | 2026-07-22 | 10671/0504 | Cartridge Mechanical Seal, 16DMC-4, 304SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-30 |  | FALSE
In Production | Emilka Guerra | 2026-06-03 | OC00294 | Stock | 2026-07-22 | 10685/5001 | Spider Bearing, 16DMC-4, Teflon | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-30 |  | FALSE
In Production | Emilka Guerra | 2026-06-03 | OC00294 | Stock | 2026-07-22 | 10694/5001 | Discharge Bowl Bearing, 16DMC-4, Teflon | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-30 |  | FALSE
In Production | Emilka Guerra | 2026-06-03 | OC00294 | Stock | 2026-07-22 | 10700/5001 | Intermediate Bowl Bearing, 16DMC-4, Teflon | 3 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-30 |  | FALSE
In Production | Emilka Guerra | 2026-06-03 | OC00294 | Stock | 2026-07-22 | 10705/5001 | Suction Bowl Bearing, 16DMC-4, Teflon | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-30 |  | FALSE
In Production | Yannett Yeomans | 2026-06-05 | OC00295 | Stock | 2026-07-06 | D-SH645 | Submersible Sewage Pump, SH645, Ductile Iron w/Impeller in High Chrome | 1 | Super Cast Limited | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-04 |  | FALSE
In Production | Emilka Guerra | 2026-06-05 | OC00296 | Stock | 2026-07-10 | SZ-3822790584 | Static Seal | 10 | Super Cast Limited | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-09-04 |  | FALSE
In Production | Emilka Guerra | 2026-06-05 | OC00296 | Stock | 2026-07-10 | D-500S-98B-03/C21 | Wear Ring, 500S-98B, 420SS | 4 | Super Cast Limited | China | MX WAREHOUSE |  | SEA | [8 empty] | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## DR
STATUS | CREATED BY | ISSUE DATE | PO NUMBER | REFERENCE | DUE DATE FACTORY | SKU | PRODUCT NAME | INCOMING STOCK | SUPPLIER | ORIGIN | SHIP TO | SHIPPING DATE SUPPLIER | TRANSIT | ETA WAREHOUSE | SHIPPING INSTRUCTIONS | TRACKING NUMBER / UPDATES | IMPORTANT NOTE | PETER UPDATES | DELAY ISSUES | EST RECEIPT DATE ODOO | RECEPTION DATE WAREHOUSE | COMPLETED
IN TRANSIT | Yannett Yeomans | 2025-12-16 18:13 | PODR00008 | Stock HPCW Parts | 23/02/26 | 10JKH, 7-Vane Impeller, CD4MCu | Impeller, 10JKH, Double Keyed, w/Wear Ring | 4 | Jiangsu Win-win International Trading Co., Ltd. | China | DR WAREHOUSE | 2026-05-04 | SEA | ETA Manzanillo: May 29. ETA DR Warehouse June 22nd | Peter can Consolidate orders: SHIP TO RIO HAINA Wangyang's PODR00008, PODR00009 and AMOS' PODR00011: ETD May 4, 2026, Tianjin to Rio Haina | The packing size and weight is 940*550*610mm-278KG. | payment of the remaining 70% for the order PODR00008 has been processed. |  |  | 2026-04-20 |  | FALSE
IN TRANSIT | Yannett Yeomans | 2025-12-16 18:13 | PODR00008 | Stock HPCW Parts | 23/02/26 | D-2001408-2507 | Impeller Wear Ring, 10JKH/M, 5.12x5.48x0.88, Duplex SS 2507 w/Ion Nitriding | 8 | Jiangsu Win-win International Trading Co., Ltd. | China | DR WAREHOUSE | 2026-05-04 | SEA | ETA Manzanillo: May 29. ETA DR Warehouse June 22nd | Peter can Consolidate orders: SHIP TO RIO HAINA Wangyang's PODR00008, PODR00009 and AMOS' PODR00011: ETD May 4, 2026, Tianjin to Rio Haina | The packing size and weight is 940*550*610mm-278KG. | payment of the remaining 70% for the order PODR00008 has been processed. |  |  | 2026-04-20 |  | FALSE
IN TRANSIT | Yannett Yeomans | 2025-12-16 18:13 | PODR00008 | Stock HPCW Parts | 23/02/26 | D-2001407-2507 | Bowl Wear Ring, 10JKH/M, 05.50x05.88x0.88, Duplex SS 2507 w/Ion Nitriding | 8 | Jiangsu Win-win International Trading Co., Ltd. | China | DR WAREHOUSE | 2026-05-04 | SEA | ETA Manzanillo: May 29. ETA DR Warehouse June 22nd | Peter can Consolidate orders: SHIP TO RIO HAINA Wangyang's PODR00008, PODR00009 and AMOS' PODR00011: ETD May 4, 2026, Tianjin to Rio Haina | The packing size and weight is 940*550*610mm-278KG. | payment of the remaining 70% for the order PODR00008 has been processed. |  |  | 2026-04-20 |  | FALSE
IN TRANSIT | Yannett Yeomans | 2025-12-16 18:13 | PODR00008 | Stock HPCW Parts | 23/02/26 | D-2001405-CD4 | Bowl,10JKH/M, BW-INT-STEP-NO-SL-SP, CD4MCu | 7 | Jiangsu Win-win International Trading Co., Ltd. | China | DR WAREHOUSE | 2026-05-04 | SEA | ETA Manzanillo: May 29. ETA DR Warehouse June 22nd | Peter can Consolidate orders: SHIP TO RIO HAINA Wangyang's PODR00008, PODR00009 and AMOS' PODR00011: ETD May 4, 2026, Tianjin to Rio Haina | The packing size and weight is 940*550*610mm-278KG. | payment of the remaining 70% for the order PODR00008 has been processed. |  |  | 2026-04-20 |  | FALSE
IN TRANSIT | Yannett Yeomans | 2025-12-16 18:13 | PODR00008 | Stock HPCW Parts | 23/02/26 | D-2001434-CD4 | Bowl (Top),10JKH/M, w/"O" Ring, CD4MCu | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | DR WAREHOUSE | 2026-05-04 | SEA | ETA Manzanillo: May 29. ETA DR Warehouse June 22nd | Peter can Consolidate orders: SHIP TO RIO HAINA | The packing size and weight is 940*550*610mm-278KG. | payment of the remaining 70% for the order PODR00008 has been processed. |  |  | 2026-04-20 |  | FALSE
IN TRANSIT | Yannett Yeomans | 2025-12-16 18:13 | PODR00008 | Stock HPCW Parts | 23/02/26 | D-2001417-CD4 | Bell,10JKH/M, BW-FLG-STD-STEP-CUT_NR, CD4MCu | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | DR WAREHOUSE | 2026-05-04 | SEA | ETA Manzanillo: May 29. ETA DR Warehouse June 22nd | Peter can Consolidate orders: SHIP TO RIO HAINA Wangyang's PODR00008, PODR00009 and AMOS' PODR00011: ETD May 4, 2026, Tianjin to Rio Haina | The packing size and weight is 940*550*610mm-278KG. | payment of the remaining 70% for the order PODR00008 has been processed. |  |  | 2026-04-20 |  | FALSE
IN TRANSIT | Yannett Yeomans | 2025-12-16 18:13 | PODR00008 | Stock HPCW Parts | 23/02/26 | D-2001412-4PHSS | Hex Cap Screw, 10JKH/M, 0.44-14NCx1.50, 17-4PH SS | 96 | Jiangsu Win-win International Trading Co., Ltd. | China | DR WAREHOUSE | 2026-05-04 | SEA | ETA Manzanillo: May 29. ETA DR Warehouse June 22nd | Peter can Consolidate orders: SHIP TO RIO HAINA Wangyang's PODR00008, PODR00009 and AMOS' PODR00011: ETD May 4, 2026, Tianjin to Rio Haina | The packing size and weight is 940*550*610mm-278KG. | payment of the remaining 70% for the order PODR00008 has been processed. |  |  | 2026-04-20 |  | FALSE
IN TRANSIT | Yannett Yeomans | 2025-12-16 18:13 | PODR00008 | Stock HPCW Parts | 23/02/26 | 10JKM, 6-Vane Impeller, CD4 | Impeller, 10JKM, Double Keyed, w/Wear Ring | 4 | Jiangsu Win-win International Trading Co., Ltd. | China | DR WAREHOUSE | 2026-05-04 | SEA | ETA Manzanillo: May 29. ETA DR Warehouse June 22nd | Peter can Consolidate orders: SHIP TO RIO HAINA Wangyang's PODR00008, PODR00009 and AMOS' PODR00011: ETD May 4, 2026, Tianjin to Rio Haina | The packing size and weight is 940*550*610mm-278KG. | payment of the remaining 70% for the order PODR00008 has been processed. |  |  | 2026-04-20 |  | FALSE
IN TRANSIT | Emilka Guerra | 2026-02-18 16:55 | PODR00009 | Stock HPCW Parts | 15/05/26 | D-2001414-2507 | Key (Square), 10JKH/M, 0.38x1.13LG, Duplex SS 2507 | 8 | Jiangsu Win-win International Trading Co., Ltd. | China | DR WAREHOUSE | 2026-05-04 | SEA | ETA Manzanillo: May 29. ETA DR Warehouse June 22nd | Peter can Consolidate orders: SHIP TO RIO HAINA Wangyang's PODR00008, PODR00009 and AMOS' PODR00011: ETD May 4, 2026, Tianjin to Rio Haina |  | The packing size and weight is 200*170*130mm and 4.1KG. | Pending Peter instructions so winwin can send |  | 2026-02-21 |  | FALSE
IN TRANSIT | Emilka Guerra | 2026-02-18 16:55 | PODR00009 | Stock HPCW Parts | 15/05/26 | D-2001416-174PH | Hex-Head Socket Cap Screw, 10JKH/M, 0.31-18NCx0.750, 17-4PH SS | 300 | Jiangsu Win-win International Trading Co., Ltd. | China | DR WAREHOUSE | 2026-05-04 | SEA | ETA Manzanillo: May 29. ETA DR Warehouse June 22nd | Peter can Consolidate orders: SHIP TO RIO HAINA Wangyang's PODR00008, PODR00009 and AMOS' PODR00011: ETD May 4, 2026, Tianjin to Rio Haina |  | The packing size and weight is 200*170*130mm and 4.1KG. | Pending Peter instructions so winwin can send |  | 2026-08-07 |  | FALSE
IN TRANSIT | Emilka Guerra | 2026-02-18 20:18 | PODR00010 | Stock 400ZJD & M150KSH-EB Parts | 2026-08-05 | W-STL40147BF/A49 | Impeller, 400 ZJD, BF, Ultrachrome | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | DR WAREHOUSE | 2026-05-17 | SEA | ETA DR Warehouse 1st week of july | Peter can Consolidate orders: SHIP TO RIO HAINA | LS15TJ2605785 | Status email sent on May 8th Naipu's PODR00010: ETD May 14, 2026, Tianjin to Rio Haina | Peter May 8th: Already booked the vessel of ETD May 14 from Tianjin to Rio Haina, Dominican Republic. | left Tianjin for Rio Haina by sea on May 17, 2026 | 2026-08-07 |  | FALSE
IN TRANSIT | Emilka Guerra | 2026-02-18 20:18 | PODR00010 | Stock 400ZJD & M150KSH-EB Parts | 2026-08-05 | W-TL40083M/A49 | Throatbush, 400 ZJD, Ultrachrome | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | DR WAREHOUSE | 2026-05-17 | SEA | ETA DR Warehouse 1st week of july | Peter can Consolidate orders: SHIP TO RIO HAINA | LS15TJ2605785 | Status email sent on May 8th Naipu's PODR00010: ETD May 14, 2026, Tianjin to Rio Haina | Peter May 8th: Already booked the vessel of ETD May 14 from Tianjin to Rio Haina, Dominican Republic. | left Tianjin for Rio Haina by sea on May 17, 2026 | 2026-08-07 |  | FALSE
IN TRANSIT | Emilka Guerra | 2026-02-18 20:18 | PODR00010 | Stock 400ZJD & M150KSH-EB Parts | 2026-08-05 | W-TL40110/A49 | Volute Liner, 400 ZJD, Ultrachrome | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | DR WAREHOUSE | 2026-05-17 | SEA | ETA DR Warehouse 1st week of july | Peter can Consolidate orders: SHIP TO RIO HAINA | LS15TJ2605785 | Status email sent on May 8th Naipu's PODR00010: ETD May 14, 2026, Tianjin to Rio Haina | Peter May 8th: Already booked the vessel of ETD May 14 from Tianjin to Rio Haina, Dominican Republic. | left Tianjin for Rio Haina by sea on May 17, 2026 | 2026-08-07 |  | FALSE
IN TRANSIT | Emilka Guerra | 2026-02-18 20:18 | PODR00010 | Stock 400ZJD & M150KSH-EB Parts | 2026-08-05 | W-T40041MS1M/A49 | Frame Plate Liner Insert (Mech Seal), 400 ZJD, Ultrachrome | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | DR WAREHOUSE | 2026-05-17 | SEA | ETA DR Warehouse 1st week of july | Peter can Consolidate orders: SHIP TO RIO HAINA | LS15TJ2605785 | Status email sent on May 8th Naipu's PODR00010: ETD May 14, 2026, Tianjin to Rio Haina | Peter May 8th: Already booked the vessel of ETD May 14 from Tianjin to Rio Haina, Dominican Republic. | left Tianjin for Rio Haina by sea on May 17, 2026 | 2026-08-07 |  | FALSE
IN TRANSIT | Emilka Guerra | 2026-02-18 20:18 | PODR00010 | Stock 400ZJD & M150KSH-EB Parts | 2026-08-05 | W-S076/C41 | Shaft Sleeve (Mech Seal), 400 ZJD, 2205 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | DR WAREHOUSE | 2026-05-17 | SEA | ETA DR Warehouse 1st week of july | Peter can Consolidate orders: SHIP TO RIO HAINA | LS15TJ2605785 | Status email sent on May 8th Naipu's PODR00010: ETD May 14, 2026, Tianjin to Rio Haina | Peter May 8th: Already booked the vessel of ETD May 14 from Tianjin to Rio Haina, Dominican Republic. | left Tianjin for Rio Haina by sea on May 17, 2026 | 2026-08-07 |  | FALSE
IN TRANSIT | Emilka Guerra | 2026-02-18 20:18 | PODR00010 | Stock 400ZJD & M150KSH-EB Parts | 2026-08-05 | W-F6110/A49 | Volute Liner, 8/6, Ultrachrome, Corrosion Resistant | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | DR WAREHOUSE | 2026-05-17 | SEA | ETA DR Warehouse 1st week of july | Peter can Consolidate orders: SHIP TO RIO HAINA | LS15TJ2605785 | Status email sent on May 8th Naipu's PODR00010: ETD May 14, 2026, Tianjin to Rio Haina | Peter May 8th: Already booked the vessel of ETD May 14 from Tianjin to Rio Haina, Dominican Republic. | left Tianjin for Rio Haina by sea on May 17, 2026 | 2026-08-07 |  | FALSE
IN TRANSIT | Emilka Guerra | 2026-02-18 20:18 | PODR00010 | Stock 400ZJD & M150KSH-EB Parts | 2026-08-05 | W-F6147/A49 | Impeller, 8/6 Ultrachrome, Corrosion-Resistant | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | DR WAREHOUSE | 2026-05-17 | SEA | ETA DR Warehouse 1st week of july | Peter can Consolidate orders: SHIP TO RIO HAINA | LS15TJ2605785 | Status email sent on May 8th Naipu's PODR00010: ETD May 14, 2026, Tianjin to Rio Haina | Peter May 8th: Already booked the vessel of ETD May 14 from Tianjin to Rio Haina, Dominican Republic. | left Tianjin for Rio Haina by sea on May 17, 2026 | 2026-08-07 |  | FALSE
IN TRANSIT | Emilka Guerra | 2026-02-18 20:18 | PODR00010 | Stock 400ZJD & M150KSH-EB Parts | 2026-08-05 | W-F6083/A49 | Throatbush, 8/6 Ultrachrome, Corrosion-Resistant | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | DR WAREHOUSE | 2026-05-17 | SEA | ETA DR Warehouse 1st week of july | Peter can Consolidate orders: SHIP TO RIO HAINA | LS15TJ2605785 | Status email sent on May 8th Naipu's PODR00010: ETD May 14, 2026, Tianjin to Rio Haina | Peter May 8th: Already booked the vessel of ETD May 14 from Tianjin to Rio Haina, Dominican Republic. | left Tianjin for Rio Haina by sea on May 17, 2026 | 2026-08-07 |  | FALSE
IN TRANSIT | Emilka Guerra | 2026-02-18 20:30 | PODR00011 | Stock DW-ME6/6-12S Parts | 17/04/26 | AM-MH150S12-18-CD4 | Suction flange, DW-ME6/6-12S, CD4MCu | 1 | AMOS Fluid Technology Co., Ltd | China | DR WAREHOUSE | 2026-05-04 | SEA | ETA Manzanillo: May 29. ETA DR Warehouse June 22nd | Peter can Consolidate orders: SHIP TO RIO HAINA Wangyang's PODR00008, PODR00009 and AMOS' PODR00011: ETD May 4, 2026, Tianjin to Rio Haina |  |  | Peter will consolidate order to Caucedo |  | 2026-07-31 |  | FALSE
IN TRANSIT | Emilka Guerra | 2026-02-18 20:30 | PODR00011 | Stock DW-ME6/6-12S Parts | 17/04/26 | AM-MH150S12-15-CD4 | Backplate, DW-ME6/6-12S, CD4MCu | 1 | AMOS Fluid Technology Co., Ltd | China | DR WAREHOUSE | 2026-05-04 | SEA | ETA DR Warehouse June 22nd | Peter can Consolidate orders: SHIP TO RIO HAINA Wangyang's PODR00008, PODR00009 and AMOS' PODR00011: ETD May 4, 2026, Tianjin to Rio Haina |  |  | Peter will consolidate order to Caucedo |  | 2026-07-31 |  | FALSE
IN TRANSIT | Emilka Guerra | 2026-02-19 19:53 | PODR00012 | Stock D-196 Parts | 17/04/26 | G-247-45 1204 | Casing, 3x4-8G, 3196 MTX, Alloy 20 | 1 | Shandong Furkey Pumps Co., Ltd. | China | DR WAREHOUSE | 2026-05-04 | SEA | ETA RIO HAINA around 21st June | Furkey's PODR00012 May 4, 2026, Shanghai to Rio Haina | DYNR-001 | 50% payment done ✅ |  |  | 2026-07-10 |  | FALSE
IN TRANSIT | Emilka Guerra | 2026-02-19 19:53 | PODR00012 | Stock D-196 Parts | 17/04/26 | G-0100-165 1204 | Impeller, 3x4-8G, 3196 MTX, Alloy 20, 5-Vane | 1 | Shandong Furkey Pumps Co., Ltd. | China | DR WAREHOUSE | 2026-05-04 | SEA | ETA RIO HAINA around 21st June | Furkey's PODR00012 May 4, 2026, Shanghai to Rio Haina | DYNR-001 | 50% payment done ✅ |  |  | 2026-07-10 |  | FALSE
IN TRANSIT | Emilka Guerra | 2026-02-19 19:53 | PODR00012 | Stock D-196 Parts | 17/04/26 | G-R100-788 1204 | Stuffing Box Cover, 7" & 8", 3196 MTX, Alloy 20, Standard Bore, Non-Jacketed | 1 | Shandong Furkey Pumps Co., Ltd. | China | DR WAREHOUSE | 2026-05-04 | SEA | ETA RIO HAINA around 21st June | Furkey's PODR00012 May 4, 2026, Shanghai to Rio Haina | DYNR-001 | 50% payment done ✅ |  |  | 2026-07-10 |  | FALSE
IN TRANSIT | Emilka Guerra | 2026-02-19 19:53 | PODR00012 | Stock D-196 Parts | 17/04/26 | G-262-92 1216 | Frame Adapter, 7" or 8", 3196 MTX, CD4MCu | 1 | Shandong Furkey Pumps Co., Ltd. | China | DR WAREHOUSE | 2026-05-04 | SEA | ETA RIO HAINA around 21st June | Furkey's PODR00012 May 4, 2026, Shanghai to Rio Haina | DYNR-001 | 50% payment done ✅ |  |  | 2026-07-10 |  | FALSE
IN TRANSIT | Emilka Guerra | 2026-02-19 19:53 | PODR00012 | Stock D-196 Parts | 17/04/26 | G-R104-731 2230 | Shaft (Less Sleeve), 3196 MTX, Alloy 20 | 1 | Shandong Furkey Pumps Co., Ltd. | China | DR WAREHOUSE | 2026-05-04 | SEA | ETA RIO HAINA around 21st June | Furkey's PODR00012 May 4, 2026, Shanghai to Rio Haina | DYNR-001 | 50% payment done ✅ |  |  | 2026-07-10 |  | FALSE
IN TRANSIT | Emilka Guerra | 2026-02-19 19:53 | PODR00012 | Stock D-196 Parts | 17/04/26 | G-P1600M0S00 X050 1204 | Power End, 3196 MTX, Oil Lubed, Alloy 20 Solid Shaft (Less Sleeve), Oil Lubed | 1 | Shandong Furkey Pumps Co., Ltd. | China | DR WAREHOUSE | 2026-05-04 | SEA | ETA RIO HAINA around 21st June | Furkey's PODR00012 May 4, 2026, Shanghai to Rio Haina | DYNR-001 | 50% payment done ✅ |  |  | 2026-07-10 |  | FALSE
IN TRANSIT | Emilka Guerra | 2026-02-19 19:53 | PODR00012 | Stock D-196 Parts | 17/04/26 | G-RD04540AA 1216 | Bearing Frame, 3196 MTX, CD4MCu, Includes Sight Glass and Plugs | 1 | Shandong Furkey Pumps Co., Ltd. | China | DR WAREHOUSE | 2026-05-04 | SEA | ETA RIO HAINA around 21st June | Furkey's PODR00012 May 4, 2026, Shanghai to Rio Haina | DYNR-001 | 50% payment done ✅ |  |  | 2026-07-10 |  | FALSE
Ready to Ship & Delayed | Emilka Guerra | 2026-02-20 03:47 | PODR00013 | Stock for D-CVD-3/3 & D-M150KSS-SVB/0003 & M250KSS-SVB | 15/05/26 | W-SP15041/A05 | Back Liner, 150SV-SP, High Chrome | 2 | Super Cast Limited | China | DR WAREHOUSE |  | SEA |  |  |  | Email for status sent on May 8th | Peter May 8th: Some parts of Metslrurry not ready until next Friday (May 15). Peter 06/16: is now in Tianjin seaport waiting for the vessel of ETD June 20 from Tianjin to Rio Haina, Dominican Republic. | SCL's PODR00013: Some parts of Metslrurry not ready until next Friday (May 15), estimated Shipping date is May 25, 2026 | 2026-07-31 |  | FALSE
Ready to Ship & Delayed | Emilka Guerra | 2026-02-20 03:47 | PODR00013 | Stock for D-CVD-3/3 & D-M150KSS-SVB/0003 & M250KSS-SVB | 15/05/26 | W-DH2125/R55 | Volute Frame Seal, 150SV-SP, Natural Rubber | 2 | Super Cast Limited | China | DR WAREHOUSE |  | SEA |  |  |  | Email for status sent on May 8th | Peter May 8th: Some parts of Metslrurry not ready until next Friday (May 15). Peter 06/16: is now in Tianjin seaport waiting for the vessel of ETD June 20 from Tianjin to Rio Haina, Dominican Republic. | SCL's PODR00013: Some parts of Metslrurry not ready until next Friday (May 15), estimated Shipping date is May 25, 2026 | 2026-07-31 |  | FALSE
Ready to Ship & Delayed | Emilka Guerra | 2026-02-20 03:47 | PODR00013 | Stock for D-CVD-3/3 & D-M150KSS-SVB/0003 & M250KSS-SVB | 15/05/26 | W-C025 | End Cover Shim Set, 3/2 or 4/3 C-AH | 1 | Super Cast Limited | China | DR WAREHOUSE |  | SEA |  |  |  | Email for status sent on May 8th | Peter May 8th: Some parts of Metslrurry not ready until next Friday (May 15). Peter 06/16: is now in Tianjin seaport waiting for the vessel of ETD June 20 from Tianjin to Rio Haina, Dominican Republic. | SCL's PODR00013: Some parts of Metslrurry not ready until next Friday (May 15), estimated Shipping date is May 25, 2026 | 2026-07-31 |  | FALSE
Ready to Ship & Delayed | Emilka Guerra | 2026-02-20 03:47 | PODR00013 | Stock for D-CVD-3/3 & D-M150KSS-SVB/0003 & M250KSS-SVB | 15/05/26 | W-TC3041MS1/A05 | Back Liner, 3/3 TC, High Chrome | 1 | Super Cast Limited | China | DR WAREHOUSE |  | SEA |  |  |  | Email for status sent on May 8th | Peter May 8th: Some parts of Metslrurry not ready until next Friday (May 15). Peter 06/16: is now in Tianjin seaport waiting for the vessel of ETD June 20 from Tianjin to Rio Haina, Dominican Republic. | SCL's PODR00013: Some parts of Metslrurry not ready until next Friday (May 15), estimated Shipping date is May 25, 2026 | 2026-07-31 |  | FALSE
Ready to Ship & Delayed | Emilka Guerra | 2026-02-20 03:47 | PODR00013 | Stock for D-CVD-3/3 & D-M150KSS-SVB/0003 & M250KSS-SVB | 15/05/26 | W-TC3124/S10 | Casing O-ring, 3/3 TC, Nitrile | 1 | Super Cast Limited | China | DR WAREHOUSE |  | SEA |  |  |  | Email for status sent on May 8th | Peter May 8th: Some parts of Metslrurry not ready until next Friday (May 15). Peter 06/16: is now in Tianjin seaport waiting for the vessel of ETD June 20 from Tianjin to Rio Haina, Dominican Republic. | SCL's PODR00013: Some parts of Metslrurry not ready until next Friday (May 15), estimated Shipping date is May 25, 2026 | 2026-07-31 |  | FALSE
Ready to Ship & Delayed | Emilka Guerra | 2026-02-20 03:47 | PODR00013 | Stock for D-CVD-3/3 & D-M150KSS-SVB/0003 & M250KSS-SVB | 15/05/26 | W-TC3191/A05 | Impeller, 3/3 TC, High Chrome | 1 | Super Cast Limited | China | DR WAREHOUSE |  | SEA |  |  |  | Email for status sent on May 8th | Peter May 8th: Some parts of Metslrurry not ready until next Friday (May 15). Peter 06/16: is now in Tianjin seaport waiting for the vessel of ETD June 20 from Tianjin to Rio Haina, Dominican Republic. | SCL's PODR00013: Some parts of Metslrurry not ready until next Friday (May 15), estimated Shipping date is May 25, 2026 Metslurry still needs about 7 to 10 days to get it ready. | 2026-07-31 |  | FALSE
Ready to Ship & Delayed | Emilka Guerra | 2026-02-20 03:47 | PODR00013 | Stock for D-CVD-3/3 & D-M150KSS-SVB/0003 & M250KSS-SVB | 15/05/26 | W-C009 | Bearing, 3/2 or 4/3 C-AH | 2 | Super Cast Limited | China | DR WAREHOUSE |  | SEA |  |  |  | Email for status sent on May 8th | Peter May 8th: Some parts of Metslrurry not ready until next Friday (May 15). Peter 06/16: is now in Tianjin seaport waiting for the vessel of ETD June 20 from Tianjin to Rio Haina, Dominican Republic. | SCL's PODR00013: Some parts of Metslrurry not ready until next Friday (May 15), estimated Shipping date is May 25, 2026 | 2026-07-31 |  | FALSE
Ready to Ship & Delayed | Emilka Guerra | 2026-02-20 03:47 | PODR00013 | Stock for D-CVD-3/3 & D-M150KSS-SVB/0003 & M250KSS-SVB | 15/05/26 | W-TC3076/MS1C21 | Shaft Sleeve, 3/3 TC | 1 | Super Cast Limited | China | DR WAREHOUSE |  | SEA |  |  |  | Email for status sent on May 8th | Peter May 8th: Some parts of Metslrurry not ready until next Friday (May 15). Peter 06/16: is now in Tianjin seaport waiting for the vessel of ETD June 20 from Tianjin to Rio Haina, Dominican Republic. | SCL's PODR00013: Some parts of Metslrurry not ready until next Friday (May 15), estimated Shipping date is May 25, 2026 | 2026-07-31 |  | FALSE
Ready to Ship & Delayed | Emilka Guerra | 2026-02-20 03:47 | PODR00013 | Stock for D-CVD-3/3 & D-M150KSS-SVB/0003 & M250KSS-SVB | 15/05/26 | MS-3/3TC-316SS | Mechanical Seal, 3/3 TC, 316SS | 1 | Super Cast Limited | China | DR WAREHOUSE |  | SEA |  |  |  | Email for status sent on May 8th | Peter May 8th: Some parts of Metslrurry not ready until next Friday (May 15). Peter 06/16: is now in Tianjin seaport waiting for the vessel of ETD June 20 from Tianjin to Rio Haina, Dominican Republic. | SCL's PODR00013: Some parts of Metslrurry not ready until next Friday (May 15), estimated Shipping date is May 25, 2026 | 2026-07-31 |  | FALSE
Ready to Ship & Delayed | Emilka Guerra | 2026-02-20 03:47 | PODR00013 | Stock for D-CVD-3/3 & D-M150KSS-SVB/0003 & M250KSS-SVB | 15/05/26 | W-SP25092/A05 | Casing, 250SV-SP, High Chrome | 1 | Super Cast Limited | China | DR WAREHOUSE |  | SEA |  |  |  | Email for status sent on May 8th | Peter May 8th: Some parts of Metslrurry not ready until next Friday (May 15). Peter 06/16: is now in Tianjin seaport waiting for the vessel of ETD June 20 from Tianjin to Rio Haina, Dominican Republic. | SCL's PODR00013: Some parts of Metslrurry not ready until next Friday (May 15), estimated Shipping date is May 25, 2026 | 2026-07-31 |  | FALSE
Ready to Ship & Delayed | Emilka Guerra | 2026-02-20 03:47 | PODR00013 | Stock for D-CVD-3/3 & D-M150KSS-SVB/0003 & M250KSS-SVB | 15/05/26 | W-VC25589, ZV589 | Bearing Seal, 10DTC | 1 | Super Cast Limited | China | DR WAREHOUSE |  | SEA |  |  |  | Email for status sent on May 8th | Peter May 8th: Some parts of Metslrurry not ready until next Friday (May 15). Peter 06/16: is now in Tianjin seaport waiting for the vessel of ETD June 20 from Tianjin to Rio Haina, Dominican Republic. | SCL's PODR00013: Some parts of Metslrurry not ready until next Friday (May 15), estimated Shipping date is May 25, 2026 | 2026-07-31 |  | FALSE
Ready to Ship & Delayed | Emilka Guerra | 2026-02-20 03:47 | PODR00013 | Stock for D-CVD-3/3 & D-M150KSS-SVB/0003 & M250KSS-SVB | 15/05/26 | W-VC25508, ZV508 | Bearing Sleeve, 10DTC | 1 | Super Cast Limited | China | DR WAREHOUSE |  | SEA |  |  |  | Email for status sent on May 8th | Peter May 8th: Some parts of Metslrurry not ready until next Friday (May 15). Peter 06/16: is now in Tianjin seaport waiting for the vessel of ETD June 20 from Tianjin to Rio Haina, Dominican Republic. | SCL's PODR00013: Some parts of Metslrurry not ready until next Friday (May 15), estimated Shipping date is May 25, 2026 | 2026-07-31 |  | FALSE
Ready to Ship & Delayed | Emilka Guerra | 2026-02-20 03:47 | PODR00013 | Stock for D-CVD-3/3 & D-M150KSS-SVB/0003 & M250KSS-SVB | 15/05/26 | W-K90381/K90744D U509, HM926749-90080 Timken | Bearing, 10DTC | 1 | Super Cast Limited | China | DR WAREHOUSE |  | SEA |  |  |  | Email for status sent on May 8th | Peter May 8th: Some parts of Metslrurry not ready until next Friday (May 15). Peter 06/16: is now in Tianjin seaport waiting for the vessel of ETD June 20 from Tianjin to Rio Haina, Dominican Republic. | SCL's PODR00013: Some parts of Metslrurry not ready until next Friday (May 15), estimated Shipping date is May 25, 2026 | 2026-07-31 |  | FALSE
Ready to Ship & Delayed | Emilka Guerra | 2026-02-20 03:47 | PODR00013 | Stock for D-CVD-3/3 & D-M150KSS-SVB/0003 & M250KSS-SVB | 15/05/26 | W-VC25717 | End Cover O-Ring, 10DTC | 1 | Super Cast Limited | China | DR WAREHOUSE |  | SEA |  |  |  | Email for status sent on May 8th | Peter May 8th: Some parts of Metslrurry not ready until next Friday (May 15). Peter 06/16: is now in Tianjin seaport waiting for the vessel of ETD June 20 from Tianjin to Rio Haina, Dominican Republic. | SCL's PODR00013: Some parts of Metslrurry not ready until next Friday (May 15), estimated Shipping date is May 25, 2026 | 2026-07-31 |  | FALSE
Ready to Ship & Delayed | Emilka Guerra | 2026-02-20 03:47 | PODR00013 | Stock for D-CVD-3/3 & D-M150KSS-SVB/0003 & M250KSS-SVB | 15/05/26 | W-RP1/4 | Grease Nipple, 10DTC | 2 | Super Cast Limited | China | DR WAREHOUSE |  | SEA |  |  |  | Email for status sent on May 8th | Peter May 8th: Some parts of Metslrurry not ready until next Friday (May 15). Peter 06/16: is now in Tianjin seaport waiting for the vessel of ETD June 20 from Tianjin to Rio Haina, Dominican Republic. | SCL's PODR00013: Some parts of Metslrurry not ready until next Friday (May 15), estimated Shipping date is May 25, 2026 | 2026-07-31 |  | FALSE
Ready to Ship & Delayed | Emilka Guerra | 2026-02-20 03:47 | PODR00013 | Stock for D-CVD-3/3 & D-M150KSS-SVB/0003 & M250KSS-SVB | 15/05/26 | W-RP1/4-45（45°） | Grease Nipple, 10DTC, 45° | 1 | Super Cast Limited | China | DR WAREHOUSE |  | SEA |  |  |  | Email for status sent on May 8th | Peter May 8th: Some parts of Metslrurry not ready until next Friday (May 15). Peter 06/16: is now in Tianjin seaport waiting for the vessel of ETD June 20 from Tianjin to Rio Haina, Dominican Republic. | SCL's PODR00013: Some parts of Metslrurry not ready until next Friday (May 15), estimated Shipping date is May 25, 2026 | 2026-07-31 |  | FALSE
Ready to Ship & Delayed | Emilka Guerra | 2026-02-20 03:47 | PODR00013 | Stock for D-CVD-3/3 & D-M150KSS-SVB/0003 & M250KSS-SVB | 15/05/26 | M115X2 | Labyrinth Lock Nut, 10DTC | 1 | Super Cast Limited | China | DR WAREHOUSE |  | SEA |  |  |  | Email for status sent on May 8th | Peter May 8th: Some parts of Metslrurry not ready until next Friday (May 15). Peter 06/16: is now in Tianjin seaport waiting for the vessel of ETD June 20 from Tianjin to Rio Haina, Dominican Republic. | SCL's PODR00013: Some parts of Metslrurry not ready until next Friday (May 15), estimated Shipping date is May 25, 2026 | 2026-07-31 |  | FALSE
Ready to Ship & Delayed | Emilka Guerra | 2026-02-20 03:47 | PODR00013 | Stock for D-CVD-3/3 & D-M150KSS-SVB/0003 & M250KSS-SVB | 15/05/26 | W-VC25562, ZV562 | Labyrinth, 10DTC | 1 | Super Cast Limited | China | DR WAREHOUSE |  | SEA |  |  |  | Email for status sent on May 8th | Peter May 8th: Some parts of Metslrurry not ready until next Friday (May 15). Peter 06/16: is now in Tianjin seaport waiting for the vessel of ETD June 20 from Tianjin to Rio Haina, Dominican Republic. | SCL's PODR00013: Some parts of Metslrurry not ready until next Friday (May 15), estimated Shipping date is May 25, 2026 | 2026-07-31 |  | FALSE
Ready to Ship & Delayed | Emilka Guerra | 2026-02-20 03:47 | PODR00013 | Stock for D-CVD-3/3 & D-M150KSS-SVB/0003 & M250KSS-SVB | 15/05/26 | W-VC25625 | O-Ring (Casing/Front Cover Plate), 10DTC | 1 | Super Cast Limited | China | DR WAREHOUSE |  | SEA |  |  |  | Email for status sent on May 8th | Peter May 8th: Some parts of Metslrurry not ready until next Friday (May 15). Peter 06/16: is now in Tianjin seaport waiting for the vessel of ETD June 20 from Tianjin to Rio Haina, Dominican Republic. | SCL's PODR00013: Some parts of Metslrurry not ready until next Friday (May 15), estimated Shipping date is May 25, 2026 | 2026-07-31 |  | FALSE
Ready to Ship & Delayed | Emilka Guerra | 2026-02-20 03:47 | PODR00013 | Stock for D-CVD-3/3 & D-M150KSS-SVB/0003 & M250KSS-SVB | 15/05/26 | W-VC25684-1 | Oil Slinger, 10DTC | 1 | Super Cast Limited | China | DR WAREHOUSE |  | SEA |  |  |  | Email for status sent on May 8th | Peter May 8th: Some parts of Metslrurry not ready until next Friday (May 15). Peter 06/16: is now in Tianjin seaport waiting for the vessel of ETD June 20 from Tianjin to Rio Haina, Dominican Republic. | SCL's PODR00013: Some parts of Metslrurry not ready until next Friday (May 15), estimated Shipping date is May 25, 2026 | 2026-07-31 |  | FALSE
Ready to Ship & Delayed | Emilka Guerra | 2026-02-20 03:47 | PODR00013 | Stock for D-CVD-3/3 & D-M150KSS-SVB/0003 & M250KSS-SVB | 15/05/26 | W-VC25608, U608 | Piston Ring, 10DTC | 2 | Super Cast Limited | China | DR WAREHOUSE |  | SEA |  |  |  | Email for status sent on May 8th | Peter May 8th: Some parts of Metslrurry not ready until next Friday (May 15). Peter 06/16: is now in Tianjin seaport waiting for the vessel of ETD June 20 from Tianjin to Rio Haina, Dominican Republic. | SCL's PODR00013: Some parts of Metslrurry not ready until next Friday (May 15), estimated Shipping date is May 25, 2026 | 2026-07-31 |  | FALSE
Ready to Ship & Delayed | Emilka Guerra | 2026-02-20 03:47 | PODR00013 | Stock for D-CVD-3/3 & D-M150KSS-SVB/0003 & M250KSS-SVB | 15/05/26 | W-VC25577, ZV577 | Shaft Seal Ejector, 10DTC | 1 | Super Cast Limited | China | DR WAREHOUSE |  | SEA |  |  |  | Email for status sent on May 8th | Peter May 8th: Some parts of Metslrurry not ready until next Friday (May 15). Peter 06/16: is now in Tianjin seaport waiting for the vessel of ETD June 20 from Tianjin to Rio Haina, Dominican Republic. | SCL's PODR00013: Some parts of Metslrurry not ready until next Friday (May 15), estimated Shipping date is May 25, 2026 | 2026-07-31 |  | FALSE
Ready to Ship & Delayed | Emilka Guerra | 2026-02-20 03:47 | PODR00013 | Stock for D-CVD-3/3 & D-M150KSS-SVB/0003 & M250KSS-SVB | 15/05/26 | W-TC3073M/E05 | Shaft, 3/3 TC | 1 | Super Cast Limited | China | DR WAREHOUSE |  | SEA |  |  |  | Email for status sent on May 8th | Peter May 8th: Some parts of Metslrurry not ready until next Friday (May 15). Peter 06/16: is now in Tianjin seaport waiting for the vessel of ETD June 20 from Tianjin to Rio Haina, Dominican Republic. | SCL's PODR00013: Some parts of Metslrurry not ready until next Friday (May 15), estimated Shipping date is May 25, 2026 | 2026-07-31 |  | FALSE
Ready to Ship & Delayed | Emilka Guerra | 2026-02-20 03:47 | PODR00013 | Stock for D-CVD-3/3 & D-M150KSS-SVB/0003 & M250KSS-SVB | 15/05/26 | W-TC3092-1/A05 | Casing, 3/3 TC, High Chrome | 1 | Super Cast Limited | China | DR WAREHOUSE |  | SEA |  |  |  | Email for status sent on May 8th | Peter May 8th: Some parts of Metslrurry not ready until next Friday (May 15). Peter 06/16: is now in Tianjin seaport waiting for the vessel of ETD June 20 from Tianjin to Rio Haina, Dominican Republic. | SCL's PODR00013: Some parts of Metslrurry not ready until next Friday (May 15), estimated Shipping date is May 25, 2026 | 2026-07-31 |  | FALSE
Ready to Ship & Delayed | Emilka Guerra | 2026-02-20 03:47 | PODR00013 | Stock for D-CVD-3/3 & D-M150KSS-SVB/0003 & M250KSS-SVB | 15/05/26 | W-U509D-1, NU2224EMA Timken | Bearing (Drive End), 10DTC | 1 | Super Cast Limited | China | DR WAREHOUSE |  | SEA |  |  |  | Email for status sent on May 8th | Peter May 8th: Some parts of Metslrurry not ready until next Friday (May 15). Peter 06/16: is now in Tianjin seaport waiting for the vessel of ETD June 20 from Tianjin to Rio Haina, Dominican Republic. | SCL's PODR00013: Some parts of Metslrurry not ready until next Friday (May 15), estimated Shipping date is May 25, 2026 | 2026-07-31 |  | FALSE
Ready to Ship & Delayed | Emilka Guerra | 2026-02-20 03:47 | PODR00013 | Stock for D-CVD-3/3 & D-M150KSS-SVB/0003 & M250KSS-SVB | 15/05/26 | W-TC3188M/D21 | Frame, 3/3 TC | 1 | Super Cast Limited | China | DR WAREHOUSE |  | SEA |  |  |  | Email for status sent on May 8th | Peter May 8th: Some parts of Metslrurry not ready until next Friday (May 15). Peter 06/16: is now in Tianjin seaport waiting for the vessel of ETD June 20 from Tianjin to Rio Haina, Dominican Republic. | SCL's PODR00013: Some parts of Metslrurry not ready until next Friday (May 15), estimated Shipping date is May 25, 2026 | 2026-07-31 |  | FALSE
Ready to Ship & Delayed | Emilka Guerra | 2026-02-20 03:47 | PODR00013 | Stock for D-CVD-3/3 & D-M150KSS-SVB/0003 & M250KSS-SVB | 15/05/26 | W-C024-10/E62 | End Cover, 3/2 or 4/3 C-AH, Carbon Steel | 2 | Super Cast Limited | China | DR WAREHOUSE |  | SEA |  |  |  | Email for status sent on May 8th | Peter May 8th: Some parts of Metslrurry not ready until next Friday (May 15). Peter 06/16: is now in Tianjin seaport waiting for the vessel of ETD June 20 from Tianjin to Rio Haina, Dominican Republic. | SCL's PODR00013: Some parts of Metslrurry not ready until next Friday (May 15), estimated Shipping date is May 25, 2026 | 2026-07-31 |  | FALSE
Ready to Ship & Delayed | Emilka Guerra | 2026-02-20 03:47 | PODR00013 | Stock for D-CVD-3/3 & D-M150KSS-SVB/0003 & M250KSS-SVB | 15/05/26 | W-C109/S10 | Shaft Sleeve O-Ring, 3/2 or 4/3 C-AH, Nitrile | 3 | Super Cast Limited | China | DR WAREHOUSE |  | SEA |  |  |  | Email for status sent on May 8th | Peter May 8th: Some parts of Metslrurry not ready until next Friday (May 15). Peter 06/16: is now in Tianjin seaport waiting for the vessel of ETD June 20 from Tianjin to Rio Haina, Dominican Republic. | SCL's PODR00013: Some parts of Metslrurry not ready until next Friday (May 15), estimated Shipping date is May 25, 2026 | 2026-07-31 |  | FALSE
Ready to Ship & Delayed | Emilka Guerra | 2026-02-20 03:47 | PODR00013 | Stock for D-CVD-3/3 & D-M150KSS-SVB/0003 & M250KSS-SVB | 15/05/26 | W-115 | Labyrinth Lock Washer, 10DTC | 1 | Super Cast Limited | China | DR WAREHOUSE |  | SEA |  |  |  | Email for status sent on May 8th | Peter May 8th: Some parts of Metslrurry not ready until next Friday (May 15). Peter 06/16: is now in Tianjin seaport waiting for the vessel of ETD June 20 from Tianjin to Rio Haina, Dominican Republic. | SCL's PODR00013: Some parts of Metslrurry not ready until next Friday (May 15), estimated Shipping date is May 25, 2026 | 2026-07-31 |  | FALSE
Ready to Ship | Emilka Guerra | 2026-02-20 18:58 | PODR00014 | Stock D-196 Parts | 27/03/26 | 28VSMS3-04C4VS4 | Single Cartridge Seal, 1 3/4", VSMS, Standard Bore, Carbon vs Silicon Carbide / TFEP | 2 | DYNAPRO EQUIPMENT LIMITED | Canada | DR WAREHOUSE |  | SEA |  | Waiting on shipping instructions to DR warehouse |  | PO08686 / PODR00014 |  |  | 2026-07-31 |  | FALSE
Ready to Ship | Emilka Guerra | 2026-02-26 21:35 | PODR00016 | Stock for HPCW | 2026-06-03 | 2-432V700 (black) | O-Ring, 10JKH/M, 5.38IDx0.25RD, Viton | 1 | DYNAPRO EQUIPMENT LIMITED | Canada | DR WAREHOUSE |  | SEA |  | Waiting on shipping instructions to DR warehouse |  | PO08699 / PODR00016 |  |  | 2026-07-31 |  | FALSE
Ready to Ship | Emilka Guerra | 2026-02-26 21:35 | PODR00016 | Stock for HPCW | 2026-06-03 | 2-461V70B (brown) | O-Ring, 10JKH/M, 16.00IDx0.25RD, Viton | 1 | DYNAPRO EQUIPMENT LIMITED | Canada | DR WAREHOUSE |  | SEA |  | Waiting on shipping instructions to DR warehouse |  | PO08699 / PODR00016 |  |  | 2026-07-31 |  | FALSE

## PA
STATUS | CREATED BY | ISSUE DATE | PO NUMBER | REFERENCE | DUE DATE FACTORY | SKU | PRODUCT NAME | INCOMING STOCK | SUPPLIER | ORIGIN | SHIP TO | SHIPPING DATE SUPPLIER | TRANSIT | ETA WAREHOUSE | SHIPPING INSTRUCTIONS | TRACKING NUMBER / UPDATES | IMPORTANT NOTE | PETER UPDATES | DELAY ISSUES | EST RECEIPT DATE ODOO | RECEPTION DATE WAREHOUSE | COMPLETED
IN TRANSIT | Yannett Yeomans | 2025-12-18 | POPN00001 | Stock HPCW Parts | 23/02/26 | 10JKM, 6-Vane Impeller, CD4 | Impeller, 10JKM, Double Keyed, w/Wear Ring | 11 | Jiangsu Win-win International Trading Co., Ltd. | China | PA WAREHOUSE | 2026-05-04 | SEA | 2026-06-04 |  | SHCFZ26252992J |  | Peter 04/28: ready to leave Shanghai for Colon on May 3, 2026 |  |  |  | FALSE
IN TRANSIT | Yannett Yeomans | 2025-12-18 | POPN00001 | Stock HPCW Parts | 23/02/26 | 10JKH, 7-Vane Impeller, CD4MCu | Impeller, 10JKH, Double Keyed, w/Wear Ring | 16 | Jiangsu Win-win International Trading Co., Ltd. | China | PA WAREHOUSE | 2026-05-04 | SEA | 2026-06-04 |  | SHCFZ26252992J |  | Peter 04/28: ready to leave Shanghai for Colon on May 3, 2026 |  |  |  | FALSE
IN TRANSIT | Yannett Yeomans | 2025-12-18 | POPN00001 | Stock HPCW Parts | 23/02/26 | D-2001408-2507 | Impeller Wear Ring, 10JKH/M, 5.12x5.48x0.88, Duplex SS 2507 w/Ion Nitriding | 15 | Jiangsu Win-win International Trading Co., Ltd. | China | PA WAREHOUSE | 2026-05-04 | SEA | 2026-06-04 |  | SHCFZ26252992J |  | Peter 04/28: ready to leave Shanghai for Colon on May 3, 2026 |  |  |  | FALSE
IN TRANSIT | Yannett Yeomans | 2025-12-18 | POPN00001 | Stock HPCW Parts | 23/02/26 | D-2001407-2507 | Bowl Wear Ring, 10JKH/M, 05.50x05.88x0.88, Duplex SS 2507 w/Ion Nitriding | 38 | Jiangsu Win-win International Trading Co., Ltd. | China | PA WAREHOUSE | 2026-05-04 | SEA | 2026-06-04 |  | SHCFZ26252992J |  | Peter 04/28: ready to leave Shanghai for Colon on May 3, 2026 |  |  |  | FALSE
IN TRANSIT | Yannett Yeomans | 2025-12-18 | POPN00001 | Stock HPCW Parts | 23/02/26 | D-2001405-CD4 | Bowl,10JKH/M, BW-INT-STEP-NO-SL-SP, CD4MCu | 17 | Jiangsu Win-win International Trading Co., Ltd. | China | PA WAREHOUSE | 2026-05-04 | SEA | 2026-06-04 |  | SHCFZ26252992J |  | Peter 04/28: ready to leave Shanghai for Colon on May 3, 2026 |  |  |  | FALSE
IN TRANSIT | Yannett Yeomans | 2025-12-18 | POPN00001 | Stock HPCW Parts | 23/02/26 | D-2001434-CD4 | Bowl (Top),10JKH/M, w/"O" Ring, CD4MCu | 2 | Jiangsu Win-win International Trading Co., Ltd. | China | PA WAREHOUSE | 2026-05-04 | SEA | 2026-06-04 |  | SHCFZ26252992J |  | Peter 04/28: ready to leave Shanghai for Colon on May 3, 2026 |  |  |  | FALSE
IN TRANSIT | Yannett Yeomans | 2025-12-18 | POPN00001 | Stock HPCW Parts | 23/02/26 | D-2001417-CD4 | Bell,10JKH/M, BW-FLG-STD-STEP-CUT_NR, CD4MCu | 3 | Jiangsu Win-win International Trading Co., Ltd. | China | PA WAREHOUSE | 2026-05-04 | SEA | 2026-06-04 |  | SHCFZ26252992J |  | Peter 04/28: ready to leave Shanghai for Colon on May 3, 2026 |  |  |  | FALSE
IN TRANSIT | Yannett Yeomans | 2025-12-18 | POPN00001 | Stock HPCW Parts | 23/02/26 | D-2001412-4PHSS | Hex Cap Screw, 10JKH/M, 0.44-14NCx1.50, 17-4PH SS | 234 | Jiangsu Win-win International Trading Co., Ltd. | China | PA WAREHOUSE | 2026-05-04 | SEA | 2026-06-04 |  | SHCFZ26252992J |  | Peter 04/28: ready to leave Shanghai for Colon on May 3, 2026 |  |  |  | FALSE
Received | Emilka Guerra | 2026-03-16 | POPN00002 | SOPN00003 | 2026-06-04 | DU-PE2YRB-LHS-4140-H | Power End, Durco Mark 3 Group 2, 4140 Steel Shaft (Hook Sleeve), 316SS Sleeve, (Power End Only - Less Adapter & Foot) | 1 | DYNAPRO EQUIPMENT LIMITED | Canada | DIRECT TO CLIENT |  | SEA | 16/03/26 | Ship to: Rosebel Gold Mines N.V. President Da Costalaan #2 Paramaribo Suriname |  |  | EG: WH/MO/00179 POWER END completed on March 26th, 2026 |  |  |  | TRUE
Ready to Ship | Amanda Qiao | 2026-03-16 | POPN00004 | SOPN00005 | 2026-04-16 | D-12RJHC-4-BRZ | Pump, Dynapro Vertical Turbine Without Motor, 12RJHC 4-Stages, Cast Iron w/Bronze Impeller | 1 | Super Cast Limited | China | PA WAREHOUSE |  | SEA |  | Please wait for Amanda's approval for shipping. |  |  | Peter: Amanda Can you confirm the Consignee and Notify Party? If the Consignee is Dynapro Pumps Panama, I will book the vessel from Shanghai to Colon, Panama. |  |  | 2026-06-16 | FALSE
In Production | Amanda Qiao | 2026-03-18 | POPN00006 | SOPN00001 | 20/04/26 | W-SPR65092/S42 | Casing, 65QV-SPR, Neoprene | 1 | Super Cast Limited | China | PA WAREHOUSE |  | SEA |  | Please wait for Amanda's approval for shipping. |  |  | Requested Update on april 21st |  |  | 2026-06-20 | FALSE
In Production | Amanda Qiao | 2026-03-18 | POPN00006 | SOPN00001 | 20/04/26 | W-SPR65041/S42 | Back Liner, 65QV-SPR, Neoprene | 1 | Super Cast Limited | China | PA WAREHOUSE |  | SEA |  | Please wait for Amanda's approval for shipping. |  |  | Requested Update on april 21st |  |  | 2026-06-20 | FALSE
In Production | Amanda Qiao | 2026-03-18 | POPN00006 | SOPN00001 | 20/04/26 | W-SPR10206A/S42 | Impeller, 100RV-SP, Neoprene | 1 | Super Cast Limited | China | PA WAREHOUSE |  | SEA |  | Please wait for Amanda's approval for shipping. |  |  | Requested Update on april 21st |  |  | 2026-06-20 | FALSE
Received | Emilka Guerra | 2026-03-23 | POPN00008 | SOPN00001 | 2026-03-04 | W-SPR65206A/S42 | Impeller, 65QV-SPR, Neoprene | 1 | DYNAPRO EQUIPMENT LIMITED | Canada | DIRECT TO CLIENT |  | SEA | 2026-01-06 |  |  | Ship to: Rosebel Gold Mines N.V. President Da Costalaan #2 Paramaribo Suriname | EG: Purchase from stock Dynapro Canada |  |  |  | TRUE
In Production | Amanda Qiao | 2026-03-23 | POPN00010 | 23/03/26 | SOPN00007 | SGB-22mmx22mm | Packing, 22mm x 22mm, Oil-Impregnated, Single Piece | 30 | Shijiazhuang Industrial Pump Factory Co., Ltd. | China | DIRECT TO CLIENT |  | SEA | 23/03/26 | Once the shipment is ready, please arrange ocean freight to Georgetown, Guyana (CIF). Please send the full set of customs documents to the logistics team. You will find more detailed instructions on the last page. Also, please send the packing slips and photos to me before shipping, as we need to review them in advance. |  | Georgetown, Guyana (CIF). |  |  |  |  | FALSE
In Production | Amanda Qiao | 2026-03-23 | POPN00010 | 23/03/26 | SOPN00007 | D-250ZJ-85-14 | Packing Gland, 250ZJ-I-A103, 316SS | 2 | Shijiazhuang Industrial Pump Factory Co., Ltd. | China | DIRECT TO CLIENT |  | SEA | 23/03/26 |  |  | Georgetown, Guyana (CIF). |  |  |  |  | FALSE
In Production | Amanda Qiao | 2026-03-23 | POPN00010 | 23/03/26 | SOPN00007 | D-250ZJ-103-8 | Shaft Sleeve, 250ZJ-I-A103, 420SS, Heat Treated, Hardened | 4 | Shijiazhuang Industrial Pump Factory Co., Ltd. | China | DIRECT TO CLIENT |  | SEA | 23/03/26 |  |  | Georgetown, Guyana (CIF). |  |  |  |  | FALSE
In Production | Amanda Qiao | 2026-03-23 | POPN00010 | 23/03/26 | SOPN00007 | D-250ZJ-103-7 | Stuffing Box, 250ZJ-I-A103, High Chrome | 2 | Shijiazhuang Industrial Pump Factory Co., Ltd. | China | DIRECT TO CLIENT |  | SEA | 23/03/26 |  |  | Georgetown, Guyana (CIF). |  |  |  |  | FALSE
In Production | Amanda Qiao | 2026-03-23 | POPN00010 | 23/03/26 | SOPN00007 | D-250ZJ-103-4 | Rear Liner Plate, 250ZJ-I-A103, High Chrome with bolts | 4 | Shijiazhuang Industrial Pump Factory Co., Ltd. | China | DIRECT TO CLIENT |  | SEA | 23/03/26 |  |  | Georgetown, Guyana (CIF). |  |  |  |  | FALSE
In Production | Amanda Qiao | 2026-03-23 | POPN00010 | 23/03/26 | SOPN00007 | D-250ZJ-103-3 | Front Liner Plate, 250ZJ-I-A103, High Chrome | 4 | Shijiazhuang Industrial Pump Factory Co., Ltd. | China | DIRECT TO CLIENT |  | SEA | 23/03/26 |  |  | Georgetown, Guyana (CIF). |  |  |  |  | FALSE
In Production | Amanda Qiao | 2026-03-23 | POPN00010 | 23/03/26 | SOPN00007 | D-250ZJ-103-2 | Volute Casing, 250ZJ-I-A103, High Chrome | 4 | Shijiazhuang Industrial Pump Factory Co., Ltd. | China | DIRECT TO CLIENT |  | SEA | 23/03/26 |  |  | Georgetown, Guyana (CIF). |  |  |  |  | FALSE
In Production | Amanda Qiao | 2026-03-23 | POPN00010 | 23/03/26 | SOPN00007 | D-250ZJ-103-1 | Impeller, 250ZJ-I-A103, High Chrome | 4 | Shijiazhuang Industrial Pump Factory Co., Ltd. | China | DIRECT TO CLIENT |  | SEA | 23/03/26 |  |  | Georgetown, Guyana (CIF). |  |  |  |  | FALSE
IN TRANSIT | Amanda Qiao | 2026-04-13 | POPN00011 | 2026-05-23 | SOPN00009 | D-196 LF 1.5x3-13 LTX DI/316 |  | 3 | Shandong Furkey Pumps Co., Ltd. | China | PA WAREHOUSE | 2026-05-04 | SEA |  | Paint OEM standard RAL 5015 Please use Dynapro's packing slip and label only on this order (Please contact Peter for the template) Please send photos of the shipments, paperwork to Amanda before shipping for approval. Ship to Panama Port, Panama. | DYNN-001 |  |  |  | 2026-07-23 |  | FALSE
In Production | Amanda Qiao | 2026-04-24 | POPN00012 | 2026-05-01 | SOPN00017 | 105924/1503 | Shaft, 100RV-SP, 100mm, Tapped, 1045 Steel | 1 | Super Cast Limited | China | PA WAREHOUSE |  | SEA |  | Please put PO# 2265831 on the packing slip and label Part number: only put Dynapro's SKU on the packing slips, do not put OEM number Please send photos to Amanda and get approval from Amanda before shipping. |  |  |  |  | 2026-07-01 |  | FALSE
In Production | Emilka Guerra | 2026-06-04 | POPN00014 | Stock | 2026-07-02 | W-SPR65092/S42 | Casing, 65QV-SPR, Neoprene | 1 | Super Cast Limited | China | PA WAREHOUSE |  | SEA | [6 empty] | 2026-08-13
In Production | Emilka Guerra | 2026-06-04 | POPN00014 | Stock | 2026-07-02 | W-SPR65206A/S42 | Impeller, 65QV-SPR, Neoprene | 1 | Super Cast Limited | China | PA WAREHOUSE |  | SEA | [6 empty] | 2026-08-13
In Production | Emilka Guerra | 2026-06-04 | POPN00014 | Stock | 2026-07-02 | W-SPR65041/S42 | Back Liner, 65QV-SPR, Neoprene | 1 | Super Cast Limited | China | PA WAREHOUSE |  | SEA | [6 empty] | 2026-08-13
In Production | Emilka Guerra | 2026-06-04 | POPN00014 | Stock | 2026-07-02 | W-SPR10092/S42 | Casing, 100RV-SP, Neoprene | 1 | Super Cast Limited | China | PA WAREHOUSE |  | SEA | [6 empty] | 2026-08-13
In Production | Emilka Guerra | 2026-06-04 | POPN00014 | Stock | 2026-07-02 | W-SPR10206A/S42 | Impeller, 100RV-SP, Neoprene | 1 | Super Cast Limited | China | PA WAREHOUSE |  | SEA | [6 empty] | 2026-08-13
In Production | Emilka Guerra | 2026-06-04 | POPN00014 | Stock | 2026-07-02 | W-SPR10041/S42 | Back Liner, 100RV-SP, Neoprene | 1 | Super Cast Limited | China | PA WAREHOUSE |  | SEA | [6 empty] | 2026-08-13
In Production | Emilka Guerra | 2026-06-04 | POPN00015 | SOPN00015 - SO19448 | 2026-08-27 | GA-556540 | Impeller, G-Series 6" VSP, 8100 Series, High Chrome | 3 | IGH | Mexico | CA WAREHOUSE |  | LAND | [6 empty] | 2026-09-17
In Production | Emilka Guerra | 2026-06-04 | POPN00016 | Stock | 2026-07-30 | D-2001422-KEY | Key (Square), 10JKH/M, 0.50x1.875LG, Duplex SS 2507 | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | PA WAREHOUSE |  | SEA | [6 empty] | 2026-10-08
In Production | Emilka Guerra | 2026-06-04 | POPN00016 | Stock | 2026-07-30 | D-2001431-KEY | Key (Square), 10JKH/M, 0.38x2.50LG, Duplex SS 2507 | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | PA WAREHOUSE |  | SEA | [6 empty] | 2026-10-08
In Production | Emilka Guerra | 2026-06-04 | POPN00016 | Stock | 2026-07-30 | D-2001434-CD4 | Bowl (Top),10JKH/M, w/"O" Ring, CD4MCu | 1 | Jiangsu Win-win International Trading Co., Ltd. | China | PA WAREHOUSE |  | SEA | [6 empty] | 2026-10-08
In Production | Emilka Guerra | 2026-06-04 | POPN00016 | Stock | 2026-07-30 | 2-170V70B (brown) | O-Ring, 10JKH/M, 07.75IDx.09RD, Viton | 12 | Jiangsu Win-win International Trading Co., Ltd. | China | PA WAREHOUSE |  | SEA | [6 empty] | 2026-10-08
In Production | Emilka Guerra | 2026-06-04 | POPN00016 | Stock | 2026-07-30 | D-2001412-4PHSS | Hex Cap Screw, 10JKH/M, 0.44-14NCx1.50, 17-4PH SS | 421 | Jiangsu Win-win International Trading Co., Ltd. | China | PA WAREHOUSE |  | SEA | [6 empty] | 2026-10-08
In Production | Emilka Guerra | 2026-06-04 | POPN00016 | Stock | 2026-07-30 | 10JKH, 7-Vane Impeller, CD4MCu | Impeller, 10JKH, Double Keyed, w/Wear Ring | 6 | Jiangsu Win-win International Trading Co., Ltd. | China | PA WAREHOUSE |  | SEA | [6 empty] | 2026-10-08
In Production | Emilka Guerra | 2026-06-04 | POPN00016 | Stock | 2026-07-30 | D-2001416-174PH | Hex-Head Socket Cap Screw, 10JKH/M, 0.31-18NCx0.750, 17-4PH SS | 88 | Jiangsu Win-win International Trading Co., Ltd. | China | PA WAREHOUSE |  | SEA | [6 empty] | 2026-10-08

## RMAs
RMA # | SO Number | Salesperson | Date | Customer | Shipping Instruction | Reason | RMA Fee | Ship back | Status
WH/RET/00141
WH/RET/00145 |  |  |  | Wesdome Gold Mines Ltd - Eagle River Mine |  |  | No
WH/RET/00143 |  | Alexis |  |  |  |  | No

## Report Barrick
STATUS | CREATED BY | ISSUE DATE | PO NUMBER | REFERENCE | DUE DATE FACTORY | SKU | PRODUCT NAME | INCOMING STOCK | SUPPLIER | ORIGIN | SHIP TO | SHIPPING DATE SUPPLIER | TRANSIT | ETA WAREHOUSE UPDATES | SHIPPING INSTRUCTIONS | TRACKING NUMBER / UPDATES | IMPORTANT NOTE | PETER UPDATES | DELAY ISSUES | EST RECEIPT DATE ODOO | RECEPTION DATE WAREHOUSE | COMPLETED | SUPPLIER DELIVERY | TOTAL REAL LEAD TIME | Total LT in weeks
IN TRANSIT & DELAYED | Jeff Bell | 2025-12-11 | PO08522 | SO16270 | 2026-02-23 | 150ZJ-F-HE2. 8/6 F-AH w/HE Impeller | Pump, W-Series, 8/6 DH, 150ZJF-HE, 28% Ultrachrome, Corrosion Resistant | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | BARRICK DIRECT SHIPPING | 2026-04-16 | SEA | Around June 5 - 10 |  | LS15TJ2603881 | Thursday 19th, march 2026 | The new ETD Tianjin is Apr 16.. shipped out. ✅ Shipping docs and pictures will be shared with you by Monday. The ETA Caucedo is June 5 to 10 | was delayed by draiwng confirmation, unable to come out until end of Feb. // now in Naipu's workshop, waiting for Naipu's PO08522 to ship together | 2026-04-05 |  | FALSE | 52 | -46002 | -6571.7143
IN TRANSIT & DELAYED | Emilka Guerra | 2025-12-16 | PO08541 | SO18419 | 2026-02-01 | 10JKH, 7-Vane Impeller, CD4MCu | Impeller, 10JKH, Double Keyed, w/Wear Ring | 3 | Nanjing Wangyang Pumps Co., Ltd | China | BARRICK DIRECT SHIPPING | 2026-04-16 | SEA | Around June 5 - 10 |  | ECU: LS15TJ2603881 | The ETA Caucedo is June 5 to 10 | The new ETD Tianjin is Apr 16.. shipped out. ✅ Shipping docs and pictures will be shared with you by Monday. | now in Naipu's workshop, waiting for Naipu's PO08522 to ship together | 2026-03-16 |  | FALSE | 74 | -46007 | -6572.4286
IN TRANSIT & DELAYED | Amanda Qiao | 2026-01-13 | PO08595 | SO18485 - Ship direct to Dominican | 2026-02-13 | W-M100KSS-TVB/0507 | Sump Pump, M100KSS-TVB, CD4MCu | 1 | Shijiazhuang Mets Machinery Co., LTD | China | BARRICK DIRECT SHIPPING | 2026-05-06 | SEA |  | Amanda May 6th: This shipment can be shipped to Barrick directly. | EASLINE OSAKA / V.2621E. LS15TJ2605852 | NEW ETD April/30 The new ETD Tianjin is May 22. It departed Tianjin on May 17, 2026. | Peter May 12: Booked the vessel of ETD May 15 from Tianjin to Caucedo. / The cargo is now at Tianjin seaport waiting for boarding. | Although the main pump is now ready, the agitator and the agitator shaft could not come out until end of April. These two parts were scrapped due to quality issue. 05/16: missed the vessel, becasue the actual volume is greater than the booked volume. No enought room to be loaded into the container. | 2026-04-24 |  | FALSE | 82 | -46035 | -6576.4286
DELAYED PRODUCTION | Leriel Reyes |  | PO08609 | SO17341 | 2026-04-27 | D-XS350-560G | Horizontal Split-Case Pump 20/14 | 1 | Super Cast Limited | China | BARRICK DIRECT SHIPPING |  | SEA | 2026-07-06 | CIF Santo Domingo |  | Barrick shipment | Peter 05/16: the performance test was done yesterday (May 15), can be ready to leave factory by next Friday (May 22). | 04/03: Just confirmed drawings this week. Estimated to be ready for shipment on May 15. | 2026-07-06 |  | FALSE | -46139 | 0 | 0
DELAYED PRODUCTION | Leriel Reyes | 2026-01-16 | PO08609 | SO17341 | 2026-04-27 | 10652/2001 | Set of Coupling and Coupling Guard XS350-560G, Cast Iron | 1 | Super Cast Limited | China | BARRICK DIRECT SHIPPING |  | SEA | 2026-07-06 | CIF Santo Domingo |  | Barrick shipment | Peter 05/16: the performance test was done yesterday (May 15), can be ready to leave factory by next Friday (May 22). | 04/03: Just confirmed drawings this week. Estimated to be ready for shipment on May 15. | 2026-07-06 |  | FALSE | -46139 | -46038 | -6576.8571
DELAYED PRODUCTION | Leriel Reyes | 2026-01-16 | PO08609 | SO17341 | 2026-04-27 | 10653/1501 | Common base XS350-560G, Carbon Steel | 1 | Super Cast Limited | China | BARRICK DIRECT SHIPPING |  | SEA | 2026-07-06 | CIF Santo Domingo |  | Barrick shipment | Peter 05/16: the performance test was done yesterday (May 15), can be ready to leave factory by next Friday (May 22). | 04/03: Just confirmed drawings this week. Estimated to be ready for shipment on May 15. | 2026-07-06 |  | FALSE | -46139 | -46038 | -6576.8571
IN TRANSIT & DELAYED | Leriel Reyes | 2026-02-05 | PO08667 | SO17754 | 2026-04-06 | W-400-DSTL-A49-UC | Pump, W-Series 400 ZJD, Ultrachrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | BARRICK DIRECT SHIPPING | 2026-05-17 | SEA | ETA CAUCEDO JUNE 28 | FOB Tianjin |  | Original Lead time for production: 60 days (9 weeks) after payment. Wrong due date in Order + regular sea transit 10 weeks | PEter 05/16: The vessel already arrived at Tianjin seaport, will depart Tianjin tomorrow: May 17. | Naipu: still need 10-14 day to complete. ETD Mar 15 from Shanghai to Caucedo New ETD MAY 8TH May 14th: ETD Tianjin May 16 early morning | 2026-04-27 |  | FALSE | 41 | -46058 | -6579.7143
IN TRANSIT & DELAYED | Leriel Reyes | 2026-02-05 | PO08667 | SO17754 | 2026-04-06 |  | Pulley and belts, 400 ZJD, Ultrachrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | BARRICK DIRECT SHIPPING | 2026-05-17 | SEA | ETA CAUCEDO JUNE 28 | FOB Tianjin |  | Original Lead time for production: 60 days (9 weeks) after payment. Wrong due date in Order + regular sea transit 10 weeks | PEter 05/16: The vessel already arrived at Tianjin seaport, will depart Tianjin tomorrow: May 17. | Naipu: still need 10-14 day to complete. ETD Mar 15 from Shanghai to Caucedo New ETD MAY 8TH May 14th: ETD Tianjin May 16 early morning | 2026-04-27 |  | FALSE | 41 | -46058 | -6579.7143
IN TRANSIT & DELAYED | Leriel Reyes | 2026-02-05 | PO08667 | SO17754 | 2026-04-06 | W-400-DSTL-A49-UC | Pump, W-Series 400 ZJD, Ultrachrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | BARRICK DIRECT SHIPPING | 2026-05-17 | SEA | ETA CAUCEDO JUNE 28 | FOB Tianjin |  | Original Lead time for production: 60 days (9 weeks) after payment. Wrong due date in Order + regular sea transit 10 weeks | PEter 05/16: The vessel already arrived at Tianjin seaport, will depart Tianjin tomorrow: May 17. | Naipu: still need 10-14 day to complete. ETD Mar 15 from Shanghai to Caucedo New ETD MAY 8TH May 14th: ETD Tianjin May 16 early morning | 2026-04-27 |  | FALSE | 41 | -46058 | -6579.7143
IN TRANSIT & DELAYED | Leriel Reyes | 2026-02-05 | PO08667 | SO17754 | 2026-04-06 |  | Pulley and belts, 400 ZJD, Ultrachrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | BARRICK DIRECT SHIPPING | 2026-05-17 | SEA | ETA CAUCEDO JUNE 28 | FOB Tianjin |  | Original Lead time for production: 60 days (9 weeks) after payment. Wrong due date in Order + regular sea transit 10 weeks | PEter 05/16: The vessel already arrived at Tianjin seaport, will depart Tianjin tomorrow: May 17. | Naipu: still need 10-14 day to complete. ETD Mar 15 from Shanghai to Caucedo New ETD MAY 8TH May 14th: ETD Tianjin May 16 early morning | 2026-04-27 |  | FALSE | 41 | -46058 | -6579.7143
IN TRANSIT | Emilka Guerra | 2026-02-20 | PO08685 | SO18775 | 2026-03-25 | W-SP25092/A05 | Casing, 250SV-SP, High Chrome | 1 | Super Cast Limited | China | BARRICK DIRECT SHIPPING | 2026-04-16 | SEA | 2026-05-05 | CIF CAUCEDO PORT | LS15TJ2604798 |  | shipped out from Tianjin to Caucedo, Dominincan Republic on Apr 16, 2026. ✅ |  | 2026-05-05 |  | FALSE | 22 | -46073 | -6581.8571
DELAYED PRODUCTION | Emilka Guerra | 2026-03-30 | PO08772 | SO18353 | 2026-05-18 | AM-HH200C21-13 | Casing Cover (Blackplate), DW-AE8/6-21W, CD4MCu | 1 | AMOS Fluid Technology Co., Ltd | China | BARRICK DIRECT SHIPPING |  | SEA | 2026-07-07 | Peter will take care of the sea shipment -- CIF Caucedo Port | BARRICK ORDER | Follow up email sen on May 7th. Follow up email sen on May 20th. | AMOS May 8th: confirmed completition by May 20th ✅ Peter: AMOS confirmed it will be ready to leave factory by May 20 (Wednesday). I will book vessel next Monday. | Delayed production: To be completed in the week 25 - 29 | 2026-07-07 |  | FALSE | -46160 | -46111 | -6587.2857
DELAYED PRODUCTION | Emilka Guerra | 2026-03-30 | PO08772 | SO18353 | 2026-05-18 | AM-HH200C21-10-CD4 | Casing, DW-AE8/6-21W, CD4MCu | 1 | AMOS Fluid Technology Co., Ltd | China | BARRICK DIRECT SHIPPING |  | SEA | 2026-07-07 | Peter will take care of the sea shipment -- CIF Caucedo Port | BARRICK ORDER | Follow up email sen on May 7th. Follow up email sen on May 20th. | AMOS May 8th: confirmed completition by May 20th ✅ Peter: AMOS confirmed it will be ready to leave factory by May 20 (Wednesday). I will book vessel next Monday. | Delayed production: To be completed in the week 25 - 29 | 2026-07-07 |  | FALSE | -46160 | -46111 | -6587.2857

## INCOMING STOCK ODOO
Created By | Fecha de creación de la orden | Purchase Order | Vendor Reference | Due Date | SKU | Product Name | Incoming Stock | Supplier | Warehouse | Receipt Date | Receipt Date
Emilka Guerra | 2025-11-11 | PO08424 | Stock | 2025-12-30 | AC-98-431-849-001 | Suction Side Casing, 3x3-10 SRL, Cast Iron | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-03-10 | 2026-03-05
Emilka Guerra | 2025-11-13 | PO08435 | DR Warehouse | 2026-01-05 | AM-LH100S8-CD4-PUMP | Self-Priming Pump, DW-BE4/4-8S, CD4MCu, Pump Only | 1 | AMOS Fluid Technology Co., Ltd | Dominican Republic | 2026-04-09
Emilka Guerra | 2025-11-13 | PO08435 | DR Warehouse | 2026-01-05 | AM-MH150S12-CD4-PUMP ONLY | Self-Priming Pump, DW-ME6/6-12S, CD4MCu, Pump Only | 1 | AMOS Fluid Technology Co., Ltd | Dominican Republic | 2026-04-09
Emilka Guerra | 2025-11-13 | PO08435 | DR Warehouse | 2026-01-05 | AM-MH200C14-CD4-PUMP | Self-Priming Pump, DW-ME10/8-14W, CD4MCu, Pump Only | 1 | AMOS Fluid Technology Co., Ltd | Dominican Republic | 2026-04-09
Emilka Guerra | 2025-11-13 | PO08435 | DR Warehouse | 2026-01-05 | AM-HH200C21-CD4-PUMP | Self-Priming Pump, DW-AE8/6-21W, CD4MCu, Pump Only | 1 | AMOS Fluid Technology Co., Ltd | Dominican Republic | 2026-04-09
Emilka Guerra | 2025-11-24 | PO08463 | Stock | 2026-01-05 | AC-98-431-799-001 | Suction Side Casing, 5x4-14 SRL-C, Cast Iron | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-03-16 | 2026-05-13
Ian Trottier | 2025-12-10 | PO08518 | Stock - JC 1J - 1x1.5-11 Project | 2026-02-06 | D-1J11511-10 | Impeller, 1x1.5-11, Goulds JC, Frame 1J, High Chrome, OEM# 056185G4701228 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-04-17
Ian Trottier | 2025-12-10 | PO08518 | Stock - JC 1J - 1x1.5-11 Project | 2026-02-06 | D-1J11511-2 | Casing, 1x1.5-11, Goulds JC, Frame 1J, High Chrome, OEM# 056185G5101228 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-04-17
Ian Trottier | 2025-12-10 | PO08518 | Stock - JC 1J - 1x1.5-11 Project | 2026-02-06 | D-1J11511-6 | Suction Cover Liner, 1x1.5-11, Goulds JC, Frame 1J, High Chrome, OEM# 048935G0001228 | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-04-17 | PO08730 | WO-9090150-183 | Impeller Nut, Worthington 6 FRBH-183/223, 316SS | 1
Ian Trottier | 2025-12-10 | PO08518 | Stock - JC 1J - 1x1.5-11 Project | 2026-02-06 | D-1J11511-14 | Suction Cover, 1x1.5-11, Goulds JC, Frame 1J, High Chrome, OEM# 050385G0001228 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-04-17
Ian Trottier | 2025-12-10 | PO08518 | Stock - JC 1J - 1x1.5-11 Project | 2026-02-06 | D-1x1.5-11-JC-HC | Pump, 1x1.5-11, Dynapro DC, Frame 1J, High Chrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-04-17
Jeff Bell | 2025-12-11 | PO08522 |  | 2026-02-23 | 150ZJ-F-HE2. 8/6 F-AH w/HE Impeller | Pump, W-Series, 8/6 DH, 150ZJF-HE, 28% Ultrachrome, Corrosion Resistant | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-05-04 | PO NUMBER | SKU | PRODUCT NAME | INCOMING STOCK
Emilka Guerra | 2025-12-16 | PO08541 | SO18419 | 2026-01-02 | 10JKH, 7-Vane Impeller, CD4MCu | Impeller, 10JKH, Double Keyed, w/Wear Ring | 3 | Jiangsu Win-win International Trading Co., Ltd. | Dynapro | 2026-03-16
Ian Trottier | 2025-12-24 | PO08570 | Stock | 2026-01-28 | G-10x12-22-JC-HC | Pump, 10x12-22, Goulds JC Frame 5J, High Chrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-03-13
Ian Trottier | 2025-12-30 | PO08574 | Stock | 2026-03-02 | G-8x10-18-JC-HC | Pump, 8x10-18, Dynapro DC, Frame 3J, High Chrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-05-18 | 2026-05-13
| 2026-01-13 | PO08595 | SO18485 - Ship direct to Dominican | 2026-02-13 | W-M100KSS-TVB/0507 | Sump Pump, M100KSS-TVB, CD4MCu | 1 | Shijiazhuang Mets Machinery Co., LTD | Dynapro | 2026-04-24
Yannett Yeomans | 2026-01-14 | PO08603 | SO18567 | 2026-02-16 | GB/T6172.1 | Nut M20, XS500-710, Carbon Steel | 2 | Super Cast Limited | México | 2026-04-13 | PO08679 | AC-52-224-289-005 | Shaft Sleeve, Allis-Chalmers CSO, Frame F4B3/F4B5/F4D1, XH-800 | 2
Yannett Yeomans | 2026-01-14 | PO08603 | SO18567 | 2026-02-16 | 10532/0539 | Cap Shape Nut, M24, XS500-710, 201SS | 8 | Super Cast Limited | México | 2026-04-13
Yannett Yeomans | 2026-01-14 | PO08603 | SO18567 | 2026-02-16 | 10470/1501 | Double Head Bolt M24x140mm, XS500-710, Carbon Steel | 8 | Super Cast Limited | México | 2026-04-13
Yannett Yeomans | 2026-01-14 | PO08603 | SO18567 | 2026-02-16 | 10469/1501 | Double Head Bolt, M27x110mm, XS500-710, Carbon Steel | 8 | Super Cast Limited | México | 2026-04-13
Yannett Yeomans | 2026-01-14 | PO08603 | SO18567 | 2026-02-16 | 10468/1501 | Nut M16, XS500-710, Carbon Steel | 4 | Super Cast Limited | México | 2026-04-13
Yannett Yeomans | 2026-01-14 | PO08603 | SO18567 | 2026-02-16 | 10461/1501 | Double Head Bolt M27x75mm, XS500-710, Carbon Steel | 76 | Super Cast Limited | México | 2026-04-13
Yannett Yeomans | 2026-01-14 | PO08603 | SO18567 | 2026-02-16 | 10456/0539 | FLAT WASHER, M27, XS500-710, 201SS | 84 | Super Cast Limited | México | 2026-04-13 | PO08729 | G-77-59 1001 | Bearing Housing, 3405-M, Cast Iron | 1
Yannett Yeomans | 2026-01-14 | PO08603 | SO18567 | 2026-02-16 | GB/T6170 | Nut M24, XS500-710, 304SS | 16 | Super Cast Limited | México | 2026-04-13
Leriel Reyes | 2026-01-16 | PO08609 | SO17341 | 2026-04-27 | D-XS350-560G | Horizontal Split-Case Pump 20/14 | 1 | Super Cast Limited | Dynapro | 2026-07-06
Leriel Reyes | 2026-01-16 | PO08609 | SO17341 | 2026-04-27 | 10652/2001 | Set of Coupling and Coupling Guard XS350-560G, Cast Iron | 1 | Super Cast Limited | Dynapro | 2026-07-06
Leriel Reyes | 2026-01-16 | PO08609 | SO17341 | 2026-04-27 | 10653/1501 | Common base XS350-560G, Carbon Steel | 1 | Super Cast Limited | Dynapro | 2026-07-06
Ian Trottier | 2026-01-22 | PO08623 | Stock - SO18744 - | 2026-03-18 | AC-98-330-286-503 | Impeller (Open), 3x3-10 SRL, Neoprene | 2 | Super Cast Limited | Dynapro | 2026-05-27
Emilka Guerra | 2026-01-28 | PO08638 | Stock | 2026-03-13 | AC-98-431-577-501 | Frame, 14", Allis Chalmers PWO, Frame A1, Oil-Lubed, Cast Iron | 2 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-05-29
Ian Trottier | 2026-01-28 | PO08639 | SO18654 | 2026-04-08 | G-0C01359A 1203 | Flush Gland Assembly, 3196 MTX, Big Bore, 316SS | 2 | Hisco Pump Inc. | Dynapro | 2026-02-27
Emilka Guerra | 2026-01-29 | PO08642 | Stock | 2026-03-20 | 571638 | Casing, Sala VS150, High Chrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-05-29
Emilka Guerra | 2026-01-29 | PO08642 | Stock | 2026-03-20 | AC-98-431-768-501 | Shaft Assembly, 8x6-18 SRL-C, 1045 Steel | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-05-29
Emilka Guerra | 2026-01-29 | PO08642 | Stock | 2026-03-20 | W-G12060/S01 | Intake Joint Ring, EPDM | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-05-29
Emilka Guerra | 2026-01-29 | PO08642 | Stock | 2026-03-20 | AC-98-131-246-511 | Deflector (Water Slinger), 5x5/5x4/6x6 SRL & SRL-C, Neoprene/Steel | 20 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-05-29
Ian Trottier | 2026-01-29 | PO08643 | SO18666 | 2026-03-09 | W-TUL55147DP1/A05 | Impeller, 5 VCG, Duty Point, No Back Vanes, 550 TU-L, High Chrome | 1 | Shijiazhuang Mets Machinery Co., LTD | Dynapro | 2026-05-18
Emilka Guerra | 2026-01-30 | PO08646 | Stock - SO19408 | 2026-03-20 | AC-98-431-641-501 | Impeller (Closed), 10x8-21 SRL-C, Natural Rubber | 10 | Super Cast Limited | Dynapro | 2026-05-29
Emilka Guerra | 2026-01-30 | PO08646 | Stock - SO19408 | 2026-03-20 | W-RSL30147/A05 | Impeller, 300 RSL, High Chrome, 5-Vane | 1 | Super Cast Limited | Dynapro | 2026-05-29
Jeff Bell | 2026-01-31 | PO08653 | SO18397 | 2026-03-22 | W-100RVSP-900-CD4 | Sump Pump, W-Series, 100RV-SP, CD4MCu, 900mm Column | 2 | Shijiazhuang Mets Machinery Co., LTD | Dynapro | 2026-05-30
Emilka Guerra | 2026-02-03 | PO08655 | SO18583 | 2026-04-28 | 9102760141-0 | Impeller, Ahlstrom, MCE 32-4, 2205 Duplex | 1 | Super Cast Limited | Dynapro | 2026-07-07
Livan Hernandez | 2026-02-04 | PO08659 | STOCK | 2026-03-25 | AC-98-331-958-822 | Shaft Sleeve, 3x3-10 SRL & SRL-C, 420SS Heat Treated, Hardened | 6 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-06-17
Livan Hernandez | 2026-02-04 | PO08659 | STOCK | 2026-03-25 | AC-98-331-901-801 | Bearing Cover (Outboard), 8x6-18 & 10x8-21 SRL-C, Cast Iron | 10 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-06-17
Livan Hernandez | 2026-02-04 | PO08659 | STOCK | 2026-03-25 | AC-98-331-936-801 | Bearing Cover (Inboard), 8x6-18 & 10x8-21 SRL-C, Cast Iron | 10 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-06-17
Livan Hernandez | 2026-02-04 | PO08659 | STOCK | 2026-03-25 | AC-98-431-858-501 | Shaft Assembly, 3x3-10 SRL & SRL-C, 1045 Steel | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-06-17 | PO08733 | G-B00296A 6956 | Shaft Sleeve, 3175-L, 316SS, Ni-Chrome Boron | 3
Amanda Qiao | 2026-02-04 | PO08664 | SO18536 | 2026-05-05 | AC-SRL 3x3-10-C | Pump, AC-SRL 3x3-10-C, Natural Rubber Lined, Motor Mounting Plate, Belt Guard | 2 | IGH | Dynapro | 2026-05-05
Leriel Reyes | 2026-02-05 | PO08667 | SO17754 | 2026-04-06 | W-400-DSTL-A49-UC | Pump, W-Series 400 ZJD, Ultrachrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-04-27
Leriel Reyes | 2026-02-05 | PO08667 | SO17754 | 2026-04-06 |  | Pulley and belts, 400 ZJD, Ultrachrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-04-27
Leriel Reyes | 2026-02-05 | PO08667 | SO17754 | 2026-04-06 | W-400-DSTL-A49-UC | Pump, W-Series 400 ZJD, Ultrachrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-04-27
Leriel Reyes | 2026-02-05 | PO08667 | SO17754 | 2026-04-06 |  | Pulley and belts, 400 ZJD, Ultrachrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-04-27
Leriel Reyes | 2026-02-06 | PO08671 | SO17754 | 2026-06-26 | PF4506 | 450 HP, 1200 RPM, 460/3/60, 5011B Frame TEFC, Optim TEFC, Teco-Westinghouse Motor | 1 | Teco-Westinghouse Motors (Canada) Inc. | Dynapro | 2026-06-26
Emilka Guerra | 2026-02-09 | PO08674 | Stock | 2026-03-30 | AC-98-330-286-503 | Impeller (Open), 3x3-10 SRL, Neoprene | 8 | Super Cast Limited | Dynapro | 2026-06-15 | 2026-03-30
Emilka Guerra | 2026-02-09 | PO08674 | Stock | 2026-03-30 | W-SP15092/A05 | Casing w/Flange, 150SV-SP, High Chrome | 4 | Super Cast Limited | Dynapro | 2026-06-15
Emilka Guerra | 2026-02-09 | PO08674 | Stock | 2026-03-30 | W-SP15206A/A05 | Impeller, 150SV-SP, 5-Vane, High Chrome | 5 | Super Cast Limited | Dynapro | 2026-06-15
Emilka Guerra | 2026-02-20 | PO08685 | SO18775 | 2026-03-25 | W-SP15092/A05 | Casing w/Flange, 150SV-SP, High Chrome | 2 | Super Cast Limited | Dynapro | 2026-06-03
Emilka Guerra | 2026-02-20 | PO08685 | SO18775 | 2026-03-25 | W-SP15206A/A05 | Impeller, 150SV-SP, 5-Vane, High Chrome | 2 | Super Cast Limited | Dynapro | 2026-06-03
Emilka Guerra | 2026-02-20 | PO08685 | SO18775 | 2026-03-25 | W-SP25092/A05 | Casing, 250SV-SP, High Chrome | 1 | Super Cast Limited | Dynapro | 2026-06-03
Carlos Leon | 2026-02-20 | PO08688 | SO18785 | 2026-04-03 | WO-9090140-183 | Impeller Nut, Worthington, 8FRBH152 316SS | 1 | Hisco Pump Inc. | Dynapro | 2026-04-17
Emilka Guerra | 2026-02-20 | PO08689 | Stock - SO19018 | 2026-04-06 | D-1J2311-2 | Casing, 2x3-11, Goulds JC, Frame 1J, High Chrome, OEM# 055891G0001228 | 7 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-06-22
Ian Trottier | 2026-02-20 | PO08690 | SO18457 | 2026-04-10 | D-PE4J-400-316 | Power End, Goulds JC, Frame 4J, Grease-Lubed, SKF Bearings, 316SS Steel Shaft | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-06-12
Emilka Guerra | 2026-02-24 | PO08697 | SO18719 | 2026-05-08 | 5340900141 | Casing, Ahlstrom, MCE 32-4, 2205 Duplex | 1 | Super Cast Limited | Dynapro | 2026-08-07
Ian Trottier | 2026-02-25 | PO08698 | Stock | 2026-04-08 |  | Baseplate, JC, 2J/3J Frame, Steel Fabricated, Adjustable Over-Head Motor Mount & Belt Guard | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-06-24
Ian Trottier | 2026-02-25 | PO08698 | Stock | 2026-04-08 | SF-PE3 | Baseplate, JC, 3J Frame, Steel Fabricated, Adjustable Over-Head Motor Mount & Belt Guard | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-06-24
Ian Trottier | 2026-02-25 | PO08698 | Stock | 2026-04-08 | SF-PE4 | Baseplate, JC, 4J Frame, Steel Fabricated, Adjustable Over-Head Motor Mount & Belt Guard | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-06-24
Ian Trottier | 2026-02-27 | PO08707 | SO18631 | 2026-05-31 | AC-SRL 5x5-14 | Pump, AC-SRL 5x5-14, Natural Rubber Lined, Motor Mounting Plate, Belt Guard | 1 | IGH | Dynapro | 2026-07-06
Emilka Guerra | 2026-03-03 | PO08714 | SO18745 & Stock | 2026-04-07 | W-SP15041/A05 | Back Liner, 150SV-SP, High Chrome | 4 | Super Cast Limited | Dynapro | 2026-06-19
Emilka Guerra | 2026-03-03 | PO08714 | SO18745 & Stock | 2026-04-07 | AC-98-332-794-501 | Suction Side Plate, 10x10-28 SRL-XT, Natural Rubber | 6 | Super Cast Limited | Dynapro | 2026-06-19
Emilka Guerra | 2026-03-03 | PO08714 | SO18745 & Stock | 2026-04-07 | W-F8147/A05 | Impeller, 10/8 E-M, High Chrome | 2 | Super Cast Limited | Dynapro | 2026-06-19
Emilka Guerra | 2026-03-03 | PO08715 | Stock | 2026-04-07 | D-2001414-2507 | Key (Square), 10JKH/M, 0.38x1.13LG, Duplex SS 2507 | 40 | Jiangsu Win-win International Trading Co., Ltd. | Dynapro | 2026-06-16
Emilka Guerra | 2026-03-03 | PO08715 | Stock | 2026-04-07 | D-2001407-2507 | Bowl Wear Ring, 10JKH/M, 05.50x05.88x0.88, Duplex SS 2507 w/Ion Nitriding | 60 | Jiangsu Win-win International Trading Co., Ltd. | Dynapro | 2026-06-16
Emilka Guerra | 2026-03-03 | PO08715 | Stock | 2026-04-07 | D-2001405-CD4 | Bowl,10JKH/M, BW-INT-STEP-NO-SL-SP, CD4MCu | 16 | Jiangsu Win-win International Trading Co., Ltd. | Dynapro | 2026-06-16
Emilka Guerra | 2026-03-03 | PO08715 | Stock | 2026-04-07 | D-2001408-2507 | Impeller Wear Ring, 10JKH/M, 5.12x5.48x0.88, Duplex SS 2507 w/Ion Nitriding | 35 | Jiangsu Win-win International Trading Co., Ltd. | Dynapro | 2026-06-16
Emilka Guerra | 2026-03-03 | PO08715 | Stock | 2026-04-07 | D-2001417-CD4 | Bell,10JKH/M, BW-FLG-STD-STEP-CUT_NR, CD4MCu | 3 | Jiangsu Win-win International Trading Co., Ltd. | Dynapro | 2026-06-16
Emilka Guerra | 2026-03-03 | PO08715 | Stock | 2026-04-07 | D-2001412-4PHSS | Hex Cap Screw, 10JKH/M, 0.44-14NCx1.50, 17-4PH SS | 300 | Jiangsu Win-win International Trading Co., Ltd. | Dynapro | 2026-06-16
Emilka Guerra | 2026-03-03 | PO08715 | Stock | 2026-04-07 | D-2001416-174PH | Hex-Head Socket Cap Screw, 10JKH/M, 0.31-18NCx0.750, 17-4PH SS | 300 | Jiangsu Win-win International Trading Co., Ltd. | Dynapro | 2026-06-16
Emilka Guerra | 2026-03-03 | PO08719 | Stock | 2026-04-07 | D-PE2J-200 | Power End, Goulds JC, Frame 2J, Grease-Lubed, SKF Bearings, 4140 Steel Shaft | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-06-16
Gerardo Hernandez | 2026-03-05 | PO08724 | SO18877 | 2026-06-11 | AC-98-431-615-007 | Impeller, 6x4-14, PWO, 317SS | 1 | Emnor Mechanical Inc. | Dynapro | 2026-06-12
Jeff Bell | 2026-03-06 | PO08728 | SO17350 | 2026-04-17 | W-250-FF-MCU/0011 | Pump, W-Series, 250 FF-MCU, Hyperchrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-06-17
Ian Trottier | 2026-03-06 | PO08730 | SO18872 | 2026-05-01 | WO-9090150-183 | Impeller Nut, Worthington 6 FRBH-183/223, 316SS | 1 | Hisco Pump Inc. | Dynapro | 2026-06-05
Ian Trottier | 2026-03-06 | PO08731 | SO18872 | 2026-05-29 | PM# 5899, WO-2112700-1 | Wear Plate, Worthington 6-FRBH-223, 316SS | 1 | M&N Alloy Cast Products, Inc. | Dynapro | 2026-03-07
Emilka Guerra | 2026-03-06 | PO08732 | SO18865 | 2026-05-29 | AC-98-5414-HC1 | Volute Casing, 5x4-14 SRL-C, High Chrome, 3-Piece Design | 1 | IGH | Dynapro | 2026-07-03
Emilka Guerra | 2026-03-06 | PO08732 | SO18865 | 2026-05-29 | AC-98-5414-HC2 | Impeller (Nesting Design), 5x4-14 SRL-C, High Chrome, 3-Piece Design | 1 | IGH | Dynapro | 2026-07-03
Yannett Yeomans | 2026-03-09 | PO08735 | SO17830 | 2026-05-22 | AC-98-530-586-001 | Pedestal, 8x6-18 & 10x8-21 SRL-C, Cast Iron | 1 | IGH | Dynapro | 2026-06-12
Yannett Yeomans | 2026-03-09 | PO08735 | SO17830 | 2026-05-22 | AC-SRL 10x8-21-C-URE | Pump, AC-SRL 10x8-21-C, Urethane Lined, Motor Mounting Plate, Belt Guard | 1 | IGH | Dynapro | 2026-06-12
Emilka Guerra | 2026-03-09 | PO08736 | SO18902 | 2026-03-20 | W-D025/P10 | End Cover Shim Set, 4/3 or 6/4 D-AH | 2 | Super Cast Limited | México | 2026-06-05
Ian Trottier | 2026-03-10 | PO08737 | Stock | 2026-04-29 | D-PE3J-300 | Power End, Goulds JC, Frame 3J, Grease-Lubed, SKF Bearings, 4140 Steel Shaft | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-07-08
Ian Trottier | 2026-03-10 | PO08738 | SO18849 | 2026-04-10 | AC-98-431-614-007 | Impeller, 6x3-14, PWO, 317SS | 2 | Emnor Mechanical Inc. | Dynapro | 2026-06-19
Emilka Guerra | 2026-03-11 | PO08739 | Stock | 2026-04-15 | AC-98-331-954-801 | Bearing Cover (Inboard), 5x4/5x5/6x6 SRL & SRL-C, Cast Iron | 6 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-07-10
Emilka Guerra | 2026-03-11 | PO08739 | Stock | 2026-04-15 | AC-98-236-256-501 | Gland Assembly, 5x4-14 SRL-C, 316SS | 10 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-07-10
Emilka Guerra | 2026-03-11 | PO08739 | Stock | 2026-04-15 | D-2J3411-2 | Casing, 3x4-11, Goulds JC, Frame 2J, High Chrome, OEM# 056185G4001228 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-07-10 | 2026-07-17
Emilka Guerra | 2026-03-11 | PO08739 | Stock | 2026-04-15 | D-2J3411-6 | Suction Cover Liner, 3x4-11, Goulds JC, Frame 2J, High Chrome, OEM# 048824G0001228 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-07-10
Emilka Guerra | 2026-03-11 | PO08739 | Stock | 2026-04-15 | AC-98-234-268-001-SS | Waterseal Bushing, 5x4/5x5/6x6 SRL, 316SS | 10 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-07-10 | 2026-07-17
Emilka Guerra | 2026-03-11 | PO08740 | Stock - SO19105 | 2026-04-22 | DU-DY51040A-CD4 | Casing, 3x2-10A, Durco Mark 2&3 Group 2, CD4MCu | 1 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-07-10
Emilka Guerra | 2026-03-11 | PO08740 | Stock - SO19105 | 2026-04-22 | DU-MY51049A100-CD4 | Impeller, 3x2-10A, Durco Mark 2&3 Group 2, CD4MCu, Reverse Vane | 1 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-07-10
Emilka Guerra | 2026-03-11 | PO08740 | Stock - SO19105 | 2026-04-22 | G-254-50 1216 | Casing, 6x8-13, 3196 XLT, CD4MCu | 1 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-07-10
Emilka Guerra | 2026-03-11 | PO08740 | Stock - SO19105 | 2026-04-22 | DU-MY49112A130-CD4 | Impeller, 3x2-13, Durco Mark 2&3 Group 2, CD4MCu, Reverse Vane | 5 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-07-10 | 2026-07-17
Emilka Guerra | 2026-03-11 | PO08740 | Stock - SO19105 | 2026-04-22 | G-D04872A 1000 | Thrust Bearing Housing, 3196 MTX, Cast Iron | 2 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-07-10
Emilka Guerra | 2026-03-11 | PO08743 | Stock | 2026-04-10 | TSSC-J01-1.375(BIG BORE)-00 | Single Cartridge Seal, 1 3/8", D-196 STX or D-III Group 1, Big Bore, Carbon vs Silicon Carbide w/Aflas Elastomers | 15 | Super Cast Limited | Dynapro | 2026-06-26
Emilka Guerra | 2026-03-11 | PO08743 | Stock | 2026-04-10 | AC-98-231-135-501 | Suction Side Plate, 10x8-21 SRL-C, Natural Rubber | 10 | Super Cast Limited | Dynapro | 2026-06-26 | 2026-07-17
Emilka Guerra | 2026-03-11 | PO08743 | Stock | 2026-04-10 | AC-98-431-651-501 | Impeller (Closed), 8x6-18 SRL-C, Natural Rubber | 6 | Super Cast Limited | Dynapro | 2026-06-26 | 2026-05-05
Emilka Guerra | 2026-03-11 | PO08743 | Stock | 2026-04-10 | AC-98-231-120-501 | Suction Side Liner, 8x6-18 SRL-C, Natural Rubber | 5 | Super Cast Limited | Dynapro | 2026-06-26 | PO08712 | E11H439392 | O-Ring, Sideplate, Ahlstrom, APT 51-10, EPDM | 1
Emilka Guerra | 2026-03-11 | PO08743 | Stock | 2026-04-10 | W-SL30083M/A05 | Throatbush, 300 RSL, High Chrome | 1 | Super Cast Limited | Dynapro | 2026-06-26 | 2026-07-17
Ian Trottier | 2026-03-13 | PO08748 | Stock - SO18931 | 2026-04-22 | SA-128214-1 | Inlet, Sala VS150, High Chrome | 6 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-07-08
Leriel Reyes | 2026-03-24 | PO08762 | SO18978 | 2026-06-16 | AC-SRL 2x2-10 | Pump, AC-SRL 2x2-10, Natural Rubber Lined, Motor Mounting Plate, Belt Guard | 1 | IGH | Dynapro | 2026-07-24 | 2026-03-06
Ian Trottier | 2026-03-26 | PO08765 | SO18990 | 2026-06-18 | PM# 510, G-R254-70 1216 | Stuffing Box Cover, 18", 3175-M, CD4MCu, Standard Bore | 2 | M&N Alloy Cast Products, Inc. | Dynapro | 2026-03-26
Ian Trottier | 2026-03-26 | PO08766 | SO18967 | 2026-06-18 | PM# 1599, AC-52-425-392-006 | Casing, 2x3-13, Allis Chalmers CSO, 316ss | 1 | M&N Alloy Cast Products, Inc. | Dynapro | 2026-06-19
Amanda Qiao | 2026-03-30 | PO08768 | SO18861 | 2026-07-05 | AC-SRL 5x5-14 | Pump, AC-SRL 5x5-14, Natural Rubber Lined, Motor Mounting Plate, Belt Guard | 1 | IGH | Dynapro | 2026-07-24 | 2026-05-13
Emilka Guerra | 2026-03-30 | PO08772 | SO18353 | 2026-05-18 | AM-HH200C21-13 | Casing Cover (Blackplate), DW-AE8/6-21W, CD4MCu | 1 | AMOS Fluid Technology Co., Ltd | Dynapro | 2026-07-07 | 2026-05-13
Emilka Guerra | 2026-03-30 | PO08772 | SO18353 | 2026-05-18 | AM-HH200C21-10-CD4 | Casing, DW-AE8/6-21W, CD4MCu | 1 | AMOS Fluid Technology Co., Ltd | Dynapro | 2026-07-07
Emilka Guerra | 2026-03-31 | PO08773 | Stock | 2026-05-22 | AC-98-331-983-801 | Bearing Cylinder, 3x3-10 SRL & SRL-C, Cast Iron | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-07-31
Ian Trottier | 2026-04-01 | PO08779 | SO18941 | 2026-06-24 | AC-98-231-134-507 | Suction Side Liner, 10x8-21 SRL-C, Urethane | 1 | IGH | Dynapro | 2026-07-30
Ian Trottier | 2026-04-01 | PO08779 | SO18941 | 2026-06-24 | AC-98-231-136-507 | Gland Side Liner, 10x8-21 SRL-C, Urethane | 1 | IGH | Dynapro | 2026-07-30
Yannett Yeomans | 2026-04-06 | PO08781 | Stock | 2026-06-08 | DU-DY55718A-CI | Bearing Housing, Durco Mark 3 Group 2, Cast Iron | 1 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-08-17
Yannett Yeomans | 2026-04-06 | PO08781 | Stock | 2026-06-08 | G-D04872A 1000 | Thrust Bearing Housing, 3196 MTX, Cast Iron | 4 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-08-17
Yannett Yeomans | 2026-04-06 | PO08781 | Stock | 2026-06-08 | G-R100-586 1012 | Stuffing Box Cover, 10", 3196 MTX, Ductile Iron, Standard Bore, Non-Jacketed | 1 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-08-17
Yannett Yeomans | 2026-04-06 | PO08781 | Stock | 2026-06-08 | G-0B10588 1216 | Impeller, 2x3-13, 3196 LTX, CD4MCu, 5-Vane | 2 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-08-17
Emilka Guerra | 2026-04-06 | PO08782 | Stock | 2026-05-25 | AC-98-231-121-501 | Suction Side Plate, 8x6-18 SRL-C, Natural Rubber | 10 | Super Cast Limited | Dynapro | 2026-08-03
Emilka Guerra | 2026-04-06 | PO08782 | Stock | 2026-05-25 | W-F6018/R55 | Cover Plate Liner, 8/6 E or F-AH, Natural Rubber | 1 | Super Cast Limited | Dynapro | 2026-08-03
Emilka Guerra | 2026-04-06 | PO08782 | Stock | 2026-05-25 | W-F6147/R55 | Impeller, 8/6 E, F or R-AH, Natural Rubber | 1 | Super Cast Limited | Dynapro | 2026-08-03
Emilka Guerra | 2026-04-06 | PO08785 | Stock | 2026-05-26 | D-WE1J-4 | Shaft Sleeve, Goulds JC Frame 1J, 420SS Heat Treated, Hardened | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-11
Emilka Guerra | 2026-04-06 | PO08785 | Stock | 2026-05-26 | AC-98-331-932-501 | Shaft Assembly, 5x4-14 SRL-C & 5x5-14 SRL, 1045 Steel | 12 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-11
Emilka Guerra | 2026-04-06 | PO08786 | Stock | 2026-05-04 | D-2001412-4PHSS | Hex Cap Screw, 10JKH/M, 0.44-14NCx1.50, 17-4PH SS | 300 | Jiangsu Win-win International Trading Co., Ltd. | Dynapro | 2026-07-13
Emilka Guerra | 2026-04-07 | PO08789 | SO19037 | 2026-05-19 | D-1J2311-14 | Suction Cover, 2x3-11, Goulds JC, Frame 1J, High Chrome, OEM# 050387G0001228 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-07-28
Ian Trottier | 2026-04-08 | PO08791 | SO19027 | 2026-07-01 | AC-52-425-753-004 | Stuffing Box Cover, 10", CSO F4B3, Alloy-20 | 1 | M&N Alloy Cast Products, Inc. | Dynapro | 2026-04-08
Emilka Guerra | 2026-04-10 | PO08800 | Stock | 2026-05-22 | D-2J3411-6 | Suction Cover Liner, 3x4-11, Goulds JC, Frame 2J, High Chrome, OEM# 048824G0001228 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-07
Emilka Guerra | 2026-04-10 | PO08800 | Stock | 2026-05-22 | D-1J2311-14 | Suction Cover, 2x3-11, Goulds JC, Frame 1J, High Chrome, OEM# 050387G0001228 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-07
Ian Trottier | 2026-04-13 | PO08801 | SO18931 | 2026-06-15 | SA-13576-M1 | Casing, Sala STHM, 33-WFR, High Chrome | 5 | Dexhor | Dynapro | 2026-06-26
Ian Trottier | 2026-04-13 | PO08802 | SO18931 | 2026-05-04 | AC-98-431-743-501 | Shaft Assembly, 10x8-21 SRL-C, 1045 Steel | 4 | Mid-Canada Manufacturing | Dynapro | 2026-05-11
Emilka Guerra | 2026-04-13 | PO08805 | Stock SO19105 | 2026-06-10 | G-R100-533 1216 | Stuffing Box Cover, 13", 3196 LTX, CD4MCu, Standard Bore, Non-Jacketed | 1 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-08-19
Emilka Guerra | 2026-04-13 | PO08805 | Stock SO19105 | 2026-06-10 | G-P1600L0S00 X060 | Power End, 3196 LTX, 316SS Shaft (Sleeved Type), Oil Lubed | 1 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-08-19
Emilka Guerra | 2026-04-13 | PO08805 | Stock SO19105 | 2026-06-10 | DU-MY36847AA130-CD4 | Impeller, 4x3-13, Durco Mark 2&3 Group 2, CD4MCu, Reverse Vane | 2 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-08-19
Emilka Guerra | 2026-04-13 | PO08805 | Stock SO19105 | 2026-06-10 | G-249-65 1216 | Casing, 3x4-13, 3196 MTX, CD4MCu | 1 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-08-19
Emilka Guerra | 2026-04-13 | PO08806 | Stock | 2026-05-13 | W-F005M | Bearing Assembly w/Shaft, 8/6 F-AH, Metric | 1 | Super Cast Limited | Dynapro | 2026-07-29
Emilka Guerra | 2026-04-13 | PO08806 | Stock | 2026-05-13 | AC-98-039-047-501 | Impeller (Closed), 5x4-14 SRL-C, Natural Rubber | 12 | Super Cast Limited | Dynapro | 2026-07-29
Emilka Guerra | 2026-04-13 | PO08806 | Stock | 2026-05-13 | AC-98-231-116-501 | Gland Side Liner, 5x4-14 SRL-C, Natural Rubber | 9 | Super Cast Limited | Dynapro | 2026-07-29
Emilka Guerra | 2026-04-13 | PO08806 | Stock | 2026-05-13 | W-F8147/R55 | Impeller, 10/8 E-M, Natural Rubber | 4 | Super Cast Limited | Dynapro | 2026-07-29
Ian Trottier | 2026-04-13 | PO08809 | SO18643 | 2026-06-22 | G-R72360 6956 | Shaft Sleeve, 3405-M, Ni-Chrome Boron On 316SS | 1 | Hisco Pump Inc. | Dynapro | 2026-06-29
Emilka Guerra | 2026-04-14 | PO08812 | SO19193 | 2026-06-09 | AC-98-037-796-503 | Impeller (Open), 6x6-15 SRL, Neoprene | 1 | IGH | Dynapro | 2026-07-07
Ian Trottier | 2026-04-14 | PO08813 | SO18681 | 2026-05-26 | AC-98-233-212-501 | Slinger Assembly, PWO Frame 3, Oil | 3 | Advanced Engineered Pump Inc. | Dynapro | 2026-06-09
Yannett Yeomans | 2026-04-14 | PO08815 | SO19071 | 2026-06-22 | AC-98-432-037-001 | Bearing Cylinder Strap (Set of 2), 8x6/10x8 SRL-C, Cast Iron | 2 | IGH | Dynapro | 2026-07-06
Ian Trottier | 2026-04-16 | PO08817 | SO19098 | 2026-07-23 | AC-98-331-596-801 | Stuffing Box Cover, 21", PWO, Frame 3, Cast Iron | 1 | Emnor Mechanical Inc. | Dynapro | 2026-07-30
Ian Trottier | 2026-04-16 | PO08818 | SO19043 | 2026-07-09 | P/N #73, AC-98-431-321-013 | Impeller, 8x6-17, PWO, 3-Vane, CD4MCu | 2 | M&N Alloy Cast Products, Inc. | Dynapro | 2026-04-17
Ian Trottier | 2026-04-16 | PO08821 | Stock | 2026-05-29 | D-1J2311-14 | Suction Cover, 2x3-11, Goulds JC, Frame 1J, High Chrome, OEM# 050387G0001228 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-05-26
Emilka Guerra | 2026-04-17 | PO08822 | SO19118 | 2026-05-22 | W-F6018TL1/R55 | Cover Plate Liner (Thick), 8/6 F-AH, Natural Rubber | 1 | Super Cast Limited | México | 2026-07-17
Emilka Guerra | 2026-04-20 | PO08826 | SO18757 | 2026-06-22 | DE-560229 | Housing Packing Gland, 10x8 SRL, Denver, Cast Iron | 2 | IGH | Dynapro | 2026-07-13
Emilka Guerra | 2026-04-20 | PO08826 | SO18757 | 2026-06-22 | DE-503397 | Lantern Ring, 10x8 SRL, Denver, Carbon Steel | 2 | IGH | Dynapro | 2026-07-13
Emilka Guerra | 2026-04-20 | PO08826 | SO18757 | 2026-06-22 | DE-503539 | Shaft Sleeve, 10x8 SRL, Denver, Carbon Steel | 2 | IGH | Dynapro | 2026-07-13
Emilka Guerra | 2026-04-20 | PO08826 | SO18757 | 2026-06-22 | DE-560227 | Split Gland, 10x8 SRL, Denver, Cast Iron | 2 | IGH | Dynapro | 2026-07-13
Emilka Guerra | 2026-04-20 | PO08827 | Stock | 2026-05-25 | AC-98-234-000-801 | Bearing Cover (Outboard), 3x3-10 SRL & SRL-C, Cast Iron | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Emilka Guerra | 2026-04-20 | PO08827 | Stock | 2026-05-25 | AC-98-431-858-501 | Shaft Assembly, 3x3-10 SRL & SRL-C, 1045 Steel | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Emilka Guerra | 2026-04-20 | PO08827 | Stock | 2026-05-25 | AC-98-331-983-801 | Bearing Cylinder, 3x3-10 SRL & SRL-C, Cast Iron | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Emilka Guerra | 2026-04-20 | PO08827 | Stock | 2026-05-25 | D-1J2311-10 | Impeller, 2x3-11, Goulds JC, Frame 1J, High Chrome, OEM# 056189G2601228 | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Emilka Guerra | 2026-04-20 | PO08827 | Stock | 2026-05-25 | D-2J3411-6 | Suction Cover Liner, 3x4-11, Goulds JC, Frame 2J, High Chrome, OEM# 048824G0001228 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Emilka Guerra | 2026-04-20 | PO08827 | Stock | 2026-05-25 | D-WE2J-8 | Stuffing Box Cover, Goulds JC, Frame 2J, High Chrome, OEM# 048877G0001228 | 5 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Emilka Guerra | 2026-04-20 | PO08827 | Stock | 2026-05-25 | D-2J3411-1 | Casing, 3x4-11, Goulds JC, Frame 2J, Cast Iron, OEM#056185G4011002 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Emilka Guerra | 2026-04-20 | PO08828 | Stock - SO19393 | 2026-06-15 | DU-DY21855A/CBS-DC20 | Rear Cover, 13", Durco Mark 2&3 Group 2, Alloy-20, Small Bore | 1 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-08-25
Emilka Guerra | 2026-04-20 | PO08828 | Stock - SO19393 | 2026-06-15 | DU-MY36846AA130-CD4 | Impeller, 6x4-13A, Durco Mark 2&3 Group 2, CD4MCu, Reverse Vane | 1 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-08-25
Emilka Guerra | 2026-04-20 | PO08828 | Stock - SO19393 | 2026-06-15 | DU-MY36847AA130-CD4 | Impeller, 4x3-13, Durco Mark 2&3 Group 2, CD4MCu, Reverse Vane | 3 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-08-25
Emilka Guerra | 2026-04-20 | PO08828 | Stock - SO19393 | 2026-06-15 | DU-MY49112A130-CD4 | Impeller, 3x2-13, Durco Mark 2&3 Group 2, CD4MCu, Reverse Vane | 4 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-08-25
Emilka Guerra | 2026-04-20 | PO08828 | Stock - SO19393 | 2026-06-15 | G-75748X 2229 | Shaft Sleeve, 3175-S, 316SS | 2 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-08-25
Emilka Guerra | 2026-04-20 | PO08828 | Stock - SO19393 | 2026-06-15 | DU-AY38913AA-316 | Shaft Sleeve, Durco Mark 2&3 Group 2, 316SS | 5 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-08-25
Emilka Guerra | 2026-04-20 | PO08829 | SO18821 & Stock | 2026-05-06 | AC-98-431-743-501 | Shaft Assembly, 10x8-21 SRL-C, 1045 Steel | 3 | Mid-Canada Manufacturing | Dynapro | 2026-05-13
Ian Trottier | 2026-04-21 | PO08834 | SO19031 | 2026-05-18 | W-F8036-19M/R55 | Frame Plate Liner (Mechanical Seal), 10/8 E-M or 200 Type L, Natural Rubber | 1 | Super Cast Limited | Dynapro | 2026-08-10
Yannett Yeomans | 2026-04-23 | PO08843 | SO19177 | 2026-04-27 | W-FMC15145EL1/A05 | Impeller, 150 MCU, High Chrome | 1 | Super Cast Limited | México | 2026-06-25
Emilka Guerra | 2026-04-24 | PO08844 | SO19176 & stock | 2026-06-05 | AC-98-231-079-503 | Gland Side Liner, 5x5-14 SRL, Neoprene | 1 | IGH | Dynapro | 2026-07-03
Emilka Guerra | 2026-04-24 | PO08844 | SO19176 & stock | 2026-06-05 | AC-98-231-081-503 | Suction Side Liner, 5x5-14 SRL, Neoprene | 1 | IGH | Dynapro | 2026-07-03
Emilka Guerra | 2026-04-24 | PO08844 | SO19176 & stock | 2026-06-05 | AC-98-432-037-001 | Bearing Cylinder Strap (Set of 2), 8x6/10x8 SRL-C, Cast Iron | 3 | IGH | Dynapro | 2026-07-03
Emilka Guerra | 2026-04-24 | PO08846 | Stock | 2026-05-25 | G-73705X 2229 | Shaft Sleeve, 3196 MTX, 316SS | 10 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-08-03
Emilka Guerra | 2026-04-24 | PO08846 | Stock | 2026-05-25 | G-RC04110A01 1216 | Stuffing Box Cover, 10", 3196 MTX, CD4, Taper Bore Plus | 1 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-08-03
Emilka Guerra | 2026-04-24 | PO08846 | Stock | 2026-05-25 | G-249-61 1216 | Casing, 2x3-10, 3196 MTX, CD4MCu | 1 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-08-03
Amanda Qiao | 2026-04-26 | PO08847 | SO18070 | 2026-05-26 | W-50ZJLF-QV | Froth Pump, 2" QV-AF, W-Series, Rubber Lined Tank | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-04
Amanda Qiao | 2026-04-26 | PO08847 | SO18070 | 2026-05-26 |  | Paint | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-04
Amanda Qiao | 2026-04-26 | PO08847 | SO18070 | 2026-05-26 | W-50ZJLF-QV-BELT | Belts, W-50ZJLF-QV | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-04
Amanda Qiao | 2026-04-26 | PO08847 | SO18070 | 2026-05-26 | W-QV008/E05 | Bearing Sleeve, QV008 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-04
Amanda Qiao | 2026-04-26 | PO08847 | SO18070 | 2026-05-26 | W-BAF2127/A05 | Impeller, 50ZJLF-QV, High Chrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-04
Amanda Qiao | 2026-04-26 | PO08847 | SO18070 | 2026-05-26 | W-BAF4041/A05 | Throat Bushing, 50ZJLF-QV, High Chrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-04 | PO08712 | E11B064594 | O-Ring, Shaft Sleeve, Ahlstrom, APT 51-10, Teflon | 1
Amanda Qiao | 2026-04-26 | PO08847 | SO18070 | 2026-05-26 | W-QVAF005 | Bearing Assembly, 50ZJLF-QV | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-04
Emilka Guerra | 2026-04-27 | PO08849 | SO19151 & Stock | 2026-05-26 | W-F062-10/D81 | Labyrinth, 8/6 to 14/12 F-AH, Zinc Plated | 3 | Super Cast Limited | Dynapro | 2026-08-04
Emilka Guerra | 2026-04-27 | PO08849 | SO19151 & Stock | 2026-05-26 | W-F108H/D21 | Piston Ring, Ductile Iron | 5 | Super Cast Limited | Dynapro | 2026-08-04
Emilka Guerra | 2026-04-27 | PO08850 | Stock | 2026-06-01 | AC-98-331-954-801 | Bearing Cover (Inboard), 5x4/5x5/6x6 SRL & SRL-C, Cast Iron | 6 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Emilka Guerra | 2026-04-27 | PO08850 | Stock | 2026-06-01 | AC-98-233-733-514 | Deflector (Water Slinger), 2x2-10 SRL, Neoprene/Steel | 8 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Emilka Guerra | 2026-04-27 | PO08851 | Stock | 2026-06-01 | W-RV10005L/0512 | Bearing Assembly (Agitator), 100ZJL-RV, 316L-SS Bearing Cylinder, 1800mm, tapped 316SS Shaft | 1 | Shijiazhuang Mets Machinery Co., LTD | Dynapro | 2026-08-11
Emilka Guerra | 2026-04-27 | PO08852 | SO19195 | 2026-06-09 | JC-SCS-1 3/4-4610-MT-BB | Single Cartridge Seal, 1 3/4", D-196 MT, Big Bore, Carbon vs | 1 | Super Cast Limited | México | 2026-08-18
Emilka Guerra | 2026-04-28 | PO08854 | SO19200 | 2026-06-10 | D-2001434-CD4 | Bowl (Top),10JKH/M, w/"O" Ring, CD4MCu | 2 | Jiangsu Win-win International Trading Co., Ltd. | Dynapro | 2026-06-17
Yannett Yeomans | 2026-04-28 | PO08855 | SO19186 | 2026-08-04 | AC-52-053-163-000 | Frame Assembly, F4D1, Allis-Chalmers CSO, c/w 316SS Shaft | 1 | Hisco Pump Inc. | Dynapro | 2026-08-14
Yannett Yeomans | 2026-04-28 | PO08856 | SO19209 | 2026-07-13 | XS500-710 | Horizontal Split Case Pump 24/20, 420SS | 2 | Super Cast Limited | México | 2026-08-31
Yannett Yeomans | 2026-04-28 | PO08856 | SO19209 | 2026-07-13 | 10364/2001 | Set of Coupling and Coupling Guard XS500-710, Cast Iron | 2 | Super Cast Limited | México | 2026-08-31
Yannett Yeomans | 2026-04-28 | PO08856 | SO19209 | 2026-07-13 | 10365/1501 | Common base XS500-710, Carbon Steel | 2 | Super Cast Limited | México | 2026-08-31
Ian Trottier | 2026-04-29 | PO08858 | SO19093 | 2026-06-19 | G-0D02490A03 1220 | Impeller, 8x10-13, 3196 XLT, Titanium, 5-Vane | 1 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-07-03
Emilka Guerra | 2026-04-29 | PO08859 | Stock | 2026-06-10 | D-2001434-CD4 | Bowl (Top),10JKH/M, w/"O" Ring, CD4MCu | 3 | Jiangsu Win-win International Trading Co., Ltd. | Dynapro | 2026-08-19
Emilka Guerra | 2026-04-29 | PO08861 | SO19156 | 2026-05-28 | W-F6036TL1HS1/R55 | Frame Plate Liner (Hi-Seal), 8/6 E-AH, Natural Rubber | 1 | Super Cast Limited | Dynapro | 2026-08-06
Ian Trottier | 2026-04-29 | PO08862 | SO19199 | 2026-06-19 | DU-CY21853A-CD4 | Casing, 3x1.5-13, Durco Mark 2&3 Group 2, CD4MCu , #300 Flat Face Flanges | 2 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-09-04
Ian Trottier | 2026-04-29 | PO08863 | SO19184 | 2026-07-07 | AC-98-330-289-503 | Impeller (Open), 5x5-14 SRL, Neoprene | 2 | IGH | Dynapro | 2026-07-21
Ian Trottier | 2026-04-30 | PO08864 | SO19125 | 2026-06-04 | G-73705X 1605 | Shaft Sleeve, 3196 MTX, Alloy 254 SMO | 1 | Hisco Pump Inc. | Dynapro | 2026-06-04
Emilka Guerra | 2026-04-30 | PO08866 | SO19221 | 2026-07-23 | SA-572855 | Impeller, Sala, STGVA-65W, High Chrome | 1 | Dexhor | Dynapro | 2026-08-13
Ian Trottier | 2026-04-30 | PO08867 | SO19147 | 2026-06-19 | AC-98-231-054-503 | Suction Side Liner, 2x2-10 SRL, Neoprene | 4 | Super Cast Limited | Dynapro | 2026-08-21
Ian Trottier | 2026-04-30 | PO08868 | Stock | 2026-06-19 | AC-98-330-289-503 | Impeller (Open), 5x5-14 SRL, Neoprene | 1 | Super Cast Limited | Dynapro | 2026-08-21
Ian Trottier | 2026-04-30 | PO08869 | SO19232 | 2026-07-23 | G-D09563A 1203 | Impeller, 12x14-22, 3175-L, 316SS, 4-Vane | 1 | M&N Alloy Cast Products, Inc. | Dynapro | 2026-07-24
Emilka Guerra | 2026-05-04 | PO08870 | SO18007 | 2026-06-30 | AC-98-5414-HC5 | Stuffing Box, 5x4-14 SRL-C, Cast Iron, 3-Piece Design | 2 | IGH | Dynapro | 2026-07-21
Emilka Guerra | 2026-05-04 | PO08872 | Stock - SO19434 | 2026-06-01 | OLPWZ011009B, G-A04951A222 | Bearing Isolator (Inboard), 3196 XLT/XLTi, 303SS Rotor / Bronze Stator w/Viton | 8 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-08-10
Emilka Guerra | 2026-05-04 | PO08872 | Stock - SO19434 | 2026-06-01 | G-70782 28 5117 | Casing Gasket, 13", 3196 MTX, Teflon | 30 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-08-10
Emilka Guerra | 2026-05-04 | PO08873 | Stock | 2026-05-18 | AC-52-108-475-013 | Deflector (Outboard), Allis-Chalmers PWO, Group 2 | 5 | Advanced Engineered Pump Inc. | Dynapro | 2026-06-01
Emilka Guerra | 2026-05-04 | PO08873 | Stock | 2026-05-18 | AC-52-050-313-000 | Shim Kit, Allis Chalmers CSO, Frame F4D1/F4B5 | 6 | Advanced Engineered Pump Inc. | Dynapro | 2026-06-01
Emilka Guerra | 2026-05-04 | PO08874 | SO19250 & Stock | 2026-07-15 | AC-98-037-796-503 | Impeller (Open), 6x6-15 SRL, Neoprene | 2 | IGH | Dynapro | 2026-08-05 | 2026-05-13
Emilka Guerra | 2026-05-04 | PO08874 | SO19250 & Stock | 2026-07-15 | AC-98-530-586-001 | Pedestal, 8x6-18 & 10x8-21 SRL-C, Cast Iron | 1 | IGH | Dynapro | 2026-08-05
Yannett Yeomans | 2026-05-04 | PO08875 | SO19243 | 2026-06-05 | 150SV-SP | Vertical Sump Pump, 150SV-SP, High Chrome | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | México | 2026-06-03
Leriel Reyes | 2026-05-06 | PO08878 | Stock | 2026-06-27 | AC-98-234-036-801 | Overhead Motor Mount, 5x4/6x6, Cast Steel Plate, Steel Jacking Bolt | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-05
Leriel Reyes | 2026-05-06 | PO08878 | Stock | 2026-06-27 | AC-98-234-082-801 | Overhead Motor Mount, 3x3-10 SRL/SRL-C, Cast Steel Plate, Steel Bolt | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-05
Ian Trottier | 2026-05-06 | PO08879 | Reverse Engineer 6x6-14LS Project | 2026-08-05 | D-WE3J-12 | Stuffing Box Cover, Goulds JC, Frame 3J, 6x6-14LS, High Chrome, OEM# 050294GG0001228 | 1 | M&N Alloy Cast Products, Inc. | Dynapro | 2026-05-06
Ian Trottier | 2026-05-06 | PO08879 | Reverse Engineer 6x6-14LS Project | 2026-08-05 | D-3J6614-10 | Impeller, 6x6-14, Dynapro DC, Frame 3J, High Chrome, OEM# 056191G3101228 | 1 | M&N Alloy Cast Products, Inc. | Dynapro | 2026-05-07
Ian Trottier | 2026-05-06 | PO08879 | Reverse Engineer 6x6-14LS Project | 2026-08-05 | D-3J6614-2 | Casing, 6x6-14, Dynapro DC, Frame 3J, High Chrome, OEM# 056191G0701228 | 1 | M&N Alloy Cast Products, Inc. | Dynapro | 2026-05-07
Ian Trottier | 2026-05-06 | PO08880 | Reverse Engineer 6x6-14LS Project | 2026-06-05 | D-WE3J-18 | Gasket (Casing to Stuffing Box), Goulds JC, Frame 3J, 6x6-14LS, Neoprene | 1 | Hisco Pump Inc. | Dynapro | 2026-06-19
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | D-2J15214-2 | Casing, 1.5x2-14, Goulds JC, Frame 2J, High Chrome, OEM# 055892G0001228 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | D-1J11511-2 | Casing, 1x1.5-11, Goulds JC, Frame 1J, High Chrome, OEM# 056185G5101228 | 8 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | D-1J2311-2 | Casing, 2x3-11, Goulds JC, Frame 1J, High Chrome, OEM# 055891G0001228 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | D-2J3411-2 | Casing, 3x4-11, Goulds JC, Frame 2J, High Chrome, OEM# 056185G4001228 | 7 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | D-3J3414-2 | Casing, 3x4-14, Goulds JC, Frame 3J, High Chrome, OEM# 056190G7801228 | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | G-056185G180 1228 | Casing, 4x6-14, Goulds JC, Frame 3J, High Chrome, OEM# 056185G1801228 | 7 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | D-1J11511-10 | Impeller, 1x1.5-11, Goulds JC, Frame 1J, High Chrome, OEM# 056185G4701228 | 6 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | D-2J3411-10 | Impeller, 3x4-11, Goulds JC, Frame 2J, High Chrome, OEM# 056185G4201228 | 6 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | D-3J3414-10 | Impeller, 3x4-14, Goulds JC, Frame 3J, High Chrome, OEM# 056190G7901228 | 5 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | D-3J4614-10 | Impeller, 4x6-14, Goulds JC, Frame 3J, High Chrome, OEM# 056185G1401228 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | D-WE3J-8 | Stuffing Box Cover, Goulds JC, Frame 3J, High Chrome, OEM# 048946G0001228 | 7 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | D-1J11511-6 | Suction Cover Liner, 1x1.5-11, Goulds JC, Frame 1J, High Chrome, OEM# 048935G0001228 | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | D-1J11511-14 | Suction Cover, 1x1.5-11, Goulds JC, Frame 1J, High Chrome, OEM# 050385G0001228 | 7 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | D-2J2314-14 | Suction Cover, 2x3-14, Goulds JC, Frame 2J, High Chrome, OEM# 050388G0001228 | 5 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | D-2J3411-14 | Suction Cover, 3x4-11, Goulds JC, Frame 2J, High Chrome, OEM# 048825G0001228 | 5 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | D-3J4614-14 | Suction Cover, 4x6-14, Goulds JC, Frame 3J, High Chrome, OEM# 048933G0001228 | 5 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | D-4J81018-2 | Casing, 8x10-18, Goulds JC, Frame 4J, High Chrome | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | D-PE2J-203 | End Cover (Inboard), Goulds JC, Frame 2J, Cast Iron | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | D-4J81018-10 | Impeller, 8x10-18, Goulds JC, Frame 4J, High Chrome, OEM #056185G8601228 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | D-PE3J-303 | End Cover (Inboard), Goulds JC, Frame 3J, Cast Iron | 5 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | D-4J81018-6 | Suction Cover Liner, 8x10-18, Goulds JC, Frame 4J, High Chrome | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | D-4J81018-14 | Suction Cover, 8x10-18, Goulds JC, Frame 4J, High Chrome, OEM # 050619G0001228 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | D-WE4J-8 | Stuffing Box Cover, 8x10-18, Goulds JC, Frame 4J, High Chrome | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | D-5J101222-10 | Impeller, 10x12-22, Goulds JC, Frame 5J, High Chrome, OEM # 056186G2801228 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | D-5J101222-6 | Suction Cover Liner, 10x12-22, Goulds JC, Frame 5J, High Chrome | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | D-5J101222-14 | Suction Cover, 10x12-22, Goulds JC, Frame 5J, High Chrome, OEM # 056090G4701228 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | D-WE5J-8 | Stuffing Box Cover, 10x12-22, Goulds JC, Frame 5J, High Chrome | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | D-1J11511-8 | Suction Cover Liner, 1x1.5-11, Goulds JC, Frame 1J, CD4MCu, OEM# 048935G0001247 | 10 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | D-WE3J-4 | Shaft Sleeve, Goulds JC Frame 3J, 420SS Heat Treated, Hardened | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | D-WE1J-1 | Lantern Ring, Goulds JC, Frame 1J, 304SS | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | D-WE2J-1 | Lantern Ring, Goulds JC, Frame 2J, 304SS | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | D-2x3-11-JC-HC | Pump, 2x3-11, Dynapro DC, Frame 1J, High Chrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | G-1.5x2-14-JC-HC | Pump, 1.5x2-14, Dynapro DC, Frame 2J, High Chrome | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | D-2x3-11-JC-HC | Pump, 2x3-11, Dynapro DC, Frame 1J, High Chrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | D-PE5J-500 | Power End, Goulds JC, Frame 5J, Grease-Lubed, SKF Bearings, 4140 Steel Shaft | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | D-1J2311-10 | Impeller, 2x3-11, Goulds JC, Frame 1J, High Chrome, OEM# 056189G2601228 | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | G-050619G000 1228 | Suction Cover, 8x10-18, Goulds JC Frame 4J, High Chrome | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | D-PE1J-103 | End Cover (Inboard), Goulds JC, Frame 1J, Cast Iron | 7 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | D-5J101222-2 | Casing, 10x12-22, Goulds JC, Frame 5J, High Chrome, OEM# 05686G4601228 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | D-WE3J-1 | Lantern Ring, Goulds JC, Frame 3J, 304SS | 6 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | D-PE4J-400 | Power End, Goulds JC, Frame 4J, Grease-Lubed, SKF Bearings, 4140 Steel Shaft | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | D1J2311-6 | Suction Cover Liner, 2x3-11, Goulds JC, Frame 1J, High Chrome, OEM# 048940G0001228 | 5 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | D-3J4614-6 | Suction Cover Liner, 4x6-14, Goulds JC, Frame 3J, High Chrome, OEM# 048944G0001228 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | D-1J2311-14 | Suction Cover, 2x3-11, Goulds JC, Frame 1J, High Chrome, OEM# 050387G0001228 | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | D-WE4J-4 | Shaft Sleeve, Goulds JC Frame 4J, 420SS Heat Treated, Hardened | 10 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Yannett Yeomans | 2026-05-06 | PO08881 | JS Stock 2nd order | 2026-07-24 | D-WE1J-4 | Shaft Sleeve, Goulds JC Frame 1J, 420SS Heat Treated, Hardened | 5 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-30
Ian Trottier | 2026-05-07 | PO08882 | SO19241 | 2026-06-26 | DU-MY36862A100-A20 | Impeller, 3x2-10, Durco Mark 2 Group 2, Alloy 20, Reverse Vane | 3 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-09-08 | 2026-05-13
Amanda Qiao | 2026-05-07 | PO08883 | SO18295 | 2026-07-14 | AC-98-530-757-001 | Suction Side Casing, 3x3-10 SRL-C HD, Carbon Steel | 1 | IGH | Dynapro | 2026-07-29
Ian Trottier | 2026-05-07 | PO08884 | SO18994 - SO18242 | 2026-07-13 | AC-52-430-274-501 | Frame, Allis-Chalmers CSO, F4D1, Cast Iron | 4 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-07-31
Ian Trottier | 2026-05-07 | PO08884 | SO18994 - SO18242 | 2026-07-13 | AC-52-319-380-001 | Frame Foot, Allis Chalmers CSO, Frame F4D1, fits 11" and 13" pumps, Cast Iron | 11 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-07-31
Emilka Guerra | 2026-05-08 | PO08886 | SO19248 | 2026-07-31 | WO-2104511-004 | Wear Plate, Worthington 6-FRBH-142, 317SS | 1 | M&N Alloy Cast Products, Inc. | Dynapro | 2026-08-21 | 2026-05-13
Emilka Guerra | 2026-05-08 | PO08887 | SO19275 | 2026-06-19 | W-SP25092/A05 | Casing, 250SV-SP, High Chrome | 1 | Super Cast Limited | Dynapro | 2026-08-07 | 2026-05-13
Emilka Guerra | 2026-05-11 | PO08888 | Stock | 2026-06-12 | W-E4110/A05 | Volute Liner, 6/4 D or E-AH, High Chrome | 2 | Super Cast Limited | Dynapro | 2026-08-21
Emilka Guerra | 2026-05-11 | PO08888 | Stock | 2026-06-12 | SA-138413-M1 | Casing, Sala 2", SPV, Rubber Lined | 4 | Super Cast Limited | Dynapro | 2026-08-21 | 2026-05-13
Emilka Guerra | 2026-05-11 | PO08888 | Stock | 2026-06-12 | SA-234602-M1 | Impeller, VT50, Natural Rubber | 3 | Super Cast Limited | Dynapro | 2026-08-21
Emilka Guerra | 2026-05-11 | PO08888 | Stock | 2026-06-12 | SA-138414-M1 | Inlet Door, Sala VT50, Natural Rubber | 3 | Super Cast Limited | Dynapro | 2026-08-21
Emilka Guerra | 2026-05-11 | PO08888 | Stock | 2026-06-12 | W-SP25092/A05 | Casing, 250SV-SP, High Chrome | 2 | Super Cast Limited | Dynapro | 2026-08-21
Emilka Guerra | 2026-05-11 | PO08888 | Stock | 2026-06-12 | W-SP25041/A05 | Back Liner, 250SV-SP, High Chrome | 1 | Super Cast Limited | Dynapro | 2026-08-21
Emilka Guerra | 2026-05-11 | PO08888 | Stock | 2026-06-12 | W-F8147/R55 | Impeller, 10/8 E-M, Natural Rubber | 5 | Super Cast Limited | Dynapro | 2026-08-21 | 2026-05-13
Emilka Guerra | 2026-05-11 | PO08888 | Stock | 2026-06-12 | SA-016628-M1 | Casing, 44 WFR, Sala ST, Rubber Lined | 50 | Super Cast Limited | Dynapro | 2026-08-21 | 2026-05-13
Emilka Guerra | 2026-05-11 | PO08889 | Stock | 2026-07-22 | AC-98-234-113-801 | Bearing Housing, 2x2-10-SRL, Cast Iron | 1 | IGH | Dynapro | 2026-08-12
Emilka Guerra | 2026-05-11 | PO08889 | Stock | 2026-07-22 | AC-98-431-857-501 | Gland Side Casing, 3x3-10 SRL-C, Cast Iron | 1 | IGH | Dynapro | 2026-08-12
Emilka Guerra | 2026-05-11 | PO08889 | Stock | 2026-07-22 | AC-98-431-766-501 | Gland Side Casing, 8x6-18 SRL-C, Cast Iron | 1 | IGH | Dynapro | 2026-08-12
Emilka Guerra | 2026-05-11 | PO08889 | Stock | 2026-07-22 | AC-98-431-775-001 | Suction Side Casing, 8x6-18 SRL-C, Cast Iron | 1 | IGH | Dynapro | 2026-08-12
Emilka Guerra | 2026-05-11 | PO08889 | Stock | 2026-07-22 | AC-98-432-037-001 | Bearing Cylinder Strap (Set of 2), 8x6/10x8 SRL-C, Cast Iron | 3 | IGH | Dynapro | 2026-08-12
Emilka Guerra | 2026-05-11 | PO08889 | Stock | 2026-07-22 | AC-98-037-796-503 | Impeller (Open), 6x6-15 SRL, Neoprene | 2 | IGH | Dynapro | 2026-08-12
Emilka Guerra | 2026-05-11 | PO08889 | Stock | 2026-07-22 | AC-98-231-084-503 | Gland Side Liner, 6x6-15 SRL, Neoprene | 1 | IGH | Dynapro | 2026-08-12
Emilka Guerra | 2026-05-11 | PO08891 | Stock | 2026-06-24 | T-034, G-C02495A34 6359 | Impeller O-Ring, 3196 XLT, Teflon | 10 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-09-02
Emilka Guerra | 2026-05-11 | PO08891 | Stock | 2026-06-24 | G-0B10588 1216 | Impeller, 2x3-13, 3196 LTX, CD4MCu, 5-Vane | 2 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-09-02
Emilka Guerra | 2026-05-11 | PO08891 | Stock | 2026-06-24 | AC-98-431-577-501 | Frame, 14", Allis Chalmers PWO, Frame A1, Oil-Lubed, Cast Iron | 1 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-09-02
Emilka Guerra | 2026-05-11 | PO08892 | Stock | 2026-06-24 | AC-98-233-998-801 | Bearing Cover (Inboard), 3x3-10 SRL & SRL-C | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-02 | 2026-03-30
Emilka Guerra | 2026-05-11 | PO08892 | Stock | 2026-06-24 | AC-98-234-000-801 | Bearing Cover (Outboard), 3x3-10 SRL & SRL-C, Cast Iron | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-02
Emilka Guerra | 2026-05-11 | PO08892 | Stock | 2026-06-24 | AC-98-332-173-001 | Bearing Cylinder Strap, 3x3-10 SRL-C | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-02
Emilka Guerra | 2026-05-11 | PO08892 | Stock | 2026-06-24 | AC-98-331-910-801 | Bearing Cylinder, 8x6-18 & 10x8-21 SRL-C, Cast Iron | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-02 | 2026-05-13
Emilka Guerra | 2026-05-11 | PO08893 | SO19267 | 2026-05-18 | AC-52-231-827-009 | Shaft (Sleeve Type), Allis-Chalmers CSO, Frame F4D1, 4140 Steel | 1 | Hisco Pump Inc. | Dynapro | 2026-06-01
Ian Trottier | 2026-05-11 | PO08894 | SO19264 | 2026-05-26 | DU-BY50424B-TSSR | Oil Seal (Outboard), Durco Mark 2&3 Group 1, Teflon/Stainless Steel/Rubber | 3 | Hisco Pump Inc. | Dynapro | 2026-06-05
Ian Trottier | 2026-05-11 | PO08894 | SO19264 | 2026-05-26 | DU-BY50424G-TSSR | Oil Seal (Inboard), Durco Mark 3 Group 1, Teflon/Stainless Steel/Rubber | 5 | Hisco Pump Inc. | Dynapro | 2026-06-05
Ian Trottier | 2026-05-11 | PO08895 | SO19214 | 2026-06-29 | GA-21630 | Impeller, G-Series 2.5" VSP, 1000 Series, Cast Iron | 1 | IGH | Dynapro | 2026-06-30
Ian Trottier | 2026-05-12 | PO08896 | SO19292 | 2026-06-10 | DU-CY21805A/CBS-DC20 | Rear Cover, 10", Durco Mark 2&3 Group 2, Alloy 20, Small Bore | 2 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-06-22 | 2026-07-17
Emilka Guerra | 2026-05-12 | PO08897 | SO19060 | 2026-05-29 | W-M12Z3-135Z | Frame Plate Liner Stud, 8/6 AH | 10 | Super Cast Limited | Dynapro | 2026-08-04 | 2026-04-19
Emilka Guerra | 2026-05-13 | PO08900 | SO19300 & Stock | 2026-06-03 | DU-BY50424D-TSSR | Oil Seal (Inboard), Durco Mark 3 Group 2, Teflon/Stainless Steel/Rubber | 2 | Hisco Pump Inc. | Dynapro | 2026-06-24
Emilka Guerra | 2026-05-14 | PO08905 | SO19271 | 2026-06-11 | AC-52-231-716-001 | Shaft, Allis-Chalmers CSO, Frame F4C1, 4140 Steel | 1 | Hisco Pump Inc. | Dynapro | 2026-07-02 | 2026-07-17
Emilka Guerra | 2026-05-14 | PO08907 | SO19301 | 2026-06-02 | P398 | Baseplate, PoxyBase Plus Black Polymer Base, Size 398 | 1 | BaseTek, LLC | Dynapro | 2026-06-16
Emilka Guerra | 2026-05-14 | PO08907 | SO19301 | 2026-06-02 | MBK400350-S625 | PoxyBlock Motor Mounting Blocks, ANSI: A90, A100, A110, A120, 14.50" Centerline | 1 | BaseTek, LLC | Dynapro | 2026-06-16 | 2026-07-06
Emilka Guerra | 2026-05-15 | PO08910 | SO19279 | 2026-06-15 | G-090407-4 1203 | Impeller w/Balance Holes, 2x3-10, 3196 MTX, 316SS, 5-Vane | 1 | Hisco Pump Inc. | Dynapro | 2026-06-30
Emilka Guerra | 2026-05-15 | PO08910 | SO19279 | 2026-06-15 | G-090407-4-1013 | Impeller w/Balance Holes, 2x3-10, 3196 MTX, Ductile Iron, 5-Vane | 1 | Hisco Pump Inc. | Dynapro | 2026-06-30
Carlos Leon | 2026-05-15 | PO08911 | SO19322 | 2026-07-03 | W-T076/C21 | Shaft Sleeve Long, 20/18 TU-AH or 550/650 Type L, 420SS | 1 | Super Cast Limited | Dynapro | 2026-09-11
Carlos Leon | 2026-05-15 | PO08911 | SO19322 | 2026-07-03 | W-UL55018M/R55 | Cover Plate Liner, 550 TU-L, Natural Rubber | 1 | Super Cast Limited | Dynapro | 2026-09-11
Carlos Leon | 2026-05-15 | PO08911 | SO19322 | 2026-07-03 | W-U55041M/R55 | Frame Plate Liner Insert, 550 TU-L, Natural Rubber | 1 | Super Cast Limited | Dynapro | 2026-09-11
Carlos Leon | 2026-05-15 | PO08911 | SO19322 | 2026-07-03 | W-UL55083M/R55 | Throat Bushing, 550 TU-L, Natural Rubber | 1 | Super Cast Limited | Dynapro | 2026-09-11 | 2026-05-13
Carlos Leon | 2026-05-15 | PO08911 | SO19322 | 2026-07-03 | W-UL55043M/R55 | Frame Plate Liner, 550 TU-L, Natural Rubber | 1 | Super Cast Limited | Dynapro | 2026-09-11 | 2026-04-10
Emilka Guerra | 2026-05-15 | PO08912 | SO19326 | 2026-06-12 | 10009/0512 | Shaft, 150FY-40, 316LSS | 1 | Jiangsu Win-win International Trading Co., Ltd. | México | 2026-08-28
Ian Trottier | 2026-05-15 | PO08913 | SO19322 | 2026-07-22 | W-TUL55147DP1/A05 | Impeller, 5 VCG, Duty Point, No Back Vanes, 550 TU-L, High Chrome | 1 | Shijiazhuang Mets Machinery Co., LTD | Dynapro | 2026-09-30
Emilka Guerra | 2026-05-18 | PO08914 | SO19327 | 2026-08-10 | G-243-90 1203 | Impeller, 6x8-13, 3171-L, 316SS | 1 | M&N Alloy Cast Products, Inc. | México | 2026-08-24
Emilka Guerra | 2026-05-18 | PO08915 | SO19329 | 2026-06-29 | SZ-2837900133-1 | Shaft, Sulzer | 5 | Super Cast Limited | México | 2026-09-07
Emilka Guerra | 2026-05-18 | PO08915 | SO19329 | 2026-06-29 | SZ-9321480153 | Bearing Housing, Sulzer | 2 | Super Cast Limited | México | 2026-09-07
Emilka Guerra | 2026-05-18 | PO08915 | SO19329 | 2026-06-29 | SZ-EL1208506M | Deflector, Sulzer | 20 | Super Cast Limited | México | 2026-09-07
Emilka Guerra | 2026-05-18 | PO08915 | SO19329 | 2026-06-29 | SZ-9268290131 | Labyrinth Ring, Sulzer | 10 | Super Cast Limited | México | 2026-09-07
Emilka Guerra | 2026-05-18 | PO08916 | SO19331 | 2026-07-06 | DC-MS000021 | Mechanical Seal, Dynapro Vertical Turbine, 12RJHC-8, A20 | 10 | Jiangsu Win-win International Trading Co., Ltd. | México | 2026-09-07
Emilka Guerra | 2026-05-18 | PO08916 | SO19331 | 2026-07-06 | 10061/0505 | Impeller Shaft, 18BHC-1, 316SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | México | 2026-09-07
Emilka Guerra | 2026-05-18 | PO08916 | SO19331 | 2026-07-06 | 10062/0505 | Impeller Collect, 18BHC-1, 316SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | México | 2026-09-07
Emilka Guerra | 2026-05-18 | PO08916 | SO19331 | 2026-07-06 | 10009/0512 | Shaft, 150FY-40, 316LSS | 2 | Jiangsu Win-win International Trading Co., Ltd. | México | 2026-09-07
Ian Trottier | 2026-05-19 | PO08917 |  | 2026-07-06 | AC-98-211-426-503 | Impeller, 2x2-10 SRL, Neoprene | 1 | Super Cast Limited | Dynapro | 2026-09-28
Ian Trottier | 2026-05-19 | PO08917 |  | 2026-07-06 | AC-98-231-055-503 | Gland Side Liner, 2x2-10 SRL, Neoprene | 1 | Super Cast Limited | Dynapro | 2026-09-28
Emilka Guerra | 2026-05-20 | PO08918 | SO19288 | 2026-06-24 | W-G10018M/R55 | Cover Plate Liner, 12/10 F or ST-AH, Natural Rubber | 1 | Super Cast Limited | Dynapro | 2026-09-09
Emilka Guerra | 2026-05-20 | PO08918 | SO19288 | 2026-06-24 | W-G10036M/R55 | Frame Plate Liner, 12/10 ST-AH, Natural Rubber | 1 | Super Cast Limited | Dynapro | 2026-09-09
Ian Trottier | 2026-05-20 | PO08919 | SO19342 | 2026-06-01 | W-T044/C02 | Gland Split w/Bolt & Nut, 20/18 TU-AH, Ni-Resist | 2 | Super Cast Limited | Dynapro | 2026-08-24
Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10671/0504 | Cartridge Mechanical Seal, 16DMC-4, 304SS | 2 | Jiangsu Win-win International Trading Co., Ltd. | México | 2026-09-01
Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10672/0526 | Coupling, 16DMC-4, 416SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | México | 2026-09-01 | 2026-05-13
Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10673/2001 | Adjusting Nut, 16DMC-4, Cast Iron | 1 | Jiangsu Win-win International Trading Co., Ltd. | México | 2026-09-01
Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10674/0526 | Motor Shaft, 16DMC-4, 416SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | México | 2026-09-01
Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10675/0504 | Stuffing Box Hex Bolts and Spring Washers, 16DMC-4, 304SS | 6 | Jiangsu Win-win International Trading Co., Ltd. | México | 2026-09-01 | 2026-05-01
Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10676/0504 | Stuffing Box Bearing Retaining Ring, 16DMC-4, 304SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | México | 2026-09-01 | 2026-04-19
Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10677/5001 | Stuffing Box Bearing,16DMC-4, Teflon | 1 | Jiangsu Win-win International Trading Co., Ltd. | México | 2026-09-01
Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10680/0504 | Discharge Head Hex Bolts and Spring Washers, 16DMC-4, 304SS | 12 | Jiangsu Win-win International Trading Co., Ltd. | México | 2026-09-01
Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10681/5010 | Inlet Flange Paper Gasket, 16DMC-4, - | 1 | Jiangsu Win-win International Trading Co., Ltd. | México | 2026-09-01
Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10683/0526 | Lineshaft, 16DMC-4, 416SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | México | 2026-09-01
Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10684/0504 | Spider Bearing Retaining Ring, 16DMC-4, 304SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | México | 2026-09-01
Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10685/5001 | Spider Bearing, 16DMC-4, Teflon | 1 | Jiangsu Win-win International Trading Co., Ltd. | México | 2026-09-01
Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10687/0526 | Coupling, 16DMC-4, 416SS | 2 | Jiangsu Win-win International Trading Co., Ltd. | México | 2026-09-01
Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10688/0526 | Lower Lineshaft, 16DMC-4, 416SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | México | 2026-09-01
Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10690/0504 | Discharge Bowl Hex Bolts, Spring Washers and Nuts, 16DMC-4, 304SS | 8 | Jiangsu Win-win International Trading Co., Ltd. | México | 2026-09-01
Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10691/0504 | Intermediate Bowl Hex Bolts and Spring Washers, 16DMC-4, 304SS | 32 | Jiangsu Win-win International Trading Co., Ltd. | México | 2026-09-01
Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10692/0526 | Impeller Shaft, 16DMC-4, 416SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | México | 2026-09-01
Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10693/0504 | Discharge Bowl Bearing Retaining Ring, 16DMC-4, 304SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | México | 2026-09-01
Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10694/5001 | Discharge Bowl Bearing, 16DMC-4, Teflon | 1 | Jiangsu Win-win International Trading Co., Ltd. | México | 2026-09-01
Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10696/0504 | Impeller Collect Hex Bolts and Spring Washers, 16DMC-4, 304SS | 16 | Jiangsu Win-win International Trading Co., Ltd. | México | 2026-09-01
Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10697/0505 | Impeller Collect, 16DMC-4, 316SS | 4 | Jiangsu Win-win International Trading Co., Ltd. | México | 2026-09-01
Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10698/0505 | Impeller, 16DMC-4, 316SS | 4 | Jiangsu Win-win International Trading Co., Ltd. | México | 2026-09-01
Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10699/0504 | Intermediate Bowl Bearing Retaining Ring, 16DMC-4, 304SS | 3 | Jiangsu Win-win International Trading Co., Ltd. | México | 2026-09-01
Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10700/5001 | Intermediate Bowl Bearing, 16DMC-4, Teflon | 3 | Jiangsu Win-win International Trading Co., Ltd. | México | 2026-09-01
Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10702/3002 | Sand Collar, 16DMC-4, Bronze | 1 | Jiangsu Win-win International Trading Co., Ltd. | México | 2026-09-01
Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10703/0504 | Suction Bell Hex Bolts and Spring Washers, 16DMC-4, 304SS | 6 | Jiangsu Win-win International Trading Co., Ltd. | México | 2026-09-01
Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10704/0504 | Suction Bell Bearing Retaining Ring, 16DMC-4, 304SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | México | 2026-09-01
Yannett Yeomans | 2026-05-21 | PO08920 | SO19348 | 2026-07-06 | 10705/5001 | Suction Bowl Bearing, 16DMC-4, Teflon | 1 | Jiangsu Win-win International Trading Co., Ltd. | México | 2026-09-01
Ian Trottier | 2026-05-21 | PO08921 | SO19347 | 2026-07-02 | AC-98-432-882-504 | Shaft, PWO, Frame 2, 317SS | 1 | Mid-Canada Manufacturing | Dynapro | 2026-05-22 | 2026-03-06
Ian Trottier | 2026-05-21 | PO08921 | SO19347 | 2026-07-02 | AC-98-130-366-012 | Shaft Sleeve, PWO Frame 1, 317SS | 1 | Mid-Canada Manufacturing | Dynapro | 2026-05-22 | 2026-05-13
Emilka Guerra | 2026-05-21 | PO08922 | SO19345 | 2026-08-13 | SA-572855 | Impeller, Sala, STGVA-65W, High Chrome | 2 | Dexhor | Dynapro | 2026-08-27
Emilka Guerra | 2026-05-21 | PO08923 | Stock | 2026-07-03 | AC-98-330-286-501 | Impeller (Open), 3x3-10 SRL, Natural Rubber | 12 | Super Cast Limited | Dynapro | 2026-09-11
Emilka Guerra | 2026-05-21 | PO08923 | Stock | 2026-07-03 | AC-98-231-071-501 | Suction Side Liner, 3x3-10 SRL, Natural Rubber | 6 | Super Cast Limited | Dynapro | 2026-09-11
Emilka Guerra | 2026-05-21 | PO08923 | Stock | 2026-07-03 | AC-98-231-070-501 | Gland Side Liner, 3x3-10 SRL, Natural Rubber | 3 | Super Cast Limited | Dynapro | 2026-09-11
Emilka Guerra | 2026-05-21 | PO08923 | Stock | 2026-07-03 | M16x55, W-E045M/C23 | Gland Bolt w/Nut & Washer, 6/4 or 8/6 E-AH and 8/6 R-AH, 316SS | 11 | Super Cast Limited | Dynapro | 2026-09-11
Emilka Guerra | 2026-05-21 | PO08923 | Stock | 2026-07-03 | AC-98-234-265-001 | Waterseal Bushing, 8x6-18 & 10x8-21 SRL-C, 316SS | 5 | Super Cast Limited | Dynapro | 2026-09-11
Emilka Guerra | 2026-05-21 | PO08923 | Stock | 2026-07-03 | AC-98-431-651-501 | Impeller (Closed), 8x6-18 SRL-C, Natural Rubber | 6 | Super Cast Limited | Dynapro | 2026-09-11
Emilka Guerra | 2026-05-21 | PO08923 | Stock | 2026-07-03 | AC-98-331-926-801 | Bearing Cover (Outboard), 5x4/5x5/6x6 SRL & SRL-C, Cast Iron | 2 | Super Cast Limited | Dynapro | 2026-09-11
Emilka Guerra | 2026-05-21 | PO08923 | Stock | 2026-07-03 | AC-98-231-134-501 | Suction Side Liner, 10x8-21 SRL-C, Natural Rubber | 6 | Super Cast Limited | Dynapro | 2026-09-11
Emilka Guerra | 2026-05-21 | PO08923 | Stock | 2026-07-03 | SA-013733-M1 | Wear Disc, 44 WFR, Sala STGVA-180, Steel, Rubber Lined | 70 | Super Cast Limited | Dynapro | 2026-09-11
Emilka Guerra | 2026-05-21 | PO08923 | Stock | 2026-07-03 | W-SL30083M/A05 | Throatbush, 300 RSL, High Chrome | 2 | Super Cast Limited | Dynapro | 2026-09-11
Emilka Guerra | 2026-05-21 | PO08923 | Stock | 2026-07-03 | W-SP10116L/D21 | Lower Strainer, 100RV-SP, Ductile Iron | 1 | Super Cast Limited | Dynapro | 2026-09-11
Emilka Guerra | 2026-05-21 | PO08924 | Stock | 2026-07-10 | G-R102-814 1013 | Frame Adapter, 15", 3196 XLT, Ductile Iron | 2 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-09-18
Emilka Guerra | 2026-05-21 | PO08924 | Stock | 2026-07-10 | RC04064A01 1216 | Stuffing Box Cover, 15", 3196 XLT, CD4MCu, Big Bore, Non-Jacketed | 1 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-09-18
Emilka Guerra | 2026-05-21 | PO08924 | Stock | 2026-07-10 | G-0256-122 1216 | Impeller, 8x10-15G, 3196 XLT, CD4MCu | 1 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-09-18 | 2026-06-26
Emilka Guerra | 2026-05-21 | PO08924 | Stock | 2026-07-10 | G-256-65 1216 | Casing, 8x10-15G, 3196 XLT, CD4MCu | 1 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-09-18
Emilka Guerra | 2026-05-21 | PO08924 | Stock | 2026-07-10 | G-102-913 1001 | Frame Foot, 3196 XLT, Cast Iron | 1 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-09-18 | 2026-03-06
Emilka Guerra | 2026-05-21 | PO08924 | Stock | 2026-07-10 | DU-MY36862A100-CD4 | Impeller, 3x2-10, Durco Mark 2 Group 2, CD4MCu, Reverse Vane | 1 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-09-18 | 2026-05-13
Emilka Guerra | 2026-05-21 | PO08924 | Stock | 2026-07-10 | DU-DY33074A-CD4 | Casing, 6x4-13A, Durco Mark 2&3 Group 2, CD4MCu | 1 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-09-18 | 2026-07-17
Emilka Guerra | 2026-05-21 | PO08925 | Stock | 2026-07-03 | AC-98-431-849-001 | Suction Side Casing, 3x3-10 SRL, Cast Iron | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-11 | 2026-05-13
Emilka Guerra | 2026-05-21 | PO08925 | Stock | 2026-07-03 | W-SP10041/A05 | Back Liner, 100RV-SP, High Chrome | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-11
Emilka Guerra | 2026-05-21 | PO08926 | Stock | 2026-08-14 | AC-98-431-676-501 | Gland Side Casing, 10x8-21 SRL-C, Cast Iron | 1 | IGH | Dynapro | 2026-09-11 | 2026-05-01
Emilka Guerra | 2026-05-21 | PO08927 | Stock | 2026-05-29 | G-73078 5130 | Frame Adapter Gasket, 3196 MTX, LTX, & XLT Vellumoid | 6 | Hisco Pump Inc. | Dynapro | 2026-06-12
Emilka Guerra | 2026-05-21 | PO08927 | Stock | 2026-05-29 | GO351-9607-NSN, G-70782 49 5127 | Casing Gasket, 15", 3196 XLT | 5 | Hisco Pump Inc. | Dynapro | 2026-06-12
Ian Trottier | 2026-05-22 | PO08928 | SO19350 | 2026-06-03 | AH-283794-0133 | Shaft, Ahlstrom APT, Frame 4, 17-4 PH | 1 | Hisco Pump Inc. | Dynapro | 2026-06-10
Amanda Qiao | 2026-05-22 | PO08929 | SO19068 | 2026-07-22 |  | Mag Drive Gear Pump, Micropump GLH-H25, With Motor | 2 | Vissers Sales Corp. | Dynapro | 2026-07-24
Emilka Guerra | 2026-05-25 | PO08930 | SO19332 | 2026-06-08 | G-B02188A04 6308 | Lantern Ring, 3180 XL, Teflon | 1 | Hisco Pump Inc. | Dynapro | 2026-06-29
Emilka Guerra | 2026-05-25 | PO08930 | SO19332 | 2026-06-08 | G-C03241A 1226 | Shaft Sleeve, 3180-XL, 316SS, Packed Box | 1 | Hisco Pump Inc. | Dynapro | 2026-06-29
Emilka Guerra | 2026-05-25 | PO08930 | SO19332 | 2026-06-08 | 383 Viton | Suction Side Plate O-Ring, 3180-XL, Viton | 1 | Hisco Pump Inc. | Dynapro | 2026-06-29
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-1J2311-1 | Casing, 2x3-11, Goulds JC, Frame 1J, Cast Iron, OEM# 055891G0001002 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-1J2311-4 | Casing, 2x3-11, Goulds JC, Frame 1J, CD4MCu, OEM# 055891G0001247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10 | 2026-04-20
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-1J2311-5 | Suction Cover Liner, 2x3-11, Goulds JC, Frame 1J, Cast Iron, OEM# 048940G0001002 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10 | 2026-07-17
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D1J2311-6 | Suction Cover Liner, 2x3-11, Goulds JC, Frame 1J, High Chrome, OEM# 048940G0001228 | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10 | 2026-07-17
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-1J2311-8 | Suction Cover Liner, 2x3-11, Goulds JC, Frame 1J, CD4MCu, OEM# 048940G0001247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-1J2311-9 | Impeller, 2x3-11, Goulds JC, Frame 1J, Cast Iron, OEM# 056189G2601002 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-1J2311-10 | Impeller, 2x3-11, Goulds JC, Frame 1J, High Chrome, OEM# 056189G2601228 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10 | PO08639 | G-0C01359A 1203 | Flush Gland Assembly, 3196 MTX, Big Bore, 316SS | 2
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-1J2311-12 | Impeller, 2x3-11, Goulds JC, Frame 1J, CD4MCu, OEM# 056189G2601247 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-1J2311-13 | Suction Cover, 2x3-11, Goulds JC, Frame 1J, Cast Iron, OEM# 050387G0001002 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10 | 2026-06-25
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-1J2311-14 | Suction Cover, 2x3-11, Goulds JC, Frame 1J, High Chrome, OEM# 050387G0001228 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-1J2311-16 | Suction Cover, 2x3-11, Goulds JC, Frame 1J, CD4MCu, OEM# 050387G0001247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-1J11511-6 | Suction Cover Liner, 1x1.5-11, Goulds JC, Frame 1J, High Chrome, OEM# 048935G0001228 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-1J11511-10 | Impeller, 1x1.5-11, Goulds JC, Frame 1J, High Chrome, OEM# 056185G4701228 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-1J11511-14 | Suction Cover, 1x1.5-11, Goulds JC, Frame 1J, High Chrome, OEM# 050385G0001228 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-WE1J-7 | Stuffing Box Cover, Goulds JC, Frame 1J, Cast Iron, OEM# 048945G0001002 | 6 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-WE1J-8 | Stuffing Box Cover, Goulds JC, Frame 1J, High Chrome, OEM# 048945G0001228 | 6 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10 | 2026-10-06
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-WE1J-10 | Stuffing Box Cover, Goulds JC, Frame 1J, CD4MCu, OEM# 048945G0001247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J15214-4 | Casing, 1.5x2-14, Goulds JC, Frame 2J, CD4MCu, OEM# 055892G0001247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J15214-5 | Suction Cover Liner, 1.5x2-14, Goulds JC Frame 2J, Cast Iron, OEM# 048938G0001002 | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J15214-6 | Suction Cover Liner, 1.5x2-14, Goulds JC Frame 2J, High Chrome, OEM# 048938G0001228 | 9 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J15214-8 | Suction Cover Liner, 1.5x2-14, Goulds JC Frame 2J, CD4MCu, OEM# 048938G0001247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J15214-9 | Impeller, 1.5x2-14, Goulds JC, Frame 2J, Cast Iron, OEM# 056189G2501002 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J15214-10 | Impeller, 1.5x2-14, Goulds JC, Frame 2J, High Chrome, OEM# 056189G2501228 | 6 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J15214-13 | Suction Cover, 1.5x2-14, Goulds JC Frame 2J, Cast Iron, OEM# 050049G0001002 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J15214-14 | Suction Cover, 1.5x2-14, Goulds JC Frame 2J, High Chrome, OEM# 050049G0001228 | 9 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J15214-16 | Suction Cover, 1.5x2-14, Goulds JC Frame 2J, CD4MCu, OEM# 050049G0001247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J2314-4 | Casing, 2x3-14, Goulds JC, Frame 2J, CD4MCu, OEM# 056190G6601247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J2314-5 | Suction Cover Liner, 2x3-14, Goulds JC, Frame 2J, Cast Iron, OEM# 048941G0001002 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J2314-6 | Suction Cover Liner, 2x3-14, Goulds JC, Frame 2J, High Chrome, OEM# 048941G0001228 | 14 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J2314-8 | Suction Cover Liner, 2x3-14, Goulds JC, Frame 2J, CD4MCu, OEM# 048941G0001247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J2314-9 | Impeller, 2x3-14, Goulds JC, Frame 2J, Cast Iron, OEM# 056189G6701002 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J2314-10 | Impeller, 2x3-14, Goulds JC, Frame 2J, High Chrome, OEM# 056189G6701228 | 7 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J2314-13 | Suction Cover, 2x3-14, Goulds JC, Frame 2J, Cast Iron, OEM# 050388G0001002 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J2314-14 | Suction Cover, 2x3-14, Goulds JC, Frame 2J, High Chrome, OEM# 050388G0001228 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J3411-1 | Casing, 3x4-11, Goulds JC, Frame 2J, Cast Iron, OEM#056185G4011002 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10 | 2026-05-13
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J3411-6 | Suction Cover Liner, 3x4-11, Goulds JC, Frame 2J, High Chrome, OEM# 048824G0001228 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J3411-12 | Impeller, 3x4-11, Goulds JC, Frame 2J, CD4MCu, OEM# 056185G4201247 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J3411-14 | Suction Cover, 3x4-11, Goulds JC, Frame 2J, High Chrome, OEM# 048825G0001228 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-WE2J-7 | Stuffing Box Cover, Goulds JC, Frame 2J, Cast Iron, OEM# 048877G0001002 | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-WE2J-8 | Stuffing Box Cover, Goulds JC, Frame 2J, High Chrome, OEM# 048877G0001228 | 8 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-WE2J-10 | Stuffing Box Cover, Goulds JC, Frame 2J, CD4MCu, OEM# 048877G0001247 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J4614-1 | Casing, 4x6-14, Goulds JC, Frame 3J, Cast Iron, OEM# 056185G1801002 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J4614-4 | Casing, 4x6-14, Goulds JC, Frame 3J, CD4MCu, OEM# 056185G1801247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10 | 2026-05-28
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J4614-5 | Suction Cover Liner, 4x6-14, Goulds JC, Frame 3J, Cast Iron, OEM# 048944G0001002 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10 | 2026-05-13
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J4614-6 | Suction Cover Liner, 4x6-14, Goulds JC, Frame 3J, High Chrome, OEM# 048944G0001228 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10 | 2026-05-01
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J4614-10 | Impeller, 4x6-14, Goulds JC, Frame 3J, High Chrome, OEM# 056185G1401228 | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10 | 2026-05-28
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J4614-13 | Suction Cover, 4x6-14, Goulds JC, Frame 3J, Cast Iron, OEM# 048933G0001002 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J4614-14 | Suction Cover, 4x6-14, Goulds JC, Frame 3J, High Chrome, OEM# 048933G0001228 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J4614-16 | Suction Cover, 4x6-14, Goulds JC, Frame 3J, CD4MCu, OEM# 048933G0001247 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J3414-1 | Casing, 3x4-14, Goulds JC, Frame 3J, Cast Iron, OEM# 056190G7801002 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J3414-2 | Casing, 3x4-14, Goulds JC, Frame 3J, High Chrome, OEM# 056190G7801228 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J3414-4 | Casing, 3x4-14, Goulds JC, Frame 3J, CD4MCu, OEM# 056190G7801247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J3414-5 | Suction Cover Liner, 3x4-14, Goulds JC, Frame 3j, Cast Iron, OEM# 048943G0001002 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J3414-6 | Suction Cover Liner, 3x4-14, Goulds JC, Frame 3J, High Chrome, OEM# 048943G0001228 | 8 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J3414-8 | Suction Cover Liner, 3x4-14, Goulds JC, Frame 3J, CD4MCu, OEM# 048943G0001247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J3414-10 | Impeller, 3x4-14, Goulds JC, Frame 3J, High Chrome, OEM# 056190G7901228 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J3414-12 | Impeller, 3x4-14, Goulds JC, Frame 3J, CD4MCu, OEM# 056190G7901247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J3414-13 | Suction Cover, 3x4-14, Goulds JC, Frame 3J, Cast Iron, OEM# 048932G0001002 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10 | 2026-03-30
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J3414-14 | Suction Cover, 3x4-14, Goulds JC, Frame 3J, High Chrome, OEM# 048932G0001228 | 10 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J3414-16 | Suction Cover, 3x4-14, Goulds JC, Frame 3J, CD4MCu, OEM# 048932G0001247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-WE3J-7 | Stuffing Box Cover, Goulds JC, Frame 3J, Cast Iron, OEM# 048946G0001002 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10 | 2026-07-17
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-WE3J-8 | Stuffing Box Cover, Goulds JC, Frame 3J, High Chrome, OEM# 048946G0001228 | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-WE3J-10 | Stuffing Box Cover, Goulds JC, Frame 3J, CD4MCu, OEM# 048946G0001247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10 | 2026-05-13
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-4J81018-6 | Suction Cover Liner, 8x10-18, Goulds JC, Frame 4J, High Chrome | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-4J81018-10 | Impeller, 8x10-18, Goulds JC, Frame 4J, High Chrome, OEM #056185G8601228 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-10
Ian Trottier | 2026-05-26 | PO08932 | SO19365 | 2026-07-21 | AC-52-224-289-005 | Shaft Sleeve, Allis-Chalmers CSO, Frame F4B3/F4B5/F4D1, XH-800 | 2 | Hisco Pump Inc. | Dynapro | 2026-07-25
Emilka Guerra | 2026-05-26 | PO08933 | SO19374 | 2026-06-30 | D-500S-98B-16/C21 | Bearing Baffle, 500S-98B, 420SS | 6 | Super Cast Limited | México | 2026-07-21
Emilka Guerra | 2026-05-27 | PO08935 | SO19319 | 2026-06-03 | WO-2103740-1 | Wear Plate, Worthington 4FRBH-141 | 1 | Hisco Pump Inc. | Dynapro | 2026-06-10
Emilka Guerra | 2026-05-28 | PO08936 | Stock | 2026-06-11 | AC-98-236-104-001 | Shaft Sleeve, 8x6-18 & 10x8-21 SRL-C, Steel | 1 | Mid-Canada Manufacturing | Dynapro | 2026-06-18
Emilka Guerra | 2026-05-28 | PO08937 | Stock | 2026-06-11 | 28VSMS3-04C4VS4 | Single Cartridge Seal, 1 3/4", VSMS, Standard Bore, Carbon vs Silicon Carbide / TFEP | 2 | Flexaseal Engineered Seals and Systems, LLC | Dynapro | 2026-06-25
Emilka Guerra | 2026-05-28 | PO08938 | Stock | 2026-07-09 | AC-98-231-115-501 | Suction Side Liner, 5x4-14 SRL-C, Natural Rubber | 8 | Super Cast Limited | Dynapro | 2026-09-17
Emilka Guerra | 2026-05-28 | PO08939 | Stock | 2026-07-09 | AC-98-431-851-501 | Gland Side Casing, 3x3-10 SRL, Cast Iron | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-17
Emilka Guerra | 2026-05-28 | PO08939 | Stock | 2026-07-09 | AC-98-431-768-501 | Shaft Assembly, 8x6-18 SRL-C, 1045 Steel | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-09-17 | 2026-04-19
Emilka Guerra | 2026-05-28 | PO08941 | SO19384 & Stock | 2026-07-09 | AC-98-331-958-809 | Shaft Sleeve, 3x3-10 SRL & SRL-C, 316SS | 1 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-09-17 | 2026-05-15
Emilka Guerra | 2026-05-28 | PO08941 | SO19384 & Stock | 2026-07-09 | DU-DY21806ACP-DI | Adapter (Bearing Housing), 10", Durco Mark 2&3 Group 2, Ductile Iron | 2 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-09-17
Emilka Guerra | 2026-05-28 | PO08942 | Stock | 2026-07-23 | DE-504978 | Impeller, 10x8-21, Denver SRL-C, Natural Rubber | 2 | IGH | Dynapro | 2026-08-20
Emilka Guerra | 2026-05-28 | PO08943 | SO19378 | 2026-06-18 | AC-98-331-958-804 | Shaft Sleeve, 3x3-10 SRL, Steel | 5 | Mid-Canada Manufacturing | Dynapro | 2026-06-25 | 2026-08-18
Emilka Guerra | 2026-05-28 | PO08943 | SO19378 | 2026-06-18 | AC-98-233-813-001 | Neck Bushing, 5x4/5x5/6x6 SRL & SRL-C | 3 | Mid-Canada Manufacturing | Dynapro | 2026-06-25
Ian Trottier | 2026-05-28 | PO08944 | SO19372 | 2026-09-03 | AC-52-222-350-503 | Stuffing Box Cover, Jacketed, 10", CSO F4B3, Cast Iron | 1 | Advanced Engineered Pump Inc. | Dynapro | 2026-05-29
Ian Trottier | 2026-05-29 | PO08945 | Stock | 2026-07-14 | AC-SRL 5x4-14-C | Pump, AC-SRL 5x4-14-C, Natural Rubber Lined, Motor Mounting Plate, Belt Guard | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-10-06 | 2026-07-17
Ian Trottier | 2026-05-29 | PO08946 | SO19365 | 2026-06-12 | AC-52-109-019-018 | Shaft Sleeve, Allis-Chalmers CSO, Frame F4B3/F4B5/F4D1, Monel | 1 | Renewal Services Inc. | Dynapro | 2026-06-26
Ian Trottier | 2026-05-29 | PO08947 | SO19365 | 2026-07-24 | AC-52-224-289-005 | Shaft Sleeve, Allis-Chalmers CSO, Frame F4B3/F4B5/F4D1, XH-800 | 2 | Hisco Pump Inc. | Dynapro | 2026-08-04
Emilka Guerra | 2026-06-01 | PO08949 | SO19378 | 2026-08-10 | AC-98-231-055-508 | Gland Side Liner, 2x2-10 SRL, Urethane | 3 | IGH | Dynapro | 2026-09-07
Emilka Guerra | 2026-06-01 | PO08949 | SO19378 | 2026-08-10 | AC-98-231-054-508 | Suction Side Liner, 2x2-10 SRL, Urethane | 3 | IGH | Dynapro | 2026-09-07
Emilka Guerra | 2026-06-01 | PO08949 | SO19378 | 2026-08-10 | AC-98-211-426-508 | Impeller, 2x2-10 SRL, Urethane | 3 | IGH | Dynapro | 2026-09-07
Emilka Guerra | 2026-06-01 | PO08949 | SO19378 | 2026-08-10 | AC-98-330-286-508 | Impeller (Open), 3x3-10 SRL, Urethane | 6 | IGH | Dynapro | 2026-09-07
Emilka Guerra | 2026-06-01 | PO08949 | SO19378 | 2026-08-10 | AC-98-231-109-506 | Gland Side Liner, 3x3-10 SRL-C, Urethane | 3 | IGH | Dynapro | 2026-09-07
Emilka Guerra | 2026-06-01 | PO08949 | SO19378 | 2026-08-10 | AC-98-231-070-507 | Gland Side Liner, 3x3-10 SRL, Urethane | 7 | IGH | Dynapro | 2026-09-07
Emilka Guerra | 2026-06-01 | PO08949 | SO19378 | 2026-08-10 | AC-98-231-071-507 | Suction Side Liner, 3x3-10 SRL, Urethane | 6 | IGH | Dynapro | 2026-09-07
Emilka Guerra | 2026-06-01 | PO08949 | SO19378 | 2026-08-10 | AC-98-231-108-506 | Suction Side Liner, 3x3-10 SRL-C, Urethane | 3 | IGH | Dynapro | 2026-09-07
Emilka Guerra | 2026-06-01 | PO08949 | SO19378 | 2026-08-10 | AC-98-330-307-506 | Impeller (Closed), 3x3-10 SRL-C, Urethane | 2 | IGH | Dynapro | 2026-09-07
Emilka Guerra | 2026-06-01 | PO08950 | To be used in the building of the pumps on PO08945 | 2026-06-30 | AC-98-231-115-501 | Suction Side Liner, 5x4-14 SRL-C, Natural Rubber | 2 | Super Cast Limited | Dynapro | 2026-07-07
Emilka Guerra | 2026-06-01 | PO08950 | To be used in the building of the pumps on PO08945 | 2026-06-30 | AC-98-231-116-501 | Gland Side Liner, 5x4-14 SRL-C, Natural Rubber | 2 | Super Cast Limited | Dynapro | 2026-07-07
Emilka Guerra | 2026-06-01 | PO08950 | To be used in the building of the pumps on PO08945 | 2026-06-30 | AC-98-039-047-501 | Impeller (Closed), 5x4-14 SRL-C, Natural Rubber | 2 | Super Cast Limited | Dynapro | 2026-07-07
Taylor Cook | 2026-06-01 | PO08952 | SO19180 | 2025-07-14 | AN18 | Bearing Lock Nut, 8x6-18 & 10x8-21 SRL-C, Steel | 6 | BDI Canada Inc. | Dynapro | 2026-06-01
Emilka Guerra | 2026-06-01 | PO08953 | SO19385 & Stock | 2026-06-22 | AC-98-234-128-001 | Bearing Gasket Cover (Inboard), 2x2-10 SRL | 5 | Specialty Gaskets Inc. | Dynapro | 2026-06-30
Emilka Guerra | 2026-06-01 | PO08953 | SO19385 & Stock | 2026-06-22 | AC-98-5414-HC7 | Suction Side Plate Gasket, 5x4-14 SRL-C, Rubber, 3-Piece Design | 1 | Specialty Gaskets Inc. | Dynapro | 2026-06-30 | 2026-07-17
Emilka Guerra | 2026-06-01 | PO08954 | SO19385 | 2026-07-27 | AC-98-5414-HC3 | Suction Side Plate, 5x4-14 SRL-C, High Chrome, 3-Piece Design | 1 | IGH | Dynapro | 2026-08-24
Emilka Guerra | 2026-06-01 | PO08955 | SO19378 | 2026-06-15 | AC-98-236-104-001 | Shaft Sleeve, 8x6-18 & 10x8-21 SRL-C, Steel | 5 | Mid-Canada Manufacturing | Dynapro | 2026-06-29
Emilka Guerra | 2026-06-02 | PO08956 | SO19403 | 2026-08-11 | AC-98-5414-HC5 | Stuffing Box, 5x4-14 SRL-C, Cast Iron, 3-Piece Design | 1 | IGH | Dynapro | 2026-09-01 | 2026-05-05
Ian Trottier | 2026-06-02 | PO08958 | SO19397 | 2026-06-17 | G-R238-21 2238 | Shaft, 3405-M, 4140 Steel, Grease-Lube | 1 | Hisco Pump Inc. | Dynapro | 2026-07-01
Ian Trottier | 2026-06-02 | PO08958 | SO19397 | 2026-06-17 | G-77-59 1001 | Bearing Housing, 3405-M, Cast Iron | 2 | Hisco Pump Inc. | Dynapro | 2026-07-01
Ian Trottier | 2026-06-02 | PO08958 | SO19397 | 2026-06-17 | G-74812 01 | Deflector, 3405-M, Plastic | 2 | Hisco Pump Inc. | Dynapro | 2026-07-01
Ian Trottier | 2026-06-02 | PO08958 | SO19397 | 2026-06-17 | G-90285-1203 | Stuffing Box Bushing, 3405-L & 3316-L, 316SS | 2 | Hisco Pump Inc. | Dynapro | 2026-07-01 | 2026-03-05
Ian Trottier | 2026-06-02 | PO08958 | SO19397 | 2026-06-17 | G-R70048X 2229 | Shaft Sleeve, 2x3-11, 3316-M, 316SS | 1 | Hisco Pump Inc. | Dynapro | 2026-07-01
Ian Trottier | 2026-06-02 | PO08958 | SO19397 | 2026-06-17 | G-R70047X 2229 | Shaft Sleeve, 3405-M, 316SS, Locking | 1 | Hisco Pump Inc. | Dynapro | 2026-07-01
Ian Trottier | 2026-06-02 | PO08959 | SO18178 | 2026-07-31 | DU-CY22235A-Ni | Casing, 4x3-10, Durco Mark 2&3 Group 2, Nickel 200 | 1 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-10-09
Emilka Guerra | 2026-06-02 | PO08960 | SO19378 & stock | 2026-06-23 | AC-98-233-813-001 | Neck Bushing, 5x4/5x5/6x6 SRL & SRL-C | 4 | Mid-Canada Manufacturing | Dynapro | 2026-07-07
Emilka Guerra | 2026-06-03 | PO08961 | SO19425 | 2026-07-22 | OLPWZ011006B, G-A04951A219 | Bearing Isolator (Outboard), 3196 MTX/MTi, 303SS Rotor / Bronze Stator w/Viton | 10 | Shandong Furkey Pumps Co., Ltd. | México | 2026-09-30
Emilka Guerra | 2026-06-03 | PO08962 | SO19427 | 2026-07-22 | JC-SCS-1 3/4-4610-MT-BB | Single Cartridge Seal, 1 3/4", D-196 MT, Big Bore, Carbon vs | 2 | Super Cast Limited | México | 2026-09-30 | 2026-10-06
Emilka Guerra | 2026-06-03 | PO08962 | SO19427 | 2026-07-22 | W-E028/A05 | Expeller, 6/4 E-AH, High Chrome | 5 | Super Cast Limited | México | 2026-09-30
Emilka Guerra | 2026-06-03 | PO08962 | SO19427 | 2026-07-22 | W-E029/A05 | Expeller Ring, 6/4 E-AH, High Chrome | 4 | Super Cast Limited | México | 2026-09-30 | 2026-05-29
Emilka Guerra | 2026-06-03 | PO08963 | SO19428 | 2026-07-22 | 10673/2001 | Adjusting Nut, 16DMC-4, Cast Iron | 1 | Jiangsu Win-win International Trading Co., Ltd. | México | 2026-09-30
Emilka Guerra | 2026-06-03 | PO08963 | SO19428 | 2026-07-22 | 10674/0526 | Motor Shaft, 16DMC-4, 416SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | México | 2026-09-30
Emilka Guerra | 2026-06-03 | PO08963 | SO19428 | 2026-07-22 | 10677/5001 | Stuffing Box Bearing,16DMC-4, Teflon | 1 | Jiangsu Win-win International Trading Co., Ltd. | México | 2026-09-30
Emilka Guerra | 2026-06-03 | PO08963 | SO19428 | 2026-07-22 | 10672/0526 | Coupling, 16DMC-4, 416SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | México | 2026-09-30
Emilka Guerra | 2026-06-03 | PO08963 | SO19428 | 2026-07-22 | 10671/0504 | Cartridge Mechanical Seal, 16DMC-4, 304SS | 1 | Jiangsu Win-win International Trading Co., Ltd. | México | 2026-09-30
Emilka Guerra | 2026-06-03 | PO08963 | SO19428 | 2026-07-22 | 10685/5001 | Spider Bearing, 16DMC-4, Teflon | 1 | Jiangsu Win-win International Trading Co., Ltd. | México | 2026-09-30
Emilka Guerra | 2026-06-03 | PO08963 | SO19428 | 2026-07-22 | 10694/5001 | Discharge Bowl Bearing, 16DMC-4, Teflon | 1 | Jiangsu Win-win International Trading Co., Ltd. | México | 2026-09-30
Emilka Guerra | 2026-06-03 | PO08963 | SO19428 | 2026-07-22 | 10700/5001 | Intermediate Bowl Bearing, 16DMC-4, Teflon | 3 | Jiangsu Win-win International Trading Co., Ltd. | México | 2026-09-30
Emilka Guerra | 2026-06-03 | PO08963 | SO19428 | 2026-07-22 | 10705/5001 | Suction Bowl Bearing, 16DMC-4, Teflon | 1 | Jiangsu Win-win International Trading Co., Ltd. | México | 2026-09-30
Ian Trottier | 2026-06-03 | PO08964 | SO19376 | 2026-08-26 | AC-52-321-473-251 | Impeller (Open), 4x3-13, Allis Chalmers CSO, 6-Vanes, CD4MCu | 1 | M&N Alloy Cast Products, Inc. | Dynapro | 2026-09-03 | 2026-07-17
Emilka Guerra | 2026-06-03 | PO08965 | SO18697 & Stock | 2026-08-12 | AC-98-5414-HC5 | Stuffing Box, 5x4-14 SRL-C, Cast Iron, 3-Piece Design | 3 | IGH | Dynapro | 2026-09-09
Ian Trottier | 2026-06-04 | PO08966 | SO19440 | 2026-07-29 | DU-CY21853A-CD4 | Casing, 3x1.5-13, Durco Mark 2&3 Group 2, CD4MCu , #300 Flat Face Flanges | 1 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-10-09 | 2026-07-17
Ian Trottier | 2026-06-04 | PO08967 | SO19038 | 2026-06-10 | 22VSMS3-04C4VS4 | 1-3/8" Style VSMS3 Vantage Series Stationary Multi-Spring Cartridge Seal with F-V-D Gland. Carbon vs. Silicon Carbide Faces, FKM Elastomers, A276 Springs, and 316 Stainless Steel Construction. | 1 | Flexaseal Engineered Seals and Systems, LLC | Dynapro | 2026-06-05
Emilka Guerra | 2026-06-04 | PO08968 | SO19448 - SOPN00015 | 2026-07-09 | GA-556540 | Impeller, G-Series 6" VSP, 8100 Series, High Chrome | 3 | IGH | Dynapro | 2026-08-06 | 2026-03-06
Emilka Guerra | 2026-06-04 | PO08969 | Stock | 2026-08-14 | AC-98-231-070-501 | Gland Side Liner, 3x3-10 SRL, Natural Rubber | 6 | Super Cast Limited | Dynapro | 2026-10-23
Emilka Guerra | 2026-06-04 | PO08969 | Stock | 2026-08-14 | AC-98-231-071-501 | Suction Side Liner, 3x3-10 SRL, Natural Rubber | 6 | Super Cast Limited | Dynapro | 2026-10-23
Emilka Guerra | 2026-06-04 | PO08969 | Stock | 2026-08-14 | AC-98-330-307-501 | Impeller (Closed), 3x3-10 SRL-C, Natural Rubber | 7 | Super Cast Limited | Dynapro | 2026-10-23
Emilka Guerra | 2026-06-04 | PO08969 | Stock | 2026-08-14 | AC-98-231-079-501 | Gland Side Liner, 5x5-14 SRL, Natural Rubber | 7 | Super Cast Limited | Dynapro | 2026-10-23
Emilka Guerra | 2026-06-04 | PO08969 | Stock | 2026-08-14 | AC-98-231-120-501 | Suction Side Liner, 8x6-18 SRL-C, Natural Rubber | 9 | Super Cast Limited | Dynapro | 2026-10-23
Emilka Guerra | 2026-06-04 | PO08969 | Stock | 2026-08-14 | AC-98-431-651-501 | Impeller (Closed), 8x6-18 SRL-C, Natural Rubber | 16 | Super Cast Limited | Dynapro | 2026-10-23
Emilka Guerra | 2026-06-04 | PO08969 | Stock | 2026-08-14 | AC-98-231-136-501 | Gland Side Liner, 10x8-21 SRL-C, Natural Rubber | 7 | Super Cast Limited | Dynapro | 2026-10-23
Emilka Guerra | 2026-06-04 | PO08969 | Stock | 2026-08-14 | AC-98-039-047-501 | Impeller (Closed), 5x4-14 SRL-C, Natural Rubber | 20 | Super Cast Limited | Dynapro | 2026-10-23
Emilka Guerra | 2026-06-04 | PO08969 | Stock | 2026-08-14 | AC-98-231-115-501 | Suction Side Liner, 5x4-14 SRL-C, Natural Rubber | 5 | Super Cast Limited | Dynapro | 2026-10-23
Emilka Guerra | 2026-06-04 | PO08969 | Stock | 2026-08-14 | AC-98-231-116-501 | Gland Side Liner, 5x4-14 SRL-C, Natural Rubber | 11 | Super Cast Limited | Dynapro | 2026-10-23
Emilka Guerra | 2026-06-04 | PO08969 | Stock | 2026-08-14 | AC-98-330-286-501 | Impeller (Open), 3x3-10 SRL, Natural Rubber | 6 | Super Cast Limited | Dynapro | 2026-10-23
Emilka Guerra | 2026-06-04 | PO08969 | Stock | 2026-08-14 | AC-98-231-121-501 | Suction Side Plate, 8x6-18 SRL-C, Natural Rubber | 9 | Super Cast Limited | Dynapro | 2026-10-23
Emilka Guerra | 2026-06-04 | PO08969 | Stock | 2026-08-14 | AC-98-231-134-501 | Suction Side Liner, 10x8-21 SRL-C, Natural Rubber | 6 | Super Cast Limited | Dynapro | 2026-10-23
Emilka Guerra | 2026-06-04 | PO08969 | Stock | 2026-08-14 | AC-98-231-135-501 | Suction Side Plate, 10x8-21 SRL-C, Natural Rubber | 5 | Super Cast Limited | Dynapro | 2026-10-23
Emilka Guerra | 2026-06-04 | PO08969 | Stock | 2026-08-14 | W-C2017/U38 | Cover Plate Liner, 3/2 C-AH, Urethane | 6 | Super Cast Limited | Dynapro | 2026-10-23
Emilka Guerra | 2026-06-04 | PO08970 | Stock | 2026-07-23 | W-SP10092/A05 | Casing w/Flange, 100RV-SP, High Chrome | 5 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-10-01
Emilka Guerra | 2026-06-04 | PO08970 | Stock | 2026-07-23 | W-SP10206A70800, W-SP10206B/A05 | Impeller (Agitator), 100RV-SP, High Chrome | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-10-01
Emilka Guerra | 2026-06-04 | PO08970 | Stock | 2026-07-23 | W-ZAG65482/A05 | Agitator, 100 to 200 SP, High Chrome | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-10-01 | 2026-05-04
Emilka Guerra | 2026-06-04 | PO08970 | Stock | 2026-07-23 | AC-98-234-268-001-SS | Waterseal Bushing, 5x4/5x5/6x6 SRL, 316SS | 10 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-10-01
Emilka Guerra | 2026-06-04 | PO08970 | Stock | 2026-07-23 | W-ZAG65482/A05 | Agitator, 100 to 200 SP, High Chrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-10-01
Emilka Guerra | 2026-06-04 | PO08970 | Stock | 2026-07-23 | AC-98-236-256-501 | Gland Assembly, 5x4-14 SRL-C, 316SS | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-10-01
Emilka Guerra | 2026-06-04 | PO08971 | Stock | 2026-07-24 | AC-98-331-958-831 | Shaft Sleeve, 5x4/5x5/6X6 SRL-C & SRL, 420SS Heat Treated, Hardened | 15 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-10-01
Emilka Guerra | 2026-06-04 | PO08971 | Stock | 2026-07-24 | DU-CY21805A/CBS-DC20 | Rear Cover, 10", Durco Mark 2&3 Group 2, Alloy 20, Small Bore | 4 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-10-01 | PO08629 | DU-CY50435A-2205 | Shaft (Solid), Durco Mark 3 Group 3, 2205 Duplex Stainless | 1
Emilka Guerra | 2026-06-04 | PO08971 | Stock | 2026-07-24 | AC-98-236-104-004 | Shaft Sleeve, 8x6-18 & 10x8-21 SRL-C, 420SS Heat Treated, Hardened | 30 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-10-01
Emilka Guerra | 2026-06-04 | PO08971 | Stock | 2026-07-24 | G-249-55 1012 | Casing, 2x3-10, 3196 MTX, Ductile Iron | 1 | Shandong Furkey Pumps Co., Ltd. | Dynapro | 2026-10-01 | 2026-07-17
Yannett Yeomans | 2026-06-04 | PO08972 | SO19444 | 2026-07-06 | D-SH645 | Submersible Sewage Pump, SH645, Ductile Iron w/Impeller in High Chrome | 1 | Super Cast Limited | México | 2026-08-31 | PO08688 | WO-9090140-183 | Impeller Nut, Worthington, 8FRBH152 316SS | 1
Emilka Guerra | 2026-06-04 | PO08973 | Stock | 2026-06-11 | AC-52-430-298-007 | Seal Cage (Lantern Ring), Allis Chalmers PWO, Group 3 | 2 | Hisco Pump Inc. | Dynapro | 2026-06-25
Emilka Guerra | 2026-06-04 | PO08974 | SO19378 & stock | 2026-06-25 | AC-98-331-963-501 | Shaft Assembly, 6x6-15 SRL | 2 | Mid-Canada Manufacturing | Dynapro | 2026-07-02
Emilka Guerra | 2026-06-05 | PO08975 | Stock | 2026-07-31 | AC-98-037-796-501 | Impeller (Open), 6x6-15 AC SRL, Natural Rubber | 3 | IGH | Dynapro | 2026-08-28
Emilka Guerra | 2026-06-05 | PO08976 | SO19449 | 2026-07-10 | SZ-3822790584 | Static Seal, Sulzer | 10 | Super Cast Limited | México | 2026-09-04 | 2026-05-14
Emilka Guerra | 2026-06-05 | PO08976 | SO19449 | 2026-07-10 | D-500S-98B-03/C21 | Wear Ring, 500S-98B, 420SS | 4 | Super Cast Limited | México | 2026-09-04
Amanda Qiao | 2026-06-08 | PO08977 | Urgent WH/MO/00200 | 2026-06-15 | DU-DY53443A/FML-316SS | Rear Cover, 13", Durco Mark 2&3 Group 2, 316SS, Flow Modifier Large Bore | 2 | Hisco Pump Inc. | Dynapro | 2026-06-19
Amanda Qiao | 2026-06-08 | PO08977 | Urgent WH/MO/00200 | 2026-06-15 | DU-MY49112A130-316 | Impeller, 3x2-13, Durco Mark 2&3 Group 2, 316SS, Reverse Vane | 2 | Hisco Pump Inc. | Dynapro | 2026-06-19
Amanda Qiao | 2026-06-08 | PO08977 | Urgent WH/MO/00200 | 2026-06-15 | DU-GUARD-M3G2 | Coupling Guard, Durco Mark 3 Group 2, Steel Fabricated, Drum Style | 2 | Hisco Pump Inc. | Dynapro | 2026-06-19
Amanda Qiao | 2026-06-08 | PO08978 | Urgent WH/MO/00200 | 2026-06-15 |  | Coupling, Raptor ES2 Full Spcr Ext Kit | 2 | Mosherflo Pumps, LLC. | Dynapro | 2026-06-18 | 2026-05-12
Amanda Qiao | 2026-06-08 | PO08979 | Rush WH/MO/00200 | 2026-06-19 | PDH0026 | 2 HP, 1200 RPM, 460/3/60, Premium Efficiency TEFC, Teco-Westinghouse Motor | 2 | Teco-Westinghouse Motors (Canada) Inc. | Dynapro | 2026-06-22
Emilka Guerra | 2026-06-08 | PO08980 | SO18891 | 2026-08-31 | G-243-90 1216 | Impeller, 6x8-13, 3171-L, CD4MCu | 1 | M&N Alloy Cast Products, Inc. | Dynapro | 2026-09-21
Emilka Guerra | 2026-06-08 | PO08980 | SO18891 | 2026-08-31 | G-101-26 1216 | Suction Cover, 6x8-13, 3171-L, CD4MCu | 1 | M&N Alloy Cast Products, Inc. | Dynapro | 2026-09-21
Emilka Guerra | 2026-06-08 | PO08981 | SO19438 | 2026-06-15 | AC125-CS02-3SS, AC-52-108-789-004 | Packing Base Ring, Allis Chalmers CSO, Frame F4B3/F4B5/F4D1, 316SS | 1 | Hisco Pump Inc. | Dynapro | 2026-06-29
Emilka Guerra | 2026-06-08 | PO08982 | SO19438 | 2026-08-31 | AC-52-425-753-005 | Stuffing Box Cover, 10", CSO F4B3, Cast Iron | 1 | M&N Alloy Cast Products, Inc. | Dynapro | 2026-09-21
Emilka Guerra | 2026-06-08 | PO08983 | SO19405 | 2026-08-17 | AC-98-231-115-506 | Suction Side Liner, 5X4-14 SRL-C, Urethane | 1 | IGH | Dynapro | 2026-09-14 | 2026-05-13
Emilka Guerra | 2026-06-09 | PO08984 | SO19430 | 2026-07-07 | AC-98-331-931-801 | Bearing Cylinder, 5x4-14 SRL-C, Cast Iron | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-04
Emilka Guerra | 2026-06-09 | PO08984 | SO19430 | 2026-07-07 | AC-98-331-926-801 | Bearing Cover (Outboard), 5x4/5x5/6x6 SRL & SRL-C, Cast Iron | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | Dynapro | 2026-08-04 | 2026-05-21
Emilka Guerra | 2026-06-09 | PO08985 | SO19430 | 2026-06-16 | 22212 EAE4C3, G-8061-22212 | Bearing (Inboard), 5x4-14 SRL/SRL-C & 6x6-15 SRL, Steel | 3 | Wajax Limited - Mississauga | Dynapro | 2026-06-30
Emilka Guerra | 2026-06-09 | PO08985 | SO19430 | 2026-06-16 | 22312 EAE4C3, G-8061-62312 | Bearing (Outboard), 5x4-14 SRL/SRL-C & 6x6-15 SRL, Steel | 3 | Wajax Limited - Mississauga | Dynapro | 2026-06-30
Yannett Yeomans | 2026-06-10 | PO08986 | SO19464 | 2026-08-03 | DA-D1961.5/3-13MT/1516/0507 | ANSI Pump, D-196 1.5x3-13 MT, Ductile Iron, Impeller CD4MCu | 2 | Shandong Furkey Pumps Co., Ltd. | México | 2026-09-29
Yannett Yeomans | 2026-06-10 | PO08986 | SO19464 | 2026-08-03 | JC-SCS-1 3/4-4610-MT-BB | Single Cartridge Seal, 1 3/4", D-196 MT, Big Bore, Carbon vs | 2 | Shandong Furkey Pumps Co., Ltd. | México | 2026-09-29
Yannett Yeomans | 2026-06-10 | PO08986 | SO19464 | 2026-08-03 | G-R196-MKM13 | Maintenance Kit, 13", 3196 MTX | 4 | Shandong Furkey Pumps Co., Ltd. | México | 2026-09-29
Yannett Yeomans | 2026-06-10 | PO08986 | SO19464 | 2026-08-03 | G-249-63 1216 | Casing, 1.5x3-13, 3196 MTX, CD4MCu | 2 | Shandong Furkey Pumps Co., Ltd. | México | 2026-09-29 | 2026-05-13
Yannett Yeomans | 2026-06-10 | PO08986 | SO19464 | 2026-08-03 | G-0100-537 1216 | Impeller, 1.5x3-13, 3196 MTX, CD4MCu, 5-Vane | 2 | Shandong Furkey Pumps Co., Ltd. | México | 2026-09-29
Yannett Yeomans | 2026-06-10 | PO08986 | SO19464 | 2026-08-03 | G-C04677A 3201 | Coupling Guard, 3196 MTX, Fabricated Steel, Drum Style | 2 | Shandong Furkey Pumps Co., Ltd. | México | 2026-09-29
Yannett Yeomans | 2026-06-10 | PO08986 | SO19464 | 2026-08-03 | RX-ES30 | Coupling, Rexnord ES30, MT/LT | 2 | Shandong Furkey Pumps Co., Ltd. | México | 2026-09-29 | 2026-07-17
Yannett Yeomans | 2026-06-10 | PO08986 | SO19464 | 2026-08-03 | G-D07086A | G-D07086A | 1 | Shandong Furkey Pumps Co., Ltd. | México | 2026-09-29
Leriel Reyes | 2026-06-10 | PO08987 | SO19049 | 2026-09-16 | GA-2.5*1100x60-CI | Sump Pump, G-Series 2.5" VSP, 1000 Series, 60" Column, Cast Iron | 1 | IGH | Dynapro | 2026-10-14
Ian Trottier | 2026-06-10 | PO08988 | SO19443 | 2026-06-15 | SKF-22340 | Bearing Seal (Inboard & Outboard), 5x4-14 SRL/SRL-C, 6x6-15 SRL | 12 | Wajax Limited - Mississauga | Dynapro | 2026-06-17
Emilka Guerra | 2026-06-10 | PO08989 | SO19387 & SO19455 | 2026-07-08 | NUP-317-ECP, G-8060-17317 | Radial Bearing (Inboard), 3180-XL, Steel | 1 | Hisco Pump Inc. | Dynapro | 2026-07-15
Emilka Guerra | 2026-06-10 | PO08989 | SO19387 & SO19455 | 2026-07-08 | G-RD04859A 2249 | Shaft, 3180 XL, AISI, 4340 Alloy Steel HT | 1 | Hisco Pump Inc. | Dynapro | 2026-07-15
Emilka Guerra | 2026-06-10 | PO08989 | SO19387 & SO19455 | 2026-07-08 | G-B02191A04 3211 | Throttle Bushing, Goulds 3180-XL | 1 | Hisco Pump Inc. | Dynapro | 2026-07-15
Emilka Guerra | 2026-06-10 | PO08989 | SO19387 & SO19455 | 2026-07-08 | G-A03189A06 5127 | Side Plate Gasket, 3180-XL | 1 | Hisco Pump Inc. | Dynapro | 2026-07-15
Emilka Guerra | 2026-06-10 | PO08989 | SO19387 & SO19455 | 2026-07-08 | G-9008-31365 | Breather, 3196 MTX, Carbon Steel | 1 | Hisco Pump Inc. | Dynapro | 2026-07-15
Emilka Guerra | 2026-06-10 | PO08990 | SO19387 | 2026-06-17 | AC-98-233-992-001 | Half Seal Cage, 3x3-10 SRL & SRL-C, Cast Iron | 3 | Mid-Canada Manufacturing | Dynapro | 2026-06-24
Emilka Guerra | 2026-06-11 | PO08991 | SO19311 | 2026-07-23 | SA-138412-M1 | Impeller, (Keyed), Sala VT50, Natural Rubber | 2 | Dexhor | Dynapro | 2026-08-07
Ian Trottier | 2026-06-11 | PO08992 | VT40 Project | 2026-06-15 | SA-VT40-NR | Tank Pump, Sala VT40, Rubber Lined Tank & Wet End, Motor Mount, and Belt Guard. | 1 | NRI Industrial | Dynapro | 2026-06-11
Emilka Guerra | 2026-06-12 | PO08993 |  | 2026-07-17 | AC-98-039-047-504 | Impeller (Closed), 5x4-14 SRL-C, Hypalon | 1 | Seal X Supply Inc. | Dynapro | 2026-07-24
Emilka Guerra | 2026-06-12 | PO08994 | SO19290 | 2026-07-24 | AC-98-231-081-503 | Suction Side Liner, 5x5-14 SRL, Neoprene | 3 | IGH | Dynapro | 2026-08-21 | 2026-10-06
3138

## CONSIGNEE & NOTIFY PARTY DATA
Consignee and Notify Party Information
Site | Consignee | Notify Party
MEXICO | DYNAPRO PUMPS MEXICO S DE RL DE CV CARRETERA BAHIA DE KINO KM 12, NO. 1279, INT. V-Z, COLONIA LA MANGA, CP 83220 HERMOSILLO, SONORA, MEXICO ATTN: YERENIS CABALLERO EMAIL:LOGISTICS@DYNAPROCO.COM | DYNAPRO PUMPS MEXICO S DE RL DE CV CARRETERA BAHIA DE KINO KM 12, NO. 1279, INT. V-Z, COLONIA LA MANGA, CP 83220 HERMOSILLO, SONORA, MEXICO ATTN: YERENIS EMAIL:LOGISTICS@DYNAPROCO.COM
PANAMÁ | Warehouse & Logistics Partners France Field Avenida 2-A, Sector Coco Solito Zona Libre de Colon, Colón Province, Panama RUC: 1973672-1-735872 DV 90 Dirección: Cocosolito, manzana 20 B, local 28 Zona Libre de Colón, Colón, Panamá Email: trafico@wlpzlc.com Tel.: 214-4415 Contact: MAYDE GÓMEZ | Warehouse & Logistics Partners France Field Avenida 2-A, Sector Coco Solito Zona Libre de Colon, Colón Province, Panama RUC: 1973672-1-735872 DV 90 Dirección: Cocosolito, manzana 20 B, local 28 Zona Libre de Colón, Colón, Panamá Email: trafico@wlpzlc.com Tel.: 214-4415 Contact: MAYDE GÓMEZ
DR | DYNAPRO CARIBE SRL AVENIDA DE LAS HORTENSIAS KM 82 1/2 BONAO, MONSEÑOR NOUEL, CP 42000 DOMINICAN REPUBLIC RNC: 133093928 TEL:001 829 715 9040 | KUEHNE-NAGEL LUIS HENRIQUEZ SALES REPRESENTATIVE SEA LOGISTICS LUIS.HENRIQUEZ@KUEHNE-NAGEL.COM P. 809-221-3900 M. +1 829-657-0224
DR-BARRICK¦ CIF | BARRICK GOLD - PUEBLO VIEJO DOMINICANA CORPORATION NOVO CENTRO PLAZA, 16TH FLOOR AV. LOPE DE VEGA NO. 29,ENS. NACO 10124 SANTO DOMINGO, DOMINICAN REPUBLIC TAX ID: 101886714 | MARITIMA DOMINICANA, S.A.S CARR. SANCHEZ KM 12 1/2 SANTO DOMINGO, DOMINICAN REPUBLIC CONTACT: JIOMARIS JAQUEZ TAX ID: 101029609 CELLPHONE: 849-785-7690 EMAIL: COORDINADORESPVDC@MARDOM.COM
CANADÁ | DYNAPRO EQUIPMENT LTD 6710 MARITZ DR,UNIT 2,MISSISSAUGA,ONTARIO, CANADA L5W 0A1 E-MAIL:LOGISTICS@DYNAPROCO.COM TEL: +1 647 946 1444 EXT. 117 TAX ID: 123232712RT0001 | DSV AIR & SEA INC. 2200 YUKON COURT MILTON,ONTARIO,CANADA L9E 1N5, PH:905-494-5519 FX:905-629-0055 E-MAIL:BROKERAGE.YYZ@CA.DSV.COM

## Contact Info
Supplier | Name | Contact | Notes | Country/City | Transit time
BDI Canada | Carmela Parasiliti | carmela.parasiliti@bdi-canada.com | Supplier in Mississagua They always deliver in our warehouse. | Canada
Hisco Pump | Joey Montineri | Joey.Montineri@hiscopumpinc.com | They consolidate, sometimes weekly. Always request Joey with updates. Very normal to ship late. | USA | 3-4 bussiness days
IGH | David Grajeda Carlos Grajeda | dgrajeda.igh@gmail.com cc. cgrajesa@gmail.com y cgrajeda@mac.com | They consolidate monthly to El Paso. XP Logistics handles these shipments from El Paso. Import to USA then Export to CAN |  | 1 week for Chihuahua to XP Logistics. 1 week for EL Paso to Tornoto. (2-3 weeks from EL Paso to Toronto)
Vissers Sales Corp. | Donovan | donovan@vissers.on.ca | They deliver in our warhouse.
Flexaseal |  | jderner@flexaseal.com lisah@flexaseal.com JDillon@flexaseal.com ishour@flexaseal.com | Normally we schedule shipment with UPS.
M&N Alloy | Tammy Smith | tsmith@mnalloy.com | Normally 4 days transit. They provide weight and dimensiones, and we look for quotes. If it is a box they normally ship with our UPS account, if it is a skid they request. |  | 4-5 business days Try to consolidate more, hold orders that are no urgent.
Mosherflo Pumps |  | Sales@MosherfloPumps.com | Suppier in USA. They sell EXW. We need to schedule the shipment. | USA
Emnor Mechanical Inv. | Steve Gee | sgee@emnor.com | They are located in Canada, They provide dimensions and we schedule the pick up. | Canada
Mid-Canada Manufacturing | Mario | mcmadmin@vianet.ca cc: mcm1@vianet.ca (Mario) | They are in Ontario, they are a workshop. They send consodlidated weekly shipments | Canada | 2-4 weeks
The Alpha Seal Corporation | Sean Lowry | alphaseal@yahoo.ca | They are in Ontario. We schedule de pick up. | Canada
Nanjing Wangyang Pumps Co., Ltd | James | james.chen@wypumps.com |  | China | 10 weeks
Super Cast Limited | Peter | lanyq716@126.com |  | China | 10 weeks
Shandong Furkey Pumps Co., Ltd. | Linda | linda<linda@furkeypumps.com> |  | China | 10 weeks
Renewal Services Inc. | Terre | <TerreM@rsipumps.com> |  | USA | 4-5 weeks
Naipu Machinery Manufacturing Lincheng Co., Ltd | Betty | pumpzhm@naipump.com <pumpzhm@naipump.com> |  | China | 10 weeks
AMOS | Cathy | cathy.wang@amospump.com |  | China | 10 weeks
Wajax Limited - Mississauga | Loma | Loma Kisnasammy <lkisnasammy@wajax.com>; Andrea Maddick <AMaddick@wajax.com>; Malavika Mathath <mmathath@wajax.com> |  | Canada | 2-4 weeks
Millstream Engineering Inc. | Alina | Alina Stepanians <alina@millstreamengineering.com> |  | Canada | 2-4 weeks
Shijiazhuang Mets Machinery Co., LTD (Met Slurry) | David /Lilyane | Lilyane Yan <lilyane.yan@metslurry.com> david@metslurry.com |  | China | 10 weeks
Specialty Gaskets Inc. | Chris Matthews | Chris Matthews <cmatthews@specialtygaskets.com> |  | Canada | 2-4 weeks
Dexhor (Hyperflo) | David Go | David Go dgo@hyperflo.ca, and Richard Knight rknight@hyperflo.ca jarseneault@hyperflo.ca schabot@hyperflo.ca mhleblanc@hyperflo.ca |  | Canada | 2-4 weeks
Zibo ZLT International Trade Co, Ltd |  | Bruce Lee<bruce.lee@zltgroup.com>,
AE Pump / Advanced Engineered Pump Inc. |  | David Wheeler <dwheeler@aepump.com> |  | USA | 4-5 weeks
NC Industrial |  | Darrin Salo <dsalo@ncindustrial.ca>; Elizabeth Aguilar <eaguilar@ncindustrial.ca> |  | Canada | 2-4 weeks
Jiangsu Win-win International Trading Co., Ltd. | James | james.chen@wypumps.com |  | China | 10 weeks
Seal X | Shane Cranston | scranston@sealxsupply.com |  | Canada | 2-4 weeks
MCB Motores | Jorge Alberto Alvarado | jalvarado@mcb.com.mx |  | Mexico
TECO | Jorge Martínez Robledo | martinej@tecowestinghouse.com.mx Luis Medina medinal@tecowestinghouse.com.mx |  | Mexico
Plastimarmol | Gabriela Zambrano | gabriela.zambrano@plastimarmol.com |  | Mexico
RYASA | Lupita Martinez | guadalupe.martinez@ryasa.com.mx |  | Mexico
BINASA | Jose Manuel Velaz / Ing. Daniel Galaz | ventas6@binasahillo.com.mx |  | Mexico
APPLIED | Lorenia Ramirez | lramirez@applied.com.mx |  | Mexico
Tomason | Miguel Ruiz | mgruiztomason@gmail.com |  | Mexico
TUVANOSA | Soledad Armenta | soledad.armenta@tuvanosa.com |  | Mexico
CIPSA | Armando Sanchez | ventashermosillo2@grupocipsa.com |  | Mexico
BOMBAS Y MOTORES HMG | Jose Ramon Trujillo | jramon.trujillo@hmgbombas.com | WEG MOTORS | Mexico
SUMMIT WATER | isabel@summitwater.ca sales@summitwater.ca | isabel@summitwater.ca sales@summitwater.ca |  | Canada | 2-4 weeks
BIJUR DELIMON | vmerritt@bijurdelimon.com | vmerritt@bijurdelimon.com |  | USA | 4-5 weeks
SEPCO | Bill stallings / bills@sepco.com | Bill stallings / bills@sepco.com |  | USA | 4-5 weeks
VELLUMOID | planning@vellumoid.com | planning@vellumoid.com | for ordering Gaskets | USA | 4-5 weeks
BASETEK | Erin | erin@basetek.com |  | USA | 4-5 weeks

## Notes
IGH | AVG 5 weeks late

## Naipu
STATUS | CREATED BY | ISSUE DATE | PO NUMBER | REFERENCE | DUE DATE FACTORY | SKU | PRODUCT NAME | INCOMING STOCK | SUPPLIER | ORIGIN | SHIP TO | SHIPPING DATE SUPPLIER | TRANSIT | ETA WAREHOUSE UPDATES | SHIPPING INSTRUCTIONS | TRACKING NUMBER / UPDATES | IMPORTANT NOTE | PETER UPDATES | DELAY ISSUES | EST RECEIPT DATE ODOO | RECEPTION DATE WAREHOUSE | COMPLETED | SUPPLIER DELIVERY | TOTAL REAL LEAD TIME | Total LT in weeks
Received | Carlos Leon | 2025-08-20 | PO08231 | Stock | 2025-10-02 | AC-98-530-594-001 | Pedestal, 5x4/5x5/6x6 SRL & SRL-C, Cast Iron | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-02-11 | SEA | Around Week of Apr. 30 - May 1 |  | TCLU8795637 |  | possible arrival to vancouver port march 21st | Delay production due spring festival | 2025-12-15 | 2026-04-28 | TRUE | 132 | 251 | 35.8571
Received | Carlos Leon | 2025-08-20 | PO08231 | Stock | 2025-10-02 | AC-98-431-799-001 | Suction Side Casing, 5x4-14 SRL-C, Cast Iron | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-02-11 | SEA | Around Week of Apr. 30 - May 1 |  | TCLU8795637 |  | possible arrival to vancouver port march 21st | Delay production due spring festival | 2025-12-15 | 2026-04-28 | TRUE | 132 | 251 | 35.8571
Received | Carlos Leon | 2025-08-20 | PO08231 | Stock | 2025-10-02 | AC-98-431-797-501 | Gland Side Casing, 5x4-14 SRL-C, Cast Iron | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-02-11 | SEA | Around Week of Apr. 30 - May 1 |  | TCLU8795637 |  | possible arrival to vancouver port march 21st | Delay production due spring festival | 2025-12-15 | 2026-04-28 | TRUE | 132 | 251 | 35.8571
Received | Carlos Leon | 2025-10-28 | PO08393 | Stock | 2025-12-23 | AC-98-234-271-001 | Waterseal Bushing, 3x3 SRL-C, 316SS | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-01-06 | SEA | 2026-03-03 |  | 1071968361 |  | Prince Rupert, march 1st / Expected to arrive first week of april | delayed due heavy congestion | 2026-03-03 | 2026-03-30 | TRUE | 14 | 153 | 21.8571
Received | Carlos Leon | 2025-10-31 | PO08399 | Stock | 2025-12-19 | AC-98-431-768-501 | Shaft Assembly, 8x6-18 SRL-C, 1045 Steel | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-01-06 | SEA | 2026-02-10 |  | 1071968361 |  | Prince Rupert, march 1st / Expected to arrive first week of april | delayed due heavy congestion | 2026-02-10 | 2026-03-30 | TRUE | 18 | 150 | 21.4286
Received | Yannett Yeomans | 2025-11-05 | PO08415 | SO18159 | 2025-12-18 | AC-98-331-958-823 | Shaft Sleeve, 2x2-10 SRL, 420SS Heat Treated, Hardened | 5 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-01-06 | SEA | 2026-02-26 |  | 1071968361 |  | Prince Rupert, march 1st / Expected to arrive first week of april | delayed due heavy congestion | 2026-02-26 | 2026-03-30 | TRUE | 19 | 145
Received | Emilka Guerra | 2025-11-11 | PO08424 | Stock | 2025-12-30 | AC-98-331-958-823 | Shaft Sleeve, 2x2-10 SRL, 420SS Heat Treated, Hardened | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA |  |  | 1071968361 |  | Prince Rupert, march 1st / Expected to arrive first week of april | delayed due heavy congestion | 2026-03-10 | 2026-03-30 | TRUE | -46021 | 139
IN TRANSIT & DELAYED | Emilka Guerra | 2025-11-11 | PO08424 | Stock | 2025-12-30 | AC-98-431-849-001 | Suction Side Casing, 3x3-10 SRL, Cast Iron | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-05-26 | SEA | ETA Warehouse mid-august | the vessel depart on May 26 | 20251217-11 Sea Waybill-No. 1074440607 | email sent on April 10th, 2026 Betty 4/23: Included in Comercial Invoice #20251217-11 | Betty 04/13: This part will be ready in about 7-10 days. Betty 04/22: The three new parts are being machined and should be ready soon. | Betty: we manufacture the two parts as one set(suction half casing&gland side casing),we hope you can oder them as a pair. | 2026-03-10 |  | FALSE | 147 | -45972 | -6567.4286
Received | Yannett Yeomans | 2025-11-20 | PO08455 | Stock | 2025-12-19 | W-32CWXR | Pump, W-Series 3/2 C-DHR, Natural Rubber | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA |  |  | 1071968361 |  | Prince Rupert, march 1st / Expected to arrive first week of april | delayed due heavy congestion | 2026-02-27 | 2026-03-30 | TRUE | -46010 | 130
Received | Emilka Guerra | 2025-11-21 | PO08459 | Stock | 2025-12-19 | W-ZAG65482/A05 | Agitator, 100 to 200 SP, High Chrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA |  |  | 1071968361 |  | Prince Rupert, march 1st / Expected to arrive first week of april | delayed due heavy congestion | 2026-02-27 | 2026-03-30 | TRUE | -46010 | 129
Received | Emilka Guerra | 2025-11-21 | PO08459 | Stock | 2025-12-19 | W-ZAS65813 | Agitator Shaft, 100 to 200 SP, 420SS | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA |  |  | 1071968361 |  | Prince Rupert, march 1st / Expected to arrive first week of april | delayed due heavy congestion | 2026-02-27 | 2026-03-30 | TRUE | -46010 | 129
Received | Emilka Guerra | 2025-11-21 | PO08459 | Stock | 2025-12-19 | W-SP10206A70800, W-SP10206B/A05 | Impeller (Agitator), 100RV-SP, High Chrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA |  |  | 1071968361 |  | Prince Rupert, march 1st / Expected to arrive first week of april | delayed due heavy congestion | 2026-02-27 | 2026-03-30 | TRUE | -46010 | 129
Received | Emilka Guerra | 2025-11-21 | PO08459 | Stock | 2025-12-19 | W-SP10092/A05 | Casing w/Flange, 100RV-SP, High Chrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA |  |  | 1071968361 |  | Prince Rupert, march 1st / Expected to arrive first week of april | delayed due heavy congestion | 2026-02-27 | 2026-03-30 | TRUE | -46010 | 129
Received | Emilka Guerra | 2025-11-21 | PO08459 | Stock | 2025-12-19 | W-RV10005N/D21 | Bearing Assembly, 100ZJL-RV, Ductile Iron Bearing Cylinder, 2100mm Steel Shaft | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA |  |  | 1071968361 |  | Prince Rupert, march 1st / Expected to arrive first week of april | delayed due heavy congestion | 2026-02-27 | 2026-03-30 | TRUE | -46010 | 129
Received | Emilka Guerra | 2025-11-21 | PO08459 | Stock | 2025-12-19 |  | Discharge Pipe, 100ZJL-RV, 2100mm, Steel | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA |  |  | 1071968361 |  | Prince Rupert, march 1st / Expected to arrive first week of april | delayed due heavy congestion | 2026-02-27 | 2026-03-30 | TRUE | -46010 | 129
Received | Emilka Guerra | 2025-11-21 | PO08459 | Stock | 2025-12-19 | W-SP10041/A05 | Back Liner, 100RV-SP, High Chrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA |  |  | 1071968361 |  | Prince Rupert, march 1st / Expected to arrive first week of april | delayed due heavy congestion | 2026-02-27 | 2026-03-30 | TRUE | -46010 | 129
Received | Emilka Guerra | 2025-11-21 | PO08459 | Stock | 2025-12-19 | D1J2311-6 | Suction Cover Liner, 2x3-11, Goulds JC, Frame 1J, High Chrome, OEM# 048940G0001228 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA |  |  | 1071968361 |  | Prince Rupert, march 1st / Expected to arrive first week of april | delayed due heavy congestion | 2026-02-27 | 2026-03-30 | TRUE | -46010 | 129
IN TRANSIT & DELAYED | Emilka Guerra | 2025-11-24 | PO08463 | Stock | 2026-01-05 | AC-98-431-799-001 | Suction Side Casing, 5x4-14 SRL-C, Cast Iron | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-05-26 | SEA | ETA Warehouse mid-august | the vessel depart on May 26 | 20251217-11 Sea Waybill-No. 1074440607 | New follow up email sent on May 8th Naipu Booked vessel for May 22nd | Betty 04/19: still not shipped out, we plan to ship it around May 08. Betty 4/23: Included in Comercial Invoice #20251217-11 | ETD May/8 | 2026-03-16 |  | FALSE | 141 | -45985
Received | Emilka Guerra | 2025-11-24 | PO08463 | Stock | 2026-01-05 | AC-98-331-932-501 | Shaft Assembly, 5x4-14 SRL-C & 5x5-14 SRL, 1045 Steel | 8 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-02-10 | SEA | Around Week of Apr. 30 - May 1 |  | 1072493563 |  |  | YC: Container held in customs / waiting to be loaded onto the train | 2026-03-16 | 2026-04-28 | TRUE | 36 | 155
Received | Emilka Guerra | 2025-11-24 | PO08463 | Stock | 2026-01-05 | D-1J2311-2 | Casing, 2x3-11, Goulds JC, Frame 1J, High Chrome, OEM# 055891G0001228 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-02-10 | SEA | Around Week of Apr. 30 - May 1 |  | 1072493563 |  |  | YC: Container held in customs / waiting to be loaded onto the train | 2026-03-16 | 2026-04-28 | TRUE | 36 | 155 | 22.1429
Received | Emilka Guerra | 2025-12-03 | PO08489 | Stock - SO18359 | 2026-01-14 | AC-98-233-733-513 | Deflector (Water Slinger), 8x6-18 & 10x8-21 SRL-C, Neoprene/Steel | 10 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-02-10 | SEA | Around Week of Apr. 30 - May 1 |  | TCLU8795637 |  | Naipu: confirmed shipped out | Email for follow up sent on April 10 | 2026-03-25 | 2026-04-28 | TRUE | 27 | 146
Received | Emilka Guerra | 2025-12-03 | PO08489 | Stock - SO18359 | 2026-01-14 | D-1J2311-14 | Suction Cover, 2x3-11, Goulds JC, Frame 1J, High Chrome, OEM# 050387G0001228 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-02-10 | SEA | Around Week of Apr. 30 - May 1 |  | TCLU8795637 |  | Naipu: confirmed shipped out | Email for follow up sent on April 10 | 2026-03-25 | 2026-04-28 | TRUE | 27 | 146
Received | Emilka Guerra | 2025-12-03 | PO08489 | Stock - SO18359 | 2026-01-14 | AC-98-331-936-801 | Bearing Cover (Inboard), 8x6-18 & 10x8-21 SRL-C, Cast Iron | 5 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-01-28 | SEA | March 27–31 |  | 1071968361 |  | Prince Rupert, march 1st / Expected to arrive first week of april |  | 2026-03-25 | 2026-03-30 | TRUE | 14 | 117
Received | Emilka Guerra | 2025-12-03 | PO08489 | Stock - SO18359 | 2026-01-14 | AC-98-331-901-801 | Bearing Cover (Outboard), 8x6-18 & 10x8-21 SRL-C, Cast Iron | 5 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-01-28 | SEA | March 27–31 |  | 1071968361 |  | Prince Rupert, march 1st / Expected to arrive first week of april |  | 2026-03-25 | 2026-03-30 | TRUE | 14 | 117
IN TRANSIT & DELAYED | Ian Trottier | 2025-12-10 | PO08518 | Stock - JC 1J - 1x1.5-11 Project | 2026-02-06 | D-1J11511-10 | Impeller, 1x1.5-11, Goulds JC, Frame 1J, High Chrome, OEM# 056185G4701228 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-05-26 | SEA | ETA Warehouse mid-august | the vessel depart on May 26 | 20251217-11 Sea Waybill-No. 1074440607 | reverse engineered | Betty 04/19: we can ship it after our Labor day holiday, around May 08. Betty 4/23: Included in Comercial Invoice #20251217-11 | email sent on April 17th | 2026-04-17 |  | FALSE | 109 | -46001
IN TRANSIT & DELAYED | Ian Trottier | 2025-12-10 | PO08518 | Stock - JC 1J - 1x1.5-11 Project | 2026-02-06 | D-1J11511-2 | Casing, 1x1.5-11, Goulds JC, Frame 1J, High Chrome, OEM# 056185G5101228 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-05-26 | SEA | ETA Warehouse mid-august | the vessel depart on May 26 | 20251217-11 Sea Waybill-No. 1074440607 | reverse engineered | Betty 04/19: we can ship it after our Labor day holiday, around May 08. Betty 4/23: Included in Comercial Invoice #20251217-11 | email sent on April 17th | 2026-04-17 |  | FALSE | 109 | -46001 | -6571.5714
IN TRANSIT & DELAYED | Ian Trottier | 2025-12-10 | PO08518 | Stock - JC 1J - 1x1.5-11 Project | 2026-02-06 | D-1J11511-6 | Suction Cover Liner, 1x1.5-11, Goulds JC, Frame 1J, High Chrome, OEM# 048935G0001228 | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-05-26 | SEA | ETA Warehouse mid-august | the vessel depart on May 26 | 20251217-11 Sea Waybill-No. 1074440607 | reverse engineered | Betty 04/19: we can ship it after our Labor day holiday, around May 08. Betty 4/23: Included in Comercial Invoice #20251217-11 | email sent on April 17th | 2026-04-17 |  | FALSE | 109 | -46001 | -6571.5714
IN TRANSIT & DELAYED | Ian Trottier | 2025-12-10 | PO08518 | Stock - JC 1J - 1x1.5-11 Project | 2026-02-06 | D-1J11511-14 | Suction Cover, 1x1.5-11, Goulds JC, Frame 1J, High Chrome, OEM# 050385G0001228 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-05-26 | SEA | ETA Warehouse mid-august | the vessel depart on May 26 | 20251217-11 Sea Waybill-No. 1074440607 | reverse engineered | Betty 04/19: we can ship it after our Labor day holiday, around May 08. Betty 4/23: Included in Comercial Invoice #20251217-11 | email sent on April 17th | 2026-04-17 |  | FALSE | 109 | -46001 | -6571.5714
IN TRANSIT & DELAYED | Ian Trottier | 2025-12-10 | PO08518 | Stock - JC 1J - 1x1.5-11 Project | 2026-02-06 | D-1x1.5-11-JC-HC | Pump, 1x1.5-11, Dynapro DC, Frame 1J, High Chrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-05-26 | SEA | ETA Warehouse mid-august | the vessel depart on May 26 | 20251217-11 Sea Waybill-No. 1074440607 | reverse engineered | Betty 04/19: we can ship it after our Labor day holiday, around May 08. Betty 4/23: Included in Comercial Invoice #20251217-11 | email sent on April 17th | 2026-04-17 |  | FALSE | 109 | -46001 | -6571.5714
Received | Ian Trottier | 2025-12-10 | PO08519 | SO18198 | 2026-03-13 | G-050619G000 1228 | Suction Cover, 8x10-18, Goulds JC Frame 4J, High Chrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-04-17 | SEA | ETA Warehouse June 10-15 |  | BL 1073610888 | EG: Included in Invoice # 20251212-11A | Betty confirmed shipment | Email requesting status sent on March 19th | 2026-05-29 | 2026-06-01 | TRUE | 35 | 173 | 24.7143
IN TRANSIT & DELAYED | Jeff Bell | 2025-12-11 | PO08522 | SO16270 | 2026-02-23 | 150ZJ-F-HE2. 8/6 F-AH w/HE Impeller | Pump, W-Series, 8/6 DH, 150ZJF-HE, 28% Ultrachrome, Corrosion Resistant | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | BARRICK DIRECT SHIPPING | 2026-04-16 | SEA | Around June 5 - 10 |  | LS15TJ2603881 | Thursday 19th, march 2026 | The new ETD Tianjin is Apr 16.. shipped out. ✅ Shipping docs and pictures will be shared with you by Monday. The ETA Caucedo is June 5 to 10 | was delayed by draiwng confirmation, unable to come out until end of Feb. // now in Naipu's workshop, waiting for Naipu's PO08522 to ship together | 2026-04-05 |  | FALSE | 52 | -46002 | -6571.7143
Received | Yannett Yeomans | 2025-12-15 | PO08536 | Stock | 2026-01-15 | D-2x3-11-JC-HC | Pump, 2x3-11, Dynapro DC, Frame 1J, High Chrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-01-15 | SEA | 2026-03-26 |  | BL 1073610888 | EG: Included in Invoice # 20251212-11A |  | Email requesting status sent on March 19th | 2026-01-15 | 2026-06-01 | TRUE | 0 | 168
Received | Emilka Guerra | 2025-12-22 | PO08562 | Stock | 2026-02-02 | AC-98-131-246-511 | Deflector (Water Slinger), 5x5/5x4/6x6 SRL & SRL-C, Neoprene/Steel | 20 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-02-10 | SEA | Around Week of Apr. 30 - May 1 |  | TCLU8795637 |  | Naipu: confirmed shipped out / included in invoice |  | 2026-04-13 | 2026-04-28 | TRUE | 8 | 127
Received | Emilka Guerra | 2025-12-22 | PO08562 | Stock | 2026-02-02 | D-3J4614-6 | Suction Cover Liner, 4x6-14, Goulds JC, Frame 3J, High Chrome, OEM# 048944G0001228 | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-02-10 | SEA | Around Week of Apr. 30 - May 1 |  | TCLU8795637 |  | Naipu: confirmed shipped out / included in invoice |  | 2026-04-13 | 2026-04-28 | TRUE | 8 | 127 | 18.1429
IN TRANSIT & DELAYED | Ian Trottier | 2025-12-24 | PO08570 | Stock | 2026-01-28 | G-10x12-22-JC-HC | Pump, 10x12-22, Goulds JC Frame 5J, High Chrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-05-26 | SEA | ETA Warehouse mid-august | the vessel depart on May 26 | 20251217-11 Sea Waybill-No. 1074440607 |  | Betty 4/23: Included in Comercial Invoice #20251217-11 | Email requesting status sent on March 19th / april 22nd | 2026-03-13 |  | FALSE | 118 | -46015 | -6573.5714
IN TRANSIT & DELAYED | Ian Trottier | 2025-12-30 | PO08574 | Stock | 2026-03-02 | G-8x10-18-JC-HC | Pump, 8x10-18, Dynapro DC, Frame 3J, High Chrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-05-26 | SEA | ETA Warehouse mid-august | the vessel depart on May 26 | 20251217-11 Sea Waybill-No. 1074440607 |  | Betty 4/23: Included in Comercial Invoice #20251217-11 | Email requesting status sent on March 19th / april 22nd | 2026-05-18 |  | FALSE | 85 | -46021 | -6574.4286
Received | Emilka Guerra | 2026-01-19 | PO08612 | Stock | 2026-02-27 | G-1.5x2-14-JC-HC | Pump, 1.5x2-14, Dynapro DC, Frame 2J, High Chrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-04-17 | SEA | ETA Warehouse June 10-15 |  | BL 1073610888 | EG: Included in Invoice # 20251212-11A | Betty confirmed shipment | Email requesting status sent on March 19th | 2026-05-08 | 2026-06-01 | TRUE | 49 | 133
Received | Ian Trottier | 2026-01-23 | PO08632 | SO18359 | 2026-05-15 | SA-128214-1 | Inlet, Sala VS150, High Chrome | 5 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | Around Week of Apr. 30 - May 1 |  | TCLU8795637 |  | Naipu: confirmed shipped out |  | 2026-03-06 | 2026-04-28 | TRUE | -46157 | 95 | 13.5714
IN TRANSIT | Emilka Guerra | 2026-01-29 | PO08642 | Stock | 2026-03-20 | 571638 | Casing, Sala VS150, High Chrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-06-19 | SEA | ETA Warehouse Mid-Sept |  |  | Follow email sent for update on June 16th . We already shipped them to Tianjin, but the vessel delayed, it shows that it will depart on June 19. | Betty 5/15: Included in Comercial Invoice / #20260205-11 | Status email sent on April 22nd Status email sent on May 15th | 2026-05-29 |  | FALSE | 91 | -46051 | -6578.7143
IN TRANSIT & DELAYED | Emilka Guerra | 2026-01-29 | PO08642 | Stock | 2026-03-20 | AC-98-431-768-501 | Shaft Assembly, 8x6-18 SRL-C, 1045 Steel | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | 2026-05-29 |  | 20251217-11 Sea Waybill-No. 1074440607 |  | Peter 05/16: the vessel already arrived at Tianjin seaport, will depart Tianjin tomorrow: May 17 | Status email sent on April 22nd Betty 04/23: It is ready, waiting on weight and dimentions, I wILL update later. | 2026-05-29 |  | FALSE | -46101 | -46051 | -6578.7143
IN TRANSIT & DELAYED | Emilka Guerra | 2026-01-29 | PO08642 | Stock | 2026-03-20 | W-G12060/S01 | Intake Joint Ring, EPDM | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | 2026-05-29 |  | 20251217-11 Sea Waybill-No. 1074440607 |  | Peter 05/16: the vessel already arrived at Tianjin seaport, will depart Tianjin tomorrow: May 17 | Status email sent on April 22nd Betty 04/23: It is ready, waiting on weight and dimentions, I wILL update later. | 2026-05-29 |  | FALSE | -46101 | -46051 | -6578.7143
IN TRANSIT | Emilka Guerra | 2026-01-29 | PO08642 | Stock | 2026-03-20 | AC-98-131-246-511 | Deflector (Water Slinger), 5x5/5x4/6x6 SRL & SRL-C, Neoprene/Steel | 20 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-04-17 | SEA | ETA Warehouse June 10-15 |  | BL 1073610888 | EG: Included in Invoice | Betty confirmed shipment |  | 2026-05-29 |  | FALSE | 28 | -46051 | -6578.7143
Received | Livan Hernandez | 2026-02-04 | PO08659 | STOCK | 2026-03-25 | AC-98-331-910-801 | Bearing Cylinder, 8x6-18 & 10x8-21 SRL-C, Cast Iron | 5 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-04-17 | SEA | ETA Warehouse June 10-15 | Follow email sent for update on June 16th | BL 1073610888 | EG: Included in Invoice | Betty confirmed shipment |  | 2026-06-17 | 2026-06-01 | TRUE | 23 | 117 | 16.7143
IN TRANSIT | Livan Hernandez | 2026-02-04 | PO08659 | STOCK | 2026-03-25 | AC-98-331-958-822 | Shaft Sleeve, 3x3-10 SRL & SRL-C, 420SS Heat Treated, Hardened | 6 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-06-19 | SEA | ETA Warehouse Mid-Sept |  |  | Follow email sent for update on June 16th . We already shipped them to Tianjin, but the vessel delayed, it shows that it will depart on June 19. | Betty 5/15: Included in Comercial Invoice / #20260205-11 | Status email sent on April 22nd Betty 04/23: 6 shaft sleeve still not ready to ship,it wll ready after the labor day holiday. | 2026-06-17 |  | FALSE | 86 | -46057 | -6579.5714
IN TRANSIT & DELAYED | Livan Hernandez | 2026-02-04 | PO08659 | STOCK | 2026-03-25 | AC-98-331-901-801 | Bearing Cover (Outboard), 8x6-18 & 10x8-21 SRL-C, Cast Iron | 10 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-05-26 | SEA | ETA Warehouse mid-august | the vessel depart on May 26 | 20251217-11 Sea Waybill-No. 1074440607 |  | Betty 4/23: Included in Comercial Invoice #20251217-11 | Status email sent on April 22nd | 2026-06-17 |  | FALSE | 62 | -46057 | -6579.5714
IN TRANSIT & DELAYED | Livan Hernandez | 2026-02-04 | PO08659 | STOCK | 2026-03-25 | AC-98-331-936-801 | Bearing Cover (Inboard), 8x6-18 & 10x8-21 SRL-C, Cast Iron | 10 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-05-26 | SEA | ETA Warehouse mid-august | the vessel depart on May 26 | 20251217-11 Sea Waybill-No. 1074440607 |  | Betty 4/23: Included in Comercial Invoice #20251217-11 | Status email sent on April 22nd | 2026-06-17 |  | FALSE | 62 | -46057 | -6579.5714
IN TRANSIT & DELAYED | Livan Hernandez | 2026-02-04 | PO08659 | STOCK | 2026-03-25 | AC-98-431-858-501 | Shaft Assembly, 3x3-10 SRL & SRL-C, 1045 Steel | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-05-26 | SEA | ETA Warehouse mid-august | the vessel depart on May 26 | 20251217-11 Sea Waybill-No. 1074440607 |  | Betty 4/23: Included in Comercial Invoice #20251217-11 | Status email sent on April 22nd | 2026-06-17 |  | FALSE | 62 | -46057 | -6579.5714
IN TRANSIT & DELAYED | Leriel Reyes | 2026-02-05 | PO08667 | SO17754 | 2026-04-06 | W-400-DSTL-A49-UC | Pump, W-Series 400 ZJD, Ultrachrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | BARRICK DIRECT SHIPPING | 2026-05-17 | SEA | ETA CAUCEDO JUNE 28 | FOB Tianjin | TS6QJ1969800 / BL. ONEYTS6QJ1969800 | Original Lead time for production: 60 days (9 weeks) after payment. Wrong due date in Order + regular sea transit 10 weeks | PEter 05/16: The vessel already arrived at Tianjin seaport, will depart Tianjin tomorrow: May 17. left Tianjin for Caucedo by sea on May 17, 2026 | Naipu: still need 10-14 day to complete. ETD Mar 15 from Shanghai to Caucedo New ETD MAY 8TH May 14th: ETD Tianjin May 16 early morning | 2026-04-27 |  | FALSE | 41 | -46058 | -6579.7143
IN TRANSIT & DELAYED | Leriel Reyes | 2026-02-05 | PO08667 | SO17754 | 2026-04-06 |  | Pulley and belts, 400 ZJD, Ultrachrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | BARRICK DIRECT SHIPPING | 2026-05-17 | SEA | ETA CAUCEDO JUNE 28 | FOB Tianjin | TS6QJ1969800 / BL. ONEYTS6QJ1969800 | Original Lead time for production: 60 days (9 weeks) after payment. Wrong due date in Order + regular sea transit 10 weeks | PEter 05/16: The vessel already arrived at Tianjin seaport, will depart Tianjin tomorrow: May 17. left Tianjin for Caucedo by sea on May 17, 2026 | Naipu: still need 10-14 day to complete. ETD Mar 15 from Shanghai to Caucedo New ETD MAY 8TH May 14th: ETD Tianjin May 16 early morning | 2026-04-27 |  | FALSE | 41 | -46058
IN TRANSIT & DELAYED | Leriel Reyes | 2026-02-05 | PO08667 | SO17754 | 2026-04-06 | W-400-DSTL-A49-UC | Pump, W-Series 400 ZJD, Ultrachrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | BARRICK DIRECT SHIPPING | 2026-05-17 | SEA | ETA CAUCEDO JUNE 28 | FOB Tianjin | TS6QJ1969800 / BL. ONEYTS6QJ1969800 | Original Lead time for production: 60 days (9 weeks) after payment. Wrong due date in Order + regular sea transit 10 weeks | PEter 05/16: The vessel already arrived at Tianjin seaport, will depart Tianjin tomorrow: May 17. left Tianjin for Caucedo by sea on May 17, 2026 | Naipu: still need 10-14 day to complete. ETD Mar 15 from Shanghai to Caucedo New ETD MAY 8TH May 14th: ETD Tianjin May 16 early morning | 2026-04-27 |  | FALSE | 41 | -46058
IN TRANSIT & DELAYED | Leriel Reyes | 2026-02-05 | PO08667 | SO17754 | 2026-04-06 |  | Pulley and belts, 400 ZJD, Ultrachrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | BARRICK DIRECT SHIPPING | 2026-05-17 | SEA | ETA CAUCEDO JUNE 28 | FOB Tianjin | TS6QJ1969800 / BL. ONEYTS6QJ1969800 | Original Lead time for production: 60 days (9 weeks) after payment. Wrong due date in Order + regular sea transit 10 weeks | PEter 05/16: The vessel already arrived at Tianjin seaport, will depart Tianjin tomorrow: May 17. left Tianjin for Caucedo by sea on May 17, 2026 | Naipu: still need 10-14 day to complete. ETD Mar 15 from Shanghai to Caucedo New ETD MAY 8TH May 14th: ETD Tianjin May 16 early morning | 2026-04-27 |  | FALSE | 41 | -46058
IN TRANSIT & DELAYED | Emilka Guerra | 2026-02-20 | PO08689 | Stock | 2026-04-06 | D-1J2311-2 | Casing, 2x3-11, Goulds JC, Frame 1J, High Chrome, OEM# 055891G0001228 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-05-26 | SEA | ETA Warehouse mid-august | the vessel depart on May 26 | 20251217-11 Sea Waybill-No. 1074440607 | EG: email follow up on this item sent april 14 | Betty 4/23: Included in Comercial Invoice ONLY 3 PCS READY / #20251217-11 | EG: email follow up on this item sent april 14 | 2026-06-22 |  | FALSE | 50 | -46073 | -6581.8571
IN TRANSIT | Emilka Guerra | 2026-02-20 | PO08689 | Stock | 2026-04-06 | D-1J2311-2 | Casing, 2x3-11, Goulds JC, Frame 1J, High Chrome, OEM# 055891G0001228 | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-06-19 | SEA | ETA Warehouse Mid-Sept |  |  | Follow email sent for update on June 16th . We already shipped them to Tianjin, but the vessel delayed, it shows that it will depart on June 19. | Betty 5/15: Included in Comercial Invoice 4 PCS remaining / #20260205-11 | EG: email follow up on this item sent MAy 15 | 2026-06-22 |  | FALSE | 74 | -46073 | -6581.8571
Received | Emilka Guerra | 2026-02-20 | PO08689 | Stock | 2026-04-06 | G-1.5x2-14-JC-HC | Pump, 1.5x2-14, Dynapro DC, Frame 2J, High Chrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-04-17 | SEA | ETA Warehouse June 10-15 |  | BL 1073610888 | EG: Included in Invoice | Betty confirmed shipment |  | 2026-06-22 | 2026-06-01 | TRUE | 11 | 101
Received | Emilka Guerra | 2026-02-20 | PO08689 | Stock | 2026-04-06 | AC-98-331-983-801 | Bearing Cylinder, 3x3-10 SRL & SRL-C, Cast Iron | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-04-17 | SEA | ETA Warehouse June 10-15 |  | BL 1073610888 | EG: Included in Invoice | Betty confirmed shipment |  | 2026-06-22 | 2026-05-29 | TRUE | 11 | 98
IN TRANSIT & DELAYED | Ian Trottier | 2026-02-20 | PO08690 | SO18457 | 2026-04-10 | D-PE4J-400-316 | Power End, Goulds JC, Frame 4J, Grease-Lubed, SKF Bearings, 316SS Steel Shaft | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-05-26 | SEA | ETA Warehouse mid-august | the vessel depart on May 26 | 20251217-11 Sea Waybill-No. 1074440607 |  | Betty 4/23: Included in Comercial Invoice #20251217-11 | Status email sent on April 22nd | 2026-06-12 |  | FALSE | 46 | -46073 | -6581.8571
DELAYED PRODUCTION | Ian Trottier | 2026-02-25 | PO08698 | Stock | 2026-04-08 | SF-PE2 | Baseplate, JC, 2J/3J Frame, Steel Fabricated, Adjustable Over-Head Motor Mount & Belt Guard | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | 2026-06-24 |  |  |  |  | Waiting on Ian confirmation to Naipu for the attached drawings | 2026-06-24 |  | FALSE | -46120 | -46078 | -6582.5714
DELAYED PRODUCTION | Ian Trottier | 2026-02-25 | PO08698 | Stock | 2026-04-08 | SF-PE3 | Baseplate, JC, 3J Frame, Steel Fabricated, Adjustable Over-Head Motor Mount & Belt Guard | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | 2026-06-24 |  |  |  |  | Waiting on Ian confirmation to Naipu for the attached drawings | 2026-06-24 |  | FALSE | -46120 | -46078 | -6582.5714
DELAYED PRODUCTION | Ian Trottier | 2026-02-25 | PO08698 | Stock | 2026-04-08 | SF-PE4 | Baseplate, JC, 4J Frame, Steel Fabricated, Adjustable Over-Head Motor Mount & Belt Guard | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | 2026-06-24 |  |  |  |  | Waiting on Ian confirmation to Naipu for the attached drawings | 2026-06-24 |  | FALSE | -46120 | -46078 | -6582.5714
IN TRANSIT & DELAYED | Emilka Guerra | 2026-03-03 | PO08719 | Stock | 2026-04-07 | D-PE2J-200 | Power End, Goulds JC, Frame 2J, Grease-Lubed, SKF Bearings, 4140 Steel Shaft | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-05-26 | SEA | ETA Warehouse mid-august | the vessel depart on May 26 |  | #20251217-11 | Betty 4/23: Included in Comercial Invoice #20251217-11 | Status email sent on April 22nd | 2026-06-16 |  | FALSE | 49 | -46084 | -6583.4286
IN TRANSIT | Jeff Bell | 2026-03-05 | PO08728 | SO17350 | 2026-04-17 | W-250-FF-MCU/0011 | Pump, W-Series, 250 FF-MCU, Hyperchrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-06-19 | SEA | ETA Warehouse Mid-Sept | Follow email sent for update on June 16th |  | We already shipped them to Tianjin, but the vessel delayed, it shows that it will depart on June 19. | Betty 5/15: Included in Comercial Invoice / #20260205-11 | 4/13: After several pushing, Naipu finally gave out the ready time of the 250 FF-MCU pump: still need more than half a month. | 2026-06-17 |  | FALSE | 63 | -46086 | -6583.7143
IN TRANSIT | Ian Trottier | 2026-03-10 | PO08737 | Stock | 2026-04-29 | D-PE3J-300 | Power End, Goulds JC, Frame 3J, Grease-Lubed, SKF Bearings, 4140 Steel Shaft | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-06-19 | SEA | ETA Warehouse Mid-Sept |  |  | Follow email sent for update on June 16th . We already shipped them to Tianjin, but the vessel delayed, it shows that it will depart on June 19. | Betty 6/9: Included in Comercial Invoice / #20260205-11 | Status email sent on April 22nd | 2026-07-08 |  | FALSE | 51 | -46091 | -6584.4286
Ready to Ship | Emilka Guerra | 2026-03-11 | PO08739 | Stock | 2026-05-15 | AC-98-331-954-801 | Bearing Cover (Inboard), 5x4/5x5/6x6 SRL & SRL-C, Cast Iron | 6 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | 2026-07-10 |  |  | Email for update sent June 2nd | Betty: These three parts are ready to ship now. KN told me that the vessel was changed yesterday, I contacted with KN try to add these parts and PO0737 in the shipment. | Betty: We estimate these spare parts need about 40-50 days | 2026-07-10 |  | FALSE | -46157 | -46092
Ready to Ship | Emilka Guerra | 2026-03-11 | PO08739 | Stock | 2026-05-15 | AC-98-236-256-501 | Gland Assembly, 5x4-14 SRL-C, 316SS | 10 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | 2026-07-10 |  |  | Email for update sent June 2nd | Betty: These three parts are ready to ship now. KN told me that the vessel was changed yesterday, I contacted with KN try to add these parts and PO0737 in the shipment. | Betty: We estimate these spare parts need about 40-50 days | 2026-07-10 |  | FALSE | -46157 | -46092
IN TRANSIT | Emilka Guerra | 2026-03-11 | PO08739 | Stock | 2026-05-15 | D-2J3411-2 | Casing, 3x4-11, Goulds JC, Frame 2J, High Chrome, OEM# 056185G4001228 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-06-19 | SEA | ETA Warehouse Mid-Sept |  |  | Follow email sent for update on June 16th . We already shipped them to Tianjin, but the vessel delayed, it shows that it will depart on June 19. | Betty 5/15: Included in Comercial Invoice / #20260205-11 | Betty: We estimate these spare parts need about 40-50 days | 2026-07-10 |  | FALSE | 35 | -46092
IN TRANSIT | Emilka Guerra | 2026-03-11 | PO08739 | Stock | 2026-05-15 | D-2J3411-6 | Suction Cover Liner, 3x4-11, Goulds JC, Frame 2J, High Chrome, OEM# 048824G0001228 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-06-19 | SEA | ETA Warehouse Mid-Sept |  |  | Follow email sent for update on June 16th . We already shipped them to Tianjin, but the vessel delayed, it shows that it will depart on June 19. | Betty 5/15: Included in Comercial Invoice / #20260205-11 | Betty: We estimate these spare parts need about 40-50 days | 2026-07-10 |  | FALSE | 35 | -46092
Ready to Ship | Emilka Guerra | 2026-03-11 | PO08739 | Stock | 2026-05-15 | AC-98-234-268-001-SS | Waterseal Bushing, 5x4/5x5/6x6 SRL, 316SS | 10 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | 2026-07-10 |  |  | Email for update sent June 2nd | Betty: These three parts are ready to ship now. KN told me that the vessel was changed yesterday, I contacted with KN try to add these parts and PO0737 in the shipment. | Betty: We estimate these spare parts need about 40-50 days | 2026-07-10 |  | FALSE | -46157 | -46092
IN TRANSIT | Ian Trottier | 2026-03-13 | PO08748 | Stock | 2026-04-22 | SA-128214-1 | Inlet, Sala VS150, High Chrome | 6 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-06-19 | SEA | ETA Warehouse Mid-Sept |  |  | Follow email sent for update on June 16th . We already shipped them to Tianjin, but the vessel delayed, it shows that it will depart on June 19. | Betty 6/9: Included in Comercial Invoice / #20260205-11 |  | 2026-07-08 |  | FALSE | 58 | -46094
IN TRANSIT | Emilka Guerra | 2026-03-31 | PO08773 | Stock | 2026-05-22 | AC-98-331-983-801 | Bearing Cylinder, 3x3-10 SRL & SRL-C, Cast Iron | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-05-26 | SEA | ETA Warehouse mid-august | the vessel depart on May 26 |  | #20251217-11 | Betty 4/23: Included in Comercial Invoice #20251217-11 |  | 2026-07-31 |  | FALSE | 4 | -46112 | -6587.4286
In Production | Emilka Guerra | 2026-04-06 | PO08785 | Stock | 2026-05-26 | D-WE1J-4 | Shaft Sleeve, Goulds JC Frame 1J, 420SS Heat Treated, Hardened | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-05-26 | SEA | 2026-08-11 |  |  | Email for update sent June 2nd |  |  | 2026-08-11 |  | FALSE | 0 | -46118 | -6588.2857
IN TRANSIT | Emilka Guerra | 2026-04-06 | PO08785 | Stock | 2026-05-26 | AC-98-331-932-501 | Shaft Assembly, 5x4-14 SRL-C & 5x5-14 SRL, 1045 Steel | 12 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-06-19 | SEA | ETA Warehouse Mid-Sept |  |  | Follow email sent for update on June 16th . We already shipped them to Tianjin, but the vessel delayed, it shows that it will depart on June 19. | Betty 6/9: Included in Comercial Invoice / #20260205-11 |  | 2026-08-11 |  | FALSE | 24 | -46118 | -6588.2857
IN TRANSIT | Emilka Guerra | 2026-04-07 | PO08789 | SO19037 | 2026-05-19 | D-1J2311-14 | Suction Cover, 2x3-11, Goulds JC, Frame 1J, High Chrome, OEM# 050387G0001228 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-06-19 | SEA | ETA Warehouse Mid-Sept |  |  | Follow email sent for update on June 16th . We already shipped them to Tianjin, but the vessel delayed, it shows that it will depart on June 19. | Betty 5/15: Included in Comercial Invoice / #20260205-11 |  | 2026-07-28 |  | FALSE | 31 | -46119 | -6588.4286
In Production | Emilka Guerra | 2026-04-10 | PO08800 | Stock | 2026-05-22 | D-2J3411-6 | Suction Cover Liner, 3x4-11, Goulds JC, Frame 2J, High Chrome, OEM# 048824G0001228 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-05-22 | SEA | 2026-07-08 |  |  | Email for update sent June 2nd |  |  | 2026-07-08 |  | FALSE | 0 | -46122 | -6588.8571
IN TRANSIT | Emilka Guerra | 2026-04-10 | PO08800 | Stock | 2026-05-22 | D-1J2311-14 | Suction Cover, 2x3-11, Goulds JC, Frame 1J, High Chrome, OEM# 050387G0001228 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-05-26 | SEA | ETA Warehouse mid-august | the vessel depart on May 26 |  | #20251217-11 | Betty 4/23: Included in Comercial Invoice #20251217-11 |  | 2026-07-08 |  | FALSE | 4 | -46122 | -6588.8571
Ready to Ship | Yannett Yeomans | 2026-04-16 | PO08821 | Stock | 2026-05-29 | D-1J2311-14 | Suction Cover, 2x3-11, Goulds JC, Frame 1J, High Chrome, OEM# 050387G0001228 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-06-19 | SEA | ETA Warehouse Mid-Sept |  |  | Follow email sent for update on June 16th . We already shipped them to Tianjin, but the vessel delayed, it shows that it will depart on June 19. | Betty 5/15: Included in Comercial Invoice / #20260205-11 |  | 2026-05-26 |  | FALSE | 21 | -46128 | -6589.7143
In Production | Emilka Guerra | 2026-04-20 | PO08827 | Stock | 2026-05-25 | AC-98-234-000-801 | Bearing Cover (Outboard), 3x3-10 SRL & SRL-C, Cast Iron | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA |  |  |  | Email for update sent June 2nd |  |  | 2026-08-10 |  | FALSE | -46167 | -46132 | -6590.2857
IN TRANSIT | Emilka Guerra | 2026-04-20 | PO08827 | Stock | 2026-05-25 | AC-98-431-858-501 | Shaft Assembly, 3x3-10 SRL & SRL-C, 1045 Steel | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-06-19 | SEA | ETA Warehouse Mid-Sept |  |  | Follow email sent for update on June 16th . We already shipped them to Tianjin, but the vessel delayed, it shows that it will depart on June 19. | Betty 6/9: Included in Comercial Invoice / #20260205-11 |  | 2026-08-10 |  | FALSE | 25 | -46132 | -6590.2857
IN TRANSIT | Emilka Guerra | 2026-04-20 | PO08827 | Stock | 2026-05-25 | AC-98-331-983-801 | Bearing Cylinder, 3x3-10 SRL & SRL-C, Cast Iron | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-06-19 | SEA | ETA Warehouse Mid-Sept |  |  | Follow email sent for update on June 16th . We already shipped them to Tianjin, but the vessel delayed, it shows that it will depart on June 19. | Betty 5/15: Included in Comercial Invoice / #20260205-11 |  | 2026-08-10 |  | FALSE | 25 | -46132 | -6590.2857
IN TRANSIT | Emilka Guerra | 2026-04-20 | PO08827 | Stock | 2026-05-25 | D-1J2311-10 | Impeller, 2x3-11, Goulds JC, Frame 1J, High Chrome, OEM# 056189G2601228 | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-06-19 | SEA | ETA Warehouse Mid-Sept |  |  | Follow email sent for update on June 16th . We already shipped them to Tianjin, but the vessel delayed, it shows that it will depart on June 19. | Betty 5/15: Included in Comercial Invoice / #20260205-11 |  | 2026-08-10 |  | FALSE | 25 | -46132 | -6590.2857
In Production | Emilka Guerra | 2026-04-20 | PO08827 | Stock | 2026-05-25 | D-2J3411-6 | Suction Cover Liner, 3x4-11, Goulds JC, Frame 2J, High Chrome, OEM# 048824G0001228 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA |  |  |  | Email for update sent June 2nd |  |  | 2026-08-10 |  | FALSE | -46167 | -46132 | -6590.2857
In Production | Emilka Guerra | 2026-04-20 | PO08827 | Stock | 2026-05-25 | D-WE2J-8 | Stuffing Box Cover, Goulds JC, Frame 2J, High Chrome, OEM# 048877G0001228 | 5 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA |  |  |  | Email for update sent June 2nd |  |  | 2026-08-10 |  | FALSE | -46167 | -46132 | -6590.2857
IN TRANSIT | Emilka Guerra | 2026-04-20 | PO08827 | Stock | 2026-05-25 | D-2J3411-1 | Casing, 3x4-11, Goulds JC, Frame 2J, Cast Iron, OEM#056185G4011002 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE | 2026-06-19 | SEA | ETA Warehouse Mid-Sept |  |  | Follow email sent for update on June 16th . We already shipped them to Tianjin, but the vessel delayed, it shows that it will depart on June 19. | Betty 5/15: Included in Comercial Invoice / #20260205-11 |  | 2026-08-10 |  | FALSE | 25 | -46132 | -6590.2857
In Production | Amanda Qiao | 2026-04-26 | PO08847 | SO18070 | 2026-05-26 | W-50ZJLF-QV | Froth Pump, 2" QV-AF, W-Series, Rubber Lined Tank | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA |  | get approval from Amanda before shipping |  | SEND FOLLOW UP ON FRIDAY TO NAIPU |  |  | 2026-04-26 |  | FALSE |  | -46138 | -6591.1429
In Production | Amanda Qiao | 2026-04-26 | PO08847 | SO18070 | 2026-05-26 |  | Paint | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA |  | get approval from Amanda before shipping |  | SEND FOLLOW UP ON FRIDAY TO NAIPU |  |  | 2026-04-26 |  | FALSE |  | -46138 | -6591.1429
In Production | Amanda Qiao | 2026-04-26 | PO08847 | SO18070 | 2026-05-26 | W-50ZJLF-QV-BELT | Belts, W-50ZJLF-QV | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA |  | get approval from Amanda before shipping |  | SEND FOLLOW UP ON FRIDAY TO NAIPU |  |  | 2026-04-26 |  | FALSE |  | -46138 | -6591.1429
In Production | Amanda Qiao | 2026-04-26 | PO08847 | SO18070 | 2026-05-26 | W-QV008/E05 | Bearing Sleeve, QV008 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA |  | get approval from Amanda before shipping |  | SEND FOLLOW UP ON FRIDAY TO NAIPU |  |  | 2026-04-26 |  | FALSE |  | -46138 | -6591.1429
In Production | Amanda Qiao | 2026-04-26 | PO08847 | SO18070 | 2026-05-26 | W-BAF2127/A05 | Impeller, 50ZJLF-QV, High Chrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA |  | get approval from Amanda before shipping |  | SEND FOLLOW UP ON FRIDAY TO NAIPU |  |  | 2026-04-27 |  | FALSE |  | -46138 | -6591.1429
In Production | Amanda Qiao | 2026-04-26 | PO08847 | SO18070 | 2026-05-26 | W-BAF4041/A05 | Throat Bushing, 50ZJLF-QV, High Chrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA |  | get approval from Amanda before shipping |  | SEND FOLLOW UP ON FRIDAY TO NAIPU |  |  | 2026-04-27 |  | FALSE |  | -46138 | -6591.1429
In Production | Amanda Qiao | 2026-04-26 | PO08847 | SO18070 | 2026-05-26 | W-QVAF005 | Bearing Assembly, 50ZJLF-QV | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA |  | get approval from Amanda before shipping |  | SEND FOLLOW UP ON FRIDAY TO NAIPU |  |  | 2026-04-27 |  | FALSE |  | -46138 | -6591.1429
In Production | Yannett Yeomans | 2026-05-04 | PO08875 | SO19243 | 2026-06-05 | 150SV-SP | Vertical Sump Pump, 150SV-SP, High Chrome | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | MX WAREHOUSE |  | SEA | [6 empty] | 2026-06-03 |  | FALSE |  | -46146 | -6592.2857
In Production | Leriel Reyes | 2026-05-06 | PO08878 | Stock | 2026-06-27 | AC-98-234-036-801 | Overhead Motor Mount, 5x4/6x6, Cast Steel Plate, Steel Jacking Bolt | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-05 |  | FALSE |  | -46148 | -6592.5714
In Production | Leriel Reyes | 2026-05-06 | PO08878 | Stock | 2026-06-27 | AC-98-234-082-801 | Overhead Motor Mount, 3x3-10 SRL/SRL-C, Cast Steel Plate, Steel Bolt | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-05 |  | FALSE |  | -46148 | -6592.5714
In Production | Emilka Guerra | 2026-05-11 | PO08892 | Stock | 2026-06-24 | AC-98-233-998-801 | Bearing Cover (Inboard), 3x3-10 SRL & SRL-C | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-02 |  | FALSE |  | -46153 | -6593.2857
In Production | Emilka Guerra | 2026-05-11 | PO08892 | Stock | 2026-06-24 | AC-98-234-000-801 | Bearing Cover (Outboard), 3x3-10 SRL & SRL-C, Cast Iron | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-02 |  | FALSE |  | -46153 | -6593.2857
In Production | Emilka Guerra | 2026-05-11 | PO08892 | Stock | 2026-06-24 | AC-98-332-173-001 | Bearing Cylinder Strap, 3x3-10 SRL-C | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-02 |  | FALSE |  | -46153 | -6593.2857
In Production | Emilka Guerra | 2026-05-11 | PO08892 | Stock | 2026-06-24 | AC-98-331-910-801 | Bearing Cylinder, 8x6-18 & 10x8-21 SRL-C, Cast Iron | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-02 |  | FALSE |  | -46153 | -6593.2857
In Production | Emilka Guerra | 2026-05-21 | PO08925 | Stock | 2026-07-03 | AC-98-431-849-001 | Suction Side Casing, 3x3-10 SRL, Cast Iron | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-11 |  | FALSE |  | -46163 | -6594.7143
In Production | Emilka Guerra | 2026-05-21 | PO08925 | Stock | 2026-07-03 | W-SP10041/A05 | Back Liner, 100RV-SP, High Chrome | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-11 |  | FALSE |  | -46163 | -6594.7143
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-1J2311-1 | Casing, 2x3-11, Goulds JC, Frame 1J, Cast Iron, OEM# 055891G0001002 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-1J2311-4 | Casing, 2x3-11, Goulds JC, Frame 1J, CD4MCu, OEM# 055891G0001247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-1J2311-5 | Suction Cover Liner, 2x3-11, Goulds JC, Frame 1J, Cast Iron, OEM# 048940G0001002 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D1J2311-6 | Suction Cover Liner, 2x3-11, Goulds JC, Frame 1J, High Chrome, OEM# 048940G0001228 | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-1J2311-8 | Suction Cover Liner, 2x3-11, Goulds JC, Frame 1J, CD4MCu, OEM# 048940G0001247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-1J2311-9 | Impeller, 2x3-11, Goulds JC, Frame 1J, Cast Iron, OEM# 056189G2601002 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-1J2311-10 | Impeller, 2x3-11, Goulds JC, Frame 1J, High Chrome, OEM# 056189G2601228 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-1J2311-12 | Impeller, 2x3-11, Goulds JC, Frame 1J, CD4MCu, OEM# 056189G2601247 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-1J2311-13 | Suction Cover, 2x3-11, Goulds JC, Frame 1J, Cast Iron, OEM# 050387G0001002 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-1J2311-14 | Suction Cover, 2x3-11, Goulds JC, Frame 1J, High Chrome, OEM# 050387G0001228 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-1J2311-16 | Suction Cover, 2x3-11, Goulds JC, Frame 1J, CD4MCu, OEM# 050387G0001247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-1J11511-6 | Suction Cover Liner, 1x1.5-11, Goulds JC, Frame 1J, High Chrome, OEM# 048935G0001228 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-1J11511-10 | Impeller, 1x1.5-11, Goulds JC, Frame 1J, High Chrome, OEM# 056185G4701228 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-1J11511-14 | Suction Cover, 1x1.5-11, Goulds JC, Frame 1J, High Chrome, OEM# 050385G0001228 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-WE1J-7 | Stuffing Box Cover, Goulds JC, Frame 1J, Cast Iron, OEM# 048945G0001002 | 6 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-WE1J-8 | Stuffing Box Cover, Goulds JC, Frame 1J, High Chrome, OEM# 048945G0001228 | 6 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-WE1J-10 | Stuffing Box Cover, Goulds JC, Frame 1J, CD4MCu, OEM# 048945G0001247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J15214-4 | Casing, 1.5x2-14, Goulds JC, Frame 2J, CD4MCu, OEM# 055892G0001247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J15214-5 | Suction Cover Liner, 1.5x2-14, Goulds JC Frame 2J, Cast Iron, OEM# 048938G0001002 | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J15214-6 | Suction Cover Liner, 1.5x2-14, Goulds JC Frame 2J, High Chrome, OEM# 048938G0001228 | 9 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J15214-8 | Suction Cover Liner, 1.5x2-14, Goulds JC Frame 2J, CD4MCu, OEM# 048938G0001247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J15214-9 | Impeller, 1.5x2-14, Goulds JC, Frame 2J, Cast Iron, OEM# 056189G2501002 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J15214-10 | Impeller, 1.5x2-14, Goulds JC, Frame 2J, High Chrome, OEM# 056189G2501228 | 6 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J15214-13 | Suction Cover, 1.5x2-14, Goulds JC Frame 2J, Cast Iron, OEM# 050049G0001002 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J15214-14 | Suction Cover, 1.5x2-14, Goulds JC Frame 2J, High Chrome, OEM# 050049G0001228 | 9 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J15214-16 | Suction Cover, 1.5x2-14, Goulds JC Frame 2J, CD4MCu, OEM# 050049G0001247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J2314-4 | Casing, 2x3-14, Goulds JC, Frame 2J, CD4MCu, OEM# 056190G6601247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J2314-5 | Suction Cover Liner, 2x3-14, Goulds JC, Frame 2J, Cast Iron, OEM# 048941G0001002 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J2314-6 | Suction Cover Liner, 2x3-14, Goulds JC, Frame 2J, High Chrome, OEM# 048941G0001228 | 14 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J2314-8 | Suction Cover Liner, 2x3-14, Goulds JC, Frame 2J, CD4MCu, OEM# 048941G0001247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J2314-9 | Impeller, 2x3-14, Goulds JC, Frame 2J, Cast Iron, OEM# 056189G6701002 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J2314-10 | Impeller, 2x3-14, Goulds JC, Frame 2J, High Chrome, OEM# 056189G6701228 | 7 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J2314-13 | Suction Cover, 2x3-14, Goulds JC, Frame 2J, Cast Iron, OEM# 050388G0001002 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J2314-14 | Suction Cover, 2x3-14, Goulds JC, Frame 2J, High Chrome, OEM# 050388G0001228 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J3411-1 | Casing, 3x4-11, Goulds JC, Frame 2J, Cast Iron, OEM#056185G4011002 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J3411-6 | Suction Cover Liner, 3x4-11, Goulds JC, Frame 2J, High Chrome, OEM# 048824G0001228 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J3411-12 | Impeller, 3x4-11, Goulds JC, Frame 2J, CD4MCu, OEM# 056185G4201247 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-2J3411-14 | Suction Cover, 3x4-11, Goulds JC, Frame 2J, High Chrome, OEM# 048825G0001228 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-WE2J-7 | Stuffing Box Cover, Goulds JC, Frame 2J, Cast Iron, OEM# 048877G0001002 | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-WE2J-8 | Stuffing Box Cover, Goulds JC, Frame 2J, High Chrome, OEM# 048877G0001228 | 8 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-WE2J-10 | Stuffing Box Cover, Goulds JC, Frame 2J, CD4MCu, OEM# 048877G0001247 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J4614-1 | Casing, 4x6-14, Goulds JC, Frame 3J, Cast Iron, OEM# 056185G1801002 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J4614-4 | Casing, 4x6-14, Goulds JC, Frame 3J, CD4MCu, OEM# 056185G1801247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J4614-5 | Suction Cover Liner, 4x6-14, Goulds JC, Frame 3J, Cast Iron, OEM# 048944G0001002 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J4614-6 | Suction Cover Liner, 4x6-14, Goulds JC, Frame 3J, High Chrome, OEM# 048944G0001228 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J4614-10 | Impeller, 4x6-14, Goulds JC, Frame 3J, High Chrome, OEM# 056185G1401228 | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J4614-13 | Suction Cover, 4x6-14, Goulds JC, Frame 3J, Cast Iron, OEM# 048933G0001002 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J4614-14 | Suction Cover, 4x6-14, Goulds JC, Frame 3J, High Chrome, OEM# 048933G0001228 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J4614-16 | Suction Cover, 4x6-14, Goulds JC, Frame 3J, CD4MCu, OEM# 048933G0001247 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J3414-1 | Casing, 3x4-14, Goulds JC, Frame 3J, Cast Iron, OEM# 056190G7801002 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J3414-2 | Casing, 3x4-14, Goulds JC, Frame 3J, High Chrome, OEM# 056190G7801228 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J3414-4 | Casing, 3x4-14, Goulds JC, Frame 3J, CD4MCu, OEM# 056190G7801247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J3414-5 | Suction Cover Liner, 3x4-14, Goulds JC, Frame 3j, Cast Iron, OEM# 048943G0001002 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J3414-6 | Suction Cover Liner, 3x4-14, Goulds JC, Frame 3J, High Chrome, OEM# 048943G0001228 | 8 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J3414-8 | Suction Cover Liner, 3x4-14, Goulds JC, Frame 3J, CD4MCu, OEM# 048943G0001247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J3414-10 | Impeller, 3x4-14, Goulds JC, Frame 3J, High Chrome, OEM# 056190G7901228 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J3414-12 | Impeller, 3x4-14, Goulds JC, Frame 3J, CD4MCu, OEM# 056190G7901247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J3414-13 | Suction Cover, 3x4-14, Goulds JC, Frame 3J, Cast Iron, OEM# 048932G0001002 | 3 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J3414-14 | Suction Cover, 3x4-14, Goulds JC, Frame 3J, High Chrome, OEM# 048932G0001228 | 10 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-3J3414-16 | Suction Cover, 3x4-14, Goulds JC, Frame 3J, CD4MCu, OEM# 048932G0001247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-WE3J-7 | Stuffing Box Cover, Goulds JC, Frame 3J, Cast Iron, OEM# 048946G0001002 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-WE3J-8 | Stuffing Box Cover, Goulds JC, Frame 3J, High Chrome, OEM# 048946G0001228 | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-WE3J-10 | Stuffing Box Cover, Goulds JC, Frame 3J, CD4MCu, OEM# 048946G0001247 | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-4J81018-6 | Suction Cover Liner, 8x10-18, Goulds JC, Frame 4J, High Chrome | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Yannett Yeomans | 2026-05-25 | PO08931 | JC Stock 1st order | 2026-06-01 | D-4J81018-10 | Impeller, 8x10-18, Goulds JC, Frame 4J, High Chrome, OEM #056185G8601228 | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-10 |  | FALSE |  | -46167 | -6595.2857
In Production | Emilka Guerra | 2026-05-28 | PO08939 | Stock | 2026-07-09 | AC-98-431-851-501 | Gland Side Casing, 3x3-10 SRL, Cast Iron | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-17 |  | FALSE |  | -46170 | -6595.7143
In Production | Emilka Guerra | 2026-05-28 | PO08939 | Stock | 2026-07-09 | AC-98-431-768-501 | Shaft Assembly, 8x6-18 SRL-C, 1045 Steel | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-09-17 |  | FALSE |  | -46170 | -6595.7143
In Production | Ian Trottier | 2026-05-29 | PO08945 | Stock | 2026-07-14 | AC-SRL 5x4-14-C | Pump, AC-SRL 5x4-14-C, Natural Rubber Lined, Motor Mounting Plate, Belt Guard | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-10-06 |  | FALSE |  | -46171 | -6595.8571
In Production | Emilka Guerra | 2026-06-04 | PO08970 | Stock | 2026-07-23 | W-SP10092/A05 | Casing w/Flange, 100RV-SP, High Chrome | 5 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-10-01 |  | FALSE |  | -46177 | -6596.7143
In Production | Emilka Guerra | 2026-06-04 | PO08970 | Stock | 2026-07-23 | W-SP10206A70800, W-SP10206B/A05 | Impeller (Agitator), 100RV-SP, High Chrome | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-10-01 |  | FALSE |  | -46177 | -6596.7143
In Production | Emilka Guerra | 2026-06-04 | PO08970 | Stock | 2026-07-23 | W-ZAG65482/A05 | Agitator, 100 to 200 SP, High Chrome | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-10-01 |  | FALSE |  | -46177 | -6596.7143
In Production | Emilka Guerra | 2026-06-04 | PO08970 | Stock | 2026-07-23 | AC-98-234-268-001-SS | Waterseal Bushing, 5x4/5x5/6x6 SRL, 316SS | 10 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-10-01 |  | FALSE |  | -46177 | -6596.7143
In Production | Emilka Guerra | 2026-06-04 | PO08970 | Stock | 2026-07-23 | W-ZAG65482/A05 | Agitator, 100 to 200 SP, High Chrome | 1 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-10-01 |  | FALSE |  | -46177 | -6596.7143
In Production | Emilka Guerra | 2026-06-04 | PO08970 | Stock | 2026-07-23 | AC-98-236-256-501 | Gland Assembly, 5x4-14 SRL-C, 316SS | 4 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-10-01 |  | FALSE |  | -46177 | -6596.7143
In Production | Emilka Guerra | 2026-06-09 | PO08984 | SO19430 | 2026-07-07 | AC-98-331-931-801 | Bearing Cylinder, 5x4-14 SRL-C, Cast Iron | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-04 |  | FALSE |  | -46182 | -6597.4286
In Production | Emilka Guerra | 2026-06-09 | PO08984 | SO19430 | 2026-07-07 | AC-98-331-926-801 | Bearing Cover (Outboard), 5x4/5x5/6x6 SRL & SRL-C, Cast Iron | 2 | Naipu Machinery Manufacturing Lincheng Co., Ltd | China | CA WAREHOUSE |  | SEA | [6 empty] | 2026-08-04 |  | FALSE |  | -46182 | -6597.4286